## NHAI_Master
| COMPANY | COMPANY_CODE | PROJECT_NAME | PROJECT_NUMBER | INDUSTRY | OWNERSHIP | TYPE_OF_UNIT | COST | PROJECT_STATUS | CONTRACT_TYPE | COMPLETION_DATE | LOCATION | STATE | EVENT_DATE_1 | EVENT_1 | DATE_OF_COST_OF_PROJECT | Cost_Event1 | Cost_Event | Cost_Overrun | CostOverrun | EVENT_DATE_2 | EVENT_2 | EVENT_DATE_ORIG | MonthDifference | NoOfDays | EVENT_DATE_3 | EVENT_3
1 | National Highways Authority Of India | 155597 | Rajahmundry City (Morampudi Junction) (NH-216A) Flyover Project | 1599 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 560.9 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Morampudi | Andhra Pradesh | 05 Oct 2018 | Date of announcement | 2022-09-21 | 560.9 | 209.8 | 351.1 | Y | [5 empty] | 2022-09-19 | Bids awarded
2 | National Highways Authority Of India | 155597 | 4 Laning of four stretches of Lakhnadon-Seoni (Chapara) ( leftout Stretches ) of NH-7 Project | 1229 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 586 | Completed | Engineering, Procurement & Construction | July 2018 | Lakhnadon | Madhya Pradesh | 01 Jan 2014 | Date of announcement | 2018-07-23 | 586 | 786.6 | -200.6 | N | 2018-07-23 | Completed | 2017-10-30 | Y | 266 | 2016-08-31 | Bids awarded
3 | National Highways Authority Of India | 155597 | 4 to 6 Lane of NH-53 connecting Paradip Port Project | 1714 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6000 | No Information |  |  | Paradip port | Odisha | 01 May 2018 | Date of announcement | 2018-05-15 | 6000 | 6000 | 0 | N
4 | National Highways Authority Of India | 155597 | 84 Kosi Parikrama Marg (NH-227B) Project | 1665 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 65000 | Under Implementation |  | December 2023 | Bikapur | Uttar Pradesh | 04 Aug 2015 | Date of announcement | 2022-10-20 | 65000 | 27500 | 37500 | Y
5 | National Highways Authority Of India | 155597 | AIIMS (Patna)-Naubatpur (NH-139) Two Lane Road Project | 2038 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 880 | Under Implementation |  |  | Aiims | Bihar | 01 Apr 2021 | Date of announcement | 2022-06-07 | 880 | 880 | 0 | N
6 | National Highways Authority Of India | 155597 | Achhampeta Junction (NH-216)-Kakinada Anchorage Port Connecting Vakalpudi Light House (NH-516F) Four Laning Project | 1955 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 957.9 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Achhampeta | Telangana | 01 Jan 2021 | Date of announcement | 2022-12-21 | 957.9 | 902 | 55.9 | Y | 2023-07-12 | Completion expected by | 2023-01-31 | Y | 162 | 2021-11-10 | Bids awarded
7 | National Highways Authority Of India | 155597 | Addahole-Bantwal Cross (NH-75) Four Lane Highway Project (Hassan-B.C. Road Pkg-II) | 1144 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19240 | Under Implementation | Engineering, Procurement & Construction | November 2023 | Addahole | Karnataka | 01 Jul 2015 | Date of announcement | 2022-02-28 | 19240 | 8700 | 10540 | Y | 2023-11-23 | Completion expected by | 2019-09-30 | Y | 1515 | 2016-03-31 | Bids awarded
8 | National Highways Authority Of India | 155597 | Adhelai village-Nari junction (NH-751) Four Lane Highway (Package-I of Pipli-Bhavnagar stretch) Project | 1339 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8200 | Completed | Hybrid Annuity | April 2022 | Bhavnagar | Gujarat | 15 Sep 2017 | Date of announcement | 2019-03-18 | 8200 | 7395.5 | 804.5 | Y | [5 empty] | 2018-03-20 | Bids awarded
9 | National Highways Authority Of India | 155597 | Adloor-Pochanpalli NH-7 Road Project | 546 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7000 | Completed | Build Operate Transfer | March 2009 | Adloor | Andhra Pradesh | 25 Sep 2006 | Financial closure achieved | 2006-09-25 | 7000 | 7000 | 0 | N
10 | National Highways Authority Of India | 155597 | Agra Bypass (NS-1/UP-1) Four-Laning Highway Project | 315 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4655 | Completed | Engineering, Procurement & Construction | December 2016 | Agra | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2008-03-01 | 4655 | 3481.6 | 1173.4 | Y | 2016-12-31 | Completed | 2010-09-30 | Y | 2284 | 2007-06-01 | Bids awarded
11 | National Highways Authority Of India | 155597 | Agra District Foot Over Bridges across NH-2 (Section of Delhi-Agra Highway) Project | 1448 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 128.9 | No Information | Engineering, Procurement & Construction |  | Abu lalaki dargah | Uttar Pradesh | 22 Dec 2017 | Date of announcement | 2017-12-22 | 128.9 | 128.9 | 0 | N
12 | National Highways Authority Of India | 155597 | Agra Four Laning Bypass (connecting NH & Expressway) Project | 1307 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4500 | No Information |  |  | Agra | Uttar Pradesh | 16 Jun 2016 | Date of announcement | 2018-07-04 | 4500 | 4500 | 0 | N
13 | National Highways Authority Of India | 155597 | Agra Fourth Flyover/Underpass (Sabji Mandi) Project | 1304 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 260 | Completed |  | May 2021 | Agra | Uttar Pradesh | 24 May 2017 | Date of announcement | 2021-05-08 | 260 | 280 | -20 | N | 2021-05-08 | Completed | 2019-08-31 | Y | 616
14 | National Highways Authority Of India | 155597 | Agra Six Lane Bypass (Northern) connecting NH-19 to Yamuna Expressway Six Lane Project | 2003 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4830.7 | Under Implementation | Engineering, Procurement & Construction |  | Agra | Uttar Pradesh | 01 Sep 2021 | Date of announcement | 2021-10-18 | 4830.7 | 4830.7 | 0 | N | [5 empty] | 2022-03-28 | Bids awarded
15 | National Highways Authority Of India | 155597 | Agra-Gwalior (NS/4) Four Lane Highway Project | 189 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 700 | Completed |  | July 2001 | Agra | Uttar Pradesh | 01 Jan 2000 | Date of announcement | 2001-07-01 | 700 | 700 | 0 | N
16 | National Highways Authority Of India | 155597 | Agra-Jalesar-Etah (NH-321-G) Two/Four Lane Highway Improvement & Upgradation Project | 1649 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10030 | Under Implementation | Engineering, Procurement & Construction |  | Agra | Uttar Pradesh | 09 Jan 2019 | Date of announcement | 2022-01-07 | 10030 | 2129.3 | 7900.7 | Y
17 | National Highways Authority Of India | 155597 | Agra-Kanpur Expressway Project | 26 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 30000 | No Information | Build Operate Transfer |  | Agra | Uttar Pradesh | 01 Dec 1997 | Date of announcement | 1997-12-01 | 30000 | 30000 | 0 | N
18 | National Highways Authority Of India | 155597 | Agra-Shikohabad (GTRIP/I-A) Road Project | 145 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4600 | Completed |  | February 2013 | Agra | Uttar Pradesh | 30 Apr 2000 | Date of announcement | 2009-10-30 | 4600 | 3674.9 | 925.1 | Y | 2013-02-28 | Completed | 2003-12-31 | Y | 3347
19 | National Highways Authority Of India | 155597 | Agra-Sikandara Highway Project | 146 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2612.2 | Completed |  | September 2006 | Agra | Uttar Pradesh | 01 Jun 2001 | Date of announcement | 2002-01-01 | 2612.2 | 2280 | 332.2 | Y
20 | National Highways Authority Of India | 155597 | Ahmadabad-Dandi Heritage Route Project | 470 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 24000 | No Information |  |  | Ahmadabad | Gujarat | 30 Apr 2005 | Date of announcement | 2013-05-01 | 24000 | 13460 | 10540 | Y
21 | National Highways Authority Of India | 155597 | Ahmednagar Four Lane Bypass Project | 1420 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7734 | Under Implementation | Hybrid Annuity |  | Ahmednagar | Maharashtra | 30 Nov 2017 | Date of announcement | 2017-11-30 | 7734 | 7734 | 0 | N | [5 empty] | 2020-09-21 | Bids awarded
22 | National Highways Authority Of India | 155597 | Ahore-Sanderao (NH-325) Highway Project (Package-III) (Jalore-Barmer-Sirohi) | 1271 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1136 | Completed | Engineering, Procurement & Construction | September 2020 | Ahore | Rajasthan | 06 Sep 2015 | Date of announcement | 2020-09-14 | 1136 | 1668.8 | -532.8 | N | 2020-09-14 | Completed | 2019-07-31 | Y | 411
23 | National Highways Authority Of India | 155597 | Akkalkot-Badadal (NH-150C) Four/Six Lane Greenfield Highway Project (Package-1 of Akkalkot-KN/TS Border Highway) | 1884 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 46213 | Announced | Hybrid Annuity |  | Akkalkot | Maharashtra | 01 Apr 2020 | Date of announcement | 2021-01-15 | 46213 | 46213 | 0 | N
24 | National Highways Authority Of India | 155597 | Akola City (NH-53) Flyovers Project | 1450 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1639.8 | Completed | Engineering, Procurement & Construction | August 2022 | Akola | Maharashtra | 01 Mar 2015 | Date of announcement | 2018-10-12 | 1639.8 | 1758.9 | -119.1 | N | 2022-08-01 | Completed | 2021-08-20 | Y | 346 | 2018-11-20 | Bids awarded
25 | National Highways Authority Of India | 155597 | Akola City (NH-6) Bypass Project | 31 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 675 | Completed | Build Operate Transfer | October 2010 | Akola | Maharashtra | 31 Mar 2007 | Date of announcement | 2009-07-01 | 675 | 468.7 | 206.3 | Y | 2010-10-01 | Completed | 2009-03-31 | Y | 549
26 | National Highways Authority Of India | 155597 | Akola-Medshi (NH-161) Four Lane Highway Project | 1814 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7321.2 | Under Implementation | Engineering, Procurement & Construction |  | Akola | Maharashtra | 01 Jan 2018 | Date of announcement | 2019-01-01 | 7321.2 | 7321.2 | 0 | N | [5 empty] | 2020-03-30 | Bids awarded
27 | National Highways Authority Of India | 155597 | Alappuzha Bypass Project | 782 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3440 | Completed | Engineering, Procurement & Construction | January 2021 | Alappuzha | Kerala | 30 Dec 1980 | Date of announcement | 2021-01-21 | 3440 | 1570 | 1870 | Y | 2021-01-28 | Completed | 2013-08-31 | Y | 2707 | 2015-02-12 | Bids awarded
28 | National Highways Authority Of India | 155597 | Alawalpur Chowk to Agra Chowk (NH-19) Elevated Corridor Project | 1264 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2150 | Completed |  | April 2022 | Agra chowk | Haryana | 05 Apr 2016 | Date of announcement | 2022-04-10 | 2150 | 2000 | 150 | Y | 2022-12-31 | Initial completion date | 2020-12-31 | Y | 730
29 | National Highways Authority Of India | 155597 | Aligarh-Kanpur (NH-91) Four/Six Laning Highway Project (Bharatmala) | 1040 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 49610 | Under Implementation | Hybrid Annuity |  | Aligarh | Uttar Pradesh | 30 Mar 2010 | Date of announcement | 2018-03-31 | 49610 | 7236.8 | 42373.2 | Y | [5 empty] | 2010-12-30 | Bids awarded
30 | National Highways Authority Of India | 155597 | Aligarh-Moradabad (NH-93) (New NH-509) Two Laning Road Project | 818 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9500 | Completed | Engineering, Procurement & Construction | May 2019 | Aligarh | Uttar Pradesh | 19 Nov 2010 | Date of announcement | 2019-02-20 | 9500 | 6980 | 2520 | Y | 2019-07-25 | Initial completion date | 2019-05-13 | Y | 73 | 2016-03-17 | Bids awarded
31 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-I Highway Project | 151 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 913.6 | Completed | Engineering, Procurement & Construction | October 2008 | Allahabad | Uttar Pradesh | 01 Jun 2001 | Date of announcement | 2001-06-01 | 913.6 | 913.6 | 0 | N | [5 empty] | 2003-09-01 | Bids awarded
32 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-II Project | 721 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6971.6 | Completed |  | December 2009 | Allahabad | Uttar Pradesh | 30 Apr 2000 | Date of announcement | 2009-10-01 | 6971.6 | 6971.6 | 0 | N
33 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-III Project | 722 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7161.5 | Completed |  | December 2009 | Allahabad | Uttar Pradesh | 30 Apr 2000 | Date of announcement | 2009-10-01 | 7161.5 | 7161.5 | 0 | N
34 | National Highways Authority Of India | 155597 | Aluva-Angamali(NS-28/KL) NH47 Highway Project | 164 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 773.8 | Completed | Engineering, Procurement & Construction | April 2004 | Aluva | Kerala | 01 Mar 2001 | Date of announcement | 2002-01-01 | 773.8 | 780 | -6.2 | N | 2004-06-30 | Initial completion date | 2003-05-31 | Y | 396 | 2001-09-01 | Bids awarded
35 | National Highways Authority Of India | 155597 | Amas-Shiwrampur Four Lane Highway (Package-I of Amas-Darbhanga Expressway) Project | 1891 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13909.2 | Under Implementation | Hybrid Annuity | September 2024 | Amas | Bihar | 01 Mar 2021 | Date of announcement | 2022-04-06 | 13909.2 | 12079.1 | 1830.1 | Y | [5 empty] | 2022-03-17 | Bids awarded
36 | National Highways Authority Of India | 155597 | Ambala Four Lane Ring Road (NH-44) (Connecting Five NH) Project | 1825 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 14850 | Under Implementation | Engineering, Procurement & Construction | September 2025 | Ambala | Haryana | 20 Jul 2015 | Date of announcement | 2022-08-17 | 14850 | 4000 | 10850 | Y | [5 empty] | 2023-03-27 | Bids awarded
37 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-I) | 612 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4580 | Completed | Engineering, Procurement & Construction | December 2019 | Ambala | Haryana | 30 Apr 2009 | Date of announcement | 2018-01-31 | 4580 | 4740.9 | -160.9 | N | 2019-12-13 | Completed | 2016-06-30 | Y | 1261 | 2015-03-30 | Bids awarded
38 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-II) | 1011 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5742.8 | Completed | Engineering, Procurement & Construction | June 2020 | Ambala | Haryana | 30 Apr 2009 | Date of announcement | 2016-06-30 | 5742.8 | 3798 | 1944.8 | Y | 2020-06-26 | Completed | 2018-07-31 | Y | 696 | 2015-03-03 | Bids awarded
39 | National Highways Authority Of India | 155597 | Ambala-Kala Amb section of NH-72 to Shahzadpur and Part of New NH-7 from Shahzadpur to Kala Amb Four Lane Highway Project | 2089 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11827.7 | Under Implementation | Hybrid Annuity |  | Ambala | Haryana | 01 Oct 2021 | Date of announcement | 2023-02-03 | 11827.7 | 11827.7 | 0 | N | [5 empty] | 2022-11-28 | Bids awarded
40 | National Highways Authority Of India | 155597 | Ambala-Zirakpur (NH-21 & 22) Highway Project | 767 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3646.2 | Completed |  | March 2009 | Ambala | Haryana | 01 May 2006 | Date of announcement | 2006-05-01 | 3646.2 | 3646.2 | 0 | N
41 | National Highways Authority Of India | 155597 | Ambalapady Junction (NH-66) Double-cell Vehicular Underpass Project | 1966 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 250 | Under Implementation |  |  | Ambalapady | Karnataka | 01 Sep 2021 | Date of announcement | 2023-03-10 | 250 | 274.9 | -24.9 | N
42 | National Highways Authority Of India | 155597 | Ambience Mall & DLF Phase 2 (NH-48) Elevated U-Turns Project | 1539 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1619 | Completed | Engineering, Procurement & Construction | March 2022 | Ambience mall | Haryana | 01 Apr 2008 | Date of announcement | 2019-01-11 | 1619 | 970 | 649 | Y | 2022-03-09 | Completed | 2020-02-28 | Y | 740 | 2018-11-09 | Bids awarded
43 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 29360 | Completed | Engineering, Procurement & Construction | April 2022 | Amra marg | Maharashtra | 23 Aug 2011 | Date of announcement | 2022-04-03 | 29360 | 22600 | 6760 | Y | 2022-04-03 | Completed | 2014-11-30 | Y | 2681 | 2015-08-01 | Bids awarded
44 | National Highways Authority Of India | 155597 | Amravati Bypass Highway Project | 13 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 449.7 | Completed | Build Operate Transfer | January 2003 | Amravati | Maharashtra | 01 Jun 1997 | Date of announcement | 2002-10-01 | 449.7 | 350 | 99.7 | Y | 2003-01-31 | Completed | 2002-05-31 | Y | 245
45 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22881.8 | Under Implementation | Hybrid Annuity |  | Amravati | Maharashtra | 01 Mar 2010 | Date of announcement | 2015-07-24 | 22881.8 | 22359.2 | 522.6 | Y | [5 empty] | 2012-04-03 | Bids awarded
46 | National Highways Authority Of India | 155597 | Amritsar Bypass Improvement (NH-1) Project | 1146 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2300 | Completed | Engineering, Procurement & Construction | April 2019 | Amritsar | Punjab | 15 May 2015 | Date of announcement | 2017-11-21 | 2300 | 2730.6 | -430.6 | N | 2019-05-31 | Initial completion date | 2017-11-30 | Y | 547 | 2015-09-04 | Bids awarded
47 | National Highways Authority Of India | 155597 | Amritsar-Bhatinda (NH-15) Four Laning Highway Project | 973 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 28930 | Completed | Design Build Finance Operate Transfer | May 2018 | Amritsar | Punjab | 01 May 2013 | Date of announcement | 2018-05-13 | 28930 | 18990 | 9940 | Y | [5 empty] | 2016-09-27 | Bids awarded
48 | National Highways Authority Of India | 155597 | Amritsar-Bhikhiwind-Khemkaran Two Laning Road project | 1761 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1499 | No Information | Engineering, Procurement & Construction |  | Amritsar | Punjab | 01 Sep 2007 | Date of announcement | 2018-03-19 | 1499 | 1499 | 0 | N | [5 empty] | 2018-03-19 | Bids awarded
49 | National Highways Authority Of India | 155597 | Amritsar-Ghoman-Tanda-Una (NH-503A) Four Lane Highway Project | 1765 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17000 | Under Implementation | Hybrid Annuity |  | Amritsar | Punjab | 05 Feb 2019 | Date of announcement | 2022-01-03 | 17000 | 17000 | 0 | N | [5 empty] | 2021-03-22 | Bids awarded
50 | National Highways Authority Of India | 155597 | Amritsar-Jodhpur Two-Laning Highway Project | 688 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 80000 | No Information |  |  | Amritsar | Punjab | 18 Nov 2009 | Date of announcement | 2009-11-18 | 80000 | 80000 | 0 | N
51 | National Highways Authority Of India | 155597 | Amritsar-Wagha Border (NH-1) Highway Project | 464 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2149 | Completed | Build Operate Transfer | October 2010 | Amritsar | Punjab | 30 Jun 2008 | Date of announcement | 2010-10-31 | 2149 | 2058.8 | 90.2 | Y | 2010-10-31 | Completed | 2010-06-30 | Y | 123
52 | National Highways Authority Of India | 155597 | Anantpur-Kurnool-Amaravati Four/Six Access Controlled Expressway Project | 1141 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 200000 | Implementation Stalled |  |  | Amaravati | Andhra Pradesh | 15 Mar 2015 | Date of announcement | 2019-06-18 | 200000 | 276350 | -76350 | N
53 | National Highways Authority Of India | 155597 | Anarbansalea village to Sagrampur village Four/Six Lane Greenfield Access Control Expressway Project (Package-7 of Varanasi-Kolkata Expressway) | 1982 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 12483.7 | Under Implementation | Hybrid Annuity |  | Anarbansalea | Bihar | 01 Nov 2021 | Date of announcement | 2023-03-31 | 12483.7 | 12483.7 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
54 | National Highways Authority Of India | 155597 | Andhra NH-5 Project | 68 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 3353.5 | No Information |  |  | Andhra Pradesh | Andhra Pradesh | 31 Mar 1998 | Expenses incurred upto | 2001-10-01 | 3353.5 | 1716 | 1637.5 | Y
55 | National Highways Authority Of India | 155597 | Andhra NH-9 Project | 69 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 673.2 | No Information |  |  | Andhra Pradesh | Andhra Pradesh | 31 Mar 1995 | Central Government approval received | 1999-12-01 | 673.2 | 673.2 | 0 | N
56 | National Highways Authority Of India | 155597 | Angamaly-Kundanoor (Ernakulam Bypass) (NH-544&46) Four Lane Bypass Project | 1786 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 56480 | Announced |  | March 2027 | Angamaly | Kerala | 01 Sep 2016 | Date of announcement | 2018-02-17 | 56480 | 56480 | 0 | N
57 | National Highways Authority Of India | 155597 | Angul-Sambalpur (NH-42) Highway Project | 820 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 24915.3 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Angul | Odisha | 25 Oct 2010 | Date of announcement | 2016-06-29 | 24915.3 | 12408.3 | 12507 | Y | 2023-12-31 | Completion expected by | 2019-08-31 | Y | 1583 | 2011-11-30 | Bids awarded
58 | National Highways Authority Of India | 155597 | Ankaleshwar-Netrang Highway Project | 1302 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7040 | No Information |  |  | Ankleshwar | Gujarat | 13 May 2017 | Date of announcement | 2018-08-24 | 7040 | 7040 | 0 | N
59 | National Highways Authority Of India | 155597 | Annojiguda-Raigiri Four Lane Road Widening Project | 853 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3000 | No Information | Build Operate Transfer |  | Annojiguda | Telangana | 01 Jul 2010 | Date of announcement | 2010-07-01 | 3000 | 3000 | 0 | N
60 | National Highways Authority Of India | 155597 | Aramgharh-Shamshabad Six Laning Highway project | 1330 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2830 | Under Implementation | Engineering, Procurement & Construction |  | Aramgarh | Telangana | 28 Jul 2015 | Date of announcement | 2022-11-14 | 2830 | 2900 | -70 | N
61 | National Highways Authority Of India | 155597 | Arapalayam-Viraganoor (Vaigai River) Two Lane Road Widening Project | 1787 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2860 | No Information |  |  | Arappalayam | Tamil Nadu | 06 Dec 2018 | Date of announcement | 2019-08-20 | 2860 | 2860 | 0 | N
62 | National Highways Authority Of India | 155597 | Armur-(K)adloor-Yellareddy (NH-7) Four-Laning Highway Project | 483 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6350 | Completed |  | June 2013 | Adloor | Andhra Pradesh | 12 Aug 2008 | Date of announcement | 2012-12-31 | 6350 | 4905 | 1445 | Y | 2013-06-30 | Completed | 2012-02-28 | Y | 488
63 | National Highways Authority Of India | 155597 | Armur-Kalkallu Highway Project | 320 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4900 | No Information | Build Operate Transfer Annuity |  | Armur | Telangana | 01 Dec 2003 | Date of announcement | 2008-07-01 | 4900 | 4900 | 0 | N
64 | National Highways Authority Of India | 155597 | Aroor to Thuravoor Thekku Six Lane (NH-66) Elevated Corridor Project | 2074 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 29270 | Under Implementation | Engineering, Procurement & Construction |  | Aroor | Kerala | 01 Jul 2020 | Date of announcement | 2022-12-15 | 29270 | 19938.8 | 9331.2 | Y | [5 empty] | 2022-12-02 | Bids awarded
65 | National Highways Authority Of India | 155597 | Arrah-Pararia Four Lane Highway (NH-319) Project (Package 1 of Mohania-Arrah) (Bharatmala) | 1838 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8860 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Arrah | Bihar | 01 Jul 2011 | Date of announcement | 2020-09-22 | 8860 | 6904.8 | 1955.2 | Y | 2023-07-25 | Completion expected by | 2014-06-30 | Y | 3312 | 2011-08-11 | Bids awarded
66 | National Highways Authority Of India | 155597 | Ashok Square-Agrasen Square Flyover Project | 1273 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2130 | No Information |  |  | Agrasen square | Maharashtra | 23 Mar 2017 | Date of announcement | 2017-03-23 | 2130 | 2130 | 0 | N
67 | National Highways Authority Of India | 155597 | Ashram-Badarpur Highway Upgradation Project | 372 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 265 | No Information |  |  | Badarpur | Assam | 01 Mar 2004 | Date of announcement | 2004-03-01 | 265 | 265 | 0 | N
68 | National Highways Authority Of India | 155597 | Assam/WB Border to Gairkata (WB-1) Highway Project | 285 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | Completed |  | March 2013 | Gairkatta | West Bengal | 01 Dec 2003 | Date of announcement | 2012-12-31 | 3000 | 2218.2 | 781.8 | Y | 2013-03-31 | Initial completion date | 2010-06-30 | Y | 1005
69 | National Highways Authority Of India | 155597 | Atmakur-Dornala (NH-340C) Two Lane Highway Project (Kurnool-Dornala) | 1490 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1850.5 | Announced | Engineering, Procurement & Construction |  | Atmakur | Andhra Pradesh | 01 Apr 2015 | Date of announcement | 2018-04-27 | 1850.5 | 1850.5 | 0 | N
70 | National Highways Authority Of India | 155597 | Atul-Kajali (NH-8) Highway Project | 52 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1745.9 | Completed |  | February 2004 | Atul | Gujarat | 15 Mar 2000 | Date of announcement | 2002-09-01 | 1745.9 | 1745.9 | 0 | N | 2004-02-22 | Completed | 2003-04-30 | Y | 298 | 2000-11-01 | Bids awarded
71 | National Highways Authority Of India | 155597 | Aurad-Bidar (NH-161A) Two Lane Highway Project | 1656 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4241.6 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Aurad | Karnataka | 29 Jan 2019 | Date of announcement | 2020-12-19 | 4241.6 | 8931.6 | -4690 | N | [5 empty] | 2020-12-18 | Bids awarded
72 | National Highways Authority Of India | 155597 | Aurangabad-Barwa-Adda(Aurangabad-Barachatti) Highway Project | 157 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3204.2 | Completed | Engineering, Procurement & Construction | July 2007 | Aurangabad | Bihar | 01 Mar 2001 | Date of announcement | 2002-01-01 | 3204.2 | 2400 | 804.2 | Y | 2007-07-30 | Completed | 2004-12-31 | Y | 941 | 2001-09-01 | Bids awarded
73 | National Highways Authority Of India | 155597 | Aurangabad-Bihar/Jharkhand Border (Chordaha) (NH-2) Six Laning Highway Project (Package-I) | 897 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15160.9 | Under Implementation | Engineering, Procurement & Construction |  | Aurangabad | Bihar | 01 Jun 2011 | Date of announcement | 2019-12-31 | 15160.9 | 10055.2 | 5105.7 | Y | [5 empty] | 2012-03-31 | Bids awarded
74 | National Highways Authority Of India | 155597 | Aurangabad-Paithan (NH-752E) Four Lane Highway Project | 1866 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8900 | Under Implementation | Engineering, Procurement & Construction |  | Aurangabad (mah) | Maharashtra | 01 Jun 2008 | Date of announcement | 2018-08-24 | 8900 | 1790 | 7110 | Y | [5 empty] | 2010-06-16 | Bids awarded
75 | National Highways Authority Of India | 155597 | Aurangabad-Telwadi (NH-52) Four-Laning Highway Project | 1006 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30620 | Completed | Engineering, Procurement & Construction | January 2022 | Aurangabad (mah) | Maharashtra | 15 Jul 2010 | Date of announcement | 2022-01-31 | 30620 | 12521.9 | 18098.1 | Y | 2022-01-31 | Completed | 2021-08-10 | Y | 174 | 2018-02-01 | Bids awarded
76 | National Highways Authority Of India | 155597 | Aut-Takoli (Tunnel) (NH-21) Highway Project (Package-V of Nerchowk-Kullu stretch) | 1047 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5561.1 | Under Implementation | Hybrid Annuity |  | Aut section | Himachal Pradesh | 15 Nov 2014 | Date of announcement | 2014-12-09 | 5561.1 | 5561.1 | 0 | N | [5 empty] | 2017-06-19 | Bids awarded
77 | National Highways Authority Of India | 155597 | Avathi village-Nandi Hills cross & Devanhalli-Meenukunte (NS-10) Six Lane Project | 957 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 258.2 | Completed | Engineering, Procurement & Construction | July 2001 | Avathi village | Karnataka | 01 Jan 2000 | Date of announcement | 2000-01-15 | 258.2 | 258.2 | 0 | N | [5 empty] | 2000-01-16 | Bids awarded
78 | National Highways Authority Of India | 155597 | Ayodhya Four Lane Ring Road project | 1662 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 50000 | Under Implementation |  | December 2025 | Ayodhya | Uttar Pradesh | 09 Aug 2017 | Date of announcement | 2022-12-16 | 50000 | 12890 | 37110 | Y
79 | National Highways Authority Of India | 155597 | Ayodhya Four/Six Lane Bypass Project | 1929 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 49000 | Under Implementation | Hybrid Annuity | December 2023 | Ayodhya | Uttar Pradesh | 01 Jul 2021 | Date of announcement | 2023-01-31 | 49000 | 57038.2 | -8038.2 | N
80 | National Highways Authority Of India | 155597 | Ayodhya-Faizabad-Sultanpur-Mohanganj-Jethwara-Kanhaiyapur-Trilokpur-Shringverpur-Kokhraj-Kaushambi-Chitrakoot Two/Four Lane Highway Project (Ram Van Gaman Marg) | 1664 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 45500 | Under Implementation |  | December 2024 | Ayodhya | Uttar Pradesh | 01 Aug 2001 | Date of announcement | 2022-10-20 | 45500 | 20200 | 25300 | Y
81 | National Highways Authority Of India | 155597 | Ayodhya-Gorakhpur (Lucknow-Muzaffarpur) Highway Project | 270 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10760 | Completed | Engineering, Procurement & Construction | December 2011 | Ayodhya | Uttar Pradesh | 01 Sep 2003 | Date of announcement | 2011-02-28 | 10760 | 6710 | 4050 | Y | 2012-01-30 | Initial completion date | 2008-10-31 | Y | 1186
82 | National Highways Authority Of India | 155597 | Ayodhya-Lucknow (LMNHP) Highway Project | 513 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10450 | Completed | Engineering, Procurement & Construction | September 2011 | Ayodhya | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2011-02-28 | 10450 | 2120 | 8330 | Y | 2011-09-30 | Initial completion date | 2008-11-01 | Y | 1063 | 2004-12-30 | Bids awarded
83 | National Highways Authority Of India | 155597 | Ayodhya-Varanasi (NH-135A) Four Lane Highway Project | 1663 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30000 | Under Implementation |  |  | Akbarpur | Uttar Pradesh | 01 Jun 2014 | Date of announcement | 2021-02-05 | 30000 | 75000 | -45000 | N
84 | National Highways Authority Of India | 155597 | Azhikkal Port-NH-Bypass Port Road Connectivity Project | 1476 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 610 | Under Implementation |  |  | Azhikkal port | Kerala | 01 Apr 2016 | Date of announcement | 2016-06-03 | 610 | 610 | 0 | N
85 | National Highways Authority Of India | 155597 | Azhikkal-Puthuvalappu Road Project (Port Connectivity) (Bharatmala) | 1748 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3500 | Announced |  | February 2024 | Azhikkal | Kerala | 01 Apr 2018 | Date of announcement | 2021-09-07 | 3500 | 1323.9 | 2176.1 | Y
86 | National Highways Authority Of India | 155597 | Azhiyur-Vengalam (NH-66) Six Lane Highway Project | 1880 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 37110 | Under Implementation | Hybrid Annuity |  | Azhiyur | Kerala | 01 Apr 2019 | Date of announcement | 2022-12-15 | 37110 | 18381 | 18729 | Y | [5 empty] | 2021-01-14 | Bids awarded
87 | National Highways Authority Of India | 155597 | BC Road-Punjalkatte (NH-234) Road Project (Mangalore-Villuppuram Section) | 1967 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1597 | Completed |  | February 2022 | Bc road | Karnataka | 01 Jan 2018 | Date of announcement | 2022-02-28 | 1597 | 980 | 617 | Y
88 | National Highways Authority Of India | 155597 | BRT Tiger Reserve-Bangalore (NH-209) Two/Four-Laning Highway Project | 1172 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12535.1 | Under Implementation | Hybrid Annuity |  | Bangalore | Karnataka | 15 Jan 2016 | Date of announcement | 2020-02-06 | 12535.1 | 10080 | 2455.1 | Y | [5 empty] | 2016-09-30 | Bids awarded
89 | National Highways Authority Of India | 155597 | Badarpur Elevated Highway Project | 405 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3400 | Completed | Build Operate Transfer | November 2010 | Badarpur (DHL) | NCT of Delhi | 26 Mar 2005 | Date of announcement | 2009-04-01 | 3400 | 2700 | 700 | Y | 2010-12-31 | Initial completion date | 2010-09-30 | Y | 92
90 | National Highways Authority Of India | 155597 | Baghpat-Ghaziabad Six Lane Expressway Project (Package 2 of Eastern Peripheral Expressway) | 1122 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7857.8 | Completed | Engineering, Procurement & Construction | May 2018 | Baghpat | Uttar Pradesh | 31 Jan 1995 | Date of announcement | 2014-10-29 | 7857.8 | 7857.8 | 0 | N | 2018-07-31 | Initial completion date | 2009-07-30 | Y | 3288 | 2015-08-30 | Bids awarded
91 | National Highways Authority Of India | 155597 | Bahalgarh Chowk (NH-1) Flyover Project | 1001 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 779.7 | Completed | Engineering, Procurement & Construction | November 2016 | Bahalgarh chowk | Haryana | 21 Jan 2008 | Date of announcement | 2014-05-31 | 779.7 | 779.7 | 0 | N | [5 empty] | 2014-05-05 | Bids awarded
92 | National Highways Authority Of India | 155597 | Baharagora-Sambalpur (NH-6) Four Lane Road project | 816 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 36364.3 | No Information | Design Build Finance Operate Transfer |  | Baharagora | Jharkhand | 25 Oct 2010 | Date of announcement | 2013-01-09 | 36364.3 | 35923.8 | 440.5 | Y
93 | National Highways Authority Of India | 155597 | Baharagora-Singhara (NH-6 & 49) Four Laning Highway Project | 1064 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 12829.4 | Completed | Engineering, Procurement & Construction | April 2022 | Baharagora | Jharkhand | 01 Sep 2014 | Date of announcement | 2015-07-06 | 12829.4 | 9087.3 | 3742.1 | Y | 2022-04-06 | Completed | 2020-04-30 | Y | 706 | 2015-07-06 | Bids awarded
94 | National Highways Authority Of India | 155597 | Bahraich-Rupaidiha (NH-28C) Highway Widening Project | 1017 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3970.4 | Completed | Engineering, Procurement & Construction | August 2018 | Bahraich | Uttar Pradesh | 21 Oct 2009 | Date of announcement | 2017-08-31 | 3970.4 | 2952.2 | 1018.2 | Y | 2018-08-13 | Completed | 2016-10-30 | Y | 652
95 | National Highways Authority Of India | 155597 | Bakaria-Gogunda NH-76 Highway Project | 644 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4570 | Completed | Engineering, Procurement & Construction | March 2009 | Bakaria | Uttar Pradesh | 31 Dec 2003 | Date of announcement | 2009-01-01 | 4570 | 4570 | 0 | N | [5 empty] | 2005-07-15 | Bids awarded
96 | National Highways Authority Of India | 155597 | Bakhtiyarpur-Mokama (NH-31) Four Laning Highway Project (Package 1 of Khagaria-Bakhtiarpur Highway) | 478 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8370 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Bakhtiarpur | Bihar | 12 Aug 2008 | Date of announcement | 2022-06-25 | 8370 | 17038.2 | -8668.2 | N | 2023-12-31 | Completion expected by | 2015-01-31 | Y | 3256 | 2011-12-03 | Bids awarded
97 | National Highways Authority Of India | 155597 | Balance work of Four Laning of Nagpur - Hyderbad Section of NH-7 (NS-62) (Package-II) (Kelapur-Pimpalkhatti) Project | 1180 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Completed | Engineering, Procurement & Construction | October 2018 | Hyderabad | Telangana | 01 Jan 2016 | Date of announcement | 2018-10-25 | 2000 | 1976.9 | 23.1 | Y | 2018-10-25 | Completed | 2018-05-31 | Y | 147 | 2016-03-31 | Bids awarded
98 | National Highways Authority Of India | 155597 | Balance work of Four Laning of Nagpur-Hyderabad Section of NH-7 (NS-60) (Package-I) Project (Wadner-Devdhari Highway) | 1179 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2440 | Completed | Engineering, Procurement & Construction | June 2019 | Devdhari | Maharashtra | 01 Jan 2016 | Date of announcement | 2016-03-31 | 2440 | 2440 | 0 | N | 2019-06-25 | Completed | 2018-05-31 | Y | 390 | 2016-03-31 | Bids awarded
99 | National Highways Authority Of India | 155597 | Balance works on Hapur Bypass-Moradabad section (NH-24) Road Project | 1255 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 416.4 | Completed | Engineering, Procurement & Construction | June 2018 | Hapur bypass | Uttar Pradesh | 30 Sep 2016 | Date of announcement | 2016-12-29 | 416.4 | 416.4 | 0 | N | [5 empty] | 2016-12-29 | Bids awarded
100 | National Highways Authority Of India | 155597 | Balasore-Bhadrak (NH-5) Highway Project | 136 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2410 | Completed |  | October 2013 | Balasore | Odisha | 30 Apr 2000 | Date of announcement | 2009-10-01 | 2410 | 2520 | -110 | N | 2013-11-30 | Initial completion date | 2003-12-31 | Y | 3622 | 2001-03-31 | Bids awarded
101 | National Highways Authority Of India | 155597 | Balasore-Chandikhole (Bridges section OR-V) Highway Project | 138 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1550 | Completed | Engineering, Procurement & Construction | April 2008 | Balasore | Odisha | 01 Mar 2001 | Date of announcement | 2001-06-01 | 1550 | 1550 | 0 | N | 2008-04-30 | Completed | 2004-05-31 | Y | 1430 | 2001-08-01 | Bids awarded
102 | National Highways Authority Of India | 155597 | Balbhadrapur (Tal Dasraha)-Bela Nawada Four Lane Access Controlled Greenfield Highway (NH-119D) Project (Package-IV of Amas-Darbhanga Expressway) | 1952 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 21857.5 | Under Implementation | Hybrid Annuity | October 2024 | Bela nawada | Bihar | 01 Dec 2019 | Date of announcement | 2022-04-06 | 21857.5 | 15340 | 6517.5 | Y | 2024-12-31 | Initial completion date | 2024-10-31 | Y | 61 | 2022-05-06 | Bids awarded
103 | National Highways Authority Of India | 155597 | Baleshwar-Laxmannath Road Project | 162 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3018 | Completed | Engineering, Procurement & Construction | May 2007 | Baleshwar | Odisha | 01 Jan 2001 | Date of announcement | 2007-04-01 | 3018 | 2580 | 438 | Y | 2007-05-30 | Completed | 2007-03-31 | Y | 60 | 2001-03-16 | Bids awarded
104 | National Highways Authority Of India | 155597 | Baletiya village-Nani Bhadol village Eight Lane Access-Controlled Expressway Project (Package 30 of Delhi-Mumbai Expressway) | 1634 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11853.3 | Under Implementation | Engineering, Procurement & Construction | September 2023 | Baletiya | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 11853.3 | 9263.8 | 2589.5 | Y | 2023-09-07 | Completion expected by | 2021-12-31 | Y | 615 | 2020-10-05 | Bids awarded
105 | National Highways Authority Of India | 155597 | Balongi-Khanpur Flyover Project (Mohali-Kharar) | 1194 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4480 | Completed |  | February 2021 | Balongi | Punjab | 01 Apr 2015 | Date of announcement | 2018-01-01 | 4480 | 3680 | 800 | Y | 2021-02-26 | Completed | 2018-06-30 | Y | 972 | 2015-09-30 | Bids awarded
106 | National Highways Authority Of India | 155597 | Balotra (Siwana)-Mokalsar (NH-325) Highway Project (Package-I) (Jalore-Badmer-Sirohi) | 1269 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1312.8 | Completed | Engineering, Procurement & Construction | September 2020 | Balotra | Rajasthan | 06 Sep 2015 | Date of announcement | 2020-09-14 | 1312.8 | 1564.3 | -251.5 | N
107 | National Highways Authority Of India | 155597 | Balwara-Dhangaon (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package III) (Bharatmala) | 1852 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10020 | Under Implementation | Engineering, Procurement & Construction |  | Balwara | Madhya Pradesh | 27 Jul 2016 | Date of announcement | 2021-09-16 | 10020 | 7746.8 | 2273.2 | Y | [5 empty] | 2021-06-23 | Bids awarded
108 | National Highways Authority Of India | 155597 | Bamitha-Khajuraho (NH-339B) Four Lane Highway Project | 1435 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 720 | Under Implementation | Engineering, Procurement & Construction | October 2023 | Bamitha | Madhya Pradesh | 26 Dec 2017 | Date of announcement | 2022-10-29 | 720 | 1023.2 | -303.2 | N | [5 empty] | 2021-11-28 | Bids awarded
109 | National Highways Authority Of India | 155597 | Bamni-Rajura-Warur-Devada MH/TG Border Four Lane Road (NH-930D) Project | 1987 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10670.6 | Under Implementation | Hybrid Annuity |  | Bamni | Maharashtra | 01 Apr 2020 | Date of announcement | 2022-02-18 | 10670.6 | 10670.6 | 0 | N | [5 empty] | 2022-03-30 | Bids awarded
110 | National Highways Authority Of India | 155597 | Bangalore Satellite Town Six Lane Ring Road (STRR) Project (Bharatmala) | 1610 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 150000 | Under Implementation | Hybrid Annuity | March 2024 | Belagondapalli | Tamil Nadu | 01 Apr 2005 | Date of announcement | 2023-03-19 | 150000 | 100000 | 50000 | Y | [5 empty] | 2022-03-30 | Bids awarded
111 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 148700 | Under Implementation | Hybrid Annuity | December 2024 | Bangalore | Karnataka | 01 Dec 2008 | Date of announcement | 2022-05-24 | 148700 | 40000 | 108700 | Y | 2024-12-31 | Completion expected by | 2013-06-30 | Y | 4202 | 2021-03-04 | Bids awarded
112 | National Highways Authority Of India | 155597 | Bangalore-Hoskote-Mulbagal (NH-4) Highway Project | 395 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10700 | Completed | Build Operate Transfer | June 2011 | Bangalore | Karnataka | 31 Mar 2005 | Date of announcement | 2011-04-30 | 10700 | 5650 | 5050 | Y | 2011-06-30 | Initial completion date | 2010-07-30 | Y | 335
113 | National Highways Authority Of India | 155597 | Bangalore-Hosur (NH-7) Six Laning Highway Project | 408 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1138.4 | Completed | Build Operate Transfer | April 2010 | Karnataka | Karnataka | 31 Mar 2005 | Date of announcement | 2010-02-28 | 1138.4 | 4500 | -3361.6 | N | 2010-04-30 | Completed | 2008-12-31 | Y | 485
114 | National Highways Authority Of India | 155597 | Bangalore-Nelamangala (NH-4) Highway Project | 397 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8034 | Completed | Build Operate Transfer Toll | December 2010 | Bangalore | Karnataka | 31 Mar 2005 | Date of announcement | 2010-08-31 | 8034 | 4000 | 4034 | Y | 2010-12-10 | Completed | 2010-04-30 | Y | 224
115 | National Highways Authority Of India | 155597 | Bangalore-Salem-Madurai (NS-27/TN) Highway Project | 54 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 214 | Completed | Engineering, Procurement & Construction | April 2004 | Bangalore | Karnataka | 01 Mar 1999 | Date of announcement | 2002-01-01 | 214 | 300 | -86 | N | 2004-04-30 | Completed | 2002-11-30 | Y | 517
116 | National Highways Authority Of India | 155597 | Bani village to Bardawadi village of Mandsaur Eight Lane Carriageway Project (Package 19 of Delhi-Mumbai Expressway) | 1572 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8400 | Under Implementation | Engineering, Procurement & Construction |  | Bani village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2021-07-29 | 8400 | 8806.2 | -406.2 | N | [5 empty] | 2020-02-11 | Bids awarded
117 | National Highways Authority Of India | 155597 | Banjhula (Chakia)-Shivhar-Bairgania (NH-227F) Two Laning Highway project (Bharatmala) | 1653 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10000 | Under Implementation | Engineering, Procurement & Construction |  | Bairgania | Bihar | 01 Mar 2004 | Date of announcement | 2018-05-25 | 10000 | 10000 | 0 | N
118 | National Highways Authority Of India | 155597 | Bankhandi-Jhalera (NH-503A) Highway Project | 1832 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 250 | No Information |  |  | Bankhandi | Himachal Pradesh | 01 Jul 2014 | Date of announcement | 2020-06-09 | 250 | 175 | 75 | Y
119 | National Highways Authority Of India | 155597 | Banwara-Bettadahalli (NH-206) Four Lane Highway Project (section of Tumkur-Shimoga Package-3) (Bharatmala) | 1788 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7549 | Under Implementation | Hybrid Annuity | February 2024 | Banwara | Karnataka | 06 Mar 2014 | Date of announcement | 2021-11-14 | 7549 | 9403.8 | -1854.8 | N | [5 empty] | 2018-03-07 | Bids awarded
120 | National Highways Authority Of India | 155597 | Baonli-Jhalai Road to Start of RoB near village Itawa Eight Lane Carriageway Project (Package 9 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1559 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8081.1 | Under Implementation | Engineering, Procurement & Construction |  | Baonli-jhalai road | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 8081.1 | 8081.1 | 0 | N | [5 empty] | 2020-02-26 | Bids awarded
121 | National Highways Authority Of India | 155597 | Bar-Bilara-Jodhpur (NH-112) (New NH-25) Four Lane Highway Project | 1155 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8951.8 | Completed | Engineering, Procurement & Construction | May 2023 | Barr | Rajasthan | 31 Mar 2009 | Date of announcement | 2016-02-11 | 8951.8 | 4000 | 4951.8 | Y | 2023-05-10 | Completed | 2019-09-30 | Y | 1318 | 2016-06-30 | Bids awarded
122 | National Highways Authority Of India | 155597 | Barabanki-Bahraich (NH-28C) Highway Widening Project | 945 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6960.5 | Completed | Engineering, Procurement & Construction | March 2019 | Bahraich | Uttar Pradesh | 21 Oct 2009 | Date of announcement | 2016-06-10 | 6960.5 | 6010.5 | 950 | Y | 2019-03-07 | Completed | 2018-12-31 | Y | 66 | 2014-04-30 | Bids awarded
123 | National Highways Authority Of India | 155597 | Barachatti-Gorhar (GTRIP/V-B) Highway Project | 158 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4527.1 | Completed | Engineering, Procurement & Construction | July 2007 | Barachatti | Bihar | 01 Jun 2001 | Date of announcement | 2002-01-01 | 4527.1 | 3200 | 1327.1 | Y | 2007-07-31 | Completed | 2004-11-30 | Y | 973 | 2002-02-28 | Bids awarded
124 | National Highways Authority Of India | 155597 | Baramati-Indapur Four Lane Highway (NH-965G) (Package-II of Sant Tukaram Maharaj Palkhi Marg) Project | 1897 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14710 | Under Implementation | Engineering, Procurement & Construction |  | Baramati | Maharashtra | 01 Mar 2018 | Date of announcement | 2021-11-08 | 14710 | 8068.7 | 6641.3 | Y | [5 empty] | 2021-03-27 | Bids awarded
125 | National Highways Authority Of India | 155597 | Barasat-Krishnanagar (NH-34) Four-Laning Highway Project (Bharatmala) | 1399 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 26000 | Under Implementation | Build Operate Transfer |  | Barasat | West Bengal | 01 Oct 2009 | Date of announcement | 2017-11-28 | 26000 | 8670 | 17330 | Y | [5 empty] | 2011-02-23 | Bids awarded
126 | National Highways Authority Of India | 155597 | Barasat-Raiganj (NH-34) Highway Project | 239 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 10857 | No Information |  |  | Barasat | West Bengal | 01 Dec 2002 | Date of announcement | 2002-12-01 | 10857 | 10857 | 0 | N
127 | National Highways Authority Of India | 155597 | Bardawadi village of Mandsaur to Kamliya village of Ratlam Eight Lane Carriageway Project (Package 20 of Delhi-Mumbai Expressway) | 1573 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7440 | Completed | Engineering, Procurement & Construction | April 2023 | Bardawadi village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 7440 | 7366.7 | 73.3 | Y | 2023-04-01 | Completed | 2021-12-05 | Y | 482 | 2019-03-08 | Bids awarded
128 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 26010 | Under Implementation | Design Build Finance Operate Transfer |  | Bareily | Uttar Pradesh | 30 Apr 2009 | Date of announcement | 2018-01-31 | 26010 | 10460 | 15550 | Y | [5 empty] | 2010-05-11 | Bids awarded
129 | National Highways Authority Of India | 155597 | Barhi-Hazaribagh (NH-33) Four-Laning Highway Project | 1090 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5000 | Completed | Engineering, Procurement & Construction | February 2021 | Barhi | Jharkhand | 30 Dec 2009 | Date of announcement | 2020-06-13 | 5000 | 4143.4 | 856.6 | Y | 2021-02-18 | Completed | 2014-02-28 | Y | 2547 | 2010-05-31 | Bids awarded
130 | National Highways Authority Of India | 155597 | Barhi-Koderma (NH-31) Four Laning Highway Project | 1239 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6657.5 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Barhi | Jharkhand | 01 Dec 2015 | Date of announcement | 2022-12-21 | 6657.5 | 2823.8 | 3833.7 | Y | 2023-06-30 | Completion expected by | 2021-11-17 | Y | 590 | 2018-01-31 | Bids awarded
131 | National Highways Authority Of India | 155597 | Barhi-Rajauli (NH-31) Four Laning Highway Project | 1251 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4520 | Under Implementation |  |  | Barhi | Jharkhand | 01 Apr 2008 | Date of announcement | 2016-09-06 | 4520 | 5180 | -660 | N
132 | National Highways Authority Of India | 155597 | Barmer-Sanchore-Gujarat Border (upto Gandhav Bridge) (NH-15) Two/Four Lane Highway Project | 1025 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5380.8 | Completed | Engineering, Procurement & Construction | January 2019 | Barmer | Rajasthan | 15 Jan 2014 | Date of announcement | 2015-01-09 | 5380.8 | 3745.1 | 1635.7 | Y | 2022-02-12 | Initial completion date | 2017-07-31 | Y | 1657 | 2015-01-09 | Bids awarded
133 | National Highways Authority Of India | 155597 | Barwa-Adda--Barakar Highway Project | 160 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1200 | Completed | Engineering, Procurement & Construction | December 2001 | Adda | West Bengal | 01 Jan 1999 | Date of announcement | 1999-01-01 | 1200 | 1200 | 0 | N | 2001-12-31 | Completed | 2001-06-30 | Y | 184 | 1999-03-15 | Bids awarded
134 | National Highways Authority Of India | 155597 | Basanwahi-Marangpuri Six Lane Highway (Package CG3) (NH-130CD) Project (Section of Raipur-Visakhapatnam Economic Corridor) | 1947 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11273.3 | Under Implementation | Hybrid Annuity |  | Basanwahi | Chhattisgarh | 01 Jul 2019 | Date of announcement | 2022-01-12 | 11273.3 | 11273.3 | 0 | N | [5 empty] | 2022-03-30 | Bids awarded
135 | National Highways Authority Of India | 155597 | Basukinath-Jarmundi-Deoghar (NH-114A) Four Lane Highway Project | 1311 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14000 | Under Implementation | Hybrid Annuity |  | Basukinath | Jharkhand | 13 Jun 2017 | Date of announcement | 2018-03-11 | 14000 | 14000 | 0 | N | [5 empty] | 2023-03-16 | Bids awarded
136 | National Highways Authority Of India | 155597 | Bata-Rehukaldhar (Tunnel) (NH-21) Highway Project (Package-III of Nerchowk-Kullu stretch) | 1045 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3774.3 | Under Implementation | Hybrid Annuity |  | Bata | Himachal Pradesh | 01 Nov 2014 | Date of announcement | 2014-12-03 | 3774.3 | 3774.3 | 0 | N | [5 empty] | 2017-06-19 | Bids awarded
137 | National Highways Authority Of India | 155597 | Bathinda-Malout intersection (NH-7) Four Lane Highway Project | 1771 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4538.3 | Completed | Engineering, Procurement & Construction | April 2022 | Bathinda | Punjab | 31 Jan 2019 | Date of announcement | 2019-12-31 | 4538.3 | 4397.1 | 141.2 | Y | 2022-07-12 | Initial completion date | 2022-04-06 | Y | 97 | 2019-11-27 | Bids awarded
138 | National Highways Authority Of India | 155597 | Bawadi village (Shivgarh)-Ranni Village Eight Lane Carriageway Project (Package 23 of Delhi-Vadodara Expressway (Delhi-Mumbai Expressway) (Bharatmala) | 1600 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10470 | Completed | Engineering, Procurement & Construction | February 2023 | Bawadi village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 10470 | 11398.9 | -928.9 | N | 2023-02-20 | Completed | 2021-12-31 | Y | 416 | 2019-08-07 | Bids awarded
139 | National Highways Authority Of India | 155597 | Bawal Chowk Flyover Project | 1972 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 230 | Under Implementation |  |  | Bawal | Haryana | 01 Jun 2015 | Date of announcement | 2021-12-06 | 230 | 240 | -10 | N
140 | National Highways Authority Of India | 155597 | Bawana (Delhi)-Sonepat-Panipat-Uchana-Indri-Yamunanagar Expressway Project | 1340 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 80000 | No Information |  |  | Bawana | NCT of Delhi | 01 Dec 2014 | Date of announcement | 2019-12-18 | 80000 | 10000 | 70000 | Y
141 | National Highways Authority Of India | 155597 | Bawana Industrial Area (Delhi)-Barwasani Bypass (Sonipat) (NH-352A) Link Road Project (Package 4 of Delhi 3rd Ring Road or UER-2) | 1683 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7412.5 | Under Implementation | Engineering, Procurement & Construction | October 2023 | Barwasani bypass | Haryana | 01 Apr 2016 | Date of announcement | 2019-12-26 | 7412.5 | 7648.9 | -236.4 | N | [5 empty] | 2021-07-29 | Bids awarded
142 | National Highways Authority Of India | 155597 | Beawar-Gomti (NH-8) Four Laning Highway Project | 1820 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7216.2 | Under Implementation | Engineering, Procurement & Construction |  | Beawar | Rajasthan | 01 Apr 2009 | Date of announcement | 2021-07-26 | 7216.2 | 12000 | -4783.8 | N | [5 empty] | 2012-03-28 | Bids awarded
143 | National Highways Authority Of India | 155597 | Belekeri Port-Kumta-Sirsi (SH-69) Two Lane Highway Project | 1759 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4401.6 | Under Implementation | Engineering, Procurement & Construction |  | Belekeri port | Karnataka | 31 Jan 2018 | Date of announcement | 2019-12-31 | 4401.6 | 3704 | 697.6 | Y | [5 empty] | 2018-03-27 | Bids awarded
144 | National Highways Authority Of India | 155597 | Belgaum Bypass Project | 112 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1260 | Completed | Engineering, Procurement & Construction | June 2006 | Belgaum | Karnataka | 01 Mar 2001 | Date of announcement | 2005-01-01 | 1260 | 800 | 460 | Y | 2006-06-30 | Completed | 2003-12-31 | Y | 912 | 2001-06-01 | Bids awarded
145 | National Highways Authority Of India | 155597 | Belgaum Western & Eastern (NH-4,4A&SH-54) Bypass Project | 1324 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 15000 | Under Implementation | Hybrid Annuity |  | Belgaum | Karnataka | 21 Aug 2017 | Date of announcement | 2018-02-19 | 15000 | 15000 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
146 | National Highways Authority Of India | 155597 | Belgaum-Hungund-Raichur Four Lane Highway (NH-748A) Project (Part of Hyderabad-Panaji Economic Corridor) | 2103 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 125000 | Under Implementation | Hybrid Annuity |  | Belgaum | Karnataka | 01 Nov 2020 | Date of announcement | 2022-12-01 | 125000 | 125000 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
147 | National Highways Authority Of India | 155597 | Belghoria Expressway Project | 931 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9000 | Completed |  | December 2006 | Belgharia | West Bengal | 30 Dec 1967 | Date of announcement | 2006-10-01 | 9000 | 1080 | 7920 | Y | 2006-12-31 | Completed | 2006-10-31 | Y | 61
148 | National Highways Authority Of India | 155597 | Belghoria Expressway Renovation Project | 885 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 300 | No Information |  |  | Belghoria | West Bengal | 04 Jun 2011 | Date of announcement | 2011-06-04 | 300 | 300 | 0 | N
149 | National Highways Authority Of India | 155597 | Bellampalli-Gadchiroli Four Lane Greenfield Express Highway Project (Annaram Village to Veeravelli Village) (Part of Hyderabad Raipur Economic Corridor) | 3000 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 105780 | Under Implementation |  |  | Bellampalli | Telangana | 01 Jan 2023 | Date of announcement | 2023-03-01 | 105780 | 105780 | 0 | N
150 | National Highways Authority Of India | 155597 | Betul-Indore-Nagpur Road Project | 421 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11046.1 | No Information |  |  | Betul | Madhya Pradesh | 30 Nov 2005 | Date of announcement | 2005-11-30 | 11046.1 | 11046.1 | 0 | N
151 | National Highways Authority Of India | 155597 | Beypore-Malapparamba Four-Lane Road Project (Bharatmala) | 1488 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4000 | Under Implementation |  |  | Beypore | Kerala | 01 Jul 2017 | Date of announcement | 2017-10-26 | 4000 | 4000 | 0 | N
152 | National Highways Authority Of India | 155597 | Bhadohi-Mariahu-Jaunpur (NH-135A) Highway Project | 1936 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Under Implementation |  |  | Bhadohi | Uttar Pradesh | 01 Apr 2017 | Date of announcement | 2022-10-16 | 2000 | 3950 | -1950 | N
153 | National Highways Authority Of India | 155597 | Bhadrak-Baleshwar (NH-16) Six Lane Highway Project (Package-II) | 1023 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22968.2 | Under Implementation | Hybrid Annuity |  | Baleshwar | Odisha | 25 Mar 2011 | Date of announcement | 2015-02-19 | 22968.2 | 13800 | 9168.2 | Y
154 | National Highways Authority Of India | 155597 | Bhadrak-Chandikhole (OR-II) Highway Project | 137 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3053 | Completed | Engineering, Procurement & Construction | May 2005 | Bhadrak | Odisha | 01 Nov 2000 | Date of announcement | 2002-01-01 | 3053 | 2840 | 213 | Y | 2006-09-30 | Initial completion date | 2003-10-31 | Y | 1065 | 2000-12-31 | Bids awarded
155 | National Highways Authority Of India | 155597 | Bhamaiya village-Baletiya village Eight Lane Access-Controlled Expressway Project (Package 29 of Delhi-Mumbai Expressway) | 1635 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11215.8 | Under Implementation | Engineering, Procurement & Construction |  | Baletiya | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 11215.8 | 7831.4 | 3384.4 | Y | [5 empty] | 2020-03-30 | Bids awarded
156 | National Highways Authority Of India | 155597 | Bhandara (Wainganga)-Durg Highway Project | 441 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10000 | Completed | Build Operate Transfer | March 2009 | Bhandara | Maharashtra | 18 Jan 2007 | Date of announcement | 2007-01-18 | 10000 | 10000 | 0 | N
157 | National Highways Authority Of India | 155597 | Bhandara Bypass Flyover Project | 1204 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5000 | No Information |  |  | Bhandara | Maharashtra | 18 Aug 2016 | Date of announcement | 2016-08-18 | 5000 | 5000 | 0 | N
158 | National Highways Authority Of India | 155597 | Bhaniyawala-Jollygrant-Rishikesh (NH-07) Four Lane Highway Project | 2123 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10362.3 | Announced | Hybrid Annuity | December 2025 | Bhaniyawala | Uttarakhand | 01 Jan 2022 | Date of announcement | 2023-02-09 | 10362.3 | 8924.4 | 1437.9 | Y
159 | National Highways Authority Of India | 155597 | Bharauli (Buxar)-Haidariya (NH-31) Four Lane Greenfield Link Road Project (connecting Purvanchal Expressway) | 2070 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6180 | Under Implementation |  |  | Bharauli | Bihar | 01 Jan 2022 | Date of announcement | 2022-10-13 | 6180 | 6180 | 0 | N
160 | National Highways Authority Of India | 155597 | Bharuch to Surat Package BOT- II Highway Project | 213 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4488.7 | Completed | Build Operate Transfer | September 2009 | Bharuch | Gujarat | 01 Dec 2001 | Date of announcement | 2009-07-01 | 4488.7 | 370 | 4118.7 | Y | 2009-09-05 | Completed | 2009-07-31 | Y | 36
161 | National Highways Authority Of India | 155597 | Bhavnagar-Sosiya-Alang Ship Recycling Yard Alternative Road Project (Bharatmala) | 1359 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6965 | Under Implementation |  | February 2024 | Alang ship recycling yard | Gujarat | 01 Apr 2016 | Date of announcement | 2020-08-09 | 6965 | 705.5 | 6259.5 | Y
162 | National Highways Authority Of India | 155597 | Bhavnagar-Talaja (NH-8E) (Package-I Bhavnagar-Veraval Section) Four/Six Lane Highway Project | 927 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9981.8 | Completed | Hybrid Annuity | August 2020 | Bhavnagar | Gujarat | 03 May 2012 | Date of announcement | 2016-05-26 | 9981.8 | 8411.8 | 1570 | Y | 2020-08-11 | Completed | 2015-09-30 | Y | 1777 | 2016-05-26 | Bids awarded
163 | National Highways Authority Of India | 155597 | Bheem-Parsoli (NH-148 D) Two Lane Highway Project (Phase 2) | 1013 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1138 | Completed |  | April 2016 | Bheem | Rajasthan | 02 Nov 2012 | Date of announcement | 2012-11-02 | 1138 | 1138 | 0 | N | 2016-04-30 | Completed | 2016-01-31 | Y | 90 | 2013-04-15 | Bids awarded
164 | National Highways Authority Of India | 155597 | Bheem-Parsoli Two Lane (Phase 1) Highway Widening Project | 1012 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1002.9 | Completed |  | April 2016 | Bheem | Rajasthan | 02 Nov 2012 | Date of announcement | 2012-11-02 | 1002.9 | 1002.9 | 0 | N | 2016-04-30 | Initial completion date | 2016-01-31 | Y | 90 | 2013-04-15 | Bids awarded
165 | National Highways Authority Of India | 155597 | Bhiladi-Jetpur NH-8B (Package 2) Project | 167 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3998.9 | Completed | Engineering, Procurement & Construction | January 2009 | Bhiladi | Gujarat | 01 Nov 2002 | Date of announcement | 2009-01-01 | 3998.9 | 3000 | 998.9 | Y | 2009-02-01 | Initial completion date | 2009-01-31 | N |  | 2005-02-15 | Bids awarded
166 | National Highways Authority Of India | 155597 | Bhilwara-Ladpura (NH-758) Two Lane Road Project | 916 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3530 | Completed | Engineering, Procurement & Construction | August 2018 | Bhilwara | Rajasthan | 10 Sep 2012 | Date of announcement | 2017-10-31 | 3530 | 2400 | 1130 | Y | 2018-08-31 | Completed | 2016-03-31 | Y | 883 | 2013-09-30 | Bids awarded
167 | National Highways Authority Of India | 155597 | Bhilwara-Rajsamand (NH-758) Carriageway Improvement Project | 874 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 115.5 | No Information | Build Operate Transfer |  | Bhilwara | Rajasthan | 11 Oct 2011 | Date of announcement | 2011-10-11 | 115.5 | 115.5 | 0 | N
168 | National Highways Authority Of India | 155597 | Bhiwani-Hansi (NH-148B) Four Lane Highway Project | 2073 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13221.3 | Under Implementation | Hybrid Annuity |  | Bhiwani | Haryana | 01 Jan 2022 | Date of announcement | 2022-11-24 | 13221.3 | 13949.1 | -727.8 | N | [5 empty] | 2023-03-07 | Bids awarded
169 | National Highways Authority Of India | 155597 | Bhogpur to Jalandhar (NS-16/PB) Highway Project | 197 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 711.8 | Completed | Engineering, Procurement & Construction | October 2004 | Bhogpur | Punjab | 01 Mar 2001 | Date of announcement | 2003-01-01 | 711.8 | 715 | -3.2 | N | 2004-10-31 | Completed | 2003-07-31 | Y | 458 | 2001-08-01 | Bids awarded
170 | National Highways Authority Of India | 155597 | Bhogpur-Mukerian (NH-1A) Four Laning Highway project | 768 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3600 | Completed | Engineering, Procurement & Construction | January 2014 | Bhogpur | Punjab | 01 Jan 2010 | Date of announcement | 2010-01-01 | 3600 | 3600 | 0 | N | 2014-03-31 | Initial completion date | 2012-07-30 | Y | 609 | 2010-01-05 | Bids awarded
171 | National Highways Authority Of India | 155597 | Bhogu-Sankha (NH-75) Four Lane Highway Project (Package-3) | 2048 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13910 | Under Implementation | Hybrid Annuity |  | Bhogu | Jharkhand | 01 Apr 2018 | Date of announcement | 2023-03-23 | 13910 | 11700 | 2210 | Y | [5 empty] | 2022-10-31 | Bids awarded
172 | National Highways Authority Of India | 155597 | Bhojpur-Buxar (NH-84 & NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1088 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17280 | Completed | Engineering, Procurement & Construction | November 2022 | Bhojpur | Bihar | 12 Aug 2008 | Date of announcement | 2022-11-14 | 17280 | 5937.7 | 11342.3 | Y | 2022-12-31 | Initial completion date | 2020-10-30 | Y | 792 | 2011-11-12 | Bids awarded
173 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3045.8 | Completed | Engineering, Procurement & Construction | August 2020 | Bhopal | Madhya Pradesh | 30 Apr 2009 | Date of announcement | 2020-08-25 | 3045.8 | 2090 | 955.8 | Y | 2020-08-25 | Completed | 2013-06-30 | Y | 2613 | 2010-05-30 | Bids awarded
174 | National Highways Authority Of India | 155597 | Bhuban-Dubari-Chandikhole (NH-200) Four Lane Highway Project | 925 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7322.2 | No Information | Build Operate Transfer Toll |  | Bhuban | Odisha | 07 Sep 2012 | Date of announcement | 2012-09-07 | 7322.2 | 7322.2 | 0 | N
175 | National Highways Authority Of India | 155597 | Bhubaneshwar-Ichapuram Six Laning Highway Project | 865 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18600 | Shelved | Build Operate Transfer Toll |  | Bhubaneshwar | Odisha | 01 Jul 2011 | Date of announcement | 2011-07-01 | 18600 | 18600 | 0 | N
176 | National Highways Authority Of India | 155597 | Bhubaneshwar-Khurda (OR-I) Highway Project | 139 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1495 | Completed |  | October 2013 | Bhubaneshwar | Odisha | 30 Apr 2000 | Date of announcement | 2010-03-31 | 1495 | 1190 | 305 | Y | 2013-10-31 | Completed | 2003-12-31 | Y | 3592 | 2000-12-31 | Bids awarded
177 | National Highways Authority Of India | 155597 | Bhubaneshwar-Puri (NH-203) Four-Laning Highway Project | 1402 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6800 | Completed | Engineering, Procurement & Construction | February 2019 | Bhubaneshwar | Odisha | 01 Jan 2007 | Date of announcement | 2017-04-30 | 6800 | 5002.9 | 1797.1 | Y | 2019-02-06 | Completed | 2013-06-30 | Y | 2047 | 2010-05-07 | Bids awarded
178 | National Highways Authority Of India | 155597 | Bhubbu Jot Tunnel Project | 1502 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5290 | Under Implementation |  |  | Jogindernagar | Himachal Pradesh | 15 Aug 2009 | Date of announcement | 2013-12-04 | 5290 | 857.5 | 4432.5 | Y
179 | National Highways Authority Of India | 155597 | Bidar-Kalaburagi-Ballary Four Lane Road Project | 2088 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 76500 | Announced |  |  | Ballary | Karnataka | 17 Sep 2022 | Date of announcement | 2023-02-17 | 76500 | 76500 | 0 | N
180 | National Highways Authority Of India | 155597 | Bihar (NH -2) Project | 42 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1876 | No Information |  |  | Bihar | Bihar | 01 Mar 1995 | Date of announcement | 2001-04-01 | 1876 | 1506.7 | 369.3 | Y
181 | National Highways Authority Of India | 155597 | Bihar/Jharkhand Border (Chordaha)-Gorhar (NH-2) Six Laning Highway Project (Package-II) | 1113 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16116.8 | Under Implementation | Engineering, Procurement & Construction | October 2023 | Barwa-Adda | Jharkhand | 01 Jun 2011 | Date of announcement | 2022-12-17 | 16116.8 | 9816.1 | 6300.7 | Y | 2023-10-31 | Completion expected by | 2020-08-07 | Y | 1180 | 2012-03-31 | Bids awarded
182 | National Highways Authority Of India | 155597 | Biharsharif-Barbigha-Mokama (NH-82) Two Laning Road Project | 821 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5097.5 | Completed | Engineering, Procurement & Construction | March 2021 | Biharsharif | Bihar | 22 Nov 2010 | Date of announcement | 2020-04-30 | 5097.5 | 3040 | 2057.5 | Y | 2021-03-23 | Completed | 2019-04-30 | Y | 693 | 2015-08-30 | Bids awarded
183 | National Highways Authority Of India | 155597 | Bijapur-Gulbarga-Humnabad (NH-218) Two lane Highway Project | 934 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7090 | Completed | Engineering, Procurement & Construction | September 2019 | Bijapur | Karnataka | 26 Jul 2012 | Date of announcement | 2014-10-27 | 7090 | 6807.3 | 282.7 | Y | 2019-12-31 | Initial completion date | 2017-09-30 | Y | 822 | 2014-12-31 | Bids awarded
184 | National Highways Authority Of India | 155597 | Bijni-Assam/WB Border (NH-31C) Four-Laning Highway Project | 284 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8530 | Under Implementation | Engineering, Procurement & Construction |  | Bijni | Assam | 01 Dec 2003 | Date of announcement | 2018-02-28 | 8530 | 2300 | 6230 | Y
185 | National Highways Authority Of India | 155597 | Bijnor-Kotawali (Nagina) (NH-709AD) Four Lane Highway Project (Package 4 of Panipat-Nagina Highway) | 1643 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2670 | Under Implementation | Engineering, Procurement & Construction |  | Bijnor | Uttar Pradesh | 10 Jun 2016 | Date of announcement | 2019-02-20 | 2670 | 2099.7 | 570.3 | Y | [5 empty] | 2021-07-22 | Bids awarded
186 | National Highways Authority Of India | 155597 | Biju Para-Kuru (NH-75) Four Laning Highway Project (Package-II) | 1227 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1542.7 | Completed | Engineering, Procurement & Construction | September 2019 | Biju para | Jharkhand | 09 Nov 2016 | Date of announcement | 2016-11-09 | 1542.7 | 1542.7 | 0 | N | 2019-09-25 | Completed | 2018-05-31 | Y | 482 | 2017-03-31 | Bids awarded
187 | National Highways Authority Of India | 155597 | Bilaspur Chowk Flyover Project | 1971 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 342.7 | Under Implementation |  |  | Bilaspur chowk | Haryana | 01 Jan 2013 | Date of announcement | 2022-03-09 | 342.7 | 230 | 112.7 | Y
188 | National Highways Authority Of India | 155597 | Binjhabahal-Telebani (NH-49) Four Laning Highway Project | 1021 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11614 | Completed | Hybrid Annuity | August 2021 | Binjhabahal | Odisha | 19 Nov 2013 | Date of announcement | 2017-10-31 | 11614 | 8588.4 | 3025.6 | Y | 2021-08-05 | Completed | 2020-07-31 | Y | 370 | 2016-10-13 | Bids awarded
189 | National Highways Authority Of India | 155597 | Binnamangala FOB Project | 828 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Binnamangala | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N
190 | National Highways Authority Of India | 155597 | Bodare-Dhule (NH-52) Four/Six Laning Highway Project | 1149 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10070 | Under Implementation | Hybrid Annuity |  | Bodare | Maharashtra | 15 Jul 2010 | Date of announcement | 2022-04-22 | 10070 | 8396.4 | 1673.6 | Y | [5 empty] | 2017-03-02 | Bids awarded
191 | National Highways Authority Of India | 155597 | Bokaro-Chas (NH-23) bridge over Garga river Project | 987 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 50.8 | Completed |  | April 2016 | Bokaro | Jharkhand | 01 Apr 2010 | Date of announcement | 2014-05-28 | 50.8 | 35.8 | 15 | Y | 2016-04-06 | Completed | 2014-10-31 | Y | 523
192 | National Highways Authority Of India | 155597 | Boregaon Buzurg to Shahpur Four Lane Road (NH-753L) Project (Package-I of Boregaon Buzurg-Muktainagar Road) | 2079 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11187.8 | Under Implementation | Hybrid Annuity |  | Borgaon buzurg | Madhya Pradesh | 01 Jul 2022 | Date of announcement | 2022-08-31 | 11187.8 | 11187.8 | 0 | N | [5 empty] | 2022-12-23 | Bids awarded
193 | National Highways Authority Of India | 155597 | Borkhedi-Jam (NS-22/MH) Highway Project | 258 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1150 | Completed | Engineering, Procurement & Construction | June 2015 | Borkhedi | Maharashtra | 31 Dec 2003 | Date of announcement | 2012-11-30 | 1150 | 1100 | 50 | Y | 2015-06-30 | Completed | 2009-03-31 | Y | 2282
194 | National Highways Authority Of India | 155597 | Bowdara-Vizianagaram (NH-516E) Two Lane Highway Project | 1863 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1595.1 | Under Implementation |  |  | Bowdara | Andhra Pradesh | 01 Apr 2019 | Date of announcement | 2020-10-04 | 1595.1 | 1595.1 | 0 | N
195 | National Highways Authority Of India | 155597 | Brahmani Bypass (End of NH-23)-Rajamunda (NH-143) Four Laning Highway Project (Birmitrapur-Barkote) | 981 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8600.5 | Under Implementation | Engineering, Procurement & Construction |  | Barkote | Odisha | 25 Oct 2010 | Date of announcement | 2015-04-09 | 8600.5 | 8200 | 400.5 | Y | [5 empty] | 2012-03-27 | Bids awarded
196 | National Highways Authority Of India | 155597 | Brahmaputra Express Highway Project | 1279 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 645640 | Announced & Stalled |  |  | Dhubri | Assam | 24 Jan 2017 | Date of announcement | 2017-06-12 | 645640 | 400000 | 245640 | Y
197 | National Highways Authority Of India | 155597 | Brahmputra Bridge (AS-28) Project | 281 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4537 | Completed | Engineering, Procurement & Construction | July 2019 | Brhmaputra | Assam | 01 Dec 2003 | Date of announcement | 2019-07-19 | 4537 | 2176.1 | 2360.9 | Y | 2019-07-19 | Completed | 2010-04-30 | Y | 3367 | 2006-05-01 | Bids awarded
198 | National Highways Authority Of India | 155597 | Bridge Across Narikulam Tank Project | 1278 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 210 | Completed |  | March 2019 | Narikulam tank | Tamil Nadu | 13 Jan 2017 | Date of announcement | 2017-04-04 | 210 | 210 | 0 | N | 2019-03-01 | Completed | 2018-07-31 | Y | 213
199 | National Highways Authority Of India | 155597 | Bridge Over Besu River (on Ghajipur-Balia NH-31 Highway) Project | 2094 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 110 | Completed |  | February 2023 | Besu river | Uttar Pradesh | 01 Oct 2019 | Date of announcement | 2019-10-14 | 110 | 110 | 0 | N
200 | National Highways Authority Of India | 155597 | Bridge Over River Jia Bharali (NH-715) Project | 487 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8040 | Under Implementation |  | August 2023 | Assam | Assam | 24 Jul 2008 | Date of announcement | 2021-07-29 | 8040 | 8040 | 0 | N | [5 empty] | 2020-12-21 | Bids awarded
201 | National Highways Authority Of India | 155597 | Bridge over Rapti River at Gorakhpur (Addl. 2 Lane) Project | 956 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 146 | Completed | Engineering, Procurement & Construction | June 2007 | Rapti River | Uttar Pradesh | 01 Feb 2004 | Date of announcement | 2004-02-01 | 146 | 146 | 0 | N | [5 empty] | 2004-03-15 | Bids awarded
202 | National Highways Authority Of India | 155597 | Budhel Junction-Nari Circle (NH-51) Four Lane Road (Missing Link) Project | 1805 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1866 | Under Implementation | Engineering, Procurement & Construction |  | Budhel junction | Gujarat | 22 Oct 2019 | Date of announcement | 2019-10-22 | 1866 | 1866 | 0 | N | [5 empty] | 2020-06-01 | Bids awarded
203 | National Highways Authority Of India | 155597 | Bugga-Kaipa (NH-544D) Two Lane Highway Project | 1431 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7023.4 | Under Implementation | Engineering, Procurement & Construction |  | Bugga | Andhra Pradesh | 20 Dec 2017 | Date of announcement | 2017-12-20 | 7023.4 | 7023.4 | 0 | N
204 | National Highways Authority Of India | 155597 | Butibori ROB (NS-29/MH) Project | 44 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 242.7 | Completed |  | September 2011 | Butibori | Maharashtra | 01 Sep 2002 | Date of announcement | 2011-09-30 | 242.7 | 247.2 | -4.5 | N | 2011-09-30 | Completed | 2008-11-30 | Y | 1034
205 | National Highways Authority Of India | 155597 | Butibori-MIDC T-Junction (NH-44) Flyover Project | 1276 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 700 | Completed | Engineering, Procurement & Construction | June 2021 | Butibori | Maharashtra | 29 Mar 2017 | Date of announcement | 2021-06-17 | 700 | 460.7 | 239.3 | Y | 2021-06-17 | Completed | 2020-05-31 | Y | 382
206 | National Highways Authority Of India | 155597 | Chambal Bridge (RJ-5) Project | 738 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2813.1 | Completed | Engineering, Procurement & Construction | August 2017 | Chambal | Rajasthan | 31 Dec 2003 | Date of announcement | 2003-12-31 | 2813.1 | 2813.1 | 0 | N | 2017-08-29 | Completed | 2010-02-28 | Y | 2739 | 2006-06-01 | Bids awarded
207 | National Highways Authority Of India | 155597 | Chambal Four/Six/Eight Lane Expressway Project (Chambal Progressway or Atal Progressway) | 1532 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 121703 | Under Implementation | Hybrid Annuity |  | Bhind | Madhya Pradesh | 31 Jan 2017 | Date of announcement | 2022-06-13 | 121703 | 60000 | 61703 | Y
208 | National Highways Authority Of India | 155597 | Champawati-Vishakhapatnam (AP-3) Highway Project | 103 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Completed | Engineering, Procurement & Construction | February 2005 | Champawati | Andhra Pradesh | 31 Mar 2001 | Expenses incurred upto | 2002-01-01 | 2000 | 1840 | 160 | Y | 2005-02-28 | Initial completion date | 2004-02-28 | Y | 366
209 | National Highways Authority Of India | 155597 | Chandesari-Khedakhajuria (NH-148) Four Lane Highway Project (Package 1 of Ujjain-Garoth Section) | 1883 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10340 | Under Implementation | Hybrid Annuity |  | Chandesari | Madhya Pradesh | 01 Jan 2019 | Date of announcement | 2022-02-24 | 10340 | 10340 | 0 | N | [5 empty] | 2022-02-28 | Bids awarded
210 | National Highways Authority Of India | 155597 | Chandigarh (Balongi)-Kharar Section (NH-21), (NH-205 & 05) Four Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1032 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7463.8 | Completed | Design Build Finance Operate Transfer | April 2021 | Chandigarh | Chandigarh | 01 Sep 2005 | Date of announcement | 2016-09-12 | 7463.8 | 4472.9 | 2990.9 | Y | 2021-04-29 | Completed | 2018-09-30 | Y | 942 | 2015-10-26 | Bids awarded
211 | National Highways Authority Of India | 155597 | Chandigarh-Manali (NH-21) Four Laning Highway Project | 1295 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 26000 | Under Implementation | Engineering, Procurement & Construction |  | Chandigarh | Chandigarh | 05 Feb 2010 | Date of announcement | 2016-06-20 | 26000 | 26000 | 0 | N | [5 empty] | 2016-10-26 | Bids awarded
212 | National Highways Authority Of India | 155597 | Chandikhol-Jagatpur Highway Project | 34 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1033.5 | Completed | Engineering, Procurement & Construction | January 2003 | Chandikhol | Odisha | 01 Sep 1998 | Date of announcement | 2003-01-01 | 1033.5 | 1370 | -336.5 | N | 2003-01-31 | Completed | 2002-12-31 | Y | 31 | 2000-02-01 | Bids awarded
213 | National Highways Authority Of India | 155597 | Chandikhole-Dubari-Talcher (NH-200 & NH-23) Four/Two Laning Highway Project | 517 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 14765.6 | Under Implementation | Engineering, Procurement & Construction |  | Chandikhol | Odisha | 15 Jan 2007 | Date of announcement | 2014-10-18 | 14765.6 | 9720 | 5045.6 | Y | [5 empty] | 2014-10-30 | Bids awarded
214 | National Highways Authority Of India | 155597 | Chandikhole-Paradeep (NH-5A) Six Laning Road Project (Part of Paradip-Kalinganagar Highway) | 893 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10143.6 | Under Implementation | Build Operate Transfer Toll |  | Chandikhol | Odisha | 01 Feb 2012 | Date of announcement | 2012-02-01 | 10143.6 | 10143.6 | 0 | N
215 | National Highways Authority Of India | 155597 | Chandikhole-Paradip Four lane Highway Project | 369 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3280 | Completed |  | October 2008 | Chandikhol | Odisha | 01 Feb 2004 | Date of announcement | 2008-04-01 | 3280 | 3280 | 0 | N | [5 empty] | 2004-02-08 | Bids awarded
216 | National Highways Authority Of India | 155597 | Chandni Chowk Multi-Level Bridge Project | 1555 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9000 | Under Implementation |  | June 2023 | Chandni chowk | Maharashtra | 01 Apr 2016 | Date of announcement | 2021-02-13 | 9000 | 4000 | 5000 | Y | 2023-12-31 | Initial completion date | 2021-08-26 | Y | 857 | 2018-12-21 | Bids awarded
217 | National Highways Authority Of India | 155597 | Chandrasekharapuram-Polavaram (NH-544G) Six Lane Greenfield Expressway Project (Package-11 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1976 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12926.5 | Under Implementation |  | March 2026 | Chandrasekharapuram | Andhra Pradesh | 01 Aug 2021 | Date of announcement | 2023-02-24 | 12926.5 | 12926.5 | 0 | N | [5 empty] | 2023-02-28 | Bids awarded
218 | National Highways Authority Of India | 155597 | Channarayanpatna (NH-75) Four Lane Bypass Project | 1652 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4123.1 | Under Implementation | Engineering, Procurement & Construction |  | Channarayapatna | Karnataka | 01 Jan 2017 | Date of announcement | 2019-01-15 | 4123.1 | 4123.1 | 0 | N | [5 empty] | 2020-07-06 | Bids awarded
219 | National Highways Authority Of India | 155597 | Chas-Bokaro-Gola-Ramgarh (NH-23) Two/Four Laning Road Project | 823 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3416.1 | Completed | Engineering, Procurement & Construction | February 2018 | Bokaro | Jharkhand | 22 Nov 2010 | Date of announcement | 2014-12-31 | 3416.1 | 2652.9 | 763.2 | Y | 2018-02-28 | Completed | 2017-09-30 | Y | 151 | 2014-12-31 | Bids awarded
220 | National Highways Authority Of India | 155597 | Chatra to Junc with NH-100 in Deoria Village Four/Six Lane Access Controlled Greenfield Highway Project (Package-9 of Varanasi-Kolkata Expressway) | 2119 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 24000 | Under Implementation | Engineering, Procurement & Construction |  | Chatra village | Jharkhand | 01 Aug 2021 | Date of announcement | 2023-05-01 | 24000 | 24000 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
221 | National Highways Authority Of India | 155597 | Chauka (Chhatarpur)-MP/UP Border (NH-34 & 934) Four Lane Highway Project | 2085 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9820 | Under Implementation |  |  | Chauka | Madhya Pradesh | 01 Nov 2022 | Date of announcement | 2023-01-23 | 9820 | 9820 | 0 | N
222 | National Highways Authority Of India | 155597 | Chaupala-Bareilly Flyover Project | 57 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 149.1 | No Information |  |  | Bareilly | Uttar Pradesh | 01 Mar 1999 | Date of announcement | 1999-03-01 | 149.1 | 149.1 | 0 | N
223 | National Highways Authority Of India | 155597 | Chengala-Neleshwaram-Kalikadavu Town (NH-66) Six Laning Highway Project | 1407 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17464.5 | Under Implementation | Hybrid Annuity |  | Chengala | Kerala | 01 Mar 2017 | Date of announcement | 2020-10-13 | 17464.5 | 20682.6 | -3218.1 | N | [5 empty] | 2020-10-15 | Bids awarded
224 | National Highways Authority Of India | 155597 | Chengalpattu-Tindivanam (NH-8) Highway Project | 61 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3315 | No Information |  |  | Chingleput | Tamil Nadu | 01 Sep 1999 | Date of announcement | 1999-09-01 | 3315 | 3315 | 0 | N
225 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 1 Project | 32 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 750 | Completed | Engineering, Procurement & Construction | November 2001 | Chennai | Tamil Nadu | 01 Mar 1998 | Date of announcement | 2001-04-01 | 750 | 500 | 250 | Y | 2001-11-30 | Completed | 2001-08-31 | Y | 91 | 1998-06-01 | Bids awarded
226 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 2 Project | 390 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8462 | Completed | Engineering, Procurement & Construction | January 2011 | Chennai | Tamil Nadu | 14 Jul 2004 | Date of announcement | 2011-01-31 | 8462 | 4445 | 4017 | Y | 2011-01-31 | Initial completion date | 2008-10-30 | Y | 823
227 | National Highways Authority Of India | 155597 | Chennai Dedicated Container Corridor to NHAI Road Project | 1660 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1000 | Under Implementation |  |  | Chennai | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2016-07-31 | 1000 | 1000 | 0 | N
228 | National Highways Authority Of India | 155597 | Chennai Port -Maduravoyal Double Decker Elevated Corridor Project (Bharatmala) | 1397 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 58620 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Chennai | Tamil Nadu | 15 Jun 2006 | Date of announcement | 2023-01-04 | 58620 | 13451.4 | 45168.6 | Y | 2024-12-31 | Completion expected by | 2012-03-31 | Y | 4658 | 2009-05-20 | Bids awarded
229 | National Highways Authority Of India | 155597 | Chennai-Kolkata (NH-5) Six Laning Highway Project (Vijayawada- Eluru-Gundugolanu Stretch) | 845 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 16000 | No Information |  |  | Chennai | Tamil Nadu | 13 Feb 2011 | Date of announcement | 2011-02-13 | 16000 | 16000 | 0 | N
230 | National Highways Authority Of India | 155597 | Chennai-Tada (NH-16) Six laning Highway Project | 1314 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4646.2 | Completed | Design Build Finance Operate Transfer | May 2022 | Chennai | Tamil Nadu | 07 Jun 2001 | Date of announcement | 2017-12-29 | 4646.2 | 3533.7 | 1112.5 | Y | 2022-08-31 | Initial completion date | 2011-05-31 | Y | 4110 | 2008-02-23 | Bids awarded
231 | National Highways Authority Of India | 155597 | Chennai-Trichy-Tuticorin Four/Six Lane Expressway Project | 2091 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 305020 | Announced | Hybrid Annuity |  | Chennai | Tamil Nadu | 01 Jan 2019 | Date of announcement | 2023-02-03 | 305020 | 305020 | 0 | N
232 | National Highways Authority Of India | 155597 | Cherthalai-Ochira (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 542 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20229.7 | Under Implementation |  | December 2025 | Cherthalai | Kerala | 15 Oct 2004 | Date of announcement | 2009-01-01 | 20229.7 | 12863.6 | 7366.1 | Y | 2025-12-31 | Completion expected by | 2020-12-31 | Y | 1826 | 2010-01-01 | Bids awarded
233 | National Highways Authority Of India | 155597 | Chettikulam (Madurai)-Natham (NH-785) Four Lane Highway Project (Bharatmala) | 1484 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8376.1 | Under Implementation | Engineering, Procurement & Construction |  | Chettikulam | Tamil Nadu | 26 Sep 2017 | Date of announcement | 2019-11-21 | 8376.1 | 4319.3 | 4056.8 | Y | [5 empty] | 2018-11-05 | Bids awarded
234 | National Highways Authority Of India | 155597 | Chhapra-Rewaghat-Muzaffarpur (NH-102) Two Lane Road Project | 827 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5161.3 | Completed | Engineering, Procurement & Construction | February 2019 | Chhapra | Bihar | 22 Nov 2010 | Date of announcement | 2015-08-30 | 5161.3 | 3184 | 1977.3 | Y | 2019-02-28 | Completed | 2018-04-30 | Y | 304 | 2014-06-04 | Bids awarded
235 | National Highways Authority Of India | 155597 | Chhattisgarh/Maharashtra Border-Wainganga Bridge Highway Project | 594 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2984.2 | Completed | Build Operate Transfer | September 2010 | Chattisgarh | Jharkhand | 31 Mar 2008 | Date of announcement | 2010-09-30 | 2984.2 | 5400 | -2415.8 | N | 2010-09-30 | Initial completion date | 2010-09-30 | N
236 | National Highways Authority Of India | 155597 | Chicholi-Betul (NH-47) Four Lane Highway Project (Package 3 of Harda-Betul) (Bharatmala) | 1703 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6203.6 | Under Implementation | Hybrid Annuity |  | Betul | Madhya Pradesh | 14 Mar 2018 | Date of announcement | 2020-08-23 | 6203.6 | 4865 | 1338.6 | Y | [5 empty] | 2020-09-16 | Bids awarded
237 | National Highways Authority Of India | 155597 | Chicholi-Temagaon (NH-47) Four Lane Highway Project (Package 2 of Harda-Betul) | 1822 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6630 | Under Implementation | Engineering, Procurement & Construction |  | Chicholi | Madhya Pradesh | 14 Mar 2018 | Date of announcement | 2018-05-08 | 6630 | 6630 | 0 | N | [5 empty] | 2022-03-31 | Bids awarded
238 | National Highways Authority Of India | 155597 | Chichra-Kharagpur (NH-6) Four Laning Highway Project | 1091 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11220.5 | Completed | Engineering, Procurement & Construction | June 2020 | Chichra | West Bengal | 01 Jul 2013 | Date of announcement | 2017-10-31 | 11220.5 | 7696.3 | 3524.2 | Y | 2020-12-31 | Initial completion date | 2019-09-12 | Y | 476 | 2016-09-24 | Bids awarded
239 | National Highways Authority Of India | 155597 | Chilakalapudi (Machilipatnam)-Manginapudi Beach Road Widening Project (Bharatmala) | 1693 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1950 | No Information |  |  | Chilakalapudi | Andhra Pradesh | 01 Jul 2016 | Date of announcement | 2020-10-16 | 1950 | 130 | 1820 | Y
240 | National Highways Authority Of India | 155597 | Chilakaluripet (NH-16) Six Lane Bypass Project (Bharatmala) | 1528 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4785.9 | Under Implementation | Hybrid Annuity | November 2023 | Chilkaluripet | Andhra Pradesh | 01 Apr 2007 | Date of announcement | 2022-12-21 | 4785.9 | 6000 | -1214.1 | N | [5 empty] | 2019-03-08 | Bids awarded
241 | National Highways Authority Of India | 155597 | Chilakaru Cross (NH-16)-Power Plants Road Up gradation Project (Bharatmala) | 1549 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | No Information |  |  | Chilukuru | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2016-06-03 | 3000 | 3000 | 0 | N
242 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Chilkaluripet-Ongole) Highway Project | 105 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3192.1 | Completed | Engineering, Procurement & Construction | September 2008 | Chilkaluripet | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 3192.1 | 2560 | 632.1 | Y | 2008-09-30 | Completed | 2003-12-31 | Y | 1735 | 2001-05-15 | Bids awarded
243 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Ongole-Kavali) Highway Project | 106 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3214.1 | Completed | Engineering, Procurement & Construction | August 2005 | Kavali | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 3214.1 | 2760 | 454.1 | Y | 2006-12-31 | Initial completion date | 2003-12-31 | Y | 1096 | 2001-08-31 | Bids awarded
244 | National Highways Authority Of India | 155597 | Chillakuru Cross Road-Turpu Kanupur (NH-516W) Four Lane Highway Project | 2057 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9094.7 | Under Implementation | Hybrid Annuity |  | Chillakuru cross road | Andhra Pradesh | 01 Oct 2021 | Date of announcement | 2022-08-08 | 9094.7 | 9094.7 | 0 | N | [5 empty] | 2023-01-30 | Bids awarded
245 | National Highways Authority Of India | 155597 | Chiloda-Naroda Section & Ahmedabad-Baroda Sect. Upgradation Project | 212 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 320 | Completed |  | May 2004 | Ahmedabad | Gujarat | 15 Dec 2001 | Date of announcement | 2002-03-01 | 320 | 320 | 0 | N | [5 empty] | 2002-07-15 | Bids awarded
246 | National Highways Authority Of India | 155597 | Chilodha-Naroda Six Laning Highway Project (Package-VII) (Kishangarh-Ahmadabad) | 1244 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2907.3 | Completed | Engineering, Procurement & Construction | May 2021 | Chiloda | Gujarat | 01 Jan 2012 | Date of announcement | 2016-11-15 | 2907.3 | 2907.3 | 0 | N | 2021-05-13 | Completed | 2019-05-31 | Y | 713 | 2016-11-15 | Bids awarded
247 | National Highways Authority Of India | 155597 | Chinchbhuvan-Khapri Four Lane Railway Over Bridge Project (on Wardha Road) | 1058 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 709.8 | Completed | Engineering, Procurement & Construction | February 2021 | Chinchbhuvan | Maharashtra | 15 Mar 2014 | Date of announcement | 2021-02-14 | 709.8 | 400 | 309.8 | Y | 2021-02-14 | Completed | 2018-09-30 | Y | 868 | 2017-01-18 | Bids awarded
248 | National Highways Authority Of India | 155597 | Chintagudem Village to Recherla Village Four Lane Access Controlled Greenfield Highway Project (Package 3 of Khammam-Devarapalle NH) (Bharatmala) | 1712 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8040 | Under Implementation | Hybrid Annuity |  | Chintagudem | Telangana | 28 Dec 2018 | Date of announcement | 2022-04-12 | 8040 | 8040 | 0 | N | [5 empty] | 2021-09-15 | Bids awarded
249 | National Highways Authority Of India | 155597 | Chirai-Anjar Four Lane Road including Anjar Bypass Project | 1512 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2377.5 | No Information | Public Private Partnership |  | Anjar | Gujarat | 24 Feb 2011 | Date of announcement | 2011-02-24 | 2377.5 | 2377.5 | 0 | N
250 | National Highways Authority Of India | 155597 | Chitoor-Kurnool N H-18 Road Project | 15 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 44.7 | Completed |  | December 2005 | Chitoor | Andhra Pradesh | 01 Jun 1997 | Date of announcement | 2005-10-01 | 44.7 | 23.2 | 21.5 | Y
251 | National Highways Authority Of India | 155597 | Chittorgarh Bypass (RJ-6) Project | 959 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4479 | Completed |  | December 2008 | Chittaurgarh | Rajasthan | 01 May 2005 | Date of announcement | 2005-05-01 | 4479 | 4479 | 0 | N | [5 empty] | 2005-05-31 | Bids awarded
252 | National Highways Authority Of India | 155597 | Chittorgarh Bypass Project | 220 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2100 | Completed |  | October 2009 | Chittaurgarh | Rajasthan | 01 Mar 2002 | Date of announcement | 2009-10-01 | 2100 | 1700 | 400 | Y | 2009-10-30 | Initial completion date | 2008-12-31 | Y | 303
253 | National Highways Authority Of India | 155597 | Chovvara-Kovalam Road Project | 1741 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 394.3 | No Information |  |  | Chovvara | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 394.3 | 394.3 | 0 | N
254 | National Highways Authority Of India | 155597 | Churaibari-Manu (NH-44) Highway Project | 362 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9710 | No Information |  |  | Churaibari | Tripura | 01 Dec 2003 | Date of announcement | 2003-12-01 | 9710 | 9710 | 0 | N
255 | National Highways Authority Of India | 155597 | Cloverleaf Flyover at Cheranallore on Container Road Project | 1784 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 951.4 | Shelved |  |  | Cheranallore | Kerala | 01 Apr 2018 | Date of announcement | 2019-01-30 | 951.4 | 951.4 | 0 | N
256 | National Highways Authority Of India | 155597 | Cochin Port Road Project | 211 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1417 | Completed |  | January 2011 | Cochin | Kerala | 01 Dec 2001 | Date of announcement | 2011-01-31 | 1417 | 1000 | 417 | Y | 2011-01-31 | Completed | 2006-08-31 | Y | 1614
257 | National Highways Authority Of India | 155597 | Connectivity to Enayam through Nagarcoil Port Road Project (Bharatmala) | 1615 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2225 | No Information |  |  | Enayam | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2020-08-09 | 2225 | 860 | 1365 | Y
258 | National Highways Authority Of India | 155597 | Connectivity to Katupalli through Ponnani Port Road Project | 1616 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2000 | Under Implementation |  |  | Katupalli | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2016-07-31 | 2000 | 2000 | 0 | N
259 | National Highways Authority Of India | 155597 | Convent Junction-Sheela Nagar Junction Four/Six Lane Road Project | 2072 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5016.5 | Under Implementation | Engineering, Procurement & Construction |  | Convent junction | Andhra Pradesh | 01 Apr 2022 | Date of announcement | 2023-03-14 | 5016.5 | 4622.9 | 393.6 | Y | [5 empty] | 2023-03-14 | Bids awarded
260 | National Highways Authority Of India | 155597 | Cuddalore-Chithoor Road Upgradation Project | 494 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 93.6 | No Information |  |  | Tamil Nadu | Tamil Nadu | 20 Aug 2008 | Date of announcement | 2008-08-20 | 93.6 | 93.6 | 0 | N
261 | National Highways Authority Of India | 155597 | Cuddalore-Vridhachalam-Salem (NH-532) Four laning Road Project | 1419 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1583.5 | Completed |  | March 2018 | Cuddalore | Tamil Nadu | 01 Apr 2015 | Date of announcement | 2015-07-17 | 1583.5 | 1583.5 | 0 | N
262 | National Highways Authority Of India | 155597 | Cuttack-Angul (NH-55) Highway Project | 1035 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19907 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Angul | Odisha | 25 Oct 2010 | Date of announcement | 2018-06-30 | 19907 | 11173.2 | 8733.8 | Y | 2023-12-31 | Completion expected by | 2015-06-30 | Y | 3106 | 2011-11-30 | Bids awarded
263 | National Highways Authority Of India | 155597 | DND Maharani Bagh-Junction with Jaitpur-Pushta Road (section of NH-148NA) Six Lane access controlled Highway Project (Package 1) (Delhi-Mumbai Expressway) | 1677 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18383 | Under Implementation | Hybrid Annuity | March 2024 | Dnd maharani bagh | NCT of Delhi | 26 Dec 2018 | Date of announcement | 2019-02-28 | 18383 | 18383 | 0 | N | [5 empty] | 2020-03-05 | Bids awarded
264 | National Highways Authority Of India | 155597 | Daboka-Nagaon (NH-36) Highway Project | 243 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2590 | Completed |  | December 2012 | Daboka | Assam | 31 Dec 2003 | Date of announcement | 2011-10-30 | 2590 | 2330 | 260 | Y | 2012-12-31 | Completed | 2008-06-30 | Y | 1645
265 | National Highways Authority Of India | 155597 | Dabwali Railway Over Bridge Project or Bhatinda-Suratgarh (ROB) Project | 912 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 650 | Completed | Engineering, Procurement & Construction | March 2017 | Dabwali | Haryana | 20 Nov 2008 | Date of announcement | 2013-09-23 | 650 | 625 | 25 | Y | 2017-03-31 | Completed | 2015-07-31 | Y | 609 | 2013-11-30 | Bids awarded
266 | National Highways Authority Of India | 155597 | Dagmagpur-Lalganj (NH-35) Four Lane Highway Project (Package-II) | 1429 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14940 | Completed | Engineering, Procurement & Construction | December 2021 | Dagmagpur | Uttar Pradesh | 01 Apr 2016 | Date of announcement | 2021-12-20 | 14940 | 9631.1 | 5308.9 | Y | 2021-12-20 | Completed | 2020-09-30 | Y | 446 | 2018-03-13 | Bids awarded
267 | National Highways Authority Of India | 155597 | Dahod-Padhi (NH-113) Two Laning Highway Project | 878 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3720 | Completed | Engineering, Procurement & Construction | December 2018 | Dahod | Gujarat | 25 Mar 2011 | Date of announcement | 2017-10-31 | 3720 | 3320 | 400 | Y | 2018-12-17 | Completed | 2016-11-30 | Y | 747 | 2014-01-15 | Bids awarded
268 | National Highways Authority Of India | 155597 | Dakoha (Jalandhar City NH-44) Six Lane Railway Underbridge Project | 1989 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 150 | Announced | Engineering, Procurement & Construction |  | Dakoha | Punjab | 24 Feb 2016 | Date of announcement | 2021-05-30 | 150 | 150 | 0 | N
269 | National Highways Authority Of India | 155597 | Dakshin Mechgram-Ranirbazar Four Lane Road (NH-116A) Project | 1912 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13281.5 | Announced | Hybrid Annuity | February 2024 | Dakshin mechgram | West Bengal | 01 Nov 2017 | Date of announcement | 2020-08-09 | 13281.5 | 13281.5 | 0 | N
270 | National Highways Authority Of India | 155597 | Dalkhola Four Lane Bypass Project | 422 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1200 | Completed | Engineering, Procurement & Construction | November 2022 | Dalkhola | West Bengal | 31 Dec 2005 | Date of announcement | 2022-11-17 | 1200 | 750 | 450 | Y | 2022-11-17 | Completed | 2008-03-31 | Y | 5344 | 2017-08-08 | Bids awarded
271 | National Highways Authority Of India | 155597 | Dalkhola-Islampore Subsection 2 (EW/6) Highway Project | 181 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 900.6 | Completed | Engineering, Procurement & Construction | November 2005 | Dalkhola | West Bengal | 01 Apr 2000 | Date of announcement | 2002-01-01 | 900.6 | 900 | 0.6 | Y | 2005-11-30 | Completed | 2002-07-31 | Y | 1218 | 2000-04-15 | Bids awarded
272 | National Highways Authority Of India | 155597 | Dalkhola-Islampur (EW/5) Highway Project | 223 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 725.6 | Completed | Engineering, Procurement & Construction | March 2004 | Dalkhola | West Bengal | 15 Oct 1999 | Date of announcement | 2003-07-01 | 725.6 | 730 | -4.4 | N | 2004-03-31 | Completed | 2002-03-31 | Y | 731 | 1999-12-01 | Bids awarded
273 | National Highways Authority Of India | 155597 | Dalkola-Gayakota & Purnea-Fobasganj Renovation Highway Project | 650 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1140 | No Information | Public Private Partnership |  | Dalkola | West Bengal | 01 Jul 2009 | Date of announcement | 2009-07-01 | 1140 | 1140 | 0 | N
274 | National Highways Authority Of India | 155597 | Damanganga Bridge (Surat-Manor) Project | 260 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 62 | Completed |  | May 2004 | Manor | Maharashtra | 23 Aug 2003 | Date of announcement | 2004-04-01 | 62 | 59.4 | 2.6 | Y
275 | National Highways Authority Of India | 155597 | Danapur-Bihta via Shivala Four Lane Elevated Expressway Project | 1752 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 31470 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Bihta | Bihar | 03 Mar 2017 | Date of announcement | 2023-04-15 | 31470 | 20000 | 11470 | Y | 2024-12-31 | Completion expected by | 2022-06-30 | Y | 915 | 2023-01-25 | Bids awarded
276 | National Highways Authority Of India | 155597 | Dankuni-Kharagpur (Bridge Section WB III) Highway Project | 109 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 810 | Completed |  | October 2005 | Dankuni | West Bengal | 15 Nov 2000 | Date of announcement | 2002-01-01 | 810 | 570 | 240 | Y | 2005-10-31 | Initial completion date | 2003-10-31 | Y | 731 | 2000-12-31 | Bids awarded
277 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-8) Road Project | 736 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4972 | Completed |  | March 2011 | Darbanga | Bihar | 31 Dec 2003 | Date of announcement | 2011-03-31 | 4972 | 3050 | 1922 | Y | 2011-03-31 | Completed | 2010-06-30 | Y | 274
278 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-9) Road Project | 737 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4550 | Completed |  | February 2011 | Darbanga | Bihar | 31 Dec 2003 | Date of announcement | 2011-02-28 | 4550 | 2918 | 1632 | Y | 2011-02-28 | Completed | 2010-06-30 | Y | 243
279 | National Highways Authority Of India | 155597 | Dasna-Hapur Road Project | 123 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 920 | Completed |  | March 2009 | Dasna | Uttar Pradesh | 01 Jun 2001 | Date of announcement | 2001-06-01 | 920 | 920 | 0 | N | 2009-03-30 | Completed | 2002-04-30 | Y | 2526
280 | National Highways Authority Of India | 155597 | Dasna-Meerut Expressway (NH-58) (Package-4 of Delhi-Meerut Expressway) Project (Bharatmala) | 1157 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 33320 | Completed | Engineering, Procurement & Construction | March 2022 | Dasna | Uttar Pradesh | 30 Oct 2011 | Date of announcement | 2021-12-23 | 33320 | 16580 | 16740 | Y | 2022-03-17 | Completed | 2018-03-31 | Y | 1447 | 2018-01-31 | Bids awarded
281 | National Highways Authority Of India | 155597 | Davanagere-Haveri Six Laning Highway (NH-48) Project | 1234 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11770 | Completed | Hybrid Annuity | August 2021 | Davanagere | Karnataka | 01 Dec 2016 | Date of announcement | 2017-03-29 | 11770 | 8363.9 | 3406.1 | Y | 2021-10-30 | Initial completion date | 2020-03-31 | Y | 578 | 2017-03-29 | Bids awarded
282 | National Highways Authority Of India | 155597 | Dehu-Lonavala-Khandala Bypass Project | 16 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1200 | No Information |  |  | Dehu Road | Maharashtra | 01 Jun 1997 | Date of announcement | 1997-06-01 | 1200 | 1200 | 0 | N
283 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 120000 | Under Implementation | Engineering, Procurement & Construction |  | Dehradun | Uttarakhand | 01 Jan 2018 | Date of announcement | 2023-04-06 | 120000 | 80800 | 39200 | Y | [5 empty] | 2021-02-25 | Bids awarded
284 | National Highways Authority Of India | 155597 | Delhi-Ghaziabad Fourteen Lane Highway Project | 871 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 85000 | No Information |  |  | Delhi | NCT of Delhi | 01 Sep 2011 | Date of announcement | 2011-09-01 | 85000 | 85000 | 0 | N
285 | National Highways Authority Of India | 155597 | Delhi-Gurgaon Highway Project | 96 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1080 | Completed |  | March 2001 | Delhi | NCT of Delhi | 01 Jan 2001 | Date of announcement | 2001-01-01 | 1080 | 1080 | 0 | N
287 | National Highways Authority Of India | 155597 | Delhi-Panipat Highway Project | 660 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 25 | No Information |  |  | Delhi | NCT of Delhi | 06 Oct 2009 | Date of announcement | 2009-10-06 | 25 | 25 | 0 | N
288 | National Highways Authority Of India | 155597 | Delhi-Saharanpur (NH-709B) Six Lane Highway Project (Bharatmala) | 1659 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 44050 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Akshardham | NCT of Delhi | 01 Sep 2007 | Date of announcement | 2019-01-18 | 44050 | 12770 | 31280 | Y | 2023-12-31 | Completion expected by | 2013-12-31 | Y | 3652 | 2011-08-01 | Bids awarded
289 | National Highways Authority Of India | 155597 | Dena Junction (NH-48) Flyover/Underpass Project | 2125 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 170 | Completed |  | June 2023 | Dena junction | Gujarat | 01 Apr 2018 | Date of announcement | 2023-06-02 | 170 | 140 | 30 | Y
290 | National Highways Authority Of India | 155597 | Dera Baba Nanak(Gurdaspur)-Gurudwara Darbar Sahib (Indo/Pak Border) Road Project (Kartarpur Corridor) | 1702 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1200.5 | Completed |  | November 2019 | Dera baba nanak | Punjab | 01 Feb 1999 | Date of announcement | 2019-02-02 | 1200.5 | 1000 | 200.5 | Y | 2019-11-30 | Initial completion date | 2019-09-29 | Y | 62
291 | National Highways Authority Of India | 155597 | Derabassi Flyover Project (on Ambala-Chandigarh section) | 940 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 900 | Completed | Engineering, Procurement & Construction | June 2016 | Dera bassi | Punjab | 18 Dec 2008 | Date of announcement | 2015-03-05 | 900 | 1300 | -400 | N | 2017-03-31 | Initial completion date | 2016-05-31 | Y | 304
292 | National Highways Authority Of India | 155597 | Devdhari-Kelapur (NS-61/MH) Highway Project | 730 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1440 | Completed |  | October 2010 | Devdhari | Maharashtra | 31 Dec 2003 | Date of announcement | 2003-12-31 | 1440 | 1440 | 0 | N | 2010-10-31 | Completed | 2010-03-31 | Y | 214
293 | National Highways Authority Of India | 155597 | Development of Coastal road to East of Container Terminal II at Chennai Port Project | 1534 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 630 | Completed |  | May 2018 | Chennai | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2018-05-15 | 630 | 900 | -270 | N
294 | National Highways Authority Of India | 155597 | Development of Outer Ring Road from East Breakwater to Sheelanagar Project (Sagarmala) | 1736 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | Announced |  |  | Sheela nagar junction | Andhra Pradesh | 01 May 2018 | Date of announcement | 2020-09-30 | 3000 | 3000 | 0 | N
295 | National Highways Authority Of India | 155597 | Development of roads connectivity to Cuddalore Port Project | 1537 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1250 | Under Implementation |  |  | Cuddalore | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2023-01-02 | 1250 | 1000 | 250 | Y
296 | National Highways Authority Of India | 155597 | Dewapur-UP/Bihar Border (LMNHP-9) Highway Project | 954 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | No Information | Engineering, Procurement & Construction |  | Dewapur | Bihar | 01 Aug 2005 | Date of announcement | 2005-08-01 | 3000 | 3000 | 0 | N | [5 empty] | 2005-09-30 | Bids awarded
297 | National Highways Authority Of India | 155597 | Dewas-Ujjain Four Lane (NH-148NG) Highway Project | 1821 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9920 | Under Implementation | Hybrid Annuity | July 2023 | Dewas | Madhya Pradesh | 01 Apr 2016 | Date of announcement | 2022-02-24 | 9920 | 5950 | 3970 | Y | 2023-07-31 | Completion expected by | 2022-07-06 | Y | 390 | 2020-10-29 | Bids awarded
298 | National Highways Authority Of India | 155597 | Dhanara Village-Tumbigura Highway Project (Phase 2) | 1810 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 80920 | No Information |  |  | Dhanara village | Odisha | 01 Jul 2019 | Date of announcement | 2019-12-27 | 80920 | 80920 | 0 | N
299 | National Highways Authority Of India | 155597 | Dhanara-Hatibena Six Lane Road (Package-OD-1) (NH-130 CD) Project (Part of Raipur-Visakhapatnam Economic Corridor) | 1917 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4327.6 | Under Implementation | Hybrid Annuity |  | Dhanara | Odisha | 01 Nov 2020 | Date of announcement | 2021-04-10 | 4327.6 | 4517.9 | -190.3 | N | [5 empty] | 2021-03-31 | Bids awarded
300 | National Highways Authority Of India | 155597 | Dhangaon-Borgaon (NH-347BG and 753L) Four Lane Highway Project (Package IV) | 1711 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8310 | Under Implementation | Hybrid Annuity | August 2023 | Borgaon (mp) | Madhya Pradesh | 02 Jan 2019 | Date of announcement | 2022-03-17 | 8310 | 6853 | 1457 | Y | [5 empty] | 2020-11-27 | Bids awarded
301 | National Highways Authority Of India | 155597 | Dhankuni-Kolaghat (WB-1) Four Lane Highway Project | 82 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5110.1 | Completed |  | March 2007 | Dankuni | West Bengal | 01 Dec 2000 | Date of announcement | 2006-06-30 | 5110.1 | 3930 | 1180.1 | Y | 2007-03-31 | Completed | 2003-12-30 | Y | 1187 | 2001-03-30 | Bids awarded
302 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-19) Highway Project | 711 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2860 | Completed | Engineering, Procurement & Construction | May 2015 | Dharmtul | Assam | 15 Dec 2004 | Date of announcement | 2014-08-30 | 2860 | 2000 | 860 | Y | 2015-05-31 | Completed | 2010-12-31 | Y | 1612 | 2005-04-30 | Bids awarded
303 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-20) Four-Laning Highway Project | 712 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2236.8 | Completed | Engineering, Procurement & Construction | June 2019 | Dharmtul | Assam | 01 Dec 2003 | Date of announcement | 2019-06-24 | 2236.8 | 1600 | 636.8 | Y | 2019-06-30 | Initial completion date | 2010-12-31 | Y | 3103 | 2005-04-30 | Bids awarded
304 | National Highways Authority Of India | 155597 | Dharmapuri-Lonand (NH-965) Four Lane Highway Project (Package-IV of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1874 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14120 | Under Implementation |  |  | Dharmapuri | Maharashtra | 29 Dec 2017 | Date of announcement | 2021-11-08 | 14120 | 7984.3 | 6135.7 | Y | [5 empty] | 2021-03-15 | Bids awarded
305 | National Highways Authority Of India | 155597 | Dharuhera-Bhiwadi Four Lane Link Road (NH-919) Project | 1973 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1475.1 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Bhiwadi | Rajasthan | 01 Apr 2021 | Date of announcement | 2021-09-19 | 1475.1 | 1475.1 | 0 | N | [5 empty] | 2021-12-01 | Bids awarded
306 | National Highways Authority Of India | 155597 | Dharwad-Hubli Four Lane Bypass Highway Project | 113 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1160 | Completed | Build Operate Transfer | November 2008 | Dharwad | Karnataka | 01 Jun 2001 | Date of announcement | 2001-06-01 | 1160 | 1160 | 0 | N | 2008-11-30 | Completed | 2001-08-30 | Y | 2649
308 | National Highways Authority Of India | 155597 | Dhillon Nagar (Moga) to Bajakhana (Lambwali) (NH-105B) Four Lane Highway (Greenfield Alignment) Project | 1733 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4938.4 | Under Implementation | Hybrid Annuity |  | Bajakhana | Punjab | 01 Apr 2018 | Date of announcement | 2019-02-14 | 4938.4 | 4619.3 | 319.1 | Y | [5 empty] | 2021-12-31 | Bids awarded
309 | National Highways Authority Of India | 155597 | Dholpur-Morena Section (including chambal bridge) Project | 742 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3180 | Completed | Engineering, Procurement & Construction | June 2016 | Dholpur | Rajasthan | 31 Dec 2003 | Date of announcement | 2014-08-31 | 3180 | 2324.5 | 855.5 | Y | 2016-06-30 | Completed | 2011-03-31 | Y | 1918 | 2007-06-01 | Bids awarded
310 | National Highways Authority Of India | 155597 | Dichaon Kalan-Bahadurgarh Bypass Six Lane Link Road (NH-344N) Project ( Package-5 of Delhi 3rd Ring Road Project or UER-2) | 1800 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3242.4 | Under Implementation | Engineering, Procurement & Construction | October 2023 | Bahadurgarh bypass | Haryana | 01 Apr 2016 | Date of announcement | 2019-12-26 | 3242.4 | 3242.4 | 0 | N | [5 empty] | 2021-07-29 | Bids awarded
311 | National Highways Authority Of India | 155597 | Dighi Port (NH-17) Road Connectivity Project | 1175 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6000 | No Information | Engineering, Procurement & Construction |  | Agardanda | Maharashtra | 31 Jan 2016 | Date of announcement | 2016-04-14 | 6000 | 6000 | 0 | N
312 | National Highways Authority Of India | 155597 | Dighi Port-Arunda Two Laning Coastal Highway Project | 1388 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 25000 | No Information |  |  | Arunda | Maharashtra | 01 Apr 2016 | Date of announcement | 2016-07-23 | 25000 | 25000 | 0 | N
313 | National Highways Authority Of India | 155597 | Dindigul-Coimbatore-Annur-Hasanur Road Widening Project | 855 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 24100 | No Information | Design Build Finance Operate Transfer |  | Annur | Tamil Nadu | 01 Dec 2010 | Date of announcement | 2011-06-06 | 24100 | 24100 | 0 | N
314 | National Highways Authority Of India | 155597 | Dindigul-Kumuli Four Lane Road Project | 903 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 4500 | No Information |  |  | Dindigul | Tamil Nadu | 01 Jun 2003 | Date of announcement | 2003-06-01 | 4500 | 4500 | 0 | N
315 | National Highways Authority Of India | 155597 | Dindigul-Oddanchatram (NH-83) Four Lane Highway Project (Package-1 of Dindigul-Pollachi) | 1499 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7830.3 | No Information | Hybrid Annuity |  | Dindigul | Tamil Nadu | 04 May 2018 | Date of announcement | 2018-05-04 | 7830.3 | 7830.3 | 0 | N
316 | National Highways Authority Of India | 155597 | Divancheru (near Rajahmundry)-Gowthami (AP-17) Four Lane Highway Project | 144 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1308 | Completed | Engineering, Procurement & Construction | March 2005 | Gowthami river | Andhra Pradesh | 15 May 2001 | Date of announcement | 2002-01-01 | 1308 | 2448.3 | -1140.3 | N | [5 empty] | 2001-06-01 | Bids awarded
317 | National Highways Authority Of India | 155597 | Dobbaspet-Dodaballapur Bypass (NH-648) Four/Six Lane Highway Project (Package 1) (Bharatmala) | 1657 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14381.4 | Under Implementation | Hybrid Annuity |  | Dobbaspet | Karnataka | 29 Jan 2019 | Date of announcement | 2020-12-19 | 14381.4 | 14473.5 | -92.1 | N | [5 empty] | 2020-09-07 | Bids awarded
318 | National Highways Authority Of India | 155597 | Dodaballapur Bypass-Hoskote (NH-648) Four/Six Lane Highway Project (Package 2) (Banglore Ring Road) | 1658 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13177.4 | Under Implementation | Hybrid Annuity |  | Dodaballapur bypass | Karnataka | 29 Jan 2019 | Date of announcement | 2020-12-19 | 13177.4 | 11785.9 | 1391.5 | Y | [5 empty] | 2020-08-26 | Bids awarded
319 | National Highways Authority Of India | 155597 | Donoreshan Village to Junction with NH20 in Bongabar Village Four/Six Lane Greenfield Access Control Expressway Project (Package-11 of Varanasi-Kolkata Expressway) | 2120 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 18550 | Under Implementation | Engineering, Procurement & Construction |  | Bongabar village | Jharkhand | 01 Aug 2021 | Date of announcement | 2023-05-18 | 18550 | 18550 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
320 | National Highways Authority Of India | 155597 | Duburi-Chandikhole (NH-53) Four Lane Road Project | 1405 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7325.5 | Under Implementation | Engineering, Procurement & Construction |  | Chandikhol | Odisha | 26 Oct 2017 | Date of announcement | 2020-08-09 | 7325.5 | 6336.8 | 988.7 | Y | [5 empty] | 2018-01-31 | Bids awarded
321 | National Highways Authority Of India | 155597 | Dudhadhari Elevated Four Lane (NH-34) Flyover Project (Muzaffarnagar-Haridwar Section) | 2020 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1130 | Under Implementation | Engineering, Procurement & Construction |  | Haridwar | Uttarakhand | 01 Dec 2020 | Date of announcement | 2021-12-01 | 1130 | 1677.6 | -547.6 | N | [5 empty] | 2021-11-30 | Bids awarded
322 | National Highways Authority Of India | 155597 | Dumad Chowkdi Underpass (NH-48) Project | 2126 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 270.1 | Completed |  | June 2023 | Dumad chowkdi | Gujarat | 01 Nov 2013 | Date of announcement | 2023-06-02 | 270.1 | 270.1 | 0 | N | [5 empty] | 2021-07-08 | Bids awarded
323 | National Highways Authority Of India | 155597 | Dummulapeta & Old Port Area (Kakinada) Four Lane Flyover Project | 1552 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 500 | No Information | Engineering, Procurement & Construction |  | Dummulapeta | Andhra Pradesh | 31 Jan 2016 | Date of announcement | 2018-05-15 | 500 | 800 | -300 | N
324 | National Highways Authority Of India | 155597 | Dushehra Village-Arnia Khurd Village (NH-91) Four/Six Lane Divided Carriageway (THDCIL Bypass) Project | 1769 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4702.6 | Completed | Engineering, Procurement & Construction | March 2023 | Arnia khurd village | Uttar Pradesh | 06 Sep 2019 | Date of announcement | 2021-08-02 | 4702.6 | 2197 | 2505.6 | Y | 2023-03-01 | Completed | 2022-08-10 | Y | 203 | 2020-09-09 | Bids awarded
325 | National Highways Authority Of India | 155597 | Dwarka (NH-51)-Khambalia-Dewaria Section & Jamnanagar-Dhrol-Amram-Maliya Two/Four Laning Highway (BM/2) Project (Bharatmala) | 1094 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19804.1 | Under Implementation | Hybrid Annuity |  | Amran | Gujarat | 05 Apr 2015 | Date of announcement | 2018-02-21 | 19804.1 | 19804.1 | 0 | N | [5 empty] | 2019-03-08 | Bids awarded
326 | National Highways Authority Of India | 155597 | Dwarka Expressway-IGI Airport Road Tunnel (NH-248BB) Four Lane Highway Project (Package-V of Dwarka Expressway) | 1325 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 50000 | Announced | Engineering, Procurement & Construction |  | Dwarka, delhi | NCT of Delhi | 21 Aug 2017 | Date of announcement | 2019-03-15 | 50000 | 50000 | 0 | N
327 | National Highways Authority Of India | 155597 | East break water to Convent Junction Four Lane Road (Port Connectivity) Project | 1954 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 357.9 | Under Implementation |  | June 2023 | Vishakhapatnam | Andhra Pradesh | 01 Jun 2020 | Date of announcement | 2022-12-21 | 357.9 | 1100 | -742.1 | N | [5 empty] | 2021-11-02 | Bids awarded
328 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5230.6 | Completed | Build Operate Transfer | January 2021 | Edapally | Kerala | 26 Feb 2010 | Date of announcement | 2013-11-05 | 5230.6 | 16000 | -10769.4 | N | 2021-01-09 | Completed | 2013-03-31 | Y | 2841 | 2013-05-28 | Bids awarded
329 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting after End of Bridge over Hadaf River near Hathiyavan Village with SH-152 near Matariya Vadi Project (Package 27 of Delhi-Mumbai Expressway) | 1817 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16118.3 | Under Implementation | Engineering, Procurement & Construction | February 2024 | Hathiyavan village | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 16118.3 | 8740.4 | 7377.9 | Y | [5 empty] | 2021-07-30 | Bids awarded
330 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting from Junction with SH-152 near Matariya Vadi and near Bhamaiya village Project (Package 28 of Delhi-Mumbai Expressway) | 1816 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15433.1 | Under Implementation | Engineering, Procurement & Construction | November 2023 | Bhamaiya village | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 15433.1 | 8032.9 | 7400.2 | Y | [5 empty] | 2021-05-27 | Bids awarded
331 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 90000 | Under Implementation | Engineering, Procurement & Construction | April 2024 | Dwarka, delhi | NCT of Delhi | 31 Jul 2007 | Date of announcement | 2023-05-18 | 90000 | 59294.6 | 30705.4 | Y | 2024-04-30 | Completion expected by | 2012-04-10 | Y | 4403 | 2011-03-01 | Bids awarded
332 | National Highways Authority Of India | 155597 | Eight laning of Haryana/ Delhi Border to Mukaraba Chowk (NS-18/DL) Project | 185 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 982.2 | Completed |  | July 2011 | Mukarba Chowk | NCT of Delhi | 30 Oct 2001 | Date of announcement | 2008-07-01 | 982.2 | 512 | 470.2 | Y | 2011-07-31 | Completed | 2003-04-30 | Y | 3014
333 | National Highways Authority Of India | 155597 | Ekangarsarai-Jehanabad-Arwal (NH-110)Two Lane Road Project | 838 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1650 | No Information | Build Operate Transfer |  | Arwal | Bihar | 25 Nov 2010 | Date of announcement | 2010-11-25 | 1650 | 1650 | 0 | N
334 | National Highways Authority Of India | 155597 | Electronic City Corridor Highway (NH-7) Project | 387 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 16 | No Information |  |  | Electronic City | Karnataka | 01 Jun 2004 | Date of announcement | 2004-06-01 | 16 | 16 | 0 | N
335 | National Highways Authority Of India | 155597 | Eluru-Vijaywada Highway including Eluru bypass Project | 22 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3353.5 | Completed | Engineering, Procurement & Construction | January 2002 | Eluru | Andhra Pradesh | 01 Mar 1997 | Bids invited | 2000-01-01 | 3353.5 | 1350 | 2003.5 | Y | 2002-06-30 | Initial completion date | 2002-01-31 | Y | 150 | 1997-11-17 | Bids awarded
336 | National Highways Authority Of India | 155597 | Ena-Kim Package-6 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1626 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22718.6 | Under Implementation | Hybrid Annuity | December 2023 | Ena | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 22718.6 | 15126.6 | 7592 | Y | 2023-12-10 | Completion expected by | 2021-12-31 | Y | 709 | 2020-03-05 | Bids awarded
337 | National Highways Authority Of India | 155597 | End of Hardoi District to Lucknow Ring Road (NH-731) Four Lane Highway Project (Package-IV of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2068 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2810 | Under Implementation | Engineering, Procurement & Construction |  | Hardoi | Uttar Pradesh | 01 Nov 2010 | Date of announcement | 2022-03-14 | 2810 | 2810 | 0 | N | [5 empty] | 2022-03-14 | Bids awarded
338 | National Highways Authority Of India | 155597 | Etawah Bypass Highway Project | 73 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1321.8 | Completed | Engineering, Procurement & Construction | May 2008 | Etawah | Uttar Pradesh | 01 Sep 2000 | Date of announcement | 2008-05-31 | 1321.8 | 990 | 331.8 | Y | [5 empty] | 2001-01-31 | Bids awarded
339 | National Highways Authority Of India | 155597 | Etawah-Rajpur (GTRIP/IC) Highway Project | 693 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3484.4 | Completed | Engineering, Procurement & Construction | May 2008 | Etawah | Uttar Pradesh | 01 Mar 2002 | Date of announcement | 2002-03-01 | 3484.4 | 3484.4 | 0 | N | 2008-05-30 | Completed | 2004-12-31 | Y | 1246 | 2002-03-15 | Bids awarded
340 | National Highways Authority Of India | 155597 | Exhibition Centre FOB project | 833 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Exhibition centre | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N
341 | National Highways Authority Of India | 155597 | Expressway from Dighi Industrial Cluster to JNPT Project | 1724 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 45000 | No Information |  |  | Dighi port | Maharashtra | 01 Apr 2016 | Date of announcement | 2016-07-01 | 45000 | 45000 | 0 | N
342 | National Highways Authority Of India | 155597 | FOBs on Gurgaon-Kotputli-Jaipur (NH-8 & 48) Project | 1390 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 703.6 | Under Implementation | Engineering, Procurement & Construction |  | Gurgaon | Haryana | 31 Oct 2017 | Date of announcement | 2017-10-31 | 703.6 | 703.6 | 0 | N | [5 empty] | 2020-06-25 | Bids awarded
343 | National Highways Authority Of India | 155597 | Fagne-Maharashtra/Gujarat Border (Songarh) (NH-6) Four Laning Highway Project (Bharatmala) | 1801 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18857.4 | Under Implementation | Engineering, Procurement & Construction |  | Fagne | Maharashtra | 10 Mar 2010 | Date of announcement | 2015-07-25 | 18857.4 | 19091.4 | -234 | N | [5 empty] | 2012-04-03 | Bids awarded
344 | National Highways Authority Of India | 155597 | Faridabad Road Improvement (NH-2) Project | 364 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 86.2 | No Information |  |  | Faridabad | Haryana | 01 Dec 2003 | Date of announcement | 2003-12-01 | 86.2 | 86.2 | 0 | N
345 | National Highways Authority Of India | 155597 | Faridabad-Palwal Six Lane Expressway Project (Package 6 of Eastern Peripheral Expressway) | 1124 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7685.6 | Completed | Engineering, Procurement & Construction | May 2018 | Faridabad | Haryana | 31 Jan 1995 | Date of announcement | 2014-10-29 | 7685.6 | 7685.6 | 0 | N | 2018-07-31 | Initial completion date | 2009-07-30 | Y | 3288 | 2015-08-14 | Bids awarded
346 | National Highways Authority Of India | 155597 | Farukhanagar-Kottakata(NH-7) Highway Project | 323 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5700 | Completed | Build Operate Transfer | March 2009 | Farukhnagar | Telangana | 01 Dec 2003 | Date of announcement | 2009-01-01 | 5700 | 5810 | -110 | N
347 | National Highways Authority Of India | 155597 | Farukhnagar-Jadcheria Four Laning Highway Project | 566 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5030 | Completed | Build Operate Transfer | February 2009 | Farukhnagar | Telangana | 30 Jun 2004 | Date of announcement | 2004-06-30 | 5030 | 5030 | 0 | N | 2009-02-28 | Initial completion date | 2009-02-28 | N |  | 2005-10-31 | Bids awarded
348 | National Highways Authority Of India | 155597 | Fatehpur-Khaga (TNHP/II-C) Highway Project | 149 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4060.5 | Completed |  | September 2010 | Fatehpur | Uttar Pradesh | 01 Jan 2001 | Date of announcement | 2010-09-30 | 4060.5 | 2950 | 1110.5 | Y | 2010-10-30 | Initial completion date | 2003-12-31 | Y | 2495 | 2001-01-31 | Bids awarded
349 | National Highways Authority Of India | 155597 | Fazilka-Abohar (NH-07) Four Lane Highway Project | 3012 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9698 | Under Implementation | Hybrid Annuity |  | Abohar | Punjab | 01 Jan 2023 | Date of announcement | 2023-02-09 | 9698 | 9698 | 0 | N | [5 empty] | 2023-03-23 | Bids awarded
350 | National Highways Authority Of India | 155597 | Flyover Bridge (FOB) at Nathayyapalem (Mindi) on NH-16 Project | 1749 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 450 | No Information |  |  | Nathayyapalen | Andhra Pradesh | 15 May 2018 | Date of announcement | 2020-09-30 | 450 | 450 | 0 | N
351 | National Highways Authority Of India | 155597 | Flyover on Shivpuri-Kanpur Road Project | 3003 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1260 | Under Implementation |  |  | Kanpur | Uttar Pradesh | 01 Jan 2004 | Date of announcement | 2023-03-13 | 1260 | 1260 | 0 | N
352 | National Highways Authority Of India | 155597 | Flyover/Underpass at Vizag Airport Junction Project | 1751 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 750 | Under Implementation |  |  | Vizag airport junction | Andhra Pradesh | 01 Apr 2018 | Date of announcement | 2020-09-30 | 750 | 750 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
353 | National Highways Authority Of India | 155597 | Foot Over Bridge across NH-2 Project | 1415 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 135 | No Information | Engineering, Procurement & Construction |  | Ballabhgarh grain market | Haryana | 18 Oct 2017 | Date of announcement | 2017-10-18 | 135 | 135 | 0 | N
354 | National Highways Authority Of India | 155597 | Forbesganj-Jogbani (NH-57A) Four Laning Highway Project | 978 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3120 | Under Implementation | Engineering, Procurement & Construction |  | Forbesganj | Bihar | 30 Apr 2009 | Date of announcement | 2022-06-30 | 3120 | 735.5 | 2384.5 | Y | [5 empty] | 2010-05-15 | Bids awarded
355 | National Highways Authority Of India | 155597 | Forbesganj-Simrahi (BR-3) Four-Laning Highway Project | 735 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5250 | Completed | Engineering, Procurement & Construction | September 2016 | Forbesganj | Bihar | 31 Dec 2003 | Date of announcement | 2014-08-31 | 5250 | 3329.4 | 1920.6 | Y | 2016-09-30 | Completed | 2011-03-31 | Y | 2010
356 | National Highways Authority Of India | 155597 | Fort Vypin to Matsyafed Tourist Office Road Upgradation Project (Bharatmala) | 1742 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2250 | Announced |  | February 2024 | Fort vypin | Kerala | 12 Apr 2018 | Date of announcement | 2021-09-07 | 2250 | 1333.8 | 916.2 | Y
357 | National Highways Authority Of India | 155597 | Four Lane Bridge Parallel to Vikramshila Setu over Ganga River near Barari Ghat (Connecting Naugachia with Bhagalpur) Project | 1639 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9943.1 | Under Implementation | Engineering, Procurement & Construction | December 2027 | Vikramshila setu | Bihar | 01 Aug 2015 | Date of announcement | 2022-07-08 | 9943.1 | 17000 | -7056.9 | N | 2027-12-31 | Initial completion date | 2025-05-31 | Y | 944 | 2021-02-20 | Bids awarded
358 | National Highways Authority Of India | 155597 | Four Lane Bridge across River Ganga at Farakka (including approaches connecting Farraka-Raiganj (NH-34) section) Project | 1246 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5210 | Under Implementation | Engineering, Procurement & Construction |  | Farakka | West Bengal | 10 Nov 2016 | Date of announcement | 2019-04-19 | 5210 | 5166.2 | 43.8 | Y | [5 empty] | 2018-08-20 | Bids awarded
359 | National Highways Authority Of India | 155597 | Four Lane Bypass on Western side of Gwalior Project (Rairu Nirwali-Girwai) | 1675 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5369.1 | Announced |  |  | Girwai | Madhya Pradesh | 01 Apr 2015 | Date of announcement | 2021-01-21 | 5369.1 | 4820 | 549.1 | Y
360 | National Highways Authority Of India | 155597 | Four Lane Connector from Delhi-Meerut Expressway to NH-235 (Package 5 of Delhi-Meerut Expressway) Project | 2013 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5345.8 | Under Implementation | Engineering, Procurement & Construction |  | Delhi | NCT of Delhi | 01 Jan 2021 | Date of announcement | 2021-03-11 | 5345.8 | 5345.8 | 0 | N | [5 empty] | 2021-11-15 | Bids awarded
361 | National Highways Authority Of India | 155597 | Four Lane Elevated Highway at Gopalganj Town (NH-27) Project | 2001 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2390 | Under Implementation | Engineering, Procurement & Construction | May 2024 | Gopalganj | Bihar | 01 Dec 2017 | Date of announcement | 2022-11-25 | 2390 | 2431.9 | -41.9 | N | [5 empty] | 2021-11-24 | Bids awarded
362 | National Highways Authority Of India | 155597 | Four Lane Greenfield Jabalpur City Bypass/Outer Ring Road Project | 1718 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 36000 | Under Implementation | Engineering, Procurement & Construction |  | Jabalpur | Madhya Pradesh | 17 Aug 2016 | Date of announcement | 2022-11-07 | 36000 | 20000 | 16000 | Y | [5 empty] | 2023-03-20 | Bids awarded
363 | National Highways Authority Of India | 155597 | Four Lane Highway from Ghazipur-Ballia-UP/Bihar State Border Section of NH-31 from Buxar Spur Project (Package-IV) | 2105 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3095.1 | Under Implementation | Engineering, Procurement & Construction |  | Ballia | Uttar Pradesh | 12 Apr 2017 | Date of announcement | 2022-08-02 | 3095.1 | 3095.1 | 0 | N | [5 empty] | 2022-12-07 | Bids awarded
364 | National Highways Authority Of India | 155597 | Four Lane Kumta Bypass (NH-66) Project | 1203 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1420 | Announced |  |  | Kumta | Karnataka | 19 Nov 2015 | Date of announcement | 2016-05-26 | 1420 | 1420 | 0 | N
365 | National Highways Authority Of India | 155597 | Four Lane ROB near Neleshwaram (NH-66) Project | 1409 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 831.6 | Under Implementation | Engineering, Procurement & Construction |  | Pallikara railway gate | Kerala | 26 Oct 2017 | Date of announcement | 2021-07-19 | 831.6 | 566.7 | 264.9 | Y | [5 empty] | 2018-03-14 | Bids awarded
366 | National Highways Authority Of India | 155597 | Four Lane Spur of Panipat-Shamli connecting NH-709AD (Panipat-Shamli-Muzaffarnagar) and NH709A (Karnal-Meerut) bypassing Shamli Project | 2010 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1115.5 | Under Implementation | Engineering, Procurement & Construction |  | Panipat | Haryana | 01 Jan 2022 | Date of announcement | 2022-04-06 | 1115.5 | 1115.5 | 0 | N | [5 empty] | 2022-03-15 | Bids awarded
367 | National Highways Authority Of India | 155597 | Four Lane Vehicular Underpass (VUP) at Aler-Jeedikal Cross Road on Hyderabad-Warangal Section of NH-163 Project | 2006 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 355.7 | Under Implementation | Engineering, Procurement & Construction |  | Alair | Telangana | 01 Jan 2021 | Date of announcement | 2021-03-02 | 355.7 | 355.7 | 0 | N | [5 empty] | 2021-07-02 | Bids awarded
368 | National Highways Authority Of India | 155597 | Four Lane Western Side Spur of Rampur-Rudrapur Section connecting NH-24 to NH-87 bypassing Rampur Town Project | 2019 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3117.4 | Under Implementation | Engineering, Procurement & Construction |  | Rampur | Uttar Pradesh | 01 Sep 2021 | Date of announcement | 2021-10-18 | 3117.4 | 3117.4 | 0 | N | [5 empty] | 2022-03-04 | Bids awarded
369 | National Highways Authority Of India | 155597 | Four Laning of Varagali Road from Chillakur Cross to Chintawaram (Package II) Project (Bharatmala) | 1737 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3328.7 | Announced | Engineering, Procurement & Construction |  | Chillakur cross | Andhra Pradesh | 01 Jan 2018 | Date of announcement | 2018-05-15 | 3328.7 | 3328.7 | 0 | N
370 | National Highways Authority Of India | 155597 | Four/ Six Laning of Kharar-Banur-Tepla (NH-205) Road Project | 1773 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 21000 | Shelved |  |  | Banur | Punjab | 22 Nov 2017 | Date of announcement | 2019-09-23 | 21000 | 19758.9 | 1241.1 | Y
371 | National Highways Authority Of India | 155597 | Four/Six-Lane Access Controlled Highway (NH-152D) starting from Junction with Rewari-Kanina road (SH-24) near Kanina to Narnaul Project (Package 8 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1619 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10331.9 | Completed | Engineering, Procurement & Construction | January 2022 | Kanina | Haryana | 01 Jan 2018 | Date of announcement | 2019-12-31 | 10331.9 | 6072.7 | 4259.2 | Y | 2022-07-31 | Initial completion date | 2022-01-31 | Y | 181 | 2019-03-08 | Bids awarded
372 | National Highways Authority Of India | 155597 | GB Nagar Six Lane Expressway Project (Package 4 of Eastern Peripheral Expressway) | 1123 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7893.1 | Completed | Engineering, Procurement & Construction | May 2018 | Gb nagar | Uttar Pradesh | 31 Jan 1995 | Date of announcement | 2014-10-29 | 7893.1 | 7893.1 | 0 | N | 2018-07-31 | Initial completion date | 2009-07-30 | Y | 3288 | 2015-08-13 | Bids awarded
373 | National Highways Authority Of India | 155597 | GB Nagar-Faridabad Six Lane Expressway Project (Package 5 of Eastern Peripheral Expressway) | 997 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6645.3 | Completed | Engineering, Procurement & Construction | May 2018 | Faridabad | Haryana | 31 Jan 1995 | Date of announcement | 2014-10-29 | 6645.3 | 6645.3 | 0 | N | 2018-07-31 | Initial completion date | 2009-07-30 | Y | 3288 | 2015-08-30 | Bids awarded
374 | National Highways Authority Of India | 155597 | Gadu-Porbandar (NH-8E) Two/Four lane Highway Project | 943 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5120 | Completed | Hybrid Annuity | February 2021 | Dwarka | Gujarat | 23 May 2012 | Date of announcement | 2017-10-31 | 5120 | 4019.5 | 1100.5 | Y | 2021-02-18 | Completed | 2015-09-30 | Y | 1968 | 2016-12-15 | Bids awarded
375 | National Highways Authority Of India | 155597 | Gagaria (NH-25)-Baori Kalan-Serwa-Lakdassar-Bakhasar section (NH-925) & Sata-Gandhav section (NH-925 A) Two Lane Highway Project | 1110 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11038.8 | Completed | Engineering, Procurement & Construction | December 2020 | Bawri kalan (baori kallan) | Rajasthan | 05 Apr 2015 | Date of announcement | 2019-02-28 | 11038.8 | 6250 | 4788.8 | Y | 2020-12-24 | Completed | 2020-09-30 | Y | 85 | 2018-02-26 | Bids awarded
376 | National Highways Authority Of India | 155597 | Gagodhar-Radhanpur NH-15 (Package 5) Project | 235 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2880 | Completed | Engineering, Procurement & Construction | May 2008 | Gagodhar | Gujarat | 01 Oct 2002 | Date of announcement | 2006-01-01 | 2880 | 4102.4 | -1222.4 | N | [5 empty] | 2005-02-01 | Bids awarded
377 | National Highways Authority Of India | 155597 | Gandhidham-Samakhiali (PackII) Port Connectivity Highway Project | 200 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 674 | Completed | Engineering, Procurement & Construction | July 2002 | Gandhidham | Gujarat | 01 Apr 1999 | Date of announcement | 2002-01-01 | 674 | 880 | -206 | N | 2002-07-31 | Completed | 2001-05-31 | Y | 426 | 1999-05-15 | Bids awarded
378 | National Highways Authority Of India | 155597 | Gandhidham-Samakhiali(PackIII)Port Connectivity Project | 201 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 473.5 | Completed | Engineering, Procurement & Construction | March 2002 | Gandhidham | Gujarat | 01 Mar 1999 | Date of announcement | 2002-01-01 | 473.5 | 646.4 | -172.9 | N | 2002-03-31 | Initial completion date | 2001-05-31 | Y | 304 | 1999-05-01 | Bids awarded
379 | National Highways Authority Of India | 155597 | Ganga Bridge to Rama Devi Crossing (Jajmau-Ramadevi) NH-25 Section Highway Project | 588 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2016.6 | Completed | Engineering, Procurement & Construction | June 2016 | Jajmau | Uttar Pradesh | 31 Dec 2003 | Date of announcement | 2009-10-01 | 2016.6 | 1590 | 426.6 | Y | 2016-06-30 | Completed | 2010-12-31 | Y | 2008 | 2005-05-31 | Bids awarded
380 | National Highways Authority Of India | 155597 | Gangavaram Port Greenfield Bypass Road Development Project | 1376 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 800 | No Information |  |  | Gangavaram | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2016-06-03 | 800 | 800 | 0 | N
381 | National Highways Authority Of India | 155597 | Garamore to Bamanbore (NH-8A) Highway Project | 233 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3347.2 | Completed |  | July 2009 | Bamanbore | Gujarat | 31 Dec 2003 | Date of announcement | 2009-07-01 | 3347.2 | 2899.2 | 448 | Y
382 | National Highways Authority Of India | 155597 | Garamore-Gagodhar NH-8A (Package 4) Project | 234 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4795.4 | Completed |  | February 2012 | Gagodhar | Gujarat | 05 Dec 2002 | Bids invited | 2010-04-01 | 4795.4 | 3390 | 1405.4 | Y | 2012-03-31 | Initial completion date | 2009-06-01 | Y | 1034
383 | National Highways Authority Of India | 155597 | Garhmukteshwar-Moradabad (NH-24) Highway Project | 343 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3100 | Completed |  | October 2012 | Garhmukteshwar | Uttar Pradesh | 30 Apr 2000 | Date of announcement | 2012-06-30 | 3100 | 2300 | 800 | Y | 2012-10-31 | Completed | 2009-05-31 | Y | 1249 | 2005-03-31 | Bids awarded
384 | National Highways Authority Of India | 155597 | Gauribidanur Two Lane Bypass (NH-69) Project | 1870 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 406.8 | Under Implementation | Engineering, Procurement & Construction |  | Gauribidanur | Karnataka | 01 Jul 2020 | Date of announcement | 2020-12-19 | 406.8 | 406.8 | 0 | N
385 | National Highways Authority Of India | 155597 | Ghagas-Hamirpur (NH-88) Highway Project | 1075 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2900 | No Information |  |  | Ghagas | Himachal Pradesh | 01 Jan 2015 | Date of announcement | 2015-03-23 | 2900 | 2900 | 0 | N
386 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project | 892 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15260 | Under Implementation | Engineering, Procurement & Construction |  | Ghaghar bridge | Uttar Pradesh | 01 Mar 2012 | Date of announcement | 2018-04-17 | 15260 | 13538.9 | 1721.1 | Y | [5 empty] | 2015-08-25 | Bids awarded
387 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project (Package-I) | 1081 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6740 | Completed | Engineering, Procurement & Construction | March 2019 | Basti | Uttar Pradesh | 01 Mar 2012 | Date of announcement | 2017-10-31 | 6740 | 6116.5 | 623.5 | Y | 2019-07-31 | Initial completion date | 2018-05-31 | Y | 426 | 2015-03-31 | Bids awarded
388 | National Highways Authority Of India | 155597 | Ghaziabad-GB Nagar Six Lane Expressway Project (Package 3 of Eastern Peripheral Expressway) | 996 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7885.1 | Completed | Engineering, Procurement & Construction | May 2018 | Gb nagar | Uttar Pradesh | 31 Jan 1995 | Date of announcement | 2014-10-29 | 7885.1 | 7885.1 | 0 | N | 2018-07-31 | Initial completion date | 2009-07-31 | Y | 3287 | 2015-08-30 | Bids awarded
389 | National Highways Authority Of India | 155597 | Ghaziabad-Hapur Highway & Hapur Bypass Project | 56 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1060 | Completed | Engineering, Procurement & Construction | August 2002 | Ghaziabad | Uttar Pradesh | 01 Mar 1999 | Date of announcement | 2002-07-01 | 1060 | 1000 | 60 | Y | 2002-08-13 | Completed | 2002-03-31 | Y | 135 | 1999-04-10 | Bids awarded
390 | National Highways Authority Of India | 155597 | Ghoshpukur (Dhupguri)-Salsalabari (NH-31D) Four Lane Highway Project (Package-II) | 1121 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19952 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Falakata | West Bengal | 01 Dec 2009 | Date of announcement | 2018-05-31 | 19952 | 9720 | 10232 | Y | 2024-12-31 | Completion expected by | 2013-06-30 | Y | 4202 | 2018-03-28 | Bids awarded
391 | National Highways Authority Of India | 155597 | Ghoshpukur-Salsalabari (Dhupguri) (NH-31D) Four Lane Highway Project (Package-I) | 717 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17550 | Completed | Engineering, Procurement & Construction | August 2021 | Falakata | West Bengal | 01 Dec 2009 | Date of announcement | 2017-10-31 | 17550 | 11350 | 6200 | Y | 2021-08-05 | Completed | 2013-06-30 | Y | 2958 | 2015-06-01 | Bids awarded
392 | National Highways Authority Of India | 155597 | Giddalur-Vinukonda (NH-544D) Two Lane Highway Project (Bharatmala) | 1444 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9256 | Completed | Hybrid Annuity | February 2021 | Giddalur | Andhra Pradesh | 20 Dec 2017 | Date of announcement | 2021-02-18 | 9256 | 5650.9 | 3605.1 | Y | 2021-02-28 | Initial completion date | 2021-02-04 | N |  | 2018-03-26 | Bids awarded
393 | National Highways Authority Of India | 155597 | Goa/Karnataka Border to Panaji (NH-4A) Four-Laning Highway Project | 1041 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8000 | Under Implementation | Build Operate Transfer |  | Panaji | Goa | 12 Aug 2008 | Date of announcement | 2010-01-01 | 8000 | 3824.6 | 4175.4 | Y | [5 empty] | 2009-06-17 | Bids awarded
394 | National Highways Authority Of India | 155597 | Gogunda-Udaipur NH-76 Highway Project | 642 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3130 | Completed |  | December 2009 | Gogunda | Rajasthan | 31 Dec 2003 | Date of announcement | 2009-12-31 | 3130 | 2660 | 470 | Y | 2009-12-31 | Completed | 2009-08-31 | Y | 122
395 | National Highways Authority Of India | 155597 | Gohana-Sonepat (NH-352A) Four Lane Highway Project (Package 2) (Bharatmala) | 1632 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15020 | Under Implementation | Hybrid Annuity |  | Gohana | Haryana | 01 Jan 2018 | Date of announcement | 2020-07-13 | 15020 | 6225.8 | 8794.2 | Y | [5 empty] | 2019-03-08 | Bids awarded
396 | National Highways Authority Of India | 155597 | Gola-Bokaro (Jaina More) (NH-320) Four Lane Greenfield Highway Project (Package-I) (Bharatmala) | 1992 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10070 | Under Implementation | Hybrid Annuity | April 2024 | Bokaro | Jharkhand | 01 Dec 2020 | Date of announcement | 2023-03-19 | 10070 | 10030 | 40 | Y | [5 empty] | 2022-03-29 | Bids awarded
397 | National Highways Authority Of India | 155597 | Gollapudi to Manipal Hospital Bypass Road Project | 585 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 12000 | No Information |  |  | Gollapudi | Andhra Pradesh | 22 May 2009 | Date of announcement | 2009-05-22 | 12000 | 12000 | 0 | N
398 | National Highways Authority Of India | 155597 | Gondal Chowkdi (NH-27) Six Lane Elevated Flyover (Bridge) Project | 1522 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 890 | Completed | Engineering, Procurement & Construction | March 2023 | Gondal chowkdi | Gujarat | 04 Jul 2018 | Date of announcement | 2023-03-05 | 890 | 880 | 10 | Y | 2023-03-05 | Completed | 2020-07-04 | Y | 974 | 2018-12-05 | Bids awarded
399 | National Highways Authority Of India | 155597 | Gondal-Ribda Section(EW-10/GJ) Highway Project | 195 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 405 | Completed | Engineering, Procurement & Construction | January 2003 | Gondal | Gujarat | 01 Mar 2001 | Date of announcement | 2002-01-01 | 405 | 680 | -275 | N | 2003-05-31 | Initial completion date | 2003-01-31 | Y | 120 | 2001-09-15 | Bids awarded
400 | National Highways Authority Of India | 155597 | Gopalganj-Chhapra Two-Laning Highway Project | 540 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11920 | Completed | Engineering, Procurement & Construction | December 2020 | Chhapra | Bihar | 21 Nov 2008 | Date of announcement | 2020-12-20 | 11920 | 3250 | 8670 | Y | 2020-12-20 | Completed | 2014-05-29 | Y | 2397 | 2010-05-31 | Bids awarded
401 | National Highways Authority Of India | 155597 | Gopalganj-Muzaffarpur section of NH-28 Four Lane Highway project (Lucknow - Muzaffarpur) | 1608 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 719.3 | No Information |  |  | Gopalganj | Bihar | 31 Jul 2005 | Date of announcement | 2018-10-11 | 719.3 | 719.3 | 0 | N | [5 empty] | 2005-10-20 | Bids awarded
402 | National Highways Authority Of India | 155597 | Gorakhpur-Bareilly Road Corridor Project | 2090 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 264860 | Announced |  |  | Bareilly | Uttar Pradesh | 01 Sep 2021 | Date of announcement | 2023-02-03 | 264860 | 264860 | 0 | N
403 | National Highways Authority Of India | 155597 | Gorakhpur-Forbesganj-Siliguri Four/Six Lane Expressway Project | 1932 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 320000 | Announced |  |  | Gorakhpur | Uttar Pradesh | 01 Oct 2021 | Date of announcement | 2022-01-05 | 320000 | 60000 | 260000 | Y
404 | National Highways Authority Of India | 155597 | Gorakhpur-Gopalganj (NH-28) Four Laning Highway Project | 1085 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5818.4 | Completed | Engineering, Procurement & Construction | June 2020 | Gopalganj | Bihar | 15 Mar 2003 | Date of announcement | 2015-05-26 | 5818.4 | 5818.4 | 0 | N | 2020-06-26 | Completed | 2008-12-31 | Y | 4195 | 2005-10-20 | Bids awarded
405 | National Highways Authority Of India | 155597 | Gorakhpur-Sonauli Highway Project | 645 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 181 | No Information |  |  | Gorakhpur | Uttar Pradesh | 22 Jul 2009 | Date of announcement | 2009-07-22 | 181 | 181 | 0 | N
406 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4249.6 | Completed |  | September 2010 | Barwa-Adda | Jharkhand | 01 Jun 2001 | Date of announcement | 2010-09-30 | 4249.6 | 3160 | 1089.6 | Y | 2010-10-30 | Initial completion date | 2004-12-31 | Y | 2129
407 | National Highways Authority Of India | 155597 | Govindpur (Rajgunj)-Chas-West Bengal Border (NH-32) Two/Four Laning Highway Project | 824 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11440 | Completed | Engineering, Procurement & Construction | June 2022 | Chas | Jharkhand | 22 Nov 2010 | Date of announcement | 2022-06-02 | 11440 | 2710 | 8730 | Y | 2022-06-02 | Completed | 2018-08-31 | Y | 1371 | 2016-07-19 | Bids awarded
408 | National Highways Authority Of India | 155597 | Gowthami River Bridge Project | 172 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1029 | Completed |  | April 2005 | Gowthami river | Andhra Pradesh | 01 Aug 2001 | Date of announcement | 2001-09-01 | 1029 | 1029 | 0 | N | 2005-04-30 | Completed | 2003-12-31 | Y | 486 | 2001-08-20 | Bids awarded
409 | National Highways Authority Of India | 155597 | Greenfield Road Connecting North & South Industrial Cluster of Khandaleru Creek near Krishnapatnam Port Project | 1716 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3914.2 | Under Implementation | Engineering, Procurement & Construction |  | Khandaleru creek | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2021-08-02 | 3914.2 | 5800 | -1885.8 | N | [5 empty] | 2023-03-31 | Bids awarded
410 | National Highways Authority Of India | 155597 | Guddehosur to Start of Ramanathapura Terakanambi Road Junction (NH-275) Four Lane Highway Project (Package-2 of Mysuru-Kushalnagar Highway) | 1985 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10678.1 | Under Implementation | Hybrid Annuity |  | Guddehosur | Karnataka | 01 Dec 2021 | Date of announcement | 2021-12-31 | 10678.1 | 10678.1 | 0 | N | [5 empty] | 2023-03-10 | Bids awarded
411 | National Highways Authority Of India | 155597 | Gujadal-Porbandar NH8B Project | 91 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2812 | No Information |  |  | Porbandar | Gujarat | 01 Jul 2002 | Date of announcement | 2002-07-01 | 2812 | 2812 | 0 | N
412 | National Highways Authority Of India | 155597 | Guna Bypass Project | 883 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 600 | Completed | Build Operate Transfer | December 2007 | Guna | Madhya Pradesh | 01 Mar 2003 | Date of announcement | 2005-01-01 | 600 | 400 | 200 | Y | 2007-12-31 | Initial completion date | 2007-12-31 | N |  | 2005-02-01 | Bids awarded
413 | National Highways Authority Of India | 155597 | Gundla Pochampalli to Bowenpalli, Shivarampalli to Thondapalli Highway Project | 322 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 990 | Completed | Engineering, Procurement & Construction | June 2015 | Bowenpalli | Telangana | 15 Mar 2000 | Date of announcement | 2008-07-31 | 990 | 990 | 0 | N | 2015-06-30 | Completed | 2005-01-31 | Y | 3802 | 2001-03-15 | Bids awarded
414 | National Highways Authority Of India | 155597 | Gundlapochampally-Bowenpally Six Lane Highway (NH-44) Project | 2002 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5220 | Under Implementation | Engineering, Procurement & Construction |  | Bowenpalli | Telangana | 01 Dec 2021 | Date of announcement | 2022-04-29 | 5220 | 4222.9 | 997.1 | Y | [5 empty] | 2022-03-15 | Bids awarded
415 | National Highways Authority Of India | 155597 | Gundugolanu-Kalaparru (NH-5) (New NH-16) Six Lane Highway Project (Bharatmala) | 1828 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5786.2 | Under Implementation | Engineering, Procurement & Construction |  | Gundugolanu | Andhra Pradesh | 01 Jan 2018 | Date of announcement | 2020-08-09 | 5786.2 | 5054 | 732.2 | Y | [5 empty] | 2019-10-01 | Bids awarded
416 | National Highways Authority Of India | 155597 | Gundugolanu-Rajahmundry Six Laning Highway Project | 984 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16170 | No Information | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Gundugolanu | Andhra Pradesh | 15 Sep 2011 | Date of announcement | 2012-03-30 | 16170 | 17510 | -1340 | N | [5 empty] | 2012-04-02 | Bids awarded
417 | National Highways Authority Of India | 155597 | Gurgaon-Kotputli Highway Project | 40 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3800 | Completed | Engineering, Procurement & Construction | March 2001 | Gurgaon | Haryana | 01 Mar 1998 | Date of announcement | 2001-01-01 | 3800 | 2985 | 815 | Y | 2001-03-20 | Completed | 1998-06-30 | Y | 994 | 1999-03-01 | Bids awarded
418 | National Highways Authority Of India | 155597 | Gurgaon-Pataudi-Rewari (NH-352W) Four-Laning Highway Project | 1815 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15240 | Under Implementation | Hybrid Annuity | November 2023 | Farukhnagar | Telangana | 31 Jan 2015 | Date of announcement | 2020-07-14 | 15240 | 2910 | 12330 | Y | 2023-11-30 | Completion expected by | 2022-12-31 | Y | 334 | 2020-12-10 | Bids awarded
419 | National Highways Authority Of India | 155597 | Guru Sikhar-Abu Road (connecting NH) Project | 1236 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | No Information |  |  | Abu road | Rajasthan | 20 Dec 2016 | Date of announcement | 2016-12-20 | 3000 | 3000 | 0 | N
420 | National Highways Authority Of India | 155597 | Gurvaygudem Village-Devarapalle Village Four Lane Access Controlled Greenfield Highway Project (Package 5 of Khammam-Devarapalle NH-365BG) | 1886 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8174.8 | Under Implementation |  | September 2024 | Devarapalle village | Andhra Pradesh | 01 Apr 2018 | Date of announcement | 2022-12-21 | 8174.8 | 7119.4 | 1055.4 | Y | [5 empty] | 2021-09-15 | Bids awarded
421 | National Highways Authority Of India | 155597 | Guwahati Bypass (AS 14 A) Highway Project | 716 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 337.8 | Completed |  | January 2009 | Guwahati | Assam | 31 Aug 2005 | Date of announcement | 2005-08-31 | 337.8 | 337.8 | 0 | N
422 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW-14/AS) Highway Project | 198 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 636.9 | Completed | Engineering, Procurement & Construction | June 2004 | Guwahati | Assam | 01 May 2001 | Date of announcement | 2004-04-01 | 636.9 | 420 | 216.9 | Y | 2004-06-30 | Completed | 2003-01-31 | Y | 516 | 2001-09-15 | Bids awarded
423 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW/7) Highway Project__ | 224 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 548.7 | Completed | Engineering, Procurement & Construction | December 2003 | Guwahati | Assam | 01 Jun 2000 | Date of announcement | 2002-01-01 | 548.7 | 548.7 | 0 | N | 2003-12-31 | Initial completion date | 2002-06-30 | Y | 549 | 2000-06-15 | Bids awarded
424 | National Highways Authority Of India | 155597 | Guwahati Six Lane Bypass (NH-37) (section of Jalukbari-Koinadhora Highway) Project | 1319 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3000 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Guwahati | Assam | 27 Jul 2017 | Date of announcement | 2023-05-05 | 3000 | 3560.2 | -560.2 | N | 2024-08-31 | Initial completion date | 2023-12-31 | Y | 244 | 2021-12-10 | Bids awarded
425 | National Highways Authority Of India | 155597 | Guwahati-Nalbari (NH-31) Highway Project | 282 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6230 | Completed | Engineering, Procurement & Construction | August 2016 | Guwahati | Assam | 01 Dec 2003 | Date of announcement | 2014-08-31 | 6230 | 1759.6 | 4470.4 | Y | 2016-08-31 | Completed | 2008-04-30 | Y | 3045
426 | National Highways Authority Of India | 155597 | HP/Punjab Border-Mandi (NH-20) Four Lane Highway Project | 1222 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 44325 | No Information |  |  | Mandi | Himachal Pradesh | 31 Oct 2016 | Date of announcement | 2017-06-07 | 44325 | 44325 | 0 | N
427 | National Highways Authority Of India | 155597 | Hajipur-Muzaffarpur (NH-77) Eight Lane Road Project | 1789 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6717 | Completed | Build Operate Transfer | April 2021 | Hajipur | Bihar | 29 May 2018 | Date of announcement | 2021-04-29 | 6717 | 6717 | 0 | N
428 | National Highways Authority Of India | 155597 | Halvad Cross Road (NH-8A) Flyover Project with approaches (on Bamanbore-Garamore section) | 1254 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 220 | Completed | Engineering, Procurement & Construction | June 2018 | Halvad cross raod | Gujarat | 30 Oct 2016 | Date of announcement | 2017-10-31 | 220 | 246.2 | -26.2 | N | 2018-08-31 | Initial completion date | 2018-06-27 | Y | 65 | 2016-12-28 | Bids awarded
429 | National Highways Authority Of India | 155597 | Hanamkonda (NH163) Two Lane Road Project | 2029 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3170 | Under Implementation |  |  | Hanamkonda | Telangana | 01 Apr 2022 | Date of announcement | 2022-04-29 | 3170 | 3170 | 0 | N
430 | National Highways Authority Of India | 155597 | Handia-Varanasi (TNHP/III-C) Highway Project | 690 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2860 | Completed | Engineering, Procurement & Construction | April 2008 | Handia | Uttar Pradesh | 01 Mar 2001 | Bids invited | 2001-03-01 | 2860 | 2860 | 0 | N | [5 empty] | 2001-03-15 | Bids awarded
431 | National Highways Authority Of India | 155597 | Hanspal Flyover (NH-16) Project | 1776 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 246.3 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Hanspal, bhubaneswar | Odisha | 01 Apr 2019 | Date of announcement | 2020-06-08 | 246.3 | 320 | -73.7 | N
432 | National Highways Authority Of India | 155597 | Hapur-Garhmukteshwar (NH-24) Highway Project | 342 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2850 | Completed | Engineering, Procurement & Construction | November 2013 | Garhmukteshwar | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2013-03-31 | 2850 | 2300 | 550 | Y | 2013-11-30 | Initial completion date | 2009-12-31 | Y | 1430
433 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 14104.9 | Under Implementation | Engineering, Procurement & Construction |  | Harangajo | Assam | 01 Dec 2003 | Date of announcement | 2009-07-01 | 14104.9 | 14104.9 | 0 | N | [5 empty] | 2005-11-15 | Bids awarded
434 | National Highways Authority Of India | 155597 | Harda-Temagaon (NH-47) Four Lane Highway Project (Package 1 of Harda-Betul) (Bharatmala) | 1796 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6760 | Under Implementation | Hybrid Annuity | September 2023 | Harda | Madhya Pradesh | 14 Mar 2018 | Date of announcement | 2022-03-17 | 6760 | 4991.7 | 1768.3 | Y | 2023-09-10 | Completion expected by | 2022-06-30 | Y | 437 | 2020-03-05 | Bids awarded
435 | National Highways Authority Of India | 155597 | Haridwar Ring Road Project | 1451 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 20000 | Under Implementation |  |  | Haridwar | Uttarakhand | 28 Dec 2017 | Date of announcement | 2022-06-24 | 20000 | 15660 | 4340 | Y | [5 empty] | 2022-02-23 | Bids awarded
436 | National Highways Authority Of India | 155597 | Haridwar-Nagina (NH-34&734) Four Lane Highway Project | 1024 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16590 | Under Implementation | Engineering, Procurement & Construction |  | Haridwar | Uttarakhand | 15 Dec 2009 | Date of announcement | 2017-10-31 | 16590 | 9150 | 7440 | Y | [5 empty] | 2016-03-31 | Bids awarded
437 | National Highways Authority Of India | 155597 | Hariharganj-Rudwa (Near Parwa More) (NH-98) Four Lane Highway project | 1455 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10293.6 | Under Implementation | Hybrid Annuity | February 2024 | Hariharganj | Jharkhand | 15 Jan 2018 | Date of announcement | 2022-12-17 | 10293.6 | 5440.7 | 4852.9 | Y | [5 empty] | 2020-10-26 | Bids awarded
438 | National Highways Authority Of India | 155597 | Harmu Road Flyover (LPN Nath Shahdeo Chowk-Kartik Oraon Chowk) Project | 1764 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1300 | Shelved |  |  | Harmu | Jharkhand | 01 Mar 2017 | Date of announcement | 2018-06-02 | 1300 | 1210 | 90 | Y | [5 empty] | 2017-04-27 | Bids awarded
439 | National Highways Authority Of India | 155597 | Haryana-Rajasthan border and ends at Junction with SH44 Eight Lane Carriageway Project (Package 4 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1541 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12282 | Completed | Engineering, Procurement & Construction | June 2022 | Alwar | Rajasthan | 31 Mar 1998 | Date of announcement | 2019-08-10 | 12282 | 11899.2 | 382.8 | Y | 2022-06-26 | Completed | 2021-12-31 | Y | 177
440 | National Highways Authority Of India | 155597 | Hassan (NH-75) Four Lane Bypass Project | 1650 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3721.9 | Under Implementation | Engineering, Procurement & Construction |  | Hassan | Karnataka | 01 Jan 2017 | Date of announcement | 2019-07-04 | 3721.9 | 3409.9 | 312 | Y | [5 empty] | 2020-07-06 | Bids awarded
441 | National Highways Authority Of India | 155597 | Hassan-Huliyar-Hiriyur (NH-150A) Four Lane Road Project | 1920 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22100 | Under Implementation | Engineering, Procurement & Construction |  | Hassan | Karnataka | 01 Apr 2019 | Date of announcement | 2021-07-27 | 22100 | 20000 | 2100 | Y
442 | National Highways Authority Of India | 155597 | Hassan-Maranahalli (NH-75) Four Lane Highway Project (Hassan-B.C. Road Pkg-I) | 784 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16050 | Under Implementation | Design, Build, Finance and Operate |  | B.c. road | Karnataka | 19 May 2010 | Date of announcement | 2014-10-10 | 16050 | 3900 | 12150 | Y | [5 empty] | 2016-04-05 | Bids awarded
443 | National Highways Authority Of India | 155597 | Hathipali-Hosur(NS/11) Highway Project | 45 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 470 | Completed | Engineering, Procurement & Construction | August 2002 | Hathipalli | Karnataka | 01 Dec 1998 | Date of announcement | 2002-01-01 | 470 | 400 | 70 | Y | 2002-08-31 | Completed | 2001-12-31 | Y | 243 | 1999-12-15 | Bids awarded
444 | National Highways Authority Of India | 155597 | Haveri-Harihar (NH-4) Highway Project | 749 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2040 | Completed |  | October 2013 | Harihar | Karnataka | 30 Apr 2000 | Date of announcement | 2013-08-31 | 2040 | 1966.5 | 73.5 | Y | 2013-10-31 | Initial completion date | 2010-07-31 | Y | 1188
445 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga Bypass) Highway Project | 115 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1545 | Completed |  | December 2010 | Chitradurga | Karnataka | 30 Apr 2000 | Date of announcement | 2010-03-31 | 1545 | 720 | 825 | Y | 2010-12-31 | Initial completion date | 2003-12-31 | Y | 2557 | 2001-09-01 | Bids awarded
446 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga-Sira) Highway Project | 116 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3040 | Completed |  | May 2008 | Chitradurga | Karnataka | 01 Jun 2001 | Date of announcement | 2002-01-01 | 3040 | 2680 | 360 | Y | [5 empty] | 2001-09-01 | Bids awarded
447 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Harihar-Chitradurga) Highway Project | 81 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2075.6 | Completed |  | October 2013 | Chitradurga | Karnataka | 30 Apr 2000 | Date of announcement | 2009-07-01 | 2075.6 | 3180 | -1104.4 | N | 2013-10-31 | Initial completion date | 2003-12-31 | Y | 3592 | 2001-09-01 | Bids awarded
448 | National Highways Authority Of India | 155597 | Haveri-Tumkur(Sira-Tumkur) Highway Project | 75 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1840 | Completed | Engineering, Procurement & Construction | January 2005 | Sira | Karnataka | 01 Dec 2000 | Date of announcement | 2002-01-01 | 1840 | 10000 | -8160 | N | [5 empty] | 2001-09-15 | Bids awarded
449 | National Highways Authority Of India | 155597 | Hebbal flyover to Bengaluru International Airport Road Project | 801 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6793.6 | Completed | Design Build Finance Operate Transfer | March 2014 | Bangalore | Karnataka | 13 Jan 2010 | Date of announcement | 2010-01-13 | 6793.6 | 6793.6 | 0 | N | 2014-03-31 | Initial completion date | 2012-11-30 | Y | 486
450 | National Highways Authority Of India | 155597 | Hebbal-Kempapura Junction Skywalk Project | 1065 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 24 | Completed |  | May 2017 | Kempapura | Karnataka | 01 Mar 2011 | Date of announcement | 2015-03-08 | 24 | 24 | 0 | N | 2017-06-30 | Initial completion date | 2017-05-13 | Y | 48
451 | National Highways Authority Of India | 155597 | Hero Honda Chowk Eight Lane Flyover & Underpass Project | 972 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1980 | Completed | Engineering, Procurement & Construction | May 2018 | Hero honda chowk | Haryana | 02 Mar 2009 | Date of announcement | 2017-07-24 | 1980 | 1000 | 980 | Y | 2018-05-27 | Completed | 2017-05-31 | Y | 361 | 2014-11-26 | Bids awarded
452 | National Highways Authority Of India | 155597 | Hero Honda Chowk FOB Project | 1207 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 42 | No Information |  |  | Hero honda chowk | Haryana | 01 Feb 2010 | Date of announcement | 2013-05-11 | 42 | 42 | 0 | N
453 | National Highways Authority Of India | 155597 | High Level Bridge over Cheruthoni River connecting Thodupuzha-Puliuyanmala (NH-185) Project | 1865 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 238.3 | Under Implementation |  |  | Cheruthoni river | Kerala | 15 Sep 2018 | Date of announcement | 2020-10-12 | 238.3 | 150 | 88.3 | Y
454 | National Highways Authority Of India | 155597 | Himalaya Truck Factory FOB Project | 830 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Himalaya truck factory | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N
455 | National Highways Authority Of India | 155597 | Himatnagar-Chiloda (Near Ahmedabad) (UG-IV) Highway Project | 133 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1750 | Completed | Engineering, Procurement & Construction | December 2005 | Chiloda | Gujarat | 01 Mar 2001 | Date of announcement | 2003-07-01 | 1750 | 2080 | -330 | N | 2005-12-31 | Completed | 2004-09-30 | Y | 457 | 2003-06-01 | Bids awarded
456 | National Highways Authority Of India | 155597 | Hinganghat-Nandgaon Junction (NH-44) Flyover Project | 1640 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 860 | Completed | Engineering, Procurement & Construction | June 2021 | Hinganghat | Maharashtra | 24 Oct 2018 | Date of announcement | 2021-06-17 | 860 | 665.6 | 194.4 | Y | 2021-06-17 | Completed | 2020-12-03 | Y | 196 | 2018-10-24 | Bids awarded
457 | National Highways Authority Of India | 155597 | Hiranagar CRPF Service Road Project (on NH-44 Pathankot-Jammu section) | 1753 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19.8 | No Information |  |  | Hiranagar | Jammu & Kashmir | 05 Jun 2019 | Date of announcement | 2019-06-05 | 19.8 | 19.8 | 0 | N
458 | National Highways Authority Of India | 155597 | Hiranagar-Vijaypur Highway project | 727 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1513.6 | Completed |  | October 2011 | Hiranagar | Jammu & Kashmir | 01 Sep 2005 | Date of announcement | 2005-09-01 | 1513.6 | 1513.6 | 0 | N | 2011-10-31 | Initial completion date | 2010-06-30 | Y | 488
459 | National Highways Authority Of India | 155597 | Hisar-Dabwali (NH-10) Four Lane Highway Project (Package-I) | 911 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5797.6 | Completed | Engineering, Procurement & Construction | May 2018 | Dabwali | Haryana | 01 Apr 2012 | Date of announcement | 2014-12-16 | 5797.6 | 5745.9 | 51.7 | Y | 2018-05-31 | Completed | 2018-02-28 | Y | 92 | 2015-03-03 | Bids awarded
460 | National Highways Authority Of India | 155597 | Hisar-Dabwali (NH-10) Four Lane Highway Project (Package-II) | 1005 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6480 | Completed | Engineering, Procurement & Construction | March 2018 | Dabwali | Haryana | 01 Apr 2012 | Date of announcement | 2017-10-31 | 6480 | 7016.2 | -536.2 | N | 2018-05-31 | Initial completion date | 2018-03-05 | Y | 87 | 2015-03-03 | Bids awarded
461 | National Highways Authority Of India | 155597 | Hodal-Bhiruki-Hasanpur-Kashipur-Kushak-Barauli-Ghori-Dadota-Mohna-Arwa-Chandpur-Manjhawali Four Laning Highway Project | 1028 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8000 | No Information | Engineering, Procurement & Construction |  | Arwa | Haryana | 01 Sep 2014 | Date of announcement | 2014-09-09 | 8000 | 8000 | 0 | N
462 | National Highways Authority Of India | 155597 | Hoskote-Dobbaspet (NH-648) Four/Six Laning Highway Project (Banglore Ring Road) | 1406 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11533 | Under Implementation | Hybrid Annuity |  | Dobbaspet | Karnataka | 01 Jan 2012 | Date of announcement | 2012-03-23 | 11533 | 7206.9 | 4326.1 | Y | [5 empty] | 2012-03-31 | Bids awarded
463 | National Highways Authority Of India | 155597 | Hospet-Bellary-Karnataka/AP Border Four Lane Highway Project | 1037 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16219.6 | Under Implementation | Hybrid Annuity |  | Bellary | Karnataka | 29 Oct 2010 | Date of announcement | 2016-04-06 | 16219.6 | 12541 | 3678.6 | Y | [5 empty] | 2011-10-30 | Bids awarded
464 | National Highways Authority Of India | 155597 | Hosur-Krishnagiri Four Lane Highway Project | 17 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2130 | Completed | Engineering, Procurement & Construction | February 2004 | Hosur | Tamil Nadu | 01 Jun 1997 | Date of announcement | 2002-01-01 | 2130 | 1500 | 630 | Y | 2004-06-30 | Initial completion date | 2004-02-09 | Y | 142 | 2001-06-11 | Bids awarded
465 | National Highways Authority Of India | 155597 | Hotel Radisson Blu-Hotel Pride Flyover Project (on Wardha Road) | 1054 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5000 | Completed |  | November 2020 | Hotel pride | Maharashtra | 15 Mar 2014 | Date of announcement | 2016-02-23 | 5000 | 1900 | 3100 | Y
466 | National Highways Authority Of India | 155597 | Hridaipur-Shahapur (NH-31) Four Lane Greenfield Highway Project (Package-I of Ghazipur-Ballia-UP/Bihar State Border) | 1284 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8452.8 | Under Implementation | Engineering, Procurement & Construction |  | Hridaipur | Uttar Pradesh | 12 Apr 2017 | Date of announcement | 2022-08-02 | 8452.8 | 4836.4 | 3616.4 | Y | [5 empty] | 2022-12-12 | Bids awarded
467 | National Highways Authority Of India | 155597 | Hubli-Ankola Six lane Road Project (Port Connectivity) | 1726 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 25380 | No Information |  |  | Ankola | Karnataka | 01 Dec 2016 | Date of announcement | 2019-01-31 | 25380 | 25380 | 0 | N
468 | National Highways Authority Of India | 155597 | Hubli-Bijapur(Section of NH-218) Highway Project | 67 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 83.4 | No Information |  |  | Bijapur | Karnataka | 01 Dec 1999 | Date of announcement | 1999-12-01 | 83.4 | 83.4 | 0 | N
469 | National Highways Authority Of India | 155597 | Hubli-Dharwad (NH-4) Six Lane Bypass Project (Bangalore-Pune Section) | 1849 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10500 | Under Implementation | Engineering, Procurement & Construction |  | Dharwad | Karnataka | 01 Apr 2015 | Date of announcement | 2022-02-28 | 10500 | 12000 | -1500 | N | [5 empty] | 2022-07-29 | Bids awarded
470 | National Highways Authority Of India | 155597 | Hubli-Dharwad Ring Road Project | 1333 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 170 | Under Implementation |  |  | Dharwad | Karnataka | 01 Mar 2002 | Date of announcement | 2004-09-17 | 170 | 170 | 0 | N
471 | National Highways Authority Of India | 155597 | Hubli-Hospet NH-67 (Old NH-63) Four Laning Highway Project | 902 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 27222.6 | Completed | Engineering, Procurement & Construction | February 2022 | Hospet | Karnataka | 15 Apr 2012 | Date of announcement | 2022-02-28 | 27222.6 | 13330 | 13892.6 | Y | 2022-02-28 | Completed | 2019-08-31 | Y | 912 | 2016-08-08 | Bids awarded
472 | National Highways Authority Of India | 155597 | Hyderabad (ORR Appa Junction)- Manneguda Four Lane Road (NH-163) Project | 1853 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9284.1 | Under Implementation | Hybrid Annuity |  | Hyderabad (orr appa junction) | Telangana | 28 Jul 2017 | Date of announcement | 2021-09-21 | 9284.1 | 10773.2 | -1489.1 | N | [5 empty] | 2022-03-17 | Bids awarded
473 | National Highways Authority Of India | 155597 | Hyderabad-Bangalore (NH-7,NS Corridor) Highway Project | 442 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13353.9 | Completed | Build Operate Transfer | January 2011 | Bangalore | Karnataka | 31 Oct 2006 | Date of announcement | 2009-07-01 | 13353.9 | 7440 | 5913.9 | Y | 2011-01-31 | Completed | 2009-09-30 | Y | 488
474 | National Highways Authority Of India | 155597 | Hyderabad-Narsapur-Medak Two/Four Laning Highway Project | 1331 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4265.2 | Completed |  | December 2020 | Hyderabad | Telangana | 28 Jul 2015 | Date of announcement | 2018-05-05 | 4265.2 | 4000 | 265.2 | Y | 2020-12-21 | Completed | 2020-04-26 | Y | 239
475 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Icchapuram-Korlam) Highway Project | 99 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1430.5 | Completed | Engineering, Procurement & Construction | March 2006 | Icchapuram | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1430.5 | 1360 | 70.5 | Y | 2006-03-31 | Completed | 2005-12-31 | Y | 90 | 2001-06-30 | Bids awarded
476 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Srikakulam-Champawati) Highway Project | 102 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1719.7 | Completed | Engineering, Procurement & Construction | May 2007 | Champawati | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1719.7 | 1920 | -200.3 | N | 2007-05-31 | Completed | 2003-12-31 | Y | 1247 | 2001-06-01 | Bids awarded
477 | National Highways Authority Of India | 155597 | Icchapuram-Anandapuram (NH-5) Six Laning Highway Project | 848 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17635 | No Information | Public Private Partnership |  | Anandapuram | Andhra Pradesh | 28 Jun 2010 | Date of announcement | 2011-03-18 | 17635 | 17635 | 0 | N
478 | National Highways Authority Of India | 155597 | Icchapuram-Srikakulam-Vishakhapatnam-Ankapalli-Rajahmundary Six-Laning Highway Project | 669 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 35500 | No Information | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Ankapalli | Andhra Pradesh | 28 Oct 2009 | Date of announcement | 2009-10-28 | 35500 | 35500 | 0 | N
479 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Korlam-Palasa AP-4A) Highway Project | 100 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1351.1 | Completed | Engineering, Procurement & Construction | August 2005 | Korlam | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1351.1 | 1210 | 141.1 | Y | 2005-12-31 | Initial completion date | 2004-01-31 | Y | 700 | 2001-06-30 | Bids awarded
480 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Palasa-Srikakulam) Highway Project | 101 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3240 | Completed | Engineering, Procurement & Construction | June 2005 | Palasa | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 3240 | 2960 | 280 | Y | [5 empty] | 2001-06-01 | Bids awarded
481 | National Highways Authority Of India | 155597 | Ichapuram-Sriharikota Elevated Expressway Project | 1170 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 153000 | No Information |  |  | Ichapuram | Andhra Pradesh | 01 Dec 2015 | Date of announcement | 2016-01-10 | 153000 | 153000 | 0 | N
482 | National Highways Authority Of India | 155597 | Improvement & Development to Multi Lane Carriageway (NH-211) from Nagarnaka Junction-Cambridge School Road (Aurangabad) | 1670 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 827.2 | Completed | Engineering, Procurement & Construction | September 2022 | Cambridge school road | Maharashtra | 13 Feb 2019 | Date of announcement | 2019-12-31 | 827.2 | 748.6 | 78.6 | Y | [5 empty] | 2019-11-13 | Bids awarded
483 | National Highways Authority Of India | 155597 | Improvement of Autram Ghat section NH-4 (with tunnel) part of Aurangabad-Dhule section on NH-211 Project | 1299 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7000 | Announced | Engineering, Procurement & Construction |  | Autram ghat | West Bengal | 01 Jul 2010 | Date of announcement | 2016-03-01 | 7000 | 7000 | 0 | N
484 | National Highways Authority Of India | 155597 | Improvement of Khambataki Ghat section (with tunnel) on Pune-Satara section (NH-48) Project | 1298 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9260 | Under Implementation | Engineering, Procurement & Construction |  | Khambatki ghat | Maharashtra | 06 Apr 2011 | Date of announcement | 2022-07-06 | 9260 | 3500 | 5760 | Y | [5 empty] | 2018-12-14 | Bids awarded
485 | National Highways Authority Of India | 155597 | Improvement of T-Junction near Dhaula Kuan Metro Station Project (Bharatmala) | 1321 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2700 | Completed | Engineering, Procurement & Construction | September 2019 | Dhaula Kuan | NCT of Delhi | 01 May 2017 | Date of announcement | 2019-03-01 | 2700 | 1405.4 | 1294.6 | Y | 2019-09-22 | Completed | 2019-04-30 | Y | 145 | 2017-09-12 | Bids awarded
486 | National Highways Authority Of India | 155597 | Indapur-Tondale (NH-965G) Four Lane Road Project (Package-III of Sant Tukaram Maharaj Palkhi Marg) | 1899 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16010 | Under Implementation | Engineering, Procurement & Construction |  | Indapur | Maharashtra | 10 Jan 2019 | Date of announcement | 2021-11-08 | 16010 | 8750 | 7260 | Y | [5 empty] | 2021-03-30 | Bids awarded
487 | National Highways Authority Of India | 155597 | Indora Square-Pachpaoli Square Flyover Project | 1274 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2430 | No Information |  |  | Indora square | Maharashtra | 23 Mar 2017 | Date of announcement | 2017-03-23 | 2430 | 2430 | 0 | N
489 | National Highways Authority Of India | 155597 | Indore Outer Ring Road Project | 887 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9600 | No Information | Public Private Partnership |  | Indore | Madhya Pradesh | 28 Feb 2012 | Date of announcement | 2012-02-28 | 9600 | 9600 | 0 | N
490 | National Highways Authority Of India | 155597 | Indore-Khalghat (NH-3) Highway Project | 656 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6639 | Completed | Build Operate Transfer | September 2009 | Indore | Madhya Pradesh | 23 Jun 2005 | Date of announcement | 2009-09-30 | 6639 | 4720 | 1919 | Y | 2009-09-30 | Initial completion date | 2009-09-30 | N
491 | National Highways Authority Of India | 155597 | Indore-Raghav Garh (NH-59) Four Lane Highway Project (Package-I of Indore-Harda Economic Corridor) | 1951 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5079.9 | Under Implementation | Engineering, Procurement & Construction |  | Indore | Madhya Pradesh | 01 Jan 2018 | Date of announcement | 2022-01-17 | 5079.9 | 5079.9 | 0 | N | [5 empty] | 2022-03-30 | Bids awarded
492 | National Highways Authority Of India | 155597 | Indroda Circle Flyover Project | 792 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 400 | No Information |  |  | Gandhinagar | Gujarat | 19 Jun 2010 | Date of announcement | 2010-06-19 | 400 | 400 | 0 | N
493 | National Highways Authority Of India | 155597 | Islam Nagar to Kadtal (NS-2/BOT/AP-7) Highway Project | 503 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6678 | Completed |  | July 2010 | Islam nagar | Telangana | 31 Dec 2003 | Date of announcement | 2010-07-08 | 6678 | 5468.3 | 1209.7 | Y | 2010-07-08 | Completed | 2010-03-31 | Y | 99
494 | National Highways Authority Of India | 155597 | Islampur Four Lane Bypass (NH-31) Project | 1052 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3050 | Completed | Engineering, Procurement & Construction | March 2021 | Islampur | West Bengal | 15 Dec 2004 | Date of announcement | 2018-01-31 | 3050 | 2384.7 | 665.3 | Y | 2021-03-31 | Completed | 2018-01-31 | Y | 1155 | 2015-10-23 | Bids awarded
495 | National Highways Authority Of India | 155597 | Ismailabad on NH-152 to Junction with Karnal-Pehowa Road Four/Six Lane Access Controlled Highway Project (Package 1 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1533 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9966.5 | Completed | Engineering, Procurement & Construction | March 2022 | Ismailabad | Haryana | 01 Jan 2018 | Date of announcement | 2019-10-31 | 9966.5 | 5989.7 | 3976.8 | Y | 2022-07-31 | Initial completion date | 2022-03-03 | Y | 150 | 2019-10-31 | Bids awarded
496 | National Highways Authority Of India | 155597 | Ismailabad to Ambala (NH152) Four Lane Access Controlled Highway Project (Part of Ambala-Kotputli Corridor) | 2118 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4466.2 | Under Implementation | Engineering, Procurement & Construction |  | Ambala | Haryana | 01 Sep 2022 | Date of announcement | 2023-01-05 | 4466.2 | 4466.2 | 0 | N | [5 empty] | 2023-03-27 | Bids awarded
497 | National Highways Authority Of India | 155597 | Itanagar-Banderdewa (NH-415) Four Laning Highway Project | 1217 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3418.3 | Under Implementation | Engineering, Procurement & Construction |  | Banderdewa | Arunachal Pradesh | 01 Dec 2003 | Date of announcement | 2016-11-17 | 3418.3 | 3600 | -181.7 | N | [5 empty] | 2017-05-22 | Bids awarded
498 | National Highways Authority Of India | 155597 | Jabalpur-Katni-Rewa (NH-7) Four Laning Highway Project | 1019 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 31015.5 | Completed | Engineering, Procurement & Construction | May 2020 | Jabalpur | Madhya Pradesh | 01 Dec 2009 | Date of announcement | 2020-05-22 | 31015.5 | 19068.3 | 11947.2 | Y | 2020-05-22 | Completed | 2017-03-31 | Y | 1148 | 2011-07-29 | Bids awarded
499 | National Highways Authority Of India | 155597 | Jabalpur-Lakhnadon Four Lane Highway (NH-30 and NH-34) Project | 859 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12444.3 | Completed | Engineering, Procurement & Construction | August 2020 | Jabalpur | Madhya Pradesh | 01 Jan 2005 | Date of announcement | 2020-08-25 | 12444.3 | 9197.6 | 3246.7 | Y | 2020-08-25 | Completed | 2017-09-30 | Y | 1060 | 2011-07-20 | Bids awarded
500 | National Highways Authority Of India | 155597 | Jaigaon-Changrabandha (AH-48) Road Project | 989 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9714 | No Information | Engineering, Procurement & Construction |  | Changrabandha | West Bengal | 01 Jul 2013 | Date of announcement | 2015-02-27 | 9714 | 8320 | 1394 | Y | [5 empty] | 2014-11-18 | Bids awarded
501 | National Highways Authority Of India | 155597 | Jaigarh Port-Nivali (NH-17) Four Lane Road Project | 1176 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2350 | Announced | Engineering, Procurement & Construction |  | Jaigarh port | Maharashtra | 03 Apr 2012 | Date of announcement | 2019-01-31 | 2350 | 3330 | -980 | N
502 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 1 Project | 24 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 750 | Completed | Engineering, Procurement & Construction | January 2001 | Jaipur | Rajasthan | 01 Mar 1998 | Date of announcement | 1998-03-01 | 750 | 750 | 0 | N | 2001-03-31 | Initial completion date | 2001-01-31 | Y | 59 | 1998-09-01 | Bids awarded
503 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 1 Renovation Project | 374 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 56.8 | No Information |  |  | Jaipur | Rajasthan | 01 Mar 2004 | Date of announcement | 2004-03-01 | 56.8 | 56.8 | 0 | N
504 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2730 | Completed | Engineering, Procurement & Construction | March 2005 | Jaipur | Rajasthan | 30 Oct 2000 | Date of announcement | 2000-10-30 | 2730 | 2730 | 0 | N | 2005-03-31 | Completed | 2004-03-31 | Y | 365 | 2001-12-16 | Bids awarded
505 | National Highways Authority Of India | 155597 | Jaipur Ring Road (South) Project (Bharatmala) | 1322 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 16000 | Under Implementation | Engineering, Procurement & Construction |  | Jaipur | Rajasthan | 31 Dec 2000 | Date of announcement | 2018-11-27 | 16000 | 8500 | 7500 | Y | [5 empty] | 2011-05-15 | Bids awarded
506 | National Highways Authority Of India | 155597 | Jaipur Six Lane Ring Road (North) Project (Phase III) (Bharatmala) | 1655 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 28870 | Under Implementation | Hybrid Annuity |  | Jaipur | Rajasthan | 31 Dec 2000 | Date of announcement | 2021-11-04 | 28870 | 30000 | -1130 | N | [5 empty] | 2011-05-15 | Bids awarded
507 | National Highways Authority Of India | 155597 | Jaipur-Kishangarh (NH-8) Eight Lane Highway Project | 1453 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7440 | No Information |  |  | Jaipur | Rajasthan | 01 Jan 2018 | Date of announcement | 2018-01-11 | 7440 | 7440 | 0 | N
508 | National Highways Authority Of India | 155597 | Jaisalmer (NH-11)-Bhadasar-Ramgarh-Tanot and Bhadasar-Sarkaritala-upto Pakistan Border Two/Four Laning Highway Project (BM/5) | 1097 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9536.2 | Under Implementation | Engineering, Procurement & Construction |  | Bhadasar | Rajasthan | 05 Apr 2015 | Date of announcement | 2018-02-23 | 9536.2 | 10250 | -713.8 | N | [5 empty] | 2018-02-23 | Bids awarded
509 | National Highways Authority Of India | 155597 | Jaisalmer (NH-11)-Kanod-Ghantiali-Nachna-Chinnu-Naukh and Jaisalmer-Myajilar Two/Four Laning Highway Project (BM/7) | 1099 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13200 | Under Implementation |  |  | Chinnu | Rajasthan | 05 Apr 2015 | Date of announcement | 2015-11-20 | 13200 | 13200 | 0 | N
510 | National Highways Authority Of India | 155597 | Jaisalmer-Barmer (NH-15) Two/Four Laning Highway Project | 999 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4822.7 | Completed | Engineering, Procurement & Construction | September 2018 | Barmer | Rajasthan | 01 Feb 2014 | Date of announcement | 2014-04-30 | 4822.7 | 3712.2 | 1110.5 | Y | 2018-09-30 | Completed | 2017-11-30 | Y | 304 | 2014-04-11 | Bids awarded
511 | National Highways Authority Of India | 155597 | Jakhal Railway Over Bridge Project | 914 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 260 | Completed |  | April 2017 | Jakhal | Haryana | 01 Apr 2012 | Date of announcement | 2012-04-01 | 260 | 260 | 0 | N
512 | National Highways Authority Of India | 155597 | Jalandhar Bypass(NS/1) Project | 225 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 890 | Completed | Engineering, Procurement & Construction | June 2004 | Jalandhar | Punjab | 01 May 1999 | Date of announcement | 2004-04-01 | 890 | 634.6 | 255.4 | Y | 2004-06-30 | Completed | 2002-05-31 | Y | 761 | 1999-05-19 | Bids awarded
513 | National Highways Authority Of India | 155597 | Jalandhar-Ambala Highway Project | 3 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7500 | Completed | Engineering, Procurement & Construction | May 2001 | Ambala | Haryana | 15 Nov 1985 | Date of announcement | 1996-09-01 | 7500 | 7500 | 0 | N
514 | National Highways Authority Of India | 155597 | Jalandhar-Amritsar (NH-1) Six Lane Highway Project (Bidhipur-Dhilwan) | 939 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3440 | Completed | Engineering, Procurement & Construction | July 2018 | Amritsar | Punjab | 27 Aug 2012 | Date of announcement | 2017-10-31 | 3440 | 4928.8 | -1488.8 | N | 2018-07-25 | Completed | 2016-01-30 | Y | 907 | 2013-11-15 | Bids awarded
515 | National Highways Authority Of India | 155597 | Jalandhar-Moga-Bhatinda-Kishangarh-Ajmer Six Lane Expressway Project | 1260 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 260000 | No Information |  |  | Ajmer | Rajasthan | 01 Feb 2017 | Date of announcement | 2020-06-28 | 260000 | 100000 | 160000 | Y
516 | National Highways Authority Of India | 155597 | Jalbehra-near Ismailabad-Patti Kankra near Shahbad Four/Six Lane Highway Project | 2043 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8710 | Under Implementation | Hybrid Annuity |  | Jalbehra | Haryana | 01 Oct 2021 | Date of announcement | 2021-12-07 | 8710 | 8710 | 0 | N | [5 empty] | 2022-06-02 | Bids awarded
517 | National Highways Authority Of India | 155597 | Jam-Wadner (NS-59/MH) Highway project | 744 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1450 | Completed |  | October 2011 | Jam | Maharashtra | 31 Dec 2003 | Date of announcement | 2003-12-31 | 1450 | 1450 | 0 | N | 2011-10-31 | Completed | 2010-12-31 | Y | 304
518 | National Highways Authority Of India | 155597 | Jammu Four lane Ring Road Project | 923 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20238.7 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Jammu | Jammu & Kashmir | 01 Sep 2012 | Date of announcement | 2020-02-07 | 20238.7 | 13550 | 6688.7 | Y | 2023-12-31 | Completion expected by | 2020-12-31 | Y | 1095 | 2017-12-21 | Bids awarded
519 | National Highways Authority Of India | 155597 | Jammu-Kunjwani (incl. Jammu Bypass) Highway Project | 304 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 853.4 | Completed |  | August 2012 | Jammu | Jammu & Kashmir | 01 Dec 2003 | Date of announcement | 2009-01-01 | 853.4 | 853.4 | 0 | N | 2012-08-31 | Completed | 2008-12-31 | Y | 1339 | 2005-06-30 | Bids awarded
520 | National Highways Authority Of India | 155597 | Jammu-Pathankot(NS-15/JK) Expressway Project | 180 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1100 | No Information |  |  | Jammu | Jammu & Kashmir | 01 Sep 2001 | Date of announcement | 2001-09-01 | 1100 | 1100 | 0 | N
521 | National Highways Authority Of India | 155597 | Jamujhadi-Basudevpur-Dhamara (NH-316A) Four Lane Highway Project | 1503 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11480 | Under Implementation | Engineering, Procurement & Construction |  | Basudevpur | Odisha | 01 Aug 2011 | Date of announcement | 2023-01-02 | 11480 | 6000 | 5480 | Y | [5 empty] | 2016-04-18 | Bids awarded
522 | National Highways Authority Of India | 155597 | Jatinga-Bara Narayanpur (Harangajo) (NH-54) (New NH-27) Four Lane Highway Project | 1268 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 16896.6 | Under Implementation | Hybrid Annuity | March 2025 | Boro narayanpur | Assam | 01 Mar 2017 | Date of announcement | 2021-11-25 | 16896.6 | 16896.6 | 0 | N | 2025-03-31 | Completion expected by | 2017-03-31 | Y | 2922 | 2022-03-10 | Bids awarded
523 | National Highways Authority Of India | 155597 | Jawaharlal Nehru Port Road Project(Phase 2) | 582 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1430 | Completed |  | October 2009 | Panvel | Maharashtra | 30 Nov 2004 | Date of announcement | 2009-07-01 | 1430 | 1430 | 0 | N | 2009-10-31 | Initial completion date | 2007-05-01 | Y | 914
524 | National Highways Authority Of India | 155597 | Jetpur-Somnath (NH-151) Four-Laning Highway Project | 1401 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8280 | Under Implementation | Engineering, Procurement & Construction |  | Jetpur | Gujarat | 30 Apr 2009 | Date of announcement | 2010-06-11 | 8280 | 8130 | 150 | Y | [5 empty] | 2010-09-14 | Bids awarded
525 | National Highways Authority Of India | 155597 | Jhajjar-Loharu (NH-334B) Two Lane Highway Project | 1479 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1362.5 | Completed | Engineering, Procurement & Construction | October 2021 | Jhajjar | Haryana | 22 Jan 2018 | Date of announcement | 2021-10-30 | 1362.5 | 1817.8 | -455.3 | N | 2021-10-30 | Completed | 2021-04-30 | Y | 183
526 | National Highways Authority Of India | 155597 | Jhalawar-MP/Rajasthan Border Section Two Laning Road Project | 849 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1818.9 | Completed | Design Build Finance Operate Transfer | September 2015 | Jhalawar | Rajasthan | 28 Feb 2011 | Date of announcement | 2012-09-10 | 1818.9 | 1773.2 | 45.7 | Y | 2016-01-31 | Initial completion date | 2015-09-09 | Y | 144 | 2013-04-30 | Bids awarded
527 | National Highways Authority Of India | 155597 | Jhanjhapur-Darbanga (BR-7) Highway Project | 715 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5800 | Completed |  | December 2012 | Darbanga | Bihar | 31 Dec 2003 | Date of announcement | 2012-10-31 | 5800 | 3999.5 | 1800.5 | Y | 2012-12-31 | Completed | 2011-03-31 | Y | 641
528 | National Highways Authority Of India | 155597 | Jhanki Village-Sargi Village (NH-130CD) Six Lane Highway Project (Package CG-1) (Section of Raipur-Visakhapatnam Economic Corridor) | 1809 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 40662.5 | Under Implementation | Hybrid Annuity |  | Jhanki village | Chhattisgarh | 01 Jul 2019 | Date of announcement | 2020-01-06 | 40662.5 | 40662.5 | 0 | N | [5 empty] | 2021-12-24 | Bids awarded
529 | National Highways Authority Of India | 155597 | Jhansi Bypass (NH-25) Highway Project | 551 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1635 | Completed |  | December 2010 | Jhansi | Uttar Pradesh | 31 Dec 2003 | Date of announcement | 2010-12-31 | 1635 | 1150 | 485 | Y | 2011-03-30 | Initial completion date | 2009-12-31 | Y | 454
530 | National Highways Authority Of India | 155597 | Jhansi-Lakhnadaon (NH 26) Road Project | 426 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1638.7 | No Information |  |  | Jhansi | Uttar Pradesh | 01 Dec 2005 | Date of announcement | 2005-12-01 | 1638.7 | 1638.7 | 0 | N | [5 empty] | 2006-01-30 | Bids awarded
531 | National Highways Authority Of India | 155597 | Jhansi-RJ/MP Border Highway Project | 297 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3550.6 | No Information |  |  | Jhansi | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2008-01-01 | 3550.6 | 3550.6 | 0 | N
532 | National Highways Authority Of India | 155597 | Jhansi-Shivpuri (NH-25) Highway Project | 549 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3627.1 | Completed |  | May 2009 | Jhansi | Uttar Pradesh | 31 Dec 2003 | Date of announcement | 2009-01-01 | 3627.1 | 3627.1 | 0 | N
533 | National Highways Authority Of India | 155597 | Jharpokharia-Baripada-Baleshwar (NH-5) Four Laning Highway Project | 964 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10696.5 | Completed | Engineering, Procurement & Construction | January 2022 | Baleshwar | Odisha | 01 Dec 2010 | Date of announcement | 2016-02-22 | 10696.5 | 8355.9 | 2340.6 | Y | 2022-01-31 | Completed | 2019-06-30 | Y | 946 | 2016-02-22 | Bids awarded
534 | National Highways Authority Of India | 155597 | Jind-Gohana (NH-352A) Four Lane Highway Project (Package 1) | 1481 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1325.5 | Completed | Hybrid Annuity | April 2022 | Gohana | Haryana | 05 Jun 2006 | Date of announcement | 2022-04-04 | 1325.5 | 54.2 | 1271.3 | Y | 2022-08-31 | Initial completion date | 2022-04-04 | Y | 149 | 2019-03-08 | Bids awarded
535 | National Highways Authority Of India | 155597 | Jind-Karnal (NH-709A) Two Lane Highway Project | 1847 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Completed |  | July 2020 | Jind | Haryana | 01 Apr 2016 | Date of announcement | 2019-12-13 | 2000 | 2000 | 0 | N | 2020-07-14 | Completed | 2020-03-13 | Y | 123 | 2018-09-11 | Bids awarded
536 | National Highways Authority Of India | 155597 | Jind-Mundhal-Bhiwani (NH-709A) Two Lane Highway Project | 1480 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1830 | Completed | Engineering, Procurement & Construction | November 2021 | Bhiwani | Haryana | 01 Dec 2001 | Date of announcement | 2021-03-25 | 1830 | 96.5 | 1733.5 | Y | 2021-11-30 | Completed | 2019-12-31 | Y | 700 | 2018-03-20 | Bids awarded
537 | National Highways Authority Of India | 155597 | Jittandahalli-Dharmapuri section (NH-844) Four Lane Highway Project (Package 3 of Hosur-Dharmapuri) (Bharatmala) | 1690 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9808.2 | Under Implementation | Hybrid Annuity | August 2023 | Dharmapuri (tn) | Tamil Nadu | 11 Jul 2018 | Date of announcement | 2022-07-21 | 9808.2 | 6246.9 | 3561.3 | Y | [5 empty] | 2020-03-28 | Bids awarded
538 | National Highways Authority Of India | 155597 | Jn with NH20 in Bongabar Village to Jn with NH320 in Lepo Village Six Lane Greenfield Access Control Expressway Project (Package-12 of Varanasi-Kolkata Expressway) | 2121 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30480 | Under Implementation | Engineering, Procurement & Construction |  | Bongabar village | Jharkhand | 01 Aug 2021 | Date of announcement | 2023-05-18 | 30480 | 30480 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
539 | National Highways Authority Of India | 155597 | Jodhpur Ring Road Project (Phase 1) | 2042 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13000 | Under Implementation | Hybrid Annuity |  | Jodhpur | Rajasthan | 30 Jan 2010 | Date of announcement | 2017-12-19 | 13000 | 4000 | 9000 | Y | [5 empty] | 2017-12-19 | Bids awarded
540 | National Highways Authority Of India | 155597 | Jodhpur Romana (Bathinda)-Mandi Dabwali Highway (Punjab/Haryana border) (NH-54) Six Lane Highway Project | 1839 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7571.3 | Under Implementation |  |  | Jodhpur romana | Punjab | 15 Jan 2020 | Date of announcement | 2020-08-19 | 7571.3 | 7571.3 | 0 | N | [5 empty] | 2021-02-26 | Bids awarded
541 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Bagundi-Barmer Pkg-II) | 1000 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2061.2 | Completed | Engineering, Procurement & Construction | February 2017 | Barmer | Rajasthan | 01 Feb 2014 | Date of announcement | 2016-05-31 | 2061.2 | 2061.2 | 0 | N | 2017-04-30 | Initial completion date | 2017-02-28 | Y | 61 | 2014-04-11 | Bids awarded
542 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Jodhpur-Pachpadra Pkg-I) | 979 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2124 | Completed | Engineering, Procurement & Construction | August 2017 | Barmer | Rajasthan | 01 Jan 2014 | Date of announcement | 2014-03-27 | 2124 | 2647.2 | -523.2 | N | 2017-08-29 | Completed | 2017-04-30 | Y | 121 | 2014-04-11 | Bids awarded
543 | National Highways Authority Of India | 155597 | Jodhpur-Pokaran (NH-114) Two Lane Highway Project | 985 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4556 | Completed | Engineering, Procurement & Construction | August 2017 | Jodhpur | Rajasthan | 15 Jan 2014 | Date of announcement | 2014-12-31 | 4556 | 5126 | -570 | N | [5 empty] | 2014-12-31 | Bids awarded
544 | National Highways Authority Of India | 155597 | Jodmi village to Bani village of Mandsaur Eight Lane Carriageway Project (Package 18 of Delhi-Mumbai Expressway) | 1571 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10940 | Completed | Engineering, Procurement & Construction | December 2022 | Bani village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 10940 | 9737.8 | 1202.2 | Y | 2023-01-02 | Initial completion date | 2021-12-31 | Y | 367 | 2019-10-01 | Bids awarded
545 | National Highways Authority Of India | 155597 | Jowai-Meghalaya/Assam Border (Ratacherra) (NH-6) Two Lane Highway Project | 950 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6830 | Completed | Engineering, Procurement & Construction | September 2018 | Jowai | Meghalaya | 27 Apr 2010 | Date of announcement | 2018-09-21 | 6830 | 4421 | 2409 | Y | 2018-09-24 | Completed | 2018-02-28 | Y | 208 | 2012-03-31 | Bids awarded
546 | National Highways Authority Of India | 155597 | Jujuwa to Gandeva Package-8 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1628 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 36330 | Under Implementation | Hybrid Annuity |  | Gandeva | Gujarat | 31 Mar 1998 | Date of announcement | 2023-04-11 | 36330 | 15123.2 | 21206.8 | Y | [5 empty] | 2021-05-27 | Bids awarded
547 | National Highways Authority Of India | 155597 | Junction at SH44 to Junction with Keshopura Road Eight Lane Carriageway Project (Package 5 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1542 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13811.2 | Completed | Engineering, Procurement & Construction | September 2022 | Alwar | Rajasthan | 31 Mar 1998 | Date of announcement | 2019-03-31 | 13811.2 | 11506.7 | 2304.5 | Y | 2022-09-01 | Completed | 2021-12-31 | Y | 244 | 2019-03-09 | Bids awarded
548 | National Highways Authority Of India | 155597 | Junction with Amritsar-Bathinda Greenfield Road (NH-754A) near Rampura Phul to Junction with Moga-Barnala Road near Tallewal Six Lane Highway Project (Package 1 of Ludhiana-Bhatinda Expressway) | 1997 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9065.1 | Under Implementation | Hybrid Annuity | March 2024 | Rampura phul | Punjab | 01 Nov 2020 | Date of announcement | 2023-02-22 | 9065.1 | 6390.7 | 2674.4 | Y | [5 empty] | 2021-11-11 | Bids awarded
549 | National Highways Authority Of India | 155597 | Junction with Jind-Safidon Road (SH-14) near Kheri village to Junction with NH-352 (Jind-Gohana section) near Julana Six Lane Access Controlled Highway Project (Package 4 of Ismailabad-Narnaul) | 1623 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10187.9 | Completed | Engineering, Procurement & Construction | July 2022 | Julana | Haryana | 01 Jan 2018 | Date of announcement | 2019-08-26 | 10187.9 | 6510.7 | 3677.2 | Y | 2022-07-31 | Initial completion date | 2022-07-05 | N |  | 2019-08-26 | Bids awarded
550 | National Highways Authority Of India | 155597 | Junction with Kaithal-Safidon Road (SH-11) near Rajound to Junction with Jind-Safidon Road near Kheri village Four/Six Lane Access Control Highway Project (Pkg 3 Ismailabad-Narnaul) (Bharatmala) | 1622 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8893.6 | Completed | Engineering, Procurement & Construction | July 2022 | Kheri village | Haryana | 01 Jan 2018 | Date of announcement | 2019-12-31 | 8893.6 | 5091.6 | 3802 | Y | 2022-07-31 | Initial completion date | 2022-07-05 | N |  | 2019-12-02 | Bids awarded
551 | National Highways Authority Of India | 155597 | Junction with Karnal-Pehowa Road (SH-9) near Dhand village to Junction with Kaithal-Safidon (SH-11) Road near Rajound Four/Six Lane Access Control Highway Project (Package 2 Ismailabad-Narnaul) | 1617 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 12434.5 | Completed | Engineering, Procurement & Construction | July 2022 | Dhand | Haryana | 01 Jan 2018 | Date of announcement | 2019-10-25 | 12434.5 | 7249.7 | 5184.8 | Y | 2022-07-31 | Initial completion date | 2022-07-30 | N |  | 2019-10-25 | Bids awarded
552 | National Highways Authority Of India | 155597 | Junction with Keshopura Road to Junction with NH-11 Road Eight Lane Carriageway Project (Package 6 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1543 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11254.9 | Completed | Engineering, Procurement & Construction | October 2022 | Dausa | Rajasthan | 31 Mar 1998 | Date of announcement | 2019-03-09 | 11254.9 | 10530.6 | 724.3 | Y | 2022-10-01 | Completed | 2021-12-31 | Y | 274 | 2019-03-09 | Bids awarded
553 | National Highways Authority Of India | 155597 | Junction with Moga-Barnala Road near Tallewal to Delhi-Katra Expressway (NE-5) at Ballowal (Ludhiana) Six Lane Highway Project (Package 2 of Ludhiana-Bhatinda Expressway) | 1998 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15551.3 | Under Implementation | Hybrid Annuity | March 2024 | Ballowal | Punjab | 01 Nov 2020 | Date of announcement | 2023-02-22 | 15551.3 | 9572.3 | 5979 | Y | [5 empty] | 2021-11-09 | Bids awarded
554 | National Highways Authority Of India | 155597 | Junction with NH-11 to Start of RoB near junction with NH-11A Eight Lane Carriageway Project (Package 7 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1560 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11512.2 | Completed | Engineering, Procurement & Construction | February 2023 | Dausa | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 11512.2 | 11512.2 | 0 | N | 2023-02-12 | Completed | 2021-12-31 | Y | 408 | 2019-05-28 | Bids awarded
555 | National Highways Authority Of India | 155597 | Junction with NH-119 in Malpura Village to Lerua Village including Four Lane Spur to NH-19 Four/Six Lane Access Controlled Greenfield Highway Project (Package-5 of Varanasi-Kolkata Expressway) | 1977 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 25000 | Announced | Hybrid Annuity |  | Lerua village | Bihar | 01 Aug 2021 | Date of announcement | 2021-11-25 | 25000 | 25000 | 0 | N
556 | National Highways Authority Of India | 155597 | Junction with NH-12 near village Ummedpura to Major bridge over Takli river near Nayagaon Jageer village Eight Lane Carriageway Project (Package 15) (Delhi-Mumbai Expressway) | 1568 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10000.8 | Under Implementation | Engineering, Procurement & Construction | January 2024 | Manoharpur | Rajasthan | 31 Mar 1998 | Date of announcement | 2020-12-22 | 10000.8 | 9098.4 | 902.4 | Y | 2024-01-31 | Completion expected by | 2021-12-31 | Y | 761 | 2020-12-22 | Bids awarded
557 | National Highways Authority Of India | 155597 | Junction with NH-334B (Charkhi Dadri-Jhajjar section) to Junction with Rewari-Kanina Road (SH-24) Four/Six Lane Access Controlled Highway Project (Package 7 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1618 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11374.2 | Completed | Engineering, Procurement & Construction | July 2022 | Charkhi dadri | Haryana | 01 Jan 2018 | Date of announcement | 2019-12-31 | 11374.2 | 7325.7 | 4048.5 | Y | 2022-07-31 | Initial completion date | 2022-07-05 | N |  | 2019-03-08 | Bids awarded
558 | National Highways Authority Of India | 155597 | Junction with NH-352 (Jind-Gohana) near Julana to Junction with NH-9 (Rohtak-Jind) near Kharkara Four/Six Lane Access Controlled Highway Project (Package 5 of Ismailabad-Narnaul) (Bharatmala) | 1620 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10519.1 | Completed | Engineering, Procurement & Construction | July 2022 | Julana | Haryana | 01 Jan 2018 | Date of announcement | 2019-12-31 | 10519.1 | 6214.1 | 4305 | Y | 2022-07-31 | Initial completion date | 2022-07-05 | N |  | 2019-03-01 | Bids awarded
559 | National Highways Authority Of India | 155597 | Junction with NH-65 near Patas-Vasunde Phata-Baramati (NH965G) & Baramati Bypass Four Lane Highway Project (Package-I of Sant Tukaram Maharaj Palkhi Marg) | 1896 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13430 | Under Implementation |  |  | Baramati | Maharashtra | 01 Nov 2020 | Date of announcement | 2021-11-08 | 13430 | 7026 | 6404 | Y | [5 empty] | 2021-03-27 | Bids awarded
560 | National Highways Authority Of India | 155597 | Junction with NH-76 to Junction with NH-12 (near Ummedpura village) Eight Lane Carriageway Project (Package 14 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1566 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7038.8 | Under Implementation | Engineering, Procurement & Construction |  | Nh-12 | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 7038.8 | 7038.8 | 0 | N | [5 empty] | 2020-06-30 | Bids awarded
561 | National Highways Authority Of India | 155597 | Junction with NH-9 (Rohtak-Jind section) near Kharkara to Junction with NH-334B (Charkhi Dadri Jhajjar section) Four/Six Lane Access Controlled Highway Project (Pkg 6 of Ismailabad-Narnaul NH-152D) | 1621 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11200.6 | Completed | Engineering, Procurement & Construction | July 2022 | Charkhi dadri | Haryana | 01 Jan 2018 | Date of announcement | 2019-12-31 | 11200.6 | 6538.5 | 4662.1 | Y | 2022-07-31 | Initial completion date | 2022-07-05 | N |  | 2019-03-08 | Bids awarded
562 | National Highways Authority Of India | 155597 | Junction with SH-37A to Junction with NH- 76 Eight Lane Carriageway Project (Package 13 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1565 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9409.5 | Under Implementation | Engineering, Procurement & Construction |  | Nh-76 | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 9409.5 | 9409.5 | 0 | N | [5 empty] | 2020-06-18 | Bids awarded
563 | National Highways Authority Of India | 155597 | K K Wagh College-Jatra Hotel Junction Flyover Project | 1201 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3118 | Completed |  | October 2021 | Jatra hotel | Maharashtra | 01 Feb 2016 | Date of announcement | 2018-10-29 | 3118 | 2120 | 998 | Y | 2021-10-05 | Completed | 2020-10-31 | Y | 339
564 | National Highways Authority Of India | 155597 | KGP Expressway to Aligarh-Palwal Highway Six Lane New Link Road Project | 1506 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 650 | Under Implementation | Engineering, Procurement & Construction |  | Aligarh | Uttar Pradesh | 28 Apr 2017 | Date of announcement | 2021-06-27 | 650 | 650 | 0 | N | [5 empty] | 2022-09-30 | Bids awarded
565 | National Highways Authority Of India | 155597 | KMP Expressway to Khanpur Ghati Eight Lane Carriageway Project (Package 2 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1544 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20803.9 | Completed | Engineering, Procurement & Construction | February 2023 | Khanpur ghati | Haryana | 31 Mar 1998 | Date of announcement | 2021-03-25 | 20803.9 | 11956.4 | 8847.5 | Y | 2023-02-12 | Completed | 2021-12-31 | Y | 408 | 2019-03-05 | Bids awarded
566 | National Highways Authority Of India | 155597 | KN/TS Border near Nandinne village-Kurnool Six Lane Greenfield Highway Project | 1889 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19538.6 | Under Implementation | Hybrid Annuity |  | Kurnool | Andhra Pradesh | 01 Jun 2020 | Date of announcement | 2021-01-08 | 19538.6 | 19538.6 | 0 | N | [5 empty] | 2022-03-29 | Bids awarded
567 | National Highways Authority Of India | 155597 | KPT Junction Vehicular Overpass (NH-66) Project | 1965 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 220 | Under Implementation | Engineering, Procurement & Construction |  | Kpt junction, mangalore | Karnataka | 01 Jul 2021 | Date of announcement | 2023-03-20 | 220 | 346 | -126 | N | [5 empty] | 2022-08-23 | Bids awarded
568 | National Highways Authority Of India | 155597 | Kadal to Armur (NH-7) Highway Project | 770 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3038 | Completed | Build Operate Transfer | November 2009 | Armur | Telangana | 01 Nov 2007 | Date of announcement | 2007-11-01 | 3038 | 3038 | 0 | N
569 | National Highways Authority Of India | 155597 | Kadambattukonam-Kazhakuttom (NH-66) Four/Six Highway Project | 2005 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 36850 | Under Implementation | Engineering, Procurement & Construction |  | Kadambattukonam | Kerala | 01 Oct 2019 | Date of announcement | 2022-12-15 | 36850 | 8563 | 28287 | Y | [5 empty] | 2021-09-25 | Bids awarded
570 | National Highways Authority Of India | 155597 | Kadapa-Chinna Orampadu (NH-716) Four Lane Highway Project | 2075 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17326.6 | Under Implementation | Hybrid Annuity |  | Chinna orampadu | Andhra Pradesh | 01 Apr 2022 | Date of announcement | 2022-12-01 | 17326.6 | 17326.6 | 0 | N | [5 empty] | 2023-03-24 | Bids awarded
571 | National Highways Authority Of India | 155597 | Kadloor Yellareddy to Gundla Pochampalli Highway Project | 504 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5461.5 | Completed |  | March 2009 | Gundla pochampalli | Telangana | 30 Sep 2006 | Date of announcement | 2006-09-30 | 5461.5 | 5461.5 | 0 | N
572 | National Highways Authority Of India | 155597 | Kagal-Satara (NH-4 & 48) Six-Laning Highway Project | 556 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11030 | Under Implementation | Build Operate Transfer Toll | January 2025 | Kagal | Karnataka | 29 Dec 2008 | Date of announcement | 2009-07-01 | 11030 | 14160 | -3130 | N | [5 empty] | 2022-03-31 | Bids awarded
573 | National Highways Authority Of India | 155597 | Kagavadar-Una (NH-8E) (Package-IV Bhavnagar-Veraval Section) Four Lane Highway Project | 1164 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7236.4 | Completed | Hybrid Annuity | August 2020 | Kagvadar | Gujarat | 03 May 2012 | Date of announcement | 2016-05-26 | 7236.4 | 7190 | 46.4 | Y | 2020-08-11 | Completed | 2018-12-31 | Y | 589 | 2016-05-26 | Bids awarded
574 | National Highways Authority Of India | 155597 | Kaipa-Giddalur (NH-544D) Two Lane Highway Project | 1525 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5699.2 | Under Implementation | Engineering, Procurement & Construction |  | Giddalur | Andhra Pradesh | 01 Jan 2018 | Date of announcement | 2018-01-17 | 5699.2 | 5699.2 | 0 | N
575 | National Highways Authority Of India | 155597 | Kaithal-Pehowa-Kurukshetra-Radaur-Yamuna Nagar Four Laning Highway Project | 1029 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12000 | No Information | Engineering, Procurement & Construction |  | Kaithal | Haryana | 01 Sep 2014 | Date of announcement | 2014-09-09 | 12000 | 12000 | 0 | N
576 | National Highways Authority Of India | 155597 | Kajali-Manor (NH-8) Highway Project | 77 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1986 | Completed |  | February 2004 | Kaijali | Gujarat | 15 Mar 2000 | Date of announcement | 2003-03-31 | 1986 | 1927.1 | 58.9 | Y | 2004-02-22 | Completed | 2003-04-30 | Y | 298 | 2000-11-01 | Bids awarded
577 | National Highways Authority Of India | 155597 | Kakinada Anchorage Port-Uppada Beach (NH-16) Four Laning Road Project (Bharatmala) | 1535 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13940 | Under Implementation | Engineering, Procurement & Construction | February 2024 | Kakidana anchorage port | Andhra Pradesh | 31 Jan 2016 | Date of announcement | 2023-01-02 | 13940 | 9800 | 4140 | Y
578 | National Highways Authority Of India | 155597 | Kakinada port-Rajanagaram (NH-16) Four Lane Road Connectivity Project | 1614 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10740 | No Information |  |  | Kakinada port | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2018-06-30 | 10740 | 6000 | 4740 | Y
579 | National Highways Authority Of India | 155597 | Kalaburagi(Gulbarga)-Yadgir-Wadi (NH-150) Highway Widening Project | 1082 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9000 | No Information |  |  | Kalaburagi(gulbarga) | Karnataka | 15 Jan 2015 | Date of announcement | 2015-05-04 | 9000 | 9000 | 0 | N
580 | National Highways Authority Of India | 155597 | Kalamassery-Vallarpadam (NH-47C) Four laning Highway Project | 454 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11270 | Completed | Engineering, Procurement & Construction | July 2015 | Kalamassery | Kerala | 31 Mar 2005 | Date of announcement | 2014-10-30 | 11270 | 3294 | 7976 | Y | 2015-07-31 | Completed | 2009-11-30 | Y | 2069 | 2007-05-31 | Bids awarded
581 | National Highways Authority Of India | 155597 | Kalamboli-Mumbra (NH-4) Six-Laning Highway Project | 626 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 450 | No Information | Build Operate Transfer |  | Kalamboli | Maharashtra | 30 Apr 2009 | Date of announcement | 2009-04-30 | 450 | 450 | 0 | N
582 | National Highways Authority Of India | 155597 | Kalaparru-Chinna Avutapalli Six Lane Highway (NH-16) including Hanuman Junction bypass Project | 1956 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6556.4 | Completed | Engineering, Procurement & Construction | February 2022 | China avutapalli | Andhra Pradesh | 01 Jan 2018 | Date of announcement | 2022-02-17 | 6556.4 | 5899.5 | 656.9 | Y | 2022-02-17 | Completed | 2021-02-20 | Y | 362
583 | National Highways Authority Of India | 155597 | Kalika Mata Mandir to Khote Nagar (Jalgaon City) (NH-53) Four Lane Road Project | 1700 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 618.5 | Completed | Engineering, Procurement & Construction | April 2022 | Jalgaon | Maharashtra | 01 Jan 2017 | Date of announcement | 2022-04-22 | 618.5 | 692.6 | -74.1 | N | 2022-04-22 | Completed | 2021-03-07 | Y | 411 | 2019-05-30 | Bids awarded
584 | National Highways Authority Of India | 155597 | Kalkallu village-Gundla Pochampali (NS-8) Four Lane Highway Project | 226 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 408.3 | Completed | Engineering, Procurement & Construction | April 2002 | Gundla Pochampali | Telangana | 01 Nov 1999 | Date of announcement | 1999-11-01 | 408.3 | 408.3 | 0 | N | 2002-04-30 | Completed | 2001-12-31 | Y | 120 | 1999-12-01 | Bids awarded
585 | National Highways Authority Of India | 155597 | Kalkallu-Gundla Pochanpally (NH-44) Six Lane Highway Project (Nagpur-Hyderabad section) | 1959 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9560 | Under Implementation | Engineering, Procurement & Construction |  | Gundla pochanpally | Telangana | 01 Feb 2022 | Date of announcement | 2022-04-29 | 9560 | 9560 | 0 | N | [5 empty] | 2022-08-03 | Bids awarded
586 | National Highways Authority Of India | 155597 | Kalpetta-Sulthan Bathery (NH-212) Highway Reconstruction Project | 918 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 230 | No Information |  |  | Kalpetta | Kerala | 01 Oct 2012 | Date of announcement | 2012-10-01 | 230 | 230 | 0 | N
587 | National Highways Authority Of India | 155597 | Kalyan-Nirmal Two/Four Lane (NH-222) Highway Project | 1813 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2440.8 | Completed |  | March 2019 | Kalyan | Maharashtra | 01 Jul 2013 | Date of announcement | 2014-11-27 | 2440.8 | 2440.8 | 0 | N
588 | National Highways Authority Of India | 155597 | Kamakhyanagar Bypass-Duburi (NH-53) Four Lane Road Project | 1404 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7611.1 | Completed | Engineering, Procurement & Construction | April 2022 | Duburi | Odisha | 26 Oct 2017 | Date of announcement | 2019-02-05 | 7611.1 | 7611.1 | 0 | N | 2022-04-06 | Completed | 2021-08-31 | Y | 218 | 2018-01-31 | Bids awarded
589 | National Highways Authority Of India | 155597 | Kamalapuram-Oddanchatram (NH-209, New NH-83) Four Lane Highway Project (Bharatmala) | 1848 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7245 | Under Implementation | Hybrid Annuity |  | Kamalapuram | Tamil Nadu | 01 Apr 2017 | Date of announcement | 2018-02-28 | 7245 | 7245 | 0 | N | [5 empty] | 2019-02-11 | Bids awarded
590 | National Highways Authority Of India | 155597 | Kamalpur village (Jharkhand/WB Border)-Near Uluberia Four/Six Lane Greenfield Access Control Expressway (Part of Varanasi-Kolkata Expressway) Project | 1984 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 92500 | Announced |  |  | Kamalpur village | Jharkhand | 01 Oct 2021 | Date of announcement | 2021-11-25 | 92500 | 92500 | 0 | N
591 | National Highways Authority Of India | 155597 | Kamaspur-Haryana/Delhi Border (NS/2) Six Lane Highway Project | 186 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 430 | Completed | Engineering, Procurement & Construction | November 2001 | Delhi | NCT of Delhi | 01 Nov 1999 | Date of announcement | 2001-07-01 | 430 | 430 | 0 | N | 2001-11-30 | Completed | 2001-06-30 | Y | 153 | 1999-12-12 | Bids awarded
592 | National Highways Authority Of India | 155597 | Kamliya Village-Kandarwasa Village Eight Lane Carriageway Project (Package 21 of Delhi-Mumbai Expressway) | 1602 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9910 | Completed | Engineering, Procurement & Construction | December 2022 | Kamliya village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 9910 | 9196.3 | 713.7 | Y | 2022-12-20 | Completed | 2021-12-09 | Y | 376 | 2019-05-28 | Bids awarded
593 | National Highways Authority Of India | 155597 | Kamrej-Chaltan (NH-8) Six Laning Highway Project | 1092 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4256 | Completed | Engineering, Procurement & Construction | March 2021 | Chalthan | Gujarat | 15 Jan 2011 | Date of announcement | 2016-06-16 | 4256 | 2994.4 | 1261.6 | Y | 2021-06-30 | Initial completion date | 2019-03-31 | Y | 822 | 2016-05-18 | Bids awarded
594 | National Highways Authority Of India | 155597 | Kandarwasa village to Bawadi village (Shivgarh) Eight Lane Carriageway Project (Package 22 of Delhi-Mumbai Expressway) | 1601 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10375.3 | Completed | Engineering, Procurement & Construction | January 2023 | Bawadi village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2018-10-06 | 10375.3 | 10375.3 | 0 | N | 2023-01-01 | Completed | 2021-12-31 | Y | 366 | 2020-06-23 | Bids awarded
595 | National Highways Authority Of India | 155597 | Kandla Port Road Project | 165 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 75 | Completed |  | July 2002 | Kandla | Gujarat | 01 Jun 2001 | Date of announcement | 2001-06-01 | 75 | 75 | 0 | N
596 | National Highways Authority Of India | 155597 | Kanniyakumari-Panagudi Highway Project | 370 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2540 | Completed |  | July 2011 | Kanyakumari | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2011-07-31 | 2540 | 1200 | 1340 | Y | 2011-07-31 | Completed | 2006-09-30 | Y | 1765
597 | National Highways Authority Of India | 155597 | Kannur-Vengalam (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 538 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17608.6 | Under Implementation |  | December 2025 | Kannur | Kerala | 31 Dec 1977 | Date of announcement | 2009-01-01 | 17608.6 | 11436.6 | 6172 | Y | 2025-12-31 | Completion expected by | 2020-12-31 | Y | 1826 | 2009-08-31 | Bids awarded
598 | National Highways Authority Of India | 155597 | Kanpur Six Lane Outer Ring Road Project | 840 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 100000 | Under Implementation | Build Operate Transfer | December 2025 | Kanpur | Uttar Pradesh | 20 Jan 2011 | Date of announcement | 2022-10-25 | 100000 | 12000 | 88000 | Y | [5 empty] | 2023-03-20 | Bids awarded
599 | National Highways Authority Of India | 155597 | Kanpur-Fatehpur (GTRIP/II-B) Highway Project | 695 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4953.5 | Completed | Engineering, Procurement & Construction | May 2008 | Fatehpur | Uttar Pradesh | 15 Feb 2001 | Date of announcement | 2002-02-01 | 4953.5 | 2040 | 2913.5 | Y | [5 empty] | 2002-03-15 | Bids awarded
600 | National Highways Authority Of India | 155597 | Kanpur-Varanasi Highway Upgradation Project | 35 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 62.7 | No Information |  |  | Kanpur | Uttar Pradesh | 31 Jul 2002 | Bids invited | 2002-09-01 | 62.7 | 62.7 | 0 | N
601 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9239.1 | Under Implementation | Hybrid Annuity | October 2024 | Aluru | Andhra Pradesh | 01 Jul 2019 | Date of announcement | 2022-12-21 | 9239.1 | 9239.1 | 0 | N | [5 empty] | 2021-09-24 | Bids awarded
602 | National Highways Authority Of India | 155597 | Kapasia Chowk-Begusarai Jail Area (NH-31) Four Lane Elevated Road Project | 1999 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2560 | Under Implementation | Engineering, Procurement & Construction |  | Begusarai | Bihar | 01 Dec 2017 | Date of announcement | 2022-06-07 | 2560 | 3710 | -1150 | N | [5 empty] | 2022-03-23 | Bids awarded
603 | National Highways Authority Of India | 155597 | Kappirikkad-Thalikulam (NH-66) Six Lane Highway Project | 1877 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 39240 | Under Implementation | Hybrid Annuity |  | Kappirikkad | Kerala | 01 Nov 2020 | Date of announcement | 2022-12-15 | 39240 | 11681.9 | 27558.1 | Y | [5 empty] | 2021-09-24 | Bids awarded
604 | National Highways Authority Of India | 155597 | Karaikudi-Ramanathapuram (NH-210) Two-Laning Road Project | 557 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6530 | Completed | Engineering, Procurement & Construction | July 2022 | Karaikudi | Tamil Nadu | 03 Jan 2009 | Date of announcement | 2018-02-06 | 6530 | 5303.3 | 1226.7 | Y | 2022-07-05 | Completed | 2017-06-30 | Y | 1831 | 2014-10-27 | Bids awarded
605 | National Highways Authority Of India | 155597 | Karaipettai-Walajapet (NH-48) Six Lane Highway Project (Package-2) | 1505 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5333.6 | Under Implementation | Engineering, Procurement & Construction |  | Karaipettai | Tamil Nadu | 23 May 2018 | Date of announcement | 2021-02-17 | 5333.6 | 7515.8 | -2182.2 | N | [5 empty] | 2018-12-22 | Bids awarded
606 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Road-Nangloi Najafgarh Six Lane Road (NH-344M) Project ( Package-2 of Delhi 3rd Ring Road Project or UER-2) | 1798 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11210.4 | Under Implementation | Engineering, Procurement & Construction | September 2023 | Kanjhawala | NCT of Delhi | 01 Apr 2016 | Date of announcement | 2019-12-26 | 11210.4 | 11210.4 | 0 | N | 2023-10-30 | Initial completion date | 2023-09-15 | Y | 45 | 2021-07-23 | Bids awarded
607 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Six Lane (NH-344M) Road Project (Package 1 of Delhi 3rd Ring Road or UER-2) | 1797 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 15522.9 | Under Implementation | Engineering, Procurement & Construction | September 2023 | Kanjhawala | NCT of Delhi | 01 Apr 2016 | Date of announcement | 2019-12-26 | 15522.9 | 15522.9 | 0 | N | 2023-10-30 | Initial completion date | 2023-09-15 | Y | 45 | 2021-07-23 | Bids awarded
608 | National Highways Authority Of India | 155597 | Karanja Flyover (on NH-53) Project | 1645 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 349.5 | Under Implementation | Engineering, Procurement & Construction |  | Karanja | Maharashtra | 04 Jan 2019 | Date of announcement | 2019-01-04 | 349.5 | 349.5 | 0 | N | [5 empty] | 2020-01-20 | Bids awarded
609 | National Highways Authority Of India | 155597 | Karanodai Bridge Project | 857 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 200 | Completed |  | March 2012 | Karanodai bridge | Tamil Nadu | 01 May 2009 | Date of announcement | 2009-05-01 | 200 | 200 | 0 | N | [5 empty] | 2009-05-26 | Bids awarded
610 | National Highways Authority Of India | 155597 | Karauli-Dholpur (NH-11B) Two Laning Highway Project | 1034 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4251.9 | Completed | Engineering, Procurement & Construction | November 2017 | Dholpur | Rajasthan | 15 Jul 2010 | Date of announcement | 2014-02-28 | 4251.9 | 3364.3 | 887.6 | Y | 2017-11-30 | Completed | 2016-09-30 | Y | 426 | 2014-02-15 | Bids awarded
611 | National Highways Authority Of India | 155597 | Karimnagar-Telangana/Maharashtra Border Four Lane Highway Project | 1950 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 31780 | Announced |  |  | Karimnagar | Telangana | 01 Nov 2018 | Date of announcement | 2022-01-26 | 31780 | 31780 | 0 | N
612 | National Highways Authority Of India | 155597 | Karnal Eastern Bypass (Part of Karnal Ring Road starting from NH44 near Village Shamgarh and terminating at Karnal-Munak Road) Project | 1864 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 17000 | Under Implementation | Hybrid Annuity | November 2025 | Karnal | Haryana | 01 Jul 2019 | Date of announcement | 2023-05-22 | 17000 | 13000 | 4000 | Y | [5 empty] | 2022-12-29 | Bids awarded
613 | National Highways Authority Of India | 155597 | Karnataka/Kerala Border (Talapady)-Kannur (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 1515 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11570 | Under Implementation | Design, Build, Finance, Operate and Transfer (Toll) basis | December 2025 | Kannur | Kerala | 28 Oct 2009 | Date of announcement | 2010-08-11 | 11570 | 9100 | 2470 | Y | 2025-12-31 | Completion expected by | 2015-05-30 | Y | 3868 | 2010-05-31 | Bids awarded
614 | National Highways Authority Of India | 155597 | Karur Bypass including additional bridge across river Amrawati Project | 38 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 460.3 | Completed | Engineering, Procurement & Construction | September 2002 | Karur | Tamil Nadu | 01 Sep 1998 | Date of announcement | 2002-01-01 | 460.3 | 100 | 360.3 | Y | 2002-09-30 | Completed | 2001-11-30 | Y | 304 | 1999-08-16 | Bids awarded
615 | National Highways Authority Of India | 155597 | Karur ROB Project | 182 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 121.5 | Completed | Engineering, Procurement & Construction | September 2002 | Karur | Tamil Nadu | 15 May 1999 | Date of announcement | 2001-09-01 | 121.5 | 121.5 | 0 | N | 2002-09-30 | Completed | 2002-05-31 | Y | 122 | 1999-07-01 | Bids awarded
616 | National Highways Authority Of India | 155597 | Karur-Coimbatore (NH-67) Six Lane Highway Project | 1511 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 35000 | Announced | Build Operate Transfer |  | Coimbatore | Tamil Nadu | 19 Sep 2015 | Date of announcement | 2019-10-25 | 35000 | 20000 | 15000 | Y
617 | National Highways Authority Of India | 155597 | Karur-Kangeyam-Coimbatore (NH-67) Highway Project | 443 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1780 | Completed |  | July 2011 | Coimbatore | Tamil Nadu | 25 Feb 2006 | Date of announcement | 2006-02-25 | 1780 | 1780 | 0 | N | 2011-07-31 | Completed | 2009-03-01 | Y | 882
618 | National Highways Authority Of India | 155597 | Karur-Madurai (TN-4) or Karur-Dindigul Highway Project | 428 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4576 | Completed | Build Operate Transfer | November 2009 | Dindigul | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2009-10-01 | 4576 | 3600 | 976 | Y | 2009-11-04 | Completed | 2009-10-31 | N
619 | National Highways Authority Of India | 155597 | Karur-Madurai (TN-5) Highway Project | 334 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4483 | Completed | Build Operate Transfer | September 2009 | Karur | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2009-07-01 | 4483 | 4122.6 | 360.4 | Y | 2009-09-30 | Completed | 2009-03-31 | Y | 183
620 | National Highways Authority Of India | 155597 | Karvad-Jujuwa Package-9 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1624 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22870 | Under Implementation | Hybrid Annuity |  | Jujuwa | Gujarat | 31 Mar 1998 | Date of announcement | 2023-04-11 | 22870 | 9884.8 | 12985.2 | Y | [5 empty] | 2021-07-30 | Bids awarded
621 | National Highways Authority Of India | 155597 | Kasarghat-Nasik N H-3 Project | 50 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1500 | Shelved |  |  | Kasarghat | Maharashtra | 01 Jan 1999 | Date of announcement | 1999-01-01 | 1500 | 1500 | 0 | N
622 | National Highways Authority Of India | 155597 | Kasarkad Side of Honnavar Port to NH-66 Four Lane Road Connectivity Project | 1731 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1190 | Under Implementation | Engineering, Procurement & Construction |  | Honnavar port | Karnataka | 01 May 2018 | Date of announcement | 2022-02-28 | 1190 | 500 | 690 | Y | [5 empty] | 2021-12-08 | Bids awarded
623 | National Highways Authority Of India | 155597 | Kasia-Gorakhpur (LMNHP-7) Highway Project | 502 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3350 | Completed |  | January 2012 | Gorakhpur | Uttar Pradesh | 31 Dec 2003 | Date of announcement | 2010-10-31 | 3350 | 2420 | 930 | Y | 2012-01-31 | Completed | 2009-06-30 | Y | 945
624 | National Highways Authority Of India | 155597 | Katni (NH-30) Four Lane Bypass Project | 1778 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1944 | Under Implementation | Engineering, Procurement & Construction |  | Katni | Madhya Pradesh | 18 Oct 2019 | Date of announcement | 2020-08-23 | 1944 | 2137.3 | -193.3 | N | [5 empty] | 2020-03-05 | Bids awarded
625 | National Highways Authority Of India | 155597 | Katpadi Junction (NH-66) Road Overbridge Project | 1902 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 227.2 | Under Implementation |  |  | Katpadi junction | Karnataka | 01 Jan 2021 | Date of announcement | 2021-06-14 | 227.2 | 227.2 | 0 | N
626 | National Highways Authority Of India | 155597 | Katraj Ghat Bypass (Pune-Satara Section) Highway Project | 205 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1200 | Completed |  | June 2006 | Katraj | Maharashtra | 01 Dec 2001 | Date of announcement | 2001-12-01 | 1200 | 1200 | 0 | N | 2006-06-30 | Completed | 2003-12-31 | Y | 912
627 | National Highways Authority Of India | 155597 | Katraj Junction Multi -Level Flyover Project | 1785 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1690 | Under Implementation |  |  | Katraj | Maharashtra | 01 Jun 2015 | Date of announcement | 2021-02-14 | 1690 | 1350 | 340 | Y
628 | National Highways Authority Of India | 155597 | Katraj-Dehu Road Bypass Widening Project | 1777 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 967.7 | No Information |  |  | Dehu | Maharashtra | 01 Jan 2019 | Date of announcement | 2019-02-27 | 967.7 | 967.7 | 0 | N
629 | National Highways Authority Of India | 155597 | Kavali-Nellore (AP-11) Four/Six Lane Highway Project | 107 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1810 | Completed | Engineering, Procurement & Construction | May 2005 | Kavali | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1810 | 1760 | 50 | Y | 2005-10-31 | Initial completion date | 2003-07-31 | Y | 823 | 2001-05-01 | Bids awarded
630 | National Highways Authority Of India | 155597 | Kavungal-Pallikuth Four Lane Highway (NH-966) Project | 1915 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2794 | Announced | Hybrid Annuity | February 2024 | Kavungal | Kerala | 01 Apr 2020 | Date of announcement | 2020-08-09 | 2794 | 2794 | 0 | N
631 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8452.4 | Completed | Engineering, Procurement & Construction | December 2022 | Chackai | Kerala | 30 Mar 2012 | Date of announcement | 2015-05-14 | 8452.4 | 5874.9 | 2577.5 | Y | 2022-12-31 | Initial completion date | 2017-11-30 | Y | 1857 | 2015-05-14 | Bids awarded
632 | National Highways Authority Of India | 155597 | Kelapur-Pimpalkhatti (NS-62) Highway Project | 733 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1174 | Completed |  | June 2011 | Kelapur | Maharashtra | 31 Dec 2003 | Date of announcement | 2003-12-31 | 1174 | 1174 | 0 | N
633 | National Highways Authority Of India | 155597 | Ken Metal Factory FOB Project | 829 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Ken metal factory | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N | [5 empty] | 2010-12-16 | Bids awarded
634 | National Highways Authority Of India | 155597 | Kerala Border-Kollegal (NH-212) Two/Four Lane Highway Project | 935 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5857.8 | No Information | Engineering, Procurement & Construction |  | Kollegal | Karnataka | 16 Dec 2010 | Date of announcement | 2014-10-10 | 5857.8 | 4400 | 1457.8 | Y | [5 empty] | 2014-06-20 | Bids awarded
635 | National Highways Authority Of India | 155597 | Kerala/Tamil Nadu Border-Villukuri (NH-47) Four Laning Highway Project | 1150 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12740 | Under Implementation | Engineering, Procurement & Construction |  | Villukuri | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2017-10-31 | 12740 | 7078.2 | 5661.8 | Y | [5 empty] | 2016-02-25 | Bids awarded
636 | National Highways Authority Of India | 155597 | Kerle-Paijarwadi Four Lane Highway (Package-II of Ratnagiri-Kolhapur section of NH-166) Project | 1446 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21910 | Under Implementation | Hybrid Annuity |  | Kerle | Maharashtra | 01 Jan 2017 | Date of announcement | 2023-01-29 | 21910 | 8546.1 | 13363.9 | Y | [5 empty] | 2022-03-30 | Bids awarded
637 | National Highways Authority Of India | 155597 | Khaga-Varanasi(Khaga-Kokhraj) Highway Project | 150 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1517 | Completed | Engineering, Procurement & Construction | January 2005 | Khaga | Uttar Pradesh | 01 Jan 2001 | Bids invited | 2002-01-01 | 1517 | 1790 | -273 | N | 2005-01-31 | Completed | 2004-06-30 | Y | 215 | 2001-01-31 | Bids awarded
638 | National Highways Authority Of India | 155597 | Khagariya-Purnea (NH-31) Four Lane Highway Project | 1442 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15950 | Announced |  |  | Khagaria | Bihar | 20 Oct 2011 | Date of announcement | 2022-03-25 | 15950 | 15950 | 0 | N
639 | National Highways Authority Of India | 155597 | Khajuri-Wyndhamganj (NH-75) Four Lane Highway Project (Package 5) | 1958 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12320 | Under Implementation | Hybrid Annuity |  | Khajuri | Jharkhand | 01 Apr 2018 | Date of announcement | 2023-03-23 | 12320 | 11782 | 538 | Y | [5 empty] | 2022-04-29 | Bids awarded
640 | National Highways Authority Of India | 155597 | Khajuwala-Poogal section and Poogal-Dantour-Jaggasar-Gokul-Goddu-Ranjeetpura-Charanwala-Naukh-Bap section of (NH-911) Two/Four Lane Highway Project | 1485 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8950 | Completed | Hybrid Annuity | February 2021 | Bap (baap) | Rajasthan | 02 Jan 2018 | Date of announcement | 2018-04-05 | 8950 | 8570 | 380 | Y | 2021-05-21 | Initial completion date | 2021-02-18 | Y | 92 | 2018-03-27 | Bids awarded
641 | National Highways Authority Of India | 155597 | Khakarhawa-Ghaghra Bridge (Indo-Nepal border) NH-233 Two Laning Road Project | 993 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6482.2 | No Information | Design Build Finance Operate Transfer |  | Ghaghar bridge | Uttar Pradesh | 01 Nov 2010 | Date of announcement | 2010-11-12 | 6482.2 | 6482.2 | 0 | N
642 | National Highways Authority Of India | 155597 | Khammam-TL/AP Border-Vijaywada (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Venkatayapalem village to Jakkampudi village) | 1953 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 22010 | Under Implementation | Hybrid Annuity | March 2025 | Jakkampudi (vijaywada) | Andhra Pradesh | 01 Nov 2018 | Date of announcement | 2022-01-26 | 22010 | 25406.5 | -3396.5 | N | [5 empty] | 2023-03-29 | Bids awarded
643 | National Highways Authority Of India | 155597 | Khanapur-Karnataka-Goa Border (NH-4A) Two Lane Highway Project (Package-II) (section of Belgaum-KNT/Goa Border) (Bharatmala) | 1554 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6090 | Under Implementation | Engineering, Procurement & Construction |  | Goa | Goa | 01 Apr 2005 | Date of announcement | 2019-07-04 | 6090 | 3800.7 | 2289.3 | Y | [5 empty] | 2010-07-30 | Bids awarded
644 | National Highways Authority Of India | 155597 | Khandagiri Chowk (NH-16) Grade Separator Project | 1223 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1156.3 | Completed | Engineering, Procurement & Construction | May 2021 | Khandagiri square | Odisha | 06 Jun 2016 | Date of announcement | 2018-12-24 | 1156.3 | 150 | 1006.3 | Y | 2021-07-31 | Initial completion date | 2019-11-30 | Y | 609 | 2017-10-30 | Bids awarded
645 | National Highways Authority Of India | 155597 | Khandsa Chowk Foot Over Bridge (FOB) Project | 1837 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 30 | Completed |  | October 2020 | Khandsa | Haryana | 01 Jun 2012 | Date of announcement | 2020-01-06 | 30 | 20 | 10 | Y | 2020-10-01 | Completed | 2020-01-31 | Y | 244
646 | National Highways Authority Of India | 155597 | Khanpur Ghati to Haryana/Rajasthan Border Eight Lane Carriageway Project (Package 3 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1545 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20792.5 | Completed | Engineering, Procurement & Construction | February 2023 | Haryana/rajasthan border | Haryana | 31 Mar 1998 | Date of announcement | 2019-05-28 | 20792.5 | 9972.1 | 10820.4 | Y | 2023-02-12 | Completed | 2021-12-31 | Y | 408 | 2019-05-28 | Bids awarded
647 | National Highways Authority Of India | 155597 | Kharagpur-Balasore (Bridges Section OR/WB-I) Highway Project | 135 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 810 | Completed | Engineering, Procurement & Construction | August 2006 | Balasore | Odisha | 01 Mar 2001 | Date of announcement | 2006-08-31 | 810 | 800 | 10 | Y | 2006-09-30 | Initial completion date | 2004-05-31 | Y | 852 | 2001-09-01 | Bids awarded
648 | National Highways Authority Of India | 155597 | Kharagpur-Burdwan-Morgram (NH-14) Four Lane Highway Project (Kharagpur-Siliguri (Till Morgram) Expressway) | 2034 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 120000 | Announced |  | May 2027 | Burdwan | West Bengal | 01 Jul 2018 | Date of announcement | 2022-05-17 | 120000 | 56710 | 63290 | Y
649 | National Highways Authority Of India | 155597 | Kharagpur-Laxmanath (WB-IV) Highway Project | 110 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4199.8 | Completed | Engineering, Procurement & Construction | June 2006 | Kharagpur | West Bengal | 31 Mar 2001 | Date of announcement | 2006-04-01 | 4199.8 | 2280 | 1919.8 | Y | 2006-06-30 | Completed | 2003-12-31 | Y | 912 | 2001-06-01 | Bids awarded
650 | National Highways Authority Of India | 155597 | Kharar-Kurali (NH-21) Four Lane Highway Project | 975 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4570 | Completed | Engineering, Procurement & Construction | October 2018 | Kharar | Punjab | 01 Mar 2014 | Date of announcement | 2016-09-14 | 4570 | 2273 | 2297 | Y | 2018-10-24 | Completed | 2017-12-30 | Y | 298 | 2015-03-31 | Bids awarded
651 | National Highways Authority Of India | 155597 | Kharar-Ludhiana (NH-5) Four/Six Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1162 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16000 | Completed | Hybrid Annuity | June 2020 | Kharar | Punjab | 01 Sep 2005 | Date of announcement | 2016-08-10 | 16000 | 14726.1 | 1273.9 | Y | 2020-08-31 | Initial completion date | 2018-09-30 | Y | 701 | 2016-08-10 | Bids awarded
652 | National Highways Authority Of India | 155597 | Khatima Two Lane Bypass (Sitarganj-Tanakpur Section on NH-125) Project | 1942 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 530 | Under Implementation | Engineering, Procurement & Construction |  | Khatima | Uttarakhand | 01 Jan 2020 | Date of announcement | 2021-12-29 | 530 | 700 | -170 | N | [5 empty] | 2021-05-18 | Bids awarded
653 | National Highways Authority Of India | 155597 | Khatti Village to Arang Village 4/6 Lane Highway Project (Package 1B of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1548 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7662 | Under Implementation | Engineering, Procurement & Construction |  | Arang village | Chhattisgarh | 01 Apr 2017 | Date of announcement | 2018-08-30 | 7662 | 7662 | 0 | N | [5 empty] | 2022-12-27 | Bids awarded
654 | National Highways Authority Of India | 155597 | Khed-Sinnar (NH-50) Four Laning Highway Project | 1824 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20152.9 | Under Implementation | Design Build Finance Operate Transfer |  | Alephata | Maharashtra | 16 Mar 2012 | Date of announcement | 2013-11-07 | 20152.9 | 15740.1 | 4412.8 | Y | [5 empty] | 2013-03-28 | Bids awarded
655 | National Highways Authority Of India | 155597 | Khedakhajuria-Suhagadi (NH-148) Four Lane Highway Project (Package-2 of Ujjain-Garoth) | 1963 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9980 | Under Implementation | Hybrid Annuity |  | Khedakhajuria | Madhya Pradesh | 01 Jan 2019 | Date of announcement | 2022-02-24 | 9980 | 9980 | 0 | N | [5 empty] | 2022-02-28 | Bids awarded
656 | National Highways Authority Of India | 155597 | Kherdi Mor to Haluwas village via Bhiwani Bypass Four Lane Road (NH-709 extn. & NH-148B) Project | 2049 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2470 | Completed |  | July 2022 | Bhiwani | Haryana | 01 Apr 2008 | Date of announcement | 2016-12-01 | 2470 | 2470 | 0 | N
657 | National Highways Authority Of India | 155597 | Kherki Daula Cloverleaf Flyover (NH-8) SPR-NPR Connectivity Project | 1210 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1730 | Under Implementation |  | May 2023 | Delhi | NCT of Delhi | 03 Sep 2016 | Date of announcement | 2016-09-10 | 1730 | 1730 | 0 | N | 2023-05-31 | Completion expected by | 2018-03-31 | Y | 1887 | 2018-05-11 | Bids awarded
658 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram (Ganjam-Icchapuram) Highway Project | 142 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2780 | Completed |  | October 2013 | Ganjam | Odisha | 30 Apr 2000 | Date of announcement | 2013-06-30 | 2780 | 2000 | 780 | Y | 2013-10-31 | Initial completion date | 2003-12-31 | Y | 3592
659 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Khurda-Sunakhala) Highway Project | 140 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1896.8 | Completed | Engineering, Procurement & Construction | March 2006 | Khurda | Odisha | 15 Apr 2001 | Date of announcement | 2002-01-01 | 1896.8 | 2000 | -103.2 | N | 2006-03-31 | Completed | 2004-06-30 | Y | 639 | 2001-05-15 | Bids awarded
660 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Sunakhala-Ganjam) Highway Project | 141 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2250 | Completed | Engineering, Procurement & Construction | October 2006 | Ganjam | Odisha | 01 Jun 2001 | Date of announcement | 2002-01-01 | 2250 | 2200 | 50 | Y | 2006-10-31 | Completed | 2003-12-31 | Y | 1035 | 2001-06-30 | Bids awarded
661 | National Highways Authority Of India | 155597 | Khurda-Manguli Four Lane Bypass Road Project | 1053 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9000 | No Information |  |  | Khurda | Odisha | 01 Jan 2015 | Date of announcement | 2015-01-20 | 9000 | 9000 | 0 | N
662 | National Highways Authority Of India | 155597 | Kiratpur-Ner Chowk Four-Laning (NH-3,154&205) Highway Project | 1819 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 22910 | Under Implementation | Hybrid Annuity | June 2023 | Kiratpur sahib | Punjab | 18 Jul 2011 | Date of announcement | 2012-05-31 | 22910 | 19167.9 | 3742.1 | Y | 2023-06-30 | Completion expected by | 2016-08-30 | Y | 2495 | 2012-02-02 | Bids awarded
663 | National Highways Authority Of India | 155597 | Kishanganj (NH-31) Four Laning Bypass Project | 1130 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2500 | No Information |  |  | Kishanganj | Bihar | 15 Jan 2012 | Date of announcement | 2015-08-18 | 2500 | 2500 | 0 | N
664 | National Highways Authority Of India | 155597 | Kishanganj Flyover (NH-31) Project | 1514 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1420 | Under Implementation | Engineering, Procurement & Construction |  | Kishanganj | Bihar | 22 Jun 2018 | Date of announcement | 2022-06-25 | 1420 | 1460.2 | -40.2 | N
665 | National Highways Authority Of India | 155597 | Kishangarh ROB Project | 124 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 180 | Completed | Build Operate Transfer | February 2000 | Kishangarh | Rajasthan | 01 Feb 1998 | Date of announcement | 1998-02-01 | 180 | 180 | 0 | N | [5 empty] | 1998-03-15 | Bids awarded
666 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Bhilwara Bypass-Chittorgarh) High. Project | 127 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2028.8 | Completed | Engineering, Procurement & Construction | April 2004 | Bhilwara Section | Rajasthan | 01 Jun 2001 | Date of announcement | 2002-01-01 | 2028.8 | 2640 | -611.2 | N | 2004-05-31 | Initial completion date | 2003-12-31 | Y | 152 | 2001-08-31 | Bids awarded
667 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Chittorgarh-Mangalwar) Highway Project | 128 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1612 | Completed | Engineering, Procurement & Construction | February 2004 | Chittaurgarh | Rajasthan | 01 Jun 2001 | Date of announcement | 2002-01-01 | 1612 | 2080 | -468 | N | 2004-03-31 | Initial completion date | 2004-02-11 | Y | 49 | 2001-10-05 | Bids awarded
668 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1642.5 | Completed | Engineering, Procurement & Construction | September 2004 | Bhilwara Section | Rajasthan | 31 Aug 2001 | Date of announcement | 2001-09-01 | 1642.5 | 1642.5 | 0 | N | [5 empty] | 2001-11-13 | Bids awarded
669 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Kishangarh-Nasirabad KU-I) Highway Project | 125 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1135 | Completed | Engineering, Procurement & Construction | February 2004 | Kishangarh | Rajasthan | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1135 | 1520 | -385 | N | [5 empty] | 2001-11-01 | Bids awarded
670 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Nasirabad-Gulabpura) Highway Project | 126 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1820.9 | Completed | Engineering, Procurement & Construction | February 2004 | Gulabpura | Rajasthan | 01 Jun 2001 | Date of announcement | 2002-01-01 | 1820.9 | 4240 | -2419.1 | N | 2004-03-31 | Initial completion date | 2004-02-11 | Y | 49 | 2001-08-31 | Bids awarded
671 | National Highways Authority Of India | 155597 | Kodad-Khammam (NH 365-A) Four-Lane Highway Project (Bharatmala) | 1196 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10400 | Under Implementation | Hybrid Annuity |  | Khammam | Telangana | 31 May 2016 | Date of announcement | 2021-03-24 | 10400 | 7000 | 3400 | Y | [5 empty] | 2021-03-24 | Bids awarded
672 | National Highways Authority Of India | 155597 | Kodebad-Dhamtari Four Laning (NH-30) Highway Project | 1245 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9671.9 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Dhamtari | Chhattisgarh | 13 Oct 2010 | Date of announcement | 2019-12-02 | 9671.9 | 4461.7 | 5210.2 | Y | 2023-06-30 | Completion expected by | 2019-03-31 | Y | 1552 | 2016-11-22 | Bids awarded
673 | National Highways Authority Of India | 155597 | Kodinar-Veraval (NH-8E) (Package-VI Bhavnagar-Veraval Section) Four Lane Highway Project | 1080 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7930 | Under Implementation | Hybrid Annuity |  | Kodinar | Gujarat | 03 May 2012 | Date of announcement | 2017-10-31 | 7930 | 7807.1 | 122.9 | Y | [5 empty] | 2016-07-26 | Bids awarded
674 | National Highways Authority Of India | 155597 | Kodumbalur Vehicular Underpass (VUP) Project | 1969 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 150.4 | Under Implementation |  | June 2023 | Kodumbalur | Tamil Nadu | 01 Jan 2022 | Date of announcement | 2022-07-15 | 150.4 | 200 | -49.6 | N | 2023-07-31 | Initial completion date | 2023-06-30 | Y | 31
675 | National Highways Authority Of India | 155597 | Kodungallur-Edapally (NH-66) Six Lane Highway Project | 1906 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 34660 | Under Implementation | Hybrid Annuity | April 2025 | Edapally | Kerala | 15 Apr 2005 | Date of announcement | 2022-12-15 | 34660 | 15014.7 | 19645.3 | Y | 2025-04-30 | Completion expected by | 2024-12-31 | Y | 120 | 2021-12-28 | Bids awarded
676 | National Highways Authority Of India | 155597 | Koilwar-Bhojpur (NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) (Bharatmala) | 1087 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16620 | Completed | Engineering, Procurement & Construction | November 2022 | Bhojpur | Bihar | 12 Aug 2008 | Date of announcement | 2022-11-14 | 16620 | 7501 | 9119 | Y | 2022-12-31 | Initial completion date | 2020-03-31 | Y | 1005 | 2011-11-12 | Bids awarded
677 | National Highways Authority Of India | 155597 | Kolaghat-Kharagpur (WB-II) Highway Project | 108 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3750 | Completed | Engineering, Procurement & Construction | October 2005 | Kharagpur | West Bengal | 15 Nov 2000 | Bids invited | 2002-01-01 | 3750 | 3920 | -170 | N | 2005-10-31 | Completed | 2003-12-31 | Y | 670 | 2000-12-31 | Bids awarded
678 | National Highways Authority Of India | 155597 | Kolkata-Dhanbad Expressway Project | 507 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 50000 | No Information | Design Build Finance Operate Transfer |  | Dhanbad | Jharkhand | 31 Mar 2008 | Date of announcement | 2008-03-31 | 50000 | 50000 | 0 | N
679 | National Highways Authority Of India | 155597 | Kollam Bypass NH-66 Project | 204 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3520.5 | Completed | Engineering, Procurement & Construction | January 2019 | Kollam | Kerala | 01 Dec 2001 | Date of announcement | 2016-01-06 | 3520.5 | 2670 | 850.5 | Y | 2019-02-02 | Initial completion date | 2014-02-28 | Y | 1800 | 2015-02-12 | Bids awarded
680 | National Highways Authority Of India | 155597 | Koppal-Metgal Four Lane Highway (NH-367A) Project | 1916 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4571.5 | Announced | Hybrid Annuity |  | Koppal | Karnataka | 01 Dec 2018 | Date of announcement | 2020-08-09 | 4571.5 | 6234.1 | -1662.6 | N
681 | National Highways Authority Of India | 155597 | Korappuzha Bridge Project | 1878 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 271.7 | Completed |  | February 2021 | Kozhikode | Kerala | 03 Aug 2010 | Date of announcement | 2020-10-30 | 271.7 | 100 | 171.7 | Y | 2021-02-28 | Initial completion date | 2012-10-31 | Y | 3042 | 2018-09-28 | Bids awarded
682 | National Highways Authority Of India | 155597 | Korlam-Kantakapalle (NH-130CD) Six Lane Road Project (Package-3 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 2000 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9574.3 | Under Implementation | Hybrid Annuity | February 2024 | Kantakapalle | Andhra Pradesh | 01 Jul 2019 | Date of announcement | 2022-12-21 | 9574.3 | 7727 | 1847.3 | Y | [5 empty] | 2021-07-30 | Bids awarded
683 | National Highways Authority Of India | 155597 | Kota Bypass (RJ-4) Project | 740 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2820 | Completed | Engineering, Procurement & Construction | April 2016 | Kota | Rajasthan | 31 Dec 2003 | Date of announcement | 2013-08-31 | 2820 | 2503.9 | 316.1 | Y | 2016-04-30 | Completed | 2010-06-30 | Y | 2131
684 | National Highways Authority Of India | 155597 | Kota to RJ/MP Border Highway (NH-76) Renovation Project | 646 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 820 | No Information | Public Private Partnership |  | Kota | Rajasthan | 01 Jul 2009 | Date of announcement | 2009-07-01 | 820 | 820 | 0 | N
685 | National Highways Authority Of India | 155597 | Kota-Chittorgarh Highway Project | 299 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10321 | Completed |  | December 2008 | Chittaurgarh | Rajasthan | 25 Nov 2003 | Date of announcement | 2008-10-01 | 10321 | 10321 | 0 | N | 2008-12-31 | Initial completion date | 2008-04-30 | Y | 245
686 | National Highways Authority Of India | 155597 | Kotputli-Jaipur Highway Project | 12 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2600 | Completed |  | March 2001 | Jaipur | Rajasthan | 01 Jan 1997 | Date of announcement | 2001-01-01 | 2600 | 15000 | -12400 | N | [5 empty] | 2000-04-01 | Bids awarded
687 | National Highways Authority Of India | 155597 | Kottukulangara-Start of Kollam Bypass (NH-66) Four/Six Lane Highway Project (Bharatmala) | 1885 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 33510 | Under Implementation | Hybrid Annuity |  | Kollam | Kerala | 01 Nov 2020 | Date of announcement | 2022-12-15 | 33510 | 11852.7 | 21657.3 | Y | [5 empty] | 2021-08-06 | Bids awarded
688 | National Highways Authority Of India | 155597 | Kotwa to Dewapur (LMNHP-10) Four-Laning Highway Project | 731 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3000 | Implementation Stalled | Engineering, Procurement & Construction |  | Dewapur | Bihar | 31 Dec 2003 | Date of announcement | 2012-08-31 | 3000 | 2400 | 600 | Y | [5 empty] | 2005-09-20 | Bids awarded
689 | National Highways Authority Of India | 155597 | Kovilpatti-Panagudi Four Lane Highway Project | 418 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6300 | No Information |  |  | Kovilpatti | Tamil Nadu | 31 Mar 2005 | Date of announcement | 2005-03-31 | 6300 | 6300 | 0 | N
690 | National Highways Authority Of India | 155597 | Koyambedu Junction Grade Separator Project | 661 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1000 | Completed |  | July 2011 | Koyambedu | Tamil Nadu | 31 Jan 2005 | Date of announcement | 2005-01-31 | 1000 | 1000 | 0 | N | 2011-07-05 | Completed | 2010-03-31 | Y | 461
691 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Krishnagiri-Vaniyambadi) Highway Project | 118 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1950 | Completed | Engineering, Procurement & Construction | October 2005 | Krishnagiri | Tamil Nadu | 01 Jun 2001 | Date of announcement | 2002-01-01 | 1950 | 1960 | -10 | N | 2005-10-31 | Completed | 2003-12-31 | Y | 670 | 2001-11-01 | Bids awarded
692 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Pallikonda-Ranipet&Walahjapet Bypass) Project | 120 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2110 | Completed | Engineering, Procurement & Construction | December 2005 | Pallikonda | Tamil Nadu | 01 Mar 2001 | Date of announcement | 2002-01-01 | 2110 | 1800 | 310 | Y | 2005-12-31 | Completed | 2003-12-31 | Y | 731 | 2001-10-01 | Bids awarded
693 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Poonamalee-Kanchipuram) Highway Project | 122 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2441 | Completed | Engineering, Procurement & Construction | May 2007 | Kanchipuram | Tamil Nadu | 01 Mar 2001 | Date of announcement | 2007-04-01 | 2441 | 2080 | 361 | Y | 2007-05-31 | Completed | 2004-04-30 | Y | 1126 | 2001-07-01 | Bids awarded
694 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Vaniyambadi-Pallikonda) Highway Project | 119 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2230 | Completed | Engineering, Procurement & Construction | December 2005 | Pallikonda | Tamil Nadu | 01 Jun 2001 | Date of announcement | 2002-01-01 | 2230 | 2040 | 190 | Y | 2005-12-31 | Completed | 2004-06-30 | Y | 549 | 2001-11-01 | Bids awarded
695 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Walahjapet-Kanchipuram) Highway Project | 121 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1300 | Completed | Engineering, Procurement & Construction | March 2004 | Kanchipuram | Tamil Nadu | 01 Jun 2001 | Date of announcement | 2002-01-01 | 1300 | 1440 | -140 | N | 2004-03-31 | Initial completion date | 2004-01-31 | Y | 60 | 2001-09-01 | Bids awarded
696 | National Highways Authority Of India | 155597 | Krishnapatnam Port (NH-16) SIx Lane Road Connectivity Project (Bharatmala) | 1487 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2544.3 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Krishnapatnam | Andhra Pradesh | 01 Jul 2017 | Date of announcement | 2022-12-21 | 2544.3 | 3145.1 | -600.8 | N | 2024-12-31 | Completion expected by | 2020-12-18 | Y | 1474 | 2018-03-26 | Bids awarded
697 | National Highways Authority Of India | 155597 | Krishnapatnam Port-NH 5 (SPSR Nellore) Four Lane Port Road Connectivity Project (Bharatmala) | 1691 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7000 | Under Implementation |  |  | Krishnapatnam | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2023-01-02 | 7000 | 3000 | 4000 | Y
698 | National Highways Authority Of India | 155597 | Kudus-Dharmapuri (NH-965) Four Lane Highway Project (Package-III of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1454 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11535.5 | Under Implementation | Engineering, Procurement & Construction |  | Dharmapuri | Maharashtra | 29 Dec 2017 | Date of announcement | 2019-12-31 | 11535.5 | 8777.6 | 2757.9 | Y | [5 empty] | 2019-09-18 | Bids awarded
699 | National Highways Authority Of India | 155597 | Kullu-Manali (NH-3) Highway Upgradation (2-Lane with Paved Shoulders) Project | 1070 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2990 | Completed | Engineering, Procurement & Construction | September 2019 | Kullu | Himachal Pradesh | 01 Jan 2014 | Date of announcement | 2017-10-31 | 2990 | 2184.7 | 805.3 | Y | 2019-09-15 | Completed | 2019-02-28 | Y | 199 | 2016-02-08 | Bids awarded
700 | National Highways Authority Of India | 155597 | Kumarajapet-Veera Kaveri Raja Puram (NH-716B) Six Laning Expressway Project (Package-II of Chittor-Thatchur Expressway) | 2031 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5919.9 | Under Implementation | Hybrid Annuity |  | Kumarajapet | Andhra Pradesh | 01 Apr 2018 | Date of announcement | 2022-02-17 | 5919.9 | 5919.9 | 0 | N | [5 empty] | 2021-02-28 | Bids awarded
701 | National Highways Authority Of India | 155597 | Kumarapalayam-Chengapalli (NH-47) Highway Project | 420 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4210 | Completed | Build Operate Transfer | March 2010 | Chengapali | Tamil Nadu | 30 Jun 2005 | Date of announcement | 2007-07-01 | 4210 | 3800 | 410 | Y
702 | National Highways Authority Of India | 155597 | Kunjwani-Vijaypur (NS-15/J&K) Highway Project | 305 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1430 | Completed |  | April 2012 | Kunjwani | Jammu & Kashmir | 30 Apr 2000 | Date of announcement | 2010-01-31 | 1430 | 1100 | 330 | Y | 2012-04-30 | Completed | 2004-12-31 | Y | 2677
703 | National Highways Authority Of India | 155597 | Kunnigal bypass FOB Project | 832 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Kunnigal bypass | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N
704 | National Highways Authority Of India | 155597 | Kurali-Kiratpur Sahib Road Widening Project | 707 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3900 | Completed |  | July 2011 | Kiratpur | Uttar Pradesh | 01 Mar 2005 | Date of announcement | 2011-07-18 | 3900 | 3090 | 810 | Y | 2011-07-31 | Completed | 2010-06-30 | Y | 396
705 | National Highways Authority Of India | 155597 | Kuru-Udaipura (NH-75) Four Lane Highway Project (Package-1) | 2051 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14230 | Under Implementation |  |  | Kuru | Jharkhand | 01 Apr 2018 | Date of announcement | 2023-03-23 | 14230 | 14230 | 0 | N
706 | National Highways Authority Of India | 155597 | Kurukshetra Bypass Project | 1980 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7500 | Announced |  |  | Kurukshetra | Haryana | 29 Jul 2017 | Date of announcement | 2022-03-09 | 7500 | 6180 | 1320 | Y
707 | National Highways Authority Of India | 155597 | Kushinagar & Gopalgarh Circle (NH-28) Flyover Project | 2044 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 430 | Under Implementation |  |  | Gopalgarh circle | Uttar Pradesh | 01 Apr 2021 | Date of announcement | 2022-07-10 | 430 | 450 | -20 | N | [5 empty] | 2022-05-25 | Bids awarded
708 | National Highways Authority Of India | 155597 | Kutchery Chowk Ranchi-Piska More-Biju Para (NH-75) Four Laning Highway Project (Package-I) | 1226 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2396.8 | Completed | Engineering, Procurement & Construction | August 2019 | Biju para | Jharkhand | 09 Nov 2016 | Date of announcement | 2016-11-09 | 2396.8 | 2396.8 | 0 | N | 2019-11-15 | Initial completion date | 2018-05-31 | Y | 533 | 2017-03-31 | Bids awarded
709 | National Highways Authority Of India | 155597 | Kuttipuram-Edapally (NH-66) Six-Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 479 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8900 | Under Implementation | Design Build Finance Operate Transfer | December 2025 | Edapally | Kerala | 12 Aug 2008 | Date of announcement | 2009-10-01 | 8900 | 11579.2 | -2679.2 | N | 2025-12-31 | Completion expected by | 2020-12-31 | Y | 1826
710 | National Highways Authority Of India | 155597 | LIC Square-Nelson Square Flyover Project | 1181 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2300 | No Information |  |  | Lic square | Maharashtra | 30 Apr 2007 | Date of announcement | 2016-05-25 | 2300 | 375.4 | 1924.6 | Y
711 | National Highways Authority Of India | 155597 | Laddowal Four Lane Bypass Project | 1168 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3900 | Completed | Hybrid Annuity | March 2021 | Laddowal | Punjab | 02 Jun 2010 | Date of announcement | 2021-03-31 | 3900 | 3701.7 | 198.3 | Y | 2021-03-31 | Completed | 2018-09-30 | Y | 913 | 2016-05-18 | Bids awarded
712 | National Highways Authority Of India | 155597 | Ladnu (Nimbi Jodha)-Degana-Merta City (NH-458) Two Lane Highway Project | 930 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5520.9 | Completed | Engineering, Procurement & Construction | February 2017 | Degana | Rajasthan | 10 Sep 2012 | Date of announcement | 2013-04-18 | 5520.9 | 3681.5 | 1839.4 | Y | 2017-02-28 | Completed | 2016-01-31 | Y | 394 | 2013-07-31 | Bids awarded
713 | National Highways Authority Of India | 155597 | Ladpura-Bhilwara (NH-758) Carriageway Improvement Project | 875 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 240.8 | No Information | Engineering, Procurement & Construction |  | Bhilwara | Rajasthan | 11 Oct 2011 | Date of announcement | 2011-10-11 | 240.8 | 240.8 | 0 | N
714 | National Highways Authority Of India | 155597 | Lakhani (NH-53) Flyover project | 1483 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3120 | Completed | Engineering, Procurement & Construction | April 2022 | Lakhani | Maharashtra | 01 Jan 2018 | Date of announcement | 2022-04-29 | 3120 | 2700 | 420 | Y | 2022-04-29 | Completed | 2020-11-22 | Y | 523 | 2018-04-03 | Bids awarded
715 | National Highways Authority Of India | 155597 | Lakhanpur-Hiranagar Highway project | 726 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1580.7 | Completed |  | October 2011 | Hiranagar | Jammu & Kashmir | 01 Sep 2005 | Date of announcement | 2005-09-01 | 1580.7 | 1580.7 | 0 | N | 2011-10-31 | Completed | 2010-06-30 | Y | 488
716 | National Highways Authority Of India | 155597 | Lakhnadon-MP/MH Border (NS-1/BOT/MP-2) Highways project | 745 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2631.7 | Completed | Build Operate Transfer Annuity | January 2014 | Lakhnadon | Madhya Pradesh | 31 Dec 2003 | Date of announcement | 2003-12-31 | 2631.7 | 2631.7 | 0 | N | 2014-09-30 | Initial completion date | 2010-09-30 | Y | 1461
717 | National Highways Authority Of India | 155597 | Lalapet ROB Project | 437 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 277.9 | Completed |  | January 2009 | Lalapet | Tamil Nadu | 10 Oct 2006 | Date of announcement | 2009-01-01 | 277.9 | 240 | 37.9 | Y | 2009-01-08 | Completed | 2008-08-31 | Y | 130
718 | National Highways Authority Of India | 155597 | Lalapet Road Over Bridge Project | 39 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 120 | No Information |  |  | Lalapet | Tamil Nadu | 01 Sep 1998 | Date of announcement | 1998-09-01 | 120 | 120 | 0 | N
719 | National Highways Authority Of India | 155597 | Lalganj-Hanumanha (NH-135) Four Lane Highway Project (Package-III) | 1469 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12850 | Completed | Engineering, Procurement & Construction | December 2021 | Hanumanha | Uttar Pradesh | 01 Apr 2016 | Date of announcement | 2021-12-20 | 12850 | 8708.7 | 4141.3 | Y | 2021-12-20 | Completed | 2020-09-30 | Y | 446 | 2018-03-22 | Bids awarded
720 | National Highways Authority Of India | 155597 | Lalghati to Bhopal Bypass (Mubarakpur) (NH-12) Four-Laning Road Project (Package-I) (Bhopal-Biaora Section) | 1258 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2210 | Completed | Engineering, Procurement & Construction | August 2020 | Bhopal bypass | Madhya Pradesh | 12 Aug 2010 | Date of announcement | 2019-09-11 | 2210 | 2434.7 | -224.7 | N | 2020-08-25 | Completed | 2019-10-31 | Y | 299 | 2012-01-10 | Bids awarded
721 | National Highways Authority Of India | 155597 | Lalitpur-Sagar (NH-26) Highway Project | 292 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4420 | Completed |  | May 2012 | Lalitpur | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2011-07-30 | 4420 | 4230 | 190 | Y | 2012-05-31 | Initial completion date | 2009-03-31 | Y | 1157
722 | National Highways Authority Of India | 155597 | Lalsot-Kishangarh-Jodhpur-Pachpadra Four Lane Expressway Project | 2095 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 107000 | Announced |  |  | Jodhpur | Rajasthan | 01 Jan 2022 | Date of announcement | 2023-02-03 | 107000 | 107000 | 0 | N
723 | National Highways Authority Of India | 155597 | Lambia-Jaitran-Raipur (NH-458) Two Lane Highway Project | 948 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1584 | Completed | Engineering, Procurement & Construction | May 2016 | Jaitran | Rajasthan | 01 Sep 2012 | Date of announcement | 2012-09-01 | 1584 | 1584 | 0 | N | 2016-07-31 | Initial completion date | 2015-12-31 | Y | 213 | 2013-04-30 | Bids awarded
724 | National Highways Authority Of India | 155597 | Lanka-Daboka (AS-16) Highway Project | 700 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2205 | Completed |  | March 2011 | Daboka | Assam | 31 Dec 2003 | Date of announcement | 2011-03-31 | 2205 | 2250 | -45 | N | 2011-03-31 | Completed | 2010-06-30 | Y | 274 | 2005-04-01 | Bids awarded
725 | National Highways Authority Of India | 155597 | Laxmannath-Baleshwar (OR-4) Highway Project | 134 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2720 | Completed | Engineering, Procurement & Construction | May 2007 | Baleshwar | Odisha | 01 Jan 2001 | Bids invited | 2002-01-01 | 2720 | 2120 | 600 | Y | 2007-05-31 | Completed | 2003-11-30 | Y | 1278 | 2001-03-01 | Bids awarded
726 | National Highways Authority Of India | 155597 | Liberty Cinema-Mental Hospital (NH-69) Flyover Project | 1206 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2181.1 | Completed | Engineering, Procurement & Construction | January 2020 | Liberty cinema | Maharashtra | 31 Jan 2015 | Date of announcement | 2017-02-17 | 2181.1 | 2449 | -267.9 | N | 2020-03-31 | Initial completion date | 2018-08-31 | Y | 578 | 2017-01-23 | Bids awarded
727 | National Highways Authority Of India | 155597 | Lucknow Bypass (EW-15/UP) Highway Project | 174 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1117.8 | Completed | Build Operate Transfer | May 2012 | Lucknow | Uttar Pradesh | 30 Apr 2000 | Date of announcement | 2001-09-01 | 1117.8 | 1117.8 | 0 | N | 2012-06-30 | Initial completion date | 2004-06-30 | Y | 2922 | 2001-09-01 | Bids awarded
728 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 58120 | Under Implementation | Public Private Partnership | October 2023 | Behta village | Uttar Pradesh | 07 Sep 2008 | Date of announcement | 2019-05-02 | 58120 | 15000 | 43120 | Y | 2023-10-31 | Completion expected by | 2019-04-30 | Y | 1645 | 2017-01-03 | Bids awarded
729 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section (EW/3B) NH-25 Project | 179 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 540 | Completed | Engineering, Procurement & Construction | September 2015 | Kanpur | Uttar Pradesh | 31 Mar 2001 | Expenses incurred upto | 2002-01-01 | 540 | 510 | 30 | Y | 2015-09-30 | Initial completion date | 2001-12-31 | Y | 5021 | 2003-12-01 | Bids awarded
730 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-8/UP) Highway Project | 184 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 949.1 | Completed | Engineering, Procurement & Construction | December 2004 | Kanpur | Uttar Pradesh | 01 Mar 2001 | Date of announcement | 2003-01-01 | 949.1 | 950 | -0.9 | N | 2004-12-31 | Completed | 2003-08-31 | Y | 488
731 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-9/UP) Highway Project | 229 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 500.2 | Completed | Engineering, Procurement & Construction | March 2005 | Kanpur | Uttar Pradesh | 01 Aug 2001 | Date of announcement | 2003-01-01 | 500.2 | 500 | 0.2 | Y | 2005-03-31 | Completed | 2003-04-30 | Y | 701 | 2001-09-15 | Bids awarded
732 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW/2) Highway Project | 183 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 330 | Completed | Engineering, Procurement & Construction | August 2002 | Kanpur | Uttar Pradesh | 01 Sep 1999 | Date of announcement | 2001-07-01 | 330 | 330 | 0 | N | 2002-08-31 | Completed | 2001-10-31 | Y | 304 | 2000-02-08 | Bids awarded
733 | National Highways Authority Of India | 155597 | Ludhiana-Talwandi Bhai (NH-95) Four Laning Highway Project (Package-II) | 1060 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 562 | Completed | Engineering, Procurement & Construction | May 2018 | Ludhiana | Punjab | 01 Feb 2014 | Date of announcement | 2018-02-28 | 562 | 390.2 | 171.8 | Y | 2018-05-31 | Completed | 2016-07-16 | Y | 684 | 2014-11-30 | Bids awarded
734 | National Highways Authority Of India | 155597 | Lumding-Daboka (AS-15) Highway Project | 277 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1300 | Completed |  | December 2011 | Daboka | Assam | 01 Dec 2003 | Date of announcement | 2009-04-01 | 1300 | 1300 | 0 | N | 2011-12-31 | Completed | 2010-09-30 | Y | 457
735 | National Highways Authority Of India | 155597 | MES College Junction-Padinajrekar Road Widening Project | 1727 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5516.3 | No Information |  |  | Mes college junction | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 5516.3 | 5516.3 | 0 | N
736 | National Highways Authority Of India | 155597 | MH/KT Border-Belgaum (NH-48) Six Lane Highway Project (Bharatmala) | 1850 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 28680 | Under Implementation | Engineering, Procurement & Construction |  | Belgaum | Karnataka | 01 Jun 2018 | Date of announcement | 2022-02-28 | 28680 | 19000 | 9680 | Y | [5 empty] | 2022-01-24 | Bids awarded
737 | National Highways Authority Of India | 155597 | MP-Gujarat Border near Chhayan village ending after Bridge Over Hadaf River near Hathiyavan village Eight Lane Carriageway Project (Package 26 of Delhi-Mumbai Expressway) | 1818 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18351 | Under Implementation | Engineering, Procurement & Construction | May 2024 | Chhayan village | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 18351 | 14177 | 4174 | Y | [5 empty] | 2021-11-11 | Bids awarded
738 | National Highways Authority Of India | 155597 | MP/Raj border-Sarai Cholla (NS/6) Highway Project | 190 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 282.7 | Completed | Engineering, Procurement & Construction | January 2003 | Madhya Pradesh | Madhya Pradesh | 01 Jun 2000 | Date of announcement | 2002-01-01 | 282.7 | 280 | 2.7 | Y | 2003-01-31 | Completed | 2001-12-31 | Y | 396 | 2000-07-15 | Bids awarded
739 | National Highways Authority Of India | 155597 | MP/UP Border near Kaimaha check post-Kabrai (NH-34&35) Four Lane Highway Project | 3004 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16810 | Under Implementation |  |  | Kabrai | Uttar Pradesh | 01 Jan 2022 | Date of announcement | 2023-03-13 | 16810 | 16810 | 0 | N
740 | National Highways Authority Of India | 155597 | Machilipatnam (North Port)-NH 216 (SH-46) Four Lane Green field Road Project (Sagarmala) | 1518 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2320 | No Information | Engineering, Procurement & Construction |  | Machilipatnam | Andhra Pradesh | 14 Apr 2016 | Date of announcement | 2016-04-14 | 2320 | 2320 | 0 | N
741 | National Highways Authority Of India | 155597 | Machilipatnam (South Port)-NH 9 Four Lane Green field Road Project (Bharatmala) | 1517 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5948.1 | No Information | Engineering, Procurement & Construction |  | Machilipatnam | Andhra Pradesh | 14 Apr 2016 | Date of announcement | 2020-08-09 | 5948.1 | 4580 | 1368.1 | Y
742 | National Highways Authority Of India | 155597 | Madathukulam-Pollachi (NH-83) Four Lane Highway Project (Package-3 of Dindigul-Pollachi) (Bharatmala) | 1501 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14093.8 | Under Implementation | Hybrid Annuity |  | Madathukulam | Tamil Nadu | 04 May 2018 | Date of announcement | 2022-07-21 | 14093.8 | 7267.2 | 6826.6 | Y | [5 empty] | 2019-02-13 | Bids awarded
743 | National Highways Authority Of India | 155597 | Madhura Bazaar-Chullikad Road Upgradation Project (Bharatmala) | 1721 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2794 | Announced |  | February 2024 | Chullikad | Kerala | 12 Apr 2018 | Date of announcement | 2020-08-09 | 2794 | 1614.9 | 1179.1 | Y
744 | National Highways Authority Of India | 155597 | Madiaon-IIM Crossing (NH-24) Elevated Corridor Project | 1310 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1280 | Under Implementation | Engineering, Procurement & Construction |  | Iim crossing | Uttar Pradesh | 23 May 2017 | Date of announcement | 2022-01-05 | 1280 | 1360 | -80 | N | [5 empty] | 2022-06-15 | Bids awarded
745 | National Highways Authority Of India | 155597 | Madurai Four Lane Ring Road Project | 1498 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7000 | Under Implementation | Engineering, Procurement & Construction |  | Arumbanur | Tamil Nadu | 28 Jan 2009 | Date of announcement | 2018-05-14 | 7000 | 2000 | 5000 | Y | [5 empty] | 2019-01-14 | Bids awarded
746 | National Highways Authority Of India | 155597 | Madurai Kamaraj University (MKU) Flyover Project | 1836 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 520.4 | Under Implementation |  |  | Madurai kamaraj university | Tamil Nadu | 07 Oct 2015 | Date of announcement | 2021-01-19 | 520.4 | 536.8 | -16.4 | N
747 | National Highways Authority Of India | 155597 | Madurai-Chettikulam (NH-785) Four Laning Elevated Highway (Flyover) Project | 1482 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6130 | Completed | Engineering, Procurement & Construction | April 2023 | Chettikulam | Tamil Nadu | 06 Feb 2018 | Date of announcement | 2023-04-06 | 6130 | 5490.9 | 639.1 | Y | 2023-04-08 | Completed | 2020-02-28 | Y | 1135 | 2018-04-03 | Bids awarded
748 | National Highways Authority Of India | 155597 | Madurai-Kanniakumari Section (NS-40/TN) NH-7 Project | 466 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2462 | Completed |  | September 2009 | Kanyakumari | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2009-07-01 | 2462 | 4742.1 | -2280.1 | N | 2009-09-30 | Completed | 2009-05-30 | Y | 123
749 | National Highways Authority Of India | 155597 | Madurai-Kanniyakumari (NS-41/TN) Highway Project | 467 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3233.6 | Completed |  | April 2011 | Kanyakumari | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2003-12-31 | 3233.6 | 3233.6 | 0 | N | 2011-04-30 | Completed | 2008-10-31 | Y | 911
750 | National Highways Authority Of India | 155597 | Madurai-Kanniyakumari Section (NS-42/TN) NH-7 Highway Project | 468 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3428 | Completed |  | August 2010 | Kanyakumari | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2010-08-31 | 3428 | 5074.9 | -1646.9 | N | 2010-08-31 | Completed | 2009-03-31 | Y | 518
751 | National Highways Authority Of India | 155597 | Madurai-Paramakudi (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 888 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13871.1 | Completed | Engineering, Procurement & Construction | March 2019 | Madurai | Tamil Nadu | 01 Nov 2010 | Date of announcement | 2015-04-07 | 13871.1 | 13871.1 | 0 | N | 2019-05-31 | Initial completion date | 2014-01-31 | Y | 1946 | 2015-04-17 | Bids awarded
752 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli Section To Panagudi (NS-43/TN) Highway Project | 414 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2204 | Completed |  | August 2009 | Madurai | Tamil Nadu | 31 Mar 2004 | Date of announcement | 2009-07-01 | 2204 | 2240 | -36 | N | 2009-08-31 | Completed | 2008-09-30 | Y | 335
753 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli section including Madurai Bypass (NS-39/TN) NH-7 Project | 268 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3825 | Completed |  | September 2009 | Madurai | Tamil Nadu | 01 Sep 2003 | Date of announcement | 2009-07-01 | 3825 | 1200 | 2625 | Y | 2009-09-30 | Initial completion date | 2008-10-31 | Y | 334 | 2008-02-18 | Bids awarded
754 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli-Panagudi (NH-7) Four Lane Road Project | 548 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6850 | No Information | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Madurai | Tamil Nadu | 17 Dec 2008 | Date of announcement | 2012-05-27 | 6850 | 1400 | 5450 | Y
755 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Belgaum-Dharwad) Highway Project | 83 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2790 | Completed | Engineering, Procurement & Construction | June 2007 | Belgaum | Karnataka | 01 Dec 2000 | Date of announcement | 2002-01-01 | 2790 | 3000 | -210 | N | 2007-06-30 | Completed | 2003-08-31 | Y | 1399 | 2002-04-16 | Bids awarded
756 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Hubli-Haveri) Highway Project | 114 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2801.9 | Completed | Engineering, Procurement & Construction | March 2008 | Haveri | Karnataka | 31 Mar 2001 | Date of announcement | 2007-10-31 | 2801.9 | 2560 | 241.9 | Y | 2008-03-31 | Completed | 2003-12-31 | Y | 1552 | 2001-06-01 | Bids awarded
757 | National Highways Authority Of India | 155597 | Mahatma Gandhi Setu Revamp Project | 879 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 17420.1 | Completed | Engineering, Procurement & Construction | June 2022 | Mahatma gandhi setu | Bihar | 30 May 2010 | Date of announcement | 2016-06-22 | 17420.1 | 290 | 17130.1 | Y | 2022-06-07 | Completed | 2017-08-31 | Y | 1741 | 2016-10-07 | Bids awarded
758 | National Highways Authority Of India | 155597 | Maheshkhunt-Saharsa-Purnea (NH-107 & 231) Two Laning Road Project (Package-II) | 1250 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7360 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Maheshkhunt | Bihar | 15 Jun 2010 | Date of announcement | 2018-04-29 | 7360 | 6419.6 | 940.4 | Y | 2023-06-30 | Completion expected by | 2020-03-31 | Y | 1186 | 2017-03-31 | Bids awarded
759 | National Highways Authority Of India | 155597 | Maheshkoot-Saharsa-Purnea (NH-107 & 231) Two Laning Road Project (Package-I) | 1129 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6445 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Maheshkhunt | Bihar | 15 Jun 2010 | Date of announcement | 2021-04-02 | 6445 | 10000 | -3555 | N | 2023-06-30 | Completion expected by | 2021-10-31 | Y | 607 | 2018-01-05 | Bids awarded
760 | National Highways Authority Of India | 155597 | Mahua-Jaipur Highway (NH-11) Project | 616 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5783 | Completed | Build Operate Transfer | September 2009 | Jaipur | Rajasthan | 15 Jul 2003 | Date of announcement | 2009-06-30 | 5783 | 4830 | 953 | Y | 2009-09-30 | Completed | 2009-03-31 | Y | 183
761 | National Highways Authority Of India | 155597 | Mahulia-Baharagora-JH/WB Border (NH-33 & NH-6) Four Laning Highway Project | 1036 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9971.5 | Completed | Engineering, Procurement & Construction | October 2019 | Baharagora | Jharkhand | 15 Mar 2010 | Date of announcement | 2016-02-11 | 9971.5 | 10832.8 | -861.3 | N | 2019-10-11 | Completed | 2018-02-28 | Y | 590 | 2011-12-15 | Bids awarded
762 | National Highways Authority Of India | 155597 | Mahuva-Kagavadar (NH-8E & NH-51) (Package-III Bhavnagar-Veraval Section) Four Lane Highway Project | 1903 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6038 | Under Implementation | Hybrid Annuity |  | Mahuva | Gujarat | 03 May 2012 | Date of announcement | 2022-12-21 | 6038 | 7640 | -1602 | N | [5 empty] | 2016-06-26 | Bids awarded
763 | National Highways Authority Of India | 155597 | Majholi-Katra-Yajuar-Kharka Basant-Majhaur-Baher-Pupri-Charout (NH-527C)Two-Lane Highway Project | 1182 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5371.7 | Under Implementation | Engineering, Procurement & Construction | May 2023 | Baher | Bihar | 31 Aug 2012 | Date of announcement | 2021-12-16 | 5371.7 | 4000 | 1371.7 | Y | 2023-05-31 | Completion expected by | 2021-11-30 | Y | 547 | 2018-11-27 | Bids awarded
764 | National Highways Authority Of India | 155597 | Major Bridge on Chakan River to Major Bridge on Mej River Eight Lane Carriageway Project (Package-11 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1562 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8849.5 | Under Implementation | Engineering, Procurement & Construction |  | Chakan river | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 8849.5 | 8849.5 | 0 | N | [5 empty] | 2020-06-23 | Bids awarded
765 | National Highways Authority Of India | 155597 | Major Bridge on Mej River to Junction with SH-37A Eight Lane Carriageway Project (Package 12 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1563 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8863.6 | Under Implementation | Engineering, Procurement & Construction |  | Mej river | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 8863.6 | 8863.6 | 0 | N | [5 empty] | 2020-06-18 | Bids awarded
766 | National Highways Authority Of India | 155597 | Major bridge over Takli river near Nayagaon Jageer village to Rajasthan/MP Border Eight Lane Carriageway Project (Package 16 of Delhi-Mumbai Expressway) | 1569 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7097 | Under Implementation | Engineering, Procurement & Construction |  | Manoharpur | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-10-03 | 7097 | 7097 | 0 | N | [5 empty] | 2020-07-08 | Bids awarded
767 | National Highways Authority Of India | 155597 | Majri Chowk (Panchkula) Flyover Project | 449 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 180 | Completed |  | February 2011 | Majri Chowk | Haryana | 04 Apr 2007 | Date of announcement | 2007-04-04 | 180 | 180 | 0 | N
768 | National Highways Authority Of India | 155597 | Malkangiri-Chintapalli-Narsipatnam-Waddai-Chodavaram-Subbavaram-Tuni (NH-326) Highway Project (Bharatmala) | 1531 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19000 | No Information |  |  | Chintapalle | Andhra Pradesh | 29 Sep 2016 | Date of announcement | 2017-08-01 | 19000 | 19000 | 0 | N
769 | National Highways Authority Of India | 155597 | Mall Road-Lal Bahadur Shastri National Academy of Administration (LBSNAA) Two Lane Tunnel (Mussoorie Tunnel) Project | 2071 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8000 | Announced |  |  | Lbsnaa, mussorie | Uttarakhand | 01 Mar 2021 | Date of announcement | 2022-09-15 | 8000 | 7000 | 1000 | Y
770 | National Highways Authority Of India | 155597 | Malout-Abohar-Sadhuwali Four Lane Road Project | 1804 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6598.9 | Under Implementation | Hybrid Annuity |  | Abohar | Punjab | 23 Dec 2019 | Date of announcement | 2020-01-08 | 6598.9 | 6598.9 | 0 | N | [5 empty] | 2021-03-31 | Bids awarded
771 | National Highways Authority Of India | 155597 | Mamallapuram-Mugaiyur section of NH-332A Four Lane Highway Project (Phase 1) | 1779 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10089.9 | Under Implementation | Hybrid Annuity | May 2024 | Mamallapuram | Tamil Nadu | 01 Nov 2017 | Date of announcement | 2022-07-21 | 10089.9 | 6174.7 | 3915.2 | Y | [5 empty] | 2020-03-23 | Bids awarded
772 | National Highways Authority Of India | 155597 | Mancherial-Chandrapur Four Lane Road Project | 1564 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 24970 | Under Implementation | Hybrid Annuity |  | Chandrapur | Maharashtra | 01 Nov 2016 | Date of announcement | 2021-02-21 | 24970 | 15000 | 9970 | Y
773 | National Highways Authority Of India | 155597 | Mancherial-Repallewada (NH-363) Four Lane Highway Project (Bharatmala) | 1426 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13569 | Completed | Hybrid Annuity | February 2023 | Mancherial | Telangana | 05 Dec 2017 | Date of announcement | 2022-08-30 | 13569 | 10506.3 | 3062.7 | Y | 2023-02-01 | Completed | 2022-11-30 | Y | 63 | 2019-03-12 | Bids awarded
774 | National Highways Authority Of India | 155597 | Mancherial-Warangal (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Ramaraopet village to Oorugonda village) | 1949 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 25000 | Under Implementation |  | March 2025 | Oorugonda | Telangana | 01 Nov 2018 | Date of announcement | 2022-11-29 | 25000 | 24549.5 | 450.5 | Y | [5 empty] | 2023-03-29 | Bids awarded
775 | National Highways Authority Of India | 155597 | Mandi Dabwali (Punjab/Haryana border)-Chautala Six Lane Road Project | 1807 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8566.6 | Under Implementation | Hybrid Annuity |  | Chautala | Haryana | 10 Jan 2020 | Date of announcement | 2020-06-05 | 8566.6 | 8566.6 | 0 | N | [5 empty] | 2021-01-22 | Bids awarded
776 | National Highways Authority Of India | 155597 | Mandi Dabwali-Panipat Four Lane Highway Project | 2093 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 143020 | Announced |  |  | Mandi dabwali | Haryana | 01 Jan 2021 | Date of announcement | 2023-02-03 | 143020 | 143020 | 0 | N
777 | National Highways Authority Of India | 155597 | Manewal (Ludhiana) to Bheora (Rupnagar) including Spur to Kharar with Ludhiana Bypass (Ludhiana-Rupnagar NH-205K) Six Lane Access Controlled Greenfield Highway Project (Package-2) | 1993 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9927.1 | Under Implementation | Hybrid Annuity |  | Bheora | Punjab | 01 Aug 2020 | Date of announcement | 2021-01-15 | 9927.1 | 9927.1 | 0 | N | [5 empty] | 2021-12-31 | Bids awarded
778 | National Highways Authority Of India | 155597 | Mangalore City Bypass (NH-66) Project (Mulki-Thokkottu Road) | 1209 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 25000 | No Information |  |  | Addur | Karnataka | 01 Sep 2016 | Date of announcement | 2019-03-05 | 25000 | 28000 | -3000 | N
779 | National Highways Authority Of India | 155597 | Mangalore-Bantwal N H-48 Project | 28 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 750 | No Information |  |  | Bantwal | Karnataka | 01 Feb 1998 | Date of announcement | 1998-03-01 | 750 | 750 | 0 | N
780 | National Highways Authority Of India | 155597 | Mangalore-Shimoga Two-Laning Highway Project | 799 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17860 | No Information |  |  | Mangalore | Karnataka | 24 Jul 2010 | Date of announcement | 2011-08-23 | 17860 | 5640 | 12220 | Y
781 | National Highways Authority Of India | 155597 | Mangalwar-Udaipur (KU-VI) Highway Project | 129 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1738 | Completed | Engineering, Procurement & Construction | January 2005 | Mangalwar | Rajasthan | 01 Jun 2001 | Date of announcement | 2004-03-31 | 1738 | 2400 | -662 | N | 2005-01-31 | Completed | 2003-12-31 | Y | 397 | 2001-11-01 | Bids awarded
782 | National Highways Authority Of India | 155597 | Mania-Dholpur Highway Project | 967 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 217.1 | Completed | Engineering, Procurement & Construction | March 2001 | Dholpur | Rajasthan | 01 Oct 1999 | Date of announcement | 1999-10-01 | 217.1 | 217.1 | 0 | N | [5 empty] | 1999-12-01 | Bids awarded
783 | National Highways Authority Of India | 155597 | Manoharpur-Dausa (NH-11A) Two-Laning Highway Project | 1190 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2240 | Completed | Engineering, Procurement & Construction | July 2019 | Dausa | Rajasthan | 01 Mar 2008 | Date of announcement | 2018-02-28 | 2240 | 2380 | -140 | N | 2019-07-17 | Completed | 2018-08-31 | Y | 320 | 2016-07-28 | Bids awarded
784 | National Highways Authority Of India | 155597 | Manu-Agartala (NH-44) Highway Project | 363 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9680 | No Information |  |  | Agartala | Tripura | 01 Dec 2003 | Date of announcement | 2007-07-01 | 9680 | 9680 | 0 | N
785 | National Highways Authority Of India | 155597 | Mataur (Kangra)-Shimla (NH-88) Four Laning Highway Project | 1219 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 100000 | Under Implementation | Hybrid Annuity |  | Ghumarwin | Himachal Pradesh | 22 Jul 2013 | Date of announcement | 2023-04-03 | 100000 | 49050 | 50950 | Y | [5 empty] | 2022-03-28 | Bids awarded
786 | National Highways Authority Of India | 155597 | Mathura-Agra Highway (NH-2) Project | 382 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 26 | No Information |  |  | Agra | Uttar Pradesh | 12 Feb 2004 | Bids invited | 2004-03-01 | 26 | 26 | 0 | N
787 | National Highways Authority Of India | 155597 | Mathura-Hathras-Badaun-Bareilly (NH-530B) Four Lane Highway Project | 1681 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 76690 | Under Implementation | Hybrid Annuity |  | Bareilly | Uttar Pradesh | 13 Jun 2017 | Date of announcement | 2022-01-07 | 76690 | 65000 | 11690 | Y | [5 empty] | 2023-03-29 | Bids awarded
788 | National Highways Authority Of India | 155597 | Matsyafed Tourist Office-Munambam Road Upgradation Project | 1739 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2587.3 | No Information |  |  | Munambam | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 2587.3 | 2587.3 | 0 | N
789 | National Highways Authority Of India | 155597 | Mayyandu Beach-Thankassery Road Project | 1746 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2304.6 | No Information |  |  | Mayyandu beach | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 2304.6 | 2304.6 | 0 | N
790 | National Highways Authority Of India | 155597 | Medical Tiraha-Kochha Bhanwar (NH-27) Four Lane Flyover Project | 3002 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 610 | Under Implementation |  |  | Kochha bhanwar | Uttar Pradesh | 01 Apr 2021 | Date of announcement | 2023-03-13 | 610 | 610 | 0 | N
791 | National Highways Authority Of India | 155597 | Medshi-Washim (NH-161) Four Lane Highway project (Package-II) | 1696 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7997.7 | Under Implementation | Engineering, Procurement & Construction |  | Medshi | Maharashtra | 01 Apr 2018 | Date of announcement | 2019-06-25 | 7997.7 | 6831 | 1166.7 | Y | [5 empty] | 2019-02-25 | Bids awarded
792 | National Highways Authority Of India | 155597 | Meensurutti-Chidambaram (NH-81 & NH-227) Two/Four Lane Highway Project (Package-III of Trichy-Chidambaram) (Bharatmala) | 1770 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7363.3 | Under Implementation | Hybrid Annuity | October 2023 | Chidambaram | Tamil Nadu | 24 Nov 2017 | Date of announcement | 2022-07-21 | 7363.3 | 6335.5 | 1027.8 | Y | 2023-10-31 | Completion expected by | 2021-02-28 | Y | 975 | 2018-03-07 | Bids awarded
793 | National Highways Authority Of India | 155597 | Meerut New Bypass (NH-58) to Meerut-Najibabad (NH-119) (NH-709A) Four Lane Link Road Project (Four Lane Spur of Meerut-GarhMukteshwar Section) | 1938 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9920 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Meerut | Uttar Pradesh | 01 Apr 2021 | Date of announcement | 2021-12-23 | 9920 | 9920 | 0 | N | [5 empty] | 2022-03-23 | Bids awarded
794 | National Highways Authority Of India | 155597 | Meerut to after bridge over river Yamuna (Haryana) via Shamli (NH-709A) Four Lane Highway Project | 1684 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5862.4 | Under Implementation | Engineering, Procurement & Construction |  | Haryana | Haryana | 08 Mar 2019 | Date of announcement | 2020-01-29 | 5862.4 | 5023.8 | 838.6 | Y | [5 empty] | 2020-07-16 | Bids awarded
795 | National Highways Authority Of India | 155597 | Meerut-Baghpat-UP/Haryana Border (Sonipat) (NH-334B) Two Lane Highway Project (Bharatmala) | 1672 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2817.2 | Completed | Engineering, Procurement & Construction | February 2023 | Baghpat | Uttar Pradesh | 01 Oct 2018 | Date of announcement | 2019-03-07 | 2817.2 | 3710 | -892.8 | N | 2023-02-01 | Completed | 2022-02-28 | Y | 338 | 2019-06-20 | Bids awarded
796 | National Highways Authority Of India | 155597 | Meerut-Budhana-Shamli-UP/Haryana Border (Karnal) NH-709A Four Lane Highway Project | 1674 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8165.5 | Under Implementation |  |  | Budhana | Uttar Pradesh | 23 Mar 2015 | Date of announcement | 2021-08-02 | 8165.5 | 7080 | 1085.5 | Y
797 | National Highways Authority Of India | 155597 | Mehrauli-Gurgaon (MG Road) Six-Laning Highway Project | 718 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1080 | Completed |  | December 2011 | Gurgaon | Haryana | 07 Dec 2009 | Date of announcement | 2010-09-24 | 1080 | 800 | 280 | Y | 2011-12-31 | Completed | 2010-09-30 | Y | 457
798 | National Highways Authority Of India | 155597 | Mehsi-Kotwa (LMNHP-11) Four-Laning Highway Project | 702 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3180 | Completed |  | June 2011 | Kotwa | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2011-03-31 | 3180 | 2390 | 790 | Y | 2011-06-30 | Completed | 2011-03-31 | Y | 91
799 | National Highways Authority Of India | 155597 | Melur-Karaikudi (NH-338, 36 & 383 Ext) Four Lane Highway Project (Thanjavur-Madurai Greenfield Project) (Bharatmala) | 1495 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11038.6 | Under Implementation | Engineering, Procurement & Construction |  | Karaikudi | Tamil Nadu | 17 May 2018 | Date of announcement | 2019-02-06 | 11038.6 | 7675.9 | 3362.7 | Y | [5 empty] | 2019-02-06 | Bids awarded
800 | National Highways Authority Of India | 155597 | Memmadpur-Dairi-Kharar Four Lane & IT City Chowk-Kurali Chandigarh Road Six Lane Highway Project (Bharatmala) | 1857 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7892.9 | Under Implementation | Engineering, Procurement & Construction |  | Kharar | Punjab | 01 Apr 2018 | Date of announcement | 2021-01-15 | 7892.9 | 8220 | -327.1 | N | [5 empty] | 2021-07-12 | Bids awarded
801 | National Highways Authority Of India | 155597 | Mettupalayam-Kakkanullah Strengthening & Widening Road Project | 826 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3270 | Announced & Stalled |  |  | Coonoor | Tamil Nadu | 01 Jan 2006 | Date of announcement | 2010-12-01 | 3270 | 3270 | 0 | N
802 | National Highways Authority Of India | 155597 | Mirya-Hatkhamba & Pali-Sakharpa Four Lane Highway (Package-I of Ratnagiri-Kolhapur section of NH-166) Project | 1445 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10325.1 | Under Implementation | Hybrid Annuity |  | Hatkhamba | Maharashtra | 01 Jan 2017 | Date of announcement | 2021-10-08 | 10325.1 | 10671.3 | -346.2 | N | [5 empty] | 2022-03-29 | Bids awarded
803 | National Highways Authority Of India | 155597 | Mirza Chauki-Farakka (NH-80) Four Lane Highway Project (Package-I) | 1486 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13020 | Under Implementation | Hybrid Annuity | July 2023 | Farakka (jharkhand) | Jharkhand | 06 Apr 2018 | Date of announcement | 2022-07-12 | 13020 | 6611.4 | 6408.6 | Y | [5 empty] | 2019-03-10 | Bids awarded
804 | National Highways Authority Of India | 155597 | Miyati Village-MP-Gujarat Border Eight Lane Carriageway Project (Package 25 of Delhi-Mumbai Expressway) | 1606 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9960 | Completed | Engineering, Procurement & Construction | November 2022 | Miyati village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 9960 | 9664.3 | 295.7 | Y | 2022-12-14 | Initial completion date | 2021-12-31 | Y | 348 | 2019-08-07 | Bids awarded
805 | National Highways Authority Of India | 155597 | Mohari-Satai Ghat (NH-934) Four Lane Highway Project (Package-II) | 2082 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7110 | Under Implementation | Engineering, Procurement & Construction |  | Mohari | Madhya Pradesh | 01 Apr 2022 | Date of announcement | 2023-01-23 | 7110 | 4687.9 | 2422.1 | Y | [5 empty] | 2022-12-31 | Bids awarded
806 | National Highways Authority Of India | 155597 | Mohol-Wakhri (NH-965) Four Lane Highway Project (Package-I of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1441 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14380 | Under Implementation | Engineering, Procurement & Construction |  | Mohol | Maharashtra | 29 Dec 2017 | Date of announcement | 2021-11-08 | 14380 | 9616.7 | 4763.3 | Y | [5 empty] | 2019-09-18 | Bids awarded
807 | National Highways Authority Of India | 155597 | Mokalsar-Jalore (NH-325) Highway Project (Package-II) (Jalore-Barmer-Sirohi) | 1270 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1130 | Completed | Engineering, Procurement & Construction | September 2020 | Jalore | Rajasthan | 06 Sep 2015 | Date of announcement | 2020-09-14 | 1130 | 1829 | -699 | N | 2020-09-14 | Completed | 2019-07-31 | Y | 411
808 | National Highways Authority Of India | 155597 | Moradabad-Jaspur-Kashipur Four/Six Lane Road (NH-734) Project | 1855 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18419.2 | Under Implementation | Engineering, Procurement & Construction | November 2024 | Jaspur | Uttarakhand | 13 Jun 2017 | Date of announcement | 2022-11-01 | 18419.2 | 40000 | -21580.8 | N | [5 empty] | 2023-03-29 | Bids awarded
809 | National Highways Authority Of India | 155597 | Morena (NH-44) Four Lane Flyover/Grade Separator Project (K.S.Choraha-New Housing Board Colony) | 1305 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1080 | Completed | Engineering, Procurement & Construction | September 2020 | K.s.choraha | Madhya Pradesh | 29 May 2017 | Date of announcement | 2020-09-28 | 1080 | 909.6 | 170.4 | Y | 2020-09-28 | Completed | 2019-09-30 | Y | 364 | 2018-01-16 | Bids awarded
810 | National Highways Authority Of India | 155597 | Morena-Rairu (Start of Gwalior bypass NS-21/MP) Highway Project | 192 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 695 | Completed | Engineering, Procurement & Construction | December 2005 | Gwalior | Madhya Pradesh | 01 Jun 2001 | Date of announcement | 2002-01-01 | 695 | 720 | -25 | N | [5 empty] | 2001-08-01 | Bids awarded
811 | National Highways Authority Of India | 155597 | Motihari (Piprakothi)-Raxaul (NH-28A) Two Lane Highway Project | 1698 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3330 | Under Implementation | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Motihari | Bihar | 30 Apr 2009 | Date of announcement | 2022-12-31 | 3330 | 3750.9 | -420.9 | N | [5 empty] | 2011-01-07 | Bids awarded
812 | National Highways Authority Of India | 155597 | Mubarakpur-Biaora (NH-12) (New NH-46) Four-Laning Road Project (Package-II of Bhopal-Biaora) | 1241 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8970 | Completed | Engineering, Procurement & Construction | January 2021 | Bhopal | Madhya Pradesh | 12 Aug 2010 | Date of announcement | 2021-01-12 | 8970 | 6980 | 1990 | Y | 2021-03-31 | Initial completion date | 2016-10-31 | Y | 1612 | 2012-01-10 | Bids awarded
813 | National Highways Authority Of India | 155597 | Mudhiyam Beach-Madhura Bazaar Road Upgradation Project (Bharatmala) | 1723 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3213.1 | Announced |  | February 2024 | Madhura bazaar | Kerala | 12 Apr 2018 | Date of announcement | 2020-08-09 | 3213.1 | 2610 | 603.1 | Y
814 | National Highways Authority Of India | 155597 | Mugaiyur-Marakkanam Four Laning section of NH-332 A Road Project (Package-II of Mahabalipuram-Puducherry section) (Bharatmala) | 1780 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8260 | Under Implementation | Hybrid Annuity |  | Marakkanam | Tamil Nadu | 01 Nov 2018 | Date of announcement | 2021-07-22 | 8260 | 5924.4 | 2335.6 | Y | [5 empty] | 2021-11-10 | Bids awarded
815 | National Highways Authority Of India | 155597 | Mukarba Chowk-Mall Road (NS-3/DL) Highway Project | 97 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 575.3 | Completed | Engineering, Procurement & Construction | January 2007 | Mukarba Chowk | NCT of Delhi | 01 Mar 2001 | Date of announcement | 2002-01-01 | 575.3 | 520 | 55.3 | Y | 2007-01-31 | Completed | 2004-11-30 | Y | 792 | 2001-11-01 | Bids awarded
816 | National Highways Authority Of India | 155597 | Mukkola-Kerala/Tamil Nadu Border (Karode) (NH-66) Four Laning Highway Project (Phase 2 of Kazhakuttam-Karode Highway) (Bharatmala) | 1084 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11477.9 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Inchivila | Kerala | 30 Mar 2012 | Date of announcement | 2021-07-19 | 11477.9 | 14000 | -2522.1 | N | 2023-08-31 | Completion expected by | 2018-06-30 | Y | 1888 | 2016-04-13 | Bids awarded
817 | National Highways Authority Of India | 155597 | Mulavukad Road Development Project | 1521 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 87 | Under Implementation |  |  | Mulavukad | Kerala | 06 Sep 2006 | Date of announcement | 2006-09-06 | 87 | 87 | 0 | N
818 | National Highways Authority Of India | 155597 | Muli-Level Carriageway Project (Kanhan-Automotive Square) | 1263 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2961.9 | No Information | Engineering, Procurement & Construction |  | Automotive square | Maharashtra | 17 Feb 2017 | Date of announcement | 2017-02-17 | 2961.9 | 2961.9 | 0 | N | [5 empty] | 2017-03-10 | Bids awarded
819 | National Highways Authority Of India | 155597 | Mumbai-Nashik Highway Project | 415 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8080 | Completed | Build Operate Transfer | September 2011 | Mumbai | Maharashtra | 01 Dec 2004 | Date of announcement | 2011-09-30 | 8080 | 8000 | 80 | Y
820 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 440000 | Under Implementation | Hybrid Annuity |  | Bharuch | Gujarat | 31 Mar 1998 | Date of announcement | 2017-10-24 | 440000 | 70000 | 370000 | Y | [5 empty] | 2018-03-29 | Bids awarded
821 | National Highways Authority Of India | 155597 | Munabao (NH-25)-Sundra-Myajlar-Dhanana-Asutar-Ghotaru-Tanot-Kishangarh (Indo-Pak Boarder) Two/Four Laning Highway Project (BM/4) (Bharatmala) | 1096 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16840 | Completed | Hybrid Annuity | August 2020 | Dhanana | Rajasthan | 05 Apr 2015 | Date of announcement | 2020-08-21 | 16840 | 13750 | 3090 | Y | 2021-06-28 | Initial completion date | 2020-05-31 | Y | 393 | 2018-03-26 | Bids awarded
822 | National Highways Authority Of India | 155597 | Munambam-Kara Beach Road Widening Project | 1730 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5089.6 | No Information |  |  | Kara beach | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 5089.6 | 5089.6 | 0 | N
823 | National Highways Authority Of India | 155597 | Munger-Bhagalpur-Mirzachowki Two Lane Road Widening (NH-80) Project | 2039 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10440 | Under Implementation |  |  | Bhagalpur | Bihar | 01 Jan 2022 | Date of announcement | 2022-06-07 | 10440 | 10440 | 0 | N
824 | National Highways Authority Of India | 155597 | Munger-Mirzachowki (NH-80) Four Lane (Greenfield Corridor) Road Project | 1131 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 57880 | Under Implementation | Hybrid Annuity | December 2024 | Deoghar choraha (sultanganj) | Bihar | 15 Jul 2009 | Date of announcement | 2022-06-07 | 57880 | 12000 | 45880 | Y | 2025-02-28 | Initial completion date | 2024-12-31 | Y | 59 | 2021-02-22 | Bids awarded
825 | National Highways Authority Of India | 155597 | Munshi Puliya-Polytechnic Chauraha (NH-24A) Four Lane Flyover Project | 1945 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1710 | Under Implementation | Engineering, Procurement & Construction | September 2024 | Munshi puliya | Uttar Pradesh | 02 Apr 2021 | Date of announcement | 2022-01-05 | 1710 | 1706 | 4 | Y | 2024-12-31 | Initial completion date | 2024-09-30 | Y | 92
826 | National Highways Authority Of India | 155597 | Muthukur Junction Four Lane Flyover Project | 1861 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 418.8 | Under Implementation |  |  | Muthukur junction | Andhra Pradesh | 15 Feb 2020 | Date of announcement | 2020-10-04 | 418.8 | 418.8 | 0 | N | [5 empty] | 2020-06-16 | Bids awarded
827 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 25850 | Completed | Build Operate Transfer | January 2023 | Dehradun | Uttarakhand | 07 Jul 2004 | Date of announcement | 2018-01-31 | 25850 | 12320 | 13530 | Y | 2023-01-01 | Completed | 2015-12-31 | Y | 2558 | 2009-12-29 | Bids awarded
828 | National Highways Authority Of India | 155597 | Muzaffarnagar-Miranpur (NH-709AD) Four Lane Highway Project (Package 3 of Panipat-Nagina Highway) | 1642 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8800 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Miranpur | Uttar Pradesh | 10 Jun 2016 | Date of announcement | 2021-08-02 | 8800 | 5576.4 | 3223.6 | Y | [5 empty] | 2021-09-24 | Bids awarded
829 | National Highways Authority Of India | 155597 | Muzaffarnagar-Nepali Farm Section of (NH-58) Four-Laning Project | 484 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12514.2 | No Information | Build Operate Transfer |  | Dehradun | Uttarakhand | 08 Aug 2008 | Date of announcement | 2008-08-11 | 12514.2 | 12514.2 | 0 | N
830 | National Highways Authority Of India | 155597 | Muzaffarpur Ring Road Project | 1066 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4000 | No Information |  |  | Muzaffarpur | Bihar | 01 Mar 2010 | Date of announcement | 2015-03-17 | 4000 | 4000 | 0 | N
831 | National Highways Authority Of India | 155597 | Muzaffarpur-Barauni (NH-28) Four Lane Highway Project (Bharatmala) | 1443 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 33370 | Under Implementation |  |  | Barauni | Bihar | 26 Dec 2017 | Date of announcement | 2022-08-02 | 33370 | 1320 | 32050 | Y
832 | National Highways Authority Of India | 155597 | Muzaffarpur-Mehsi (LMNHP-12) Highway Project | 703 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3347 | Completed |  | March 2011 | Mehsi | Bihar | 01 Oct 2003 | Date of announcement | 2011-03-31 | 3347 | 2750 | 597 | Y | [5 empty] | 2003-10-01 | Bids awarded
833 | National Highways Authority Of India | 155597 | Muzaffarpur-Sonbarsa (NH-77) Four-Laning Highway Project | 571 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10130 | Under Implementation | Build Operate Transfer |  | Muzaffarpur | Bihar | 28 Feb 2009 | Date of announcement | 2009-04-01 | 10130 | 9326 | 804 | Y
834 | National Highways Authority Of India | 155597 | NH-148AE Road Tunnel Project (connection to NH-248BB and existingDelhi internal roads) | 1842 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19840 | Announced |  |  | Delhi | NCT of Delhi | 05 Jun 2020 | Date of announcement | 2022-01-11 | 19840 | 19840 | 0 | N
835 | National Highways Authority Of India | 155597 | NH-16 to Gangavaram Port Six Lane Road Project | 1536 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 500 | No Information |  |  | Gangavaram | Andhra Pradesh | 14 Apr 2016 | Date of announcement | 2016-04-14 | 500 | 500 | 0 | N
836 | National Highways Authority Of India | 155597 | NH-325 Bypass Project (Package-IV) (Jalore-Barmer-Sirohi) | 1272 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4475.1 | Announced | Engineering, Procurement & Construction |  | Ahore | Rajasthan | 06 Sep 2015 | Date of announcement | 2017-03-19 | 4475.1 | 4475.1 | 0 | N
837 | National Highways Authority Of India | 155597 | NH-45B and NH-7A Four to Six Laning Road Project (Port Connectivity) (Sagarmala) | 1732 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3721 | Announced |  | February 2024 | Tuticorin | Tamil Nadu | 01 Dec 2016 | Date of announcement | 2021-09-07 | 3721 | 3368.2 | 352.8 | Y
838 | National Highways Authority Of India | 155597 | NH-65 (near sultan nagaram)-Machilipatnam Port Green field Road Project | 1520 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1750 | No Information | Engineering, Procurement & Construction |  | Machilipatnam | Andhra Pradesh | 31 Jan 2016 | Date of announcement | 2016-04-16 | 1750 | 1750 | 0 | N
839 | National Highways Authority Of India | 155597 | NH-75 ROB Project (between Jhinkpani-Talaburu) | 3007 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 960 | Under Implementation |  |  | Nh-75 | Jharkhand | 01 Mar 2023 | Date of announcement | 2023-03-19 | 960 | 960 | 0 | N
840 | National Highways Authority Of India | 155597 | NH-75 ROB Project (between Singhpokhariya-Jhinkpani) | 3008 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 910 | Under Implementation |  |  | Nh-75 | Jharkhand | 01 Mar 2023 | Date of announcement | 2023-03-19 | 910 | 910 | 0 | N
842 | National Highways Authority Of India | 155597 | Nachna-Balan (Babla) and Nachna-Bharewala Two/Four Laning Highway Project (BM/9) | 1111 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4350 | No Information |  |  | Balana (babla) | Rajasthan | 05 Apr 2015 | Date of announcement | 2015-11-20 | 4350 | 4350 | 0 | N
843 | National Highways Authority Of India | 155597 | Nagaon Bypass (AS-18) Highway Project | 706 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3120 | Completed |  | May 2011 | Nagaon | Assam | 01 Dec 2003 | Date of announcement | 2011-05-30 | 3120 | 2300 | 820 | Y | 2011-05-30 | Completed | 2010-03-31 | Y | 425
844 | National Highways Authority Of India | 155597 | Nagaon-Dharmtul (NH-37) Highway Project | 279 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3020 | Completed | Engineering, Procurement & Construction | September 2016 | Dharmtul | Assam | 01 Dec 2003 | Date of announcement | 2013-03-31 | 3020 | 2647.2 | 372.8 | Y | 2016-09-30 | Completed | 2010-12-31 | Y | 2100
845 | National Highways Authority Of India | 155597 | Nagapattinam-Karur Highway Project | 402 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 11000 | No Information |  |  | Karur | Tamil Nadu | 07 Feb 2005 | Date of announcement | 2005-02-07 | 11000 | 11000 | 0 | N
846 | National Highways Authority Of India | 155597 | Nagapattinam-Thanjavur (NH-83) Two-Laning Road Project | 545 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4341.2 | Under Implementation | Engineering, Procurement & Construction | May 2023 | Nagapattinam | Tamil Nadu | 21 Nov 2008 | Date of announcement | 2022-07-21 | 4341.2 | 6190 | -1848.8 | N | 2023-05-04 | Completion expected by | 2017-09-30 | Y | 2042 | 2015-03-17 | Bids awarded
847 | National Highways Authority Of India | 155597 | Nagaur (Karwar)-Dangyawas Road (NH-125A) (Phase 2 of Jodhpur Ring Road Project) | 1774 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4798.2 | Under Implementation | Engineering, Procurement & Construction |  | Dangyawas | Rajasthan | 30 Jan 2010 | Date of announcement | 2021-11-24 | 4798.2 | 5142.7 | -344.5 | N | [5 empty] | 2022-03-31 | Bids awarded
848 | National Highways Authority Of India | 155597 | Nagina-Kashipur (NH-74) Four Lane Highway Project | 1020 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 25360 | Completed | Engineering, Procurement & Construction | December 2021 | Kashipur | Uttarakhand | 15 Dec 2009 | Date of announcement | 2021-12-30 | 25360 | 10930 | 14430 | Y | 2021-12-30 | Completed | 2020-04-30 | Y | 609 | 2016-03-31 | Bids awarded
849 | National Highways Authority Of India | 155597 | Nagpur (Ajni) Inter-Modal Station Project | 1316 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10533.8 | Shelved | Engineering, Procurement & Construction |  | Congress nagar | Maharashtra | 08 Jul 2017 | Date of announcement | 2020-06-08 | 10533.8 | 16000 | -5466.2 | N | [5 empty] | 2020-11-20 | Bids awarded
852 | National Highways Authority Of India | 155597 | Nagpur-Hyd & Hyd-Bangalore(NS-23/AP) Highway Project | 194 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 880 | No Information |  |  | Bangalore | Karnataka | 31 Mar 2001 | Expenses incurred upto | 2001-09-01 | 880 | 880 | 0 | N
853 | National Highways Authority Of India | 155597 | Nagpur-Hyderabad Highway Project | 344 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 5468.3 | No Information | Build Operate Transfer |  | Hyderabad | Telangana | 31 Dec 2003 | Date of announcement | 2010-01-01 | 5468.3 | 29.8 | 5438.5 | Y
854 | National Highways Authority Of India | 155597 | Nagpur-Hyderabad-Bangalore Expressway Project | 1205 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 276470 | Announced |  |  | Bangalore | Karnataka | 31 Mar 2016 | Date of announcement | 2023-02-03 | 276470 | 350000 | -73530 | N
855 | National Highways Authority Of India | 155597 | Nagpur-Umred (NH-353 D) Four Lane Highway Project | 1685 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7819.4 | Completed | Engineering, Procurement & Construction | October 2022 | Nagpur | Maharashtra | 08 Jan 2016 | Date of announcement | 2022-10-01 | 7819.4 | 4200 | 3619.4 | Y | 2022-10-01 | Completed | 2021-08-08 | Y | 419 | 2019-03-09 | Bids awarded
856 | National Highways Authority Of India | 155597 | Nagpur-Waingang-Bhandara (NH-6) Six Lane Highway Project | 1413 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9800 | Announced | Hybrid Annuity |  | Bhandara | Maharashtra | 13 Nov 2017 | Date of announcement | 2018-03-10 | 9800 | 10533 | -733 | N
857 | National Highways Authority Of India | 155597 | Naidupeta (NH-5)-Krishnapatnam Port Four/Six Lane Greenfield Road Project (Bharatmala) | 1519 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13990 | Under Implementation | Engineering, Procurement & Construction | February 2024 | Krishnapatnam | Andhra Pradesh | 14 Apr 2016 | Date of announcement | 2023-01-02 | 13990 | 6700 | 7290 | Y
858 | National Highways Authority Of India | 155597 | Naidupeta-Turpu Kanupur Six Lane Greenfield Highway Project | 2058 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13988.4 | Under Implementation | Hybrid Annuity |  | Naidupeta | Andhra Pradesh | 01 Oct 2021 | Date of announcement | 2022-08-08 | 13988.4 | 13988.4 | 0 | N | [5 empty] | 2023-02-13 | Bids awarded
859 | National Highways Authority Of India | 155597 | Naini-Allahabad Yamuna Bridge Project | 47 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3080 | Completed |  | July 2004 | Allahabad | Uttar Pradesh | 01 Aug 1998 | Date of announcement | 2004-04-01 | 3080 | 2950 | 130 | Y | 2004-07-31 | Completed | 2003-04-30 | Y | 458
860 | National Highways Authority Of India | 155597 | Najibabad Four Lane Bypass (NH-119) Project | 1937 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5680 | Under Implementation | Engineering, Procurement & Construction |  | Najibabad | Uttar Pradesh | 01 Apr 2021 | Date of announcement | 2021-12-23 | 5680 | 4040 | 1640 | Y | [5 empty] | 2022-03-23 | Bids awarded
861 | National Highways Authority Of India | 155597 | Najibabad-Afjalgarh Four Lane Bypass Road Project | 2076 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11260 | Under Implementation |  |  | Afzalgarh | Uttar Pradesh | 01 Dec 2021 | Date of announcement | 2022-08-03 | 11260 | 7996.6 | 3263.4 | Y
862 | National Highways Authority Of India | 155597 | Nalagampalli Village-AP/Karnataka Border (NH-69) Four Lane Highway Project (Package-II) | 1218 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11000 | Completed | Engineering, Procurement & Construction | August 2019 | Andhra Pradesh | Andhra Pradesh | 30 Sep 2016 | Date of announcement | 2019-08-03 | 11000 | 6483.2 | 4516.8 | Y | 2019-11-14 | Initial completion date | 2018-10-30 | Y | 380 | 2017-03-30 | Bids awarded
863 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7750 | Completed | Engineering, Procurement & Construction | October 2021 | Bijni | Assam | 01 Dec 2003 | Date of announcement | 2009-04-01 | 7750 | 7750 | 0 | N | 2021-10-31 | Completed | 2009-06-30 | Y | 4506
864 | National Highways Authority Of India | 155597 | Nanasa-Pidgaon (NH-47) Four Lane Highway Project (Package-III of Indore-Harda Economic Corridor) (Sagarmala) | 1654 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8470 | Under Implementation | Hybrid Annuity | October 2023 | Nanasa | Madhya Pradesh | 01 Apr 2017 | Date of announcement | 2022-03-17 | 8470 | 5979.1 | 2490.9 | Y | [5 empty] | 2020-03-31 | Bids awarded
865 | National Highways Authority Of India | 155597 | Nandi Hills Cross-Devanahalli & Meenakunte-Hebbal Six Lane Highway Project | 230 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1720.6 | Completed | Engineering, Procurement & Construction | August 2008 | Devanahalli | Karnataka | 31 Mar 2001 | Date of announcement | 2001-03-31 | 1720.6 | 1720.6 | 0 | N | [5 empty] | 2001-09-01 | Bids awarded
866 | National Highways Authority Of India | 155597 | Nandigama and Kanchikacherla (NH-65) Six Lane Bypass Project | 1337 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4250 | Completed | Engineering, Procurement & Construction | April 2021 | Kanchikacherla | Andhra Pradesh | 28 Sep 2017 | Date of announcement | 2021-04-29 | 4250 | 3286.7 | 963.3 | Y | 2021-04-29 | Completed | 2019-06-30 | Y | 669 | 2017-12-27 | Bids awarded
867 | National Highways Authority Of India | 155597 | Nangloi Najafgarh Road-Dwarka Sector 24 Six Lane (NH-344M) Road Project (Package 3 of Delhi 3rd Ring Road or UER-2) | 1799 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6853.1 | Under Implementation | Engineering, Procurement & Construction | September 2023 | Dwarka sector 24 | NCT of Delhi | 01 Apr 2016 | Date of announcement | 2019-12-26 | 6853.1 | 6853.1 | 0 | N | 2023-10-30 | Initial completion date | 2023-09-15 | Y | 45 | 2021-08-12 | Bids awarded
868 | National Highways Authority Of India | 155597 | Nani Bhadol village-Dodka village Eight Lane Access-Controlled Expressway Project (Package 31 of Delhi-Mumbai Expressway) | 1636 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7894 | Under Implementation | Engineering, Procurement & Construction | May 2023 | Dodka | Gujarat | 31 Mar 1998 | Date of announcement | 2020-08-06 | 7894 | 7844.9 | 49.1 | Y | 2023-05-17 | Completion expected by | 2021-12-31 | Y | 502 | 2020-07-23 | Bids awarded
869 | National Highways Authority Of India | 155597 | Nanthoor Junction Vehicular Overpass Project | 2059 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 220 | Announced | Engineering, Procurement & Construction |  | Nanthoor junction | Karnataka | 01 Apr 2014 | Date of announcement | 2022-08-23 | 220 | 220 | 0 | N
870 | National Highways Authority Of India | 155597 | Narasannapeta-Ranastalam (NH-16) Six Laning Highway Project (Package-2) | 1253 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14575.8 | Completed | Hybrid Annuity | February 2022 | Narasannapeta | Andhra Pradesh | 17 Jan 2017 | Date of announcement | 2022-02-17 | 14575.8 | 13231.5 | 1344.3 | Y | 2022-02-17 | Completed | 2021-07-31 | Y | 201 | 2017-12-05 | Bids awarded
871 | National Highways Authority Of India | 155597 | Narayanmpet-Chandrasekharpuram Six Lane Access Controlled Highway (NH-544G) Project (Package-10 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1975 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5744.1 | Under Implementation |  | March 2026 | Chandrasekharapuram | Andhra Pradesh | 01 Aug 2021 | Date of announcement | 2022-01-25 | 5744.1 | 5744.1 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
872 | National Highways Authority Of India | 155597 | Narmada Six/Eight Lane Expressway Project | 1546 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 310000 | Under Implementation |  | March 2025 | Alirajpur | Madhya Pradesh | 31 Jan 2017 | Date of announcement | 2021-09-18 | 310000 | 310000 | 0 | N | 2025-03-31 | Completion expected by | 2023-07-31 | Y | 609 | 2022-03-30 | Bids awarded
873 | National Highways Authority Of India | 155597 | Narnaul Bypass crossing to Paniyala Mor (NH-148B) (at NH-48 junction) and, Nizampur Link Road & Narnaul Bypass crossing to Pacheri Kalan Project (Bharatmala) | 1607 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12549 | Completed | Hybrid Annuity | February 2021 | Narnaul | Haryana | 30 Mar 2018 | Date of announcement | 2018-12-18 | 12549 | 8934.2 | 3614.8 | Y | [5 empty] | 2019-01-15 | Bids awarded
875 | National Highways Authority Of India | 155597 | Nashik Phata-Khed (NH-60) Six Lane Highway Project | 1421 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9782.1 | Announced | Engineering, Procurement & Construction |  | Khed | Maharashtra | 30 Sep 2015 | Date of announcement | 2017-12-12 | 9782.1 | 8309.9 | 1472.2 | Y
876 | National Highways Authority Of India | 155597 | Natham-Tuvarankurichi section (NH-785E) Four Lane Highway Project (Bharatmala) | 1647 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5263.2 | Completed | Engineering, Procurement & Construction | March 2023 | Natham | Tamil Nadu | 13 Sep 2018 | Date of announcement | 2019-03-31 | 5263.2 | 3335.2 | 1928 | Y | 2023-03-01 | Completed | 2022-02-26 | Y | 368 | 2019-02-28 | Bids awarded
877 | National Highways Authority Of India | 155597 | Neeleshwaram-Thaliparambha (NH-66) Six Lanning Highway Project (Bharatmala) | 1802 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30416.5 | Under Implementation | Hybrid Annuity |  | Neeleshwaram | Kerala | 01 Dec 2019 | Date of announcement | 2020-10-12 | 30416.5 | 15685.9 | 14730.6 | Y | [5 empty] | 2020-10-15 | Bids awarded
878 | National Highways Authority Of India | 155597 | Nelamangala Junction to Devihalli Highway Project | 606 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6750 | Completed | Build Operate Transfer | November 2011 | Devanahalli | Karnataka | 31 Mar 2005 | Date of announcement | 2010-12-31 | 6750 | 4410 | 2340 | Y | 2011-12-31 | Initial completion date | 2010-07-31 | Y | 518
879 | National Highways Authority Of India | 155597 | Nelamangala-Tumkur (New NH-4 & 48) Six Lane Highway Project (Bharatmala) | 1668 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14070.8 | Under Implementation | Engineering, Procurement & Construction | August 2025 | Nelamangala | Karnataka | 12 Feb 2019 | Date of announcement | 2020-08-09 | 14070.8 | 11526.6 | 2544.2 | Y | 2025-12-31 | Initial completion date | 2023-02-28 | Y | 1037 | 2022-01-31 | Bids awarded
880 | National Highways Authority Of India | 155597 | Nellore-Chennai(Tada-Chennai) Highway Project | 104 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2330 | Completed | Engineering, Procurement & Construction | December 2005 | Chennai | Tamil Nadu | 01 Mar 2001 | Date of announcement | 2002-01-01 | 2330 | 1850 | 480 | Y | 2005-12-31 | Completed | 2004-03-31 | Y | 640 | 2001-06-01 | Bids awarded
881 | National Highways Authority Of India | 155597 | Ner Chowk-Pandoh (NH-21) Four Laning Highway Project (Package-I of Nerchowk-Kullu stretch) | 1033 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12737.1 | Under Implementation | Engineering, Procurement & Construction |  | Ner chowk | Himachal Pradesh | 15 Nov 2014 | Date of announcement | 2016-10-26 | 12737.1 | 7248.2 | 5488.9 | Y | [5 empty] | 2016-10-26 | Bids awarded
882 | National Highways Authority Of India | 155597 | Neraluru-Thorapalli Agraharam section (NH-844) Four Lane Highway Project (Package 1 of Hosur-Dharmapuri) (Bharatmala) | 1687 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4290.2 | Under Implementation | Hybrid Annuity |  | Neraluru | Karnataka | 11 Jul 2018 | Date of announcement | 2019-03-06 | 4290.2 | 4290.2 | 0 | N | [5 empty] | 2022-01-27 | Bids awarded
883 | National Highways Authority Of India | 155597 | New Dwar Ksuid Bridge Project | 1940 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 100 | Under Implementation |  | May 2023 | Dwar ksuid | Meghalaya | 01 Apr 2021 | Date of announcement | 2021-12-07 | 100 | 100 | 0 | N | 2023-08-31 | Initial completion date | 2022-12-31 | Y | 243
884 | National Highways Authority Of India | 155597 | New Four Lane Bridge across Varsova Creek (NH-48) (Surat-Dahisar Section) Project | 1139 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2470.2 | Completed | Engineering, Procurement & Construction | March 2023 | Varsova creek | Maharashtra | 15 Mar 2015 | Date of announcement | 2017-03-31 | 2470.2 | 1650.7 | 819.5 | Y | 2023-03-31 | Initial completion date | 2017-08-31 | Y | 2038 | 2017-03-27 | Bids awarded
885 | National Highways Authority Of India | 155597 | New Link (NH-133B) and Four Lane Bridge across Ganga connecting Sahibganj-Manihari (Katihar) (Package-I) Project | 1071 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19776.8 | Under Implementation | Engineering, Procurement & Construction | October 2024 | Manihari | Bihar | 01 Mar 2005 | Date of announcement | 2022-12-17 | 19776.8 | 10000 | 9776.8 | Y | 2025-12-31 | Initial completion date | 2019-05-31 | Y | 2406 | 2020-07-15 | Bids awarded
886 | National Highways Authority Of India | 155597 | New Mangalore Port Road Connectivity Improvement & Widening Project | 1148 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 260 | No Information |  |  | Mangalore | Karnataka | 15 May 2015 | Date of announcement | 2015-11-20 | 260 | 245.9 | 14.1 | Y | [5 empty] | 2015-11-20 | Bids awarded
887 | National Highways Authority Of India | 155597 | North-East side of Gorakhpur Bypass Four/Six Laning (Maniram (NH-29E)-Jagdispur (NH-28)) Project | 1924 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21000 | Under Implementation | Engineering, Procurement & Construction |  | Gorakhpur | Uttar Pradesh | 01 Sep 2021 | Date of announcement | 2023-03-13 | 21000 | 18817.4 | 2182.6 | Y | [5 empty] | 2023-03-29 | Bids awarded
888 | National Highways Authority Of India | 155597 | Obedullaganj-Betul (NH-69) Four-Laning Highway Project | 1296 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11990 | Under Implementation | Build Operate Transfer Toll |  | Betul | Madhya Pradesh | 14 Sep 2010 | Date of announcement | 2022-03-17 | 11990 | 12170 | -180 | N | [5 empty] | 2012-02-06 | Bids awarded
889 | National Highways Authority Of India | 155597 | Ochira-Thiruvananthapuram (Kazhakuttam) (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 543 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19871.6 | Under Implementation |  | December 2025 | Ochira | Kerala | 15 Oct 2004 | Date of announcement | 2009-01-01 | 19871.6 | 12407.9 | 7463.7 | Y | 2025-12-31 | Completion expected by | 2020-12-31 | Y | 1826
890 | National Highways Authority Of India | 155597 | Oddanchathram (NH-83) Four Lane Bypass Project | 1300 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2492.7 | Completed | Engineering, Procurement & Construction | December 2020 | Oddanchathram | Tamil Nadu | 18 May 2017 | Date of announcement | 2017-09-29 | 2492.7 | 2037.8 | 454.9 | Y | 2020-12-20 | Completed | 2019-11-30 | Y | 386 | 2017-09-29 | Bids awarded
891 | National Highways Authority Of India | 155597 | Old Pune Naka (NH-9)-Satrasta Chowk (NH-13) Four Lane Flyover Project | 1137 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4229.2 | Under Implementation | Engineering, Procurement & Construction |  | Old pune naka | Maharashtra | 15 Jul 2015 | Date of announcement | 2017-12-29 | 4229.2 | 4229.2 | 0 | N
892 | National Highways Authority Of India | 155597 | Omalur-Thumpipadi Highway Project | 330 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 166 | No Information |  |  | Omalur | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2003-12-01 | 166 | 166 | 0 | N
893 | National Highways Authority Of India | 155597 | Ongole-Chirala High Level Bridge Project | 787 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 500 | No Information | Build Operate Transfer |  | Chirala | Andhra Pradesh | 04 Jun 2010 | Date of announcement | 2010-06-04 | 500 | 500 | 0 | N
894 | National Highways Authority Of India | 155597 | Orai to Jhansi (NH-25) Highway Project | 314 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8410 | Completed | Engineering, Procurement & Construction | May 2013 | Jhansi | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2010-12-31 | 8410 | 7926.5 | 483.5 | Y | 2013-05-31 | Completed | 2010-06-30 | Y | 1066
895 | National Highways Authority Of India | 155597 | Orai-Bhognipur-Bara Highway Project | 345 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6078 | Completed | Build Operate Transfer | December 2010 | Bara | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2010-12-31 | 6078 | 5200 | 878 | Y | 2011-03-31 | Initial completion date | 2008-12-31 | Y | 820
896 | National Highways Authority Of India | 155597 | Ordnance Factory gate-Octroi Naka Flyover Project (on Amravati Road) | 1057 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 750 | No Information |  |  | Octroi naka | Maharashtra | 15 Jan 2015 | Date of announcement | 2015-01-29 | 750 | 750 | 0 | N
897 | National Highways Authority Of India | 155597 | Ormanjhi-Gola (NH-320B) Four Lane Greenfield Highway Project (Package-II) | 1991 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13300 | Under Implementation | Hybrid Annuity |  | Gola | Jharkhand | 01 Apr 2018 | Date of announcement | 2023-03-23 | 13300 | 6893.4 | 6406.6 | Y | [5 empty] | 2022-03-29 | Bids awarded
898 | National Highways Authority Of India | 155597 | Package-1 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1588 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7104.9 | Completed | Engineering, Procurement & Construction | December 2022 | Deogarh (raj) | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-06-11 | 7104.9 | 4448.9 | 2656 | Y | 2022-12-31 | Initial completion date | 2022-12-01 | N |  | 2019-06-11 | Bids awarded
899 | National Highways Authority Of India | 155597 | Package-1 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1793 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6433.4 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Sanchore | Rajasthan | 01 Apr 2017 | Date of announcement | 2022-12-07 | 6433.4 | 5165.7 | 1267.7 | Y | 2023-06-21 | Completion expected by | 2022-12-31 | Y | 172 | 2020-06-22 | Bids awarded
900 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6218.2 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 6218.2 | 4466.3 | 1751.9 | Y | [5 empty] | 2019-10-10 | Bids awarded
901 | National Highways Authority Of India | 155597 | Package-1 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1589 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7389 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 7389 | 5200.1 | 2188.9 | Y | [5 empty] | 2019-08-22 | Bids awarded
902 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8140.4 | Completed | Engineering, Procurement & Construction | August 2022 | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 8140.4 | 4405.7 | 3734.7 | Y | 2022-12-31 | Initial completion date | 2022-08-01 | Y | 152 | 2019-06-03 | Bids awarded
903 | National Highways Authority Of India | 155597 | Package-2 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1795 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7855.2 | Under Implementation | Engineering, Procurement & Construction |  | Sanchore | Rajasthan | 01 Apr 2017 | Date of announcement | 2022-12-07 | 7855.2 | 5668 | 2187.2 | Y | [5 empty] | 2020-06-30 | Bids awarded
904 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6761.9 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 6761.9 | 5356.3 | 1405.6 | Y | [5 empty] | 2019-03-08 | Bids awarded
905 | National Highways Authority Of India | 155597 | Package-2 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1594 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7551.6 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 7551.6 | 5282.3 | 2269.3 | Y | [5 empty] | 2019-06-03 | Bids awarded
906 | National Highways Authority Of India | 155597 | Package-3 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1574 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8201.9 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 8201.9 | 4680.3 | 3521.6 | Y | [5 empty] | 2019-06-03 | Bids awarded
907 | National Highways Authority Of India | 155597 | Package-3 of Rajasthan-Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1792 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7523 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Sanchore | Rajasthan | 01 Apr 2017 | Date of announcement | 2022-12-07 | 7523 | 5952.7 | 1570.3 | Y | 2023-08-10 | Completion expected by | 2022-12-31 | Y | 222 | 2021-01-27 | Bids awarded
908 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7328.4 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 7328.4 | 5415.2 | 1913.2 | Y | [5 empty] | 2019-10-10 | Bids awarded
909 | National Highways Authority Of India | 155597 | Package-3 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1595 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6727.2 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 6727.2 | 5103.7 | 1623.5 | Y | [5 empty] | 2019-09-13 | Bids awarded
910 | National Highways Authority Of India | 155597 | Package-4 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1577 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4225.4 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2018-10-03 | 4225.4 | 4225.4 | 0 | N | [5 empty] | 2020-03-03 | Bids awarded
911 | National Highways Authority Of India | 155597 | Package-4 of Rajasthan/Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1794 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7781.5 | Under Implementation | Engineering, Procurement & Construction |  | Sanchore | Rajasthan | 01 Apr 2017 | Date of announcement | 2022-12-07 | 7781.5 | 6197.8 | 1583.7 | Y | [5 empty] | 2020-06-30 | Bids awarded
912 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4883.5 | Completed | Engineering, Procurement & Construction | August 2022 | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-02-13 | 4883.5 | 4298.9 | 584.6 | Y | 2022-12-31 | Initial completion date | 2022-08-01 | Y | 152 | 2019-03-08 | Bids awarded
913 | National Highways Authority Of India | 155597 | Package-4 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1596 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5427 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 5427 | 3827.6 | 1599.4 | Y | [5 empty] | 2019-10-15 | Bids awarded
914 | National Highways Authority Of India | 155597 | Package-5 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1576 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4096.6 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2018-10-03 | 4096.6 | 4096.6 | 0 | N | [5 empty] | 2020-03-02 | Bids awarded
915 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5369.5 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-02-13 | 5369.5 | 4566.3 | 803.2 | Y | [5 empty] | 2019-03-08 | Bids awarded
916 | National Highways Authority Of India | 155597 | Package-5 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1597 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5154.5 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 5154.5 | 3629.8 | 1524.7 | Y | [5 empty] | 2019-10-15 | Bids awarded
917 | National Highways Authority Of India | 155597 | Package-6 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1578 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6684.8 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2018-10-03 | 6684.8 | 6684.8 | 0 | N | [5 empty] | 2020-02-12 | Bids awarded
918 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7173.2 | Completed | Engineering, Procurement & Construction | December 2022 | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 7173.2 | 4645.9 | 2527.3 | Y | 2022-12-31 | Initial completion date | 2022-12-01 | N |  | 2019-10-09 | Bids awarded
919 | National Highways Authority Of India | 155597 | Package-6 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1590 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6358.4 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 6358.4 | 4334.1 | 2024.3 | Y | [5 empty] | 2019-10-14 | Bids awarded
920 | National Highways Authority Of India | 155597 | Package-7 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1583 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5011.5 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-11-04 | 5011.5 | 4835.9 | 175.6 | Y | [5 empty] | 2020-02-12 | Bids awarded
921 | National Highways Authority Of India | 155597 | Package-7 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1591 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5206.3 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 5206.3 | 4066.7 | 1139.6 | Y | [5 empty] | 2019-03-08 | Bids awarded
922 | National Highways Authority Of India | 155597 | Package-8 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1584 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5434.4 | Under Implementation | Engineering, Procurement & Construction |  | Deogarh | Rajasthan | 01 Apr 2017 | Date of announcement | 2018-10-03 | 5434.4 | 5434.4 | 0 | N | [5 empty] | 2020-03-23 | Bids awarded
923 | National Highways Authority Of India | 155597 | Package-8 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1592 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5807.9 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 5807.9 | 4581.2 | 1226.7 | Y | [5 empty] | 2019-03-08 | Bids awarded
924 | National Highways Authority Of India | 155597 | Package-9 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1593 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6565.7 | Under Implementation | Engineering, Procurement & Construction |  | Rasisar | Rajasthan | 01 Apr 2017 | Date of announcement | 2019-12-31 | 6565.7 | 4840.9 | 1724.8 | Y | [5 empty] | 2019-10-15 | Bids awarded
925 | National Highways Authority Of India | 155597 | Padalur-Trichy (Pkg VI-C) Highway Project | 497 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6361 | Completed | Build Operate Transfer | April 2010 | Padalur | Tamil Nadu | 22 Aug 2005 | Date of announcement | 2009-11-30 | 6361 | 3200 | 3161 | Y | 2010-04-15 | Completed | 2009-03-31 | Y | 380
926 | National Highways Authority Of India | 155597 | Padinajrekar-Ottumpuram Road Upgradation Project | 1725 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2065.5 | No Information |  |  | Ottumpuram | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 2065.5 | 2065.5 | 0 | N
927 | National Highways Authority Of India | 155597 | Paijarwadi-Kerle & Kolhapur Bypass (Kerle-Chokak) Four Lane Highway (Package-III of Ratnagiri-Kolhapur section of NH-166) Project | 1447 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21310 | Under Implementation | Hybrid Annuity |  | Kerle | Maharashtra | 01 Jan 2017 | Date of announcement | 2023-01-29 | 21310 | 8371.1 | 12938.9 | Y | [5 empty] | 2022-03-29 | Bids awarded
928 | National Highways Authority Of India | 155597 | Palakkad-Kozhikode Four/Six Lane Greenfield Highway Project | 2052 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 79379.6 | Announced |  |  | Kozhikode | Kerala | 01 Jan 2020 | Date of announcement | 2022-03-07 | 79379.6 | 79379.6 | 0 | N
929 | National Highways Authority Of India | 155597 | Palanpur-Dessa(EW-11/GJ) Highway Project | 196 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 537.3 | Completed | Engineering, Procurement & Construction | February 2003 | Dessa | Gujarat | 01 Jun 2001 | Date of announcement | 2002-01-01 | 537.3 | 908 | -370.7 | N | 2003-07-31 | Initial completion date | 2003-02-28 | Y | 153 | 2001-08-15 | Bids awarded
930 | National Highways Authority Of India | 155597 | Palanpur-Pindwara Highway Project | 384 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4980 | No Information |  |  | Palanpur | Gujarat | 01 Mar 2004 | Date of announcement | 2010-04-01 | 4980 | 4980 | 0 | N
931 | National Highways Authority Of India | 155597 | Palanpur-Swaroopganj Highway Project | 424 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5500 | Completed | Build Operate Transfer | May 2009 | Palanpur | Gujarat | 31 Dec 2005 | Date of announcement | 2005-12-31 | 5500 | 5500 | 0 | N | 2009-06-30 | Initial completion date | 2009-05-31 | Y | 30
932 | National Highways Authority Of India | 155597 | Pali City ROB Project | 1076 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 206.4 | Completed |  | August 2013 | Pali | Rajasthan | 09 Mar 2011 | Date of announcement | 2012-09-30 | 206.4 | 220 | -13.6 | N | 2013-08-31 | Completed | 2013-04-30 | Y | 123
933 | National Highways Authority Of India | 155597 | Palma-Gumla (Section of NH-23) Four Lane Highway Project | 1440 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15718.3 | Under Implementation | Hybrid Annuity | March 2024 | Gumla | Jharkhand | 20 Dec 2017 | Date of announcement | 2022-12-21 | 15718.3 | 6898.1 | 8820.2 | Y | [5 empty] | 2020-08-28 | Bids awarded
934 | National Highways Authority Of India | 155597 | Palsit-Dankuni (NH-19) Six Lane Highway Project (Bharatmala) | 1831 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 24030 | Under Implementation | Build Operate Transfer Toll |  | Dankuni | West Bengal | 13 Feb 2020 | Date of announcement | 2022-04-04 | 24030 | 21930 | 2100 | Y | [5 empty] | 2021-03-30 | Bids awarded
935 | National Highways Authority Of India | 155597 | Palsit-Dankuni(Durgapur Expressway) Highway Project | 193 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4324 | Completed | Public Private Partnership | December 2005 | Dankuni | West Bengal | 28 Feb 2001 | Date of announcement | 2003-07-01 | 4324 | 4660 | -336 | N
936 | National Highways Authority Of India | 155597 | Panagarh-Haldia Expressway Project | 1729 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 90000 | Announced |  |  | Haldia | West Bengal | 01 Apr 2016 | Date of announcement | 2018-05-15 | 90000 | 90000 | 0 | N
937 | National Highways Authority Of India | 155597 | Panchi Gujran-Kamaspur (Delhi-Haryana Section NS-17/HR) Six Lane Highway Project | 187 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1210 | Completed |  | December 2010 | Kamaspur | Haryana | 30 Oct 2001 | Date of announcement | 2010-12-31 | 1210 | 880 | 330 | Y | 2010-12-31 | Completed | 2003-05-31 | Y | 2771
938 | National Highways Authority Of India | 155597 | Pandoh-Bata (Tunnel) (NH-21) Highway Project (Package-II of Nerchowk-Kullu stretch) | 1044 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6907.8 | Under Implementation | Hybrid Annuity |  | Bata | Himachal Pradesh | 15 Nov 2014 | Date of announcement | 2014-12-03 | 6907.8 | 6907.8 | 0 | N | [5 empty] | 2017-06-19 | Bids awarded
939 | National Highways Authority Of India | 155597 | Pangare-Warangaphata (NH-161) Four Lane Highway project (Package-IV) | 1843 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9744.8 | Under Implementation | Engineering, Procurement & Construction |  | Pangare | Maharashtra | 08 Jun 2020 | Date of announcement | 2020-08-09 | 9744.8 | 9744.8 | 0 | N | [5 empty] | 2021-03-02 | Bids awarded
940 | National Highways Authority Of India | 155597 | Panipat to Panchi Gujran Six Laning Highway Project | 310 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1216.4 | Completed |  | December 2010 | Panchi Gujran | Haryana | 31 Jan 2000 | Date of announcement | 2010-12-31 | 1216.4 | 1216.4 | 0 | N | 2011-03-31 | Initial completion date | 2009-11-30 | Y | 486
941 | National Highways Authority Of India | 155597 | Panipat-Bawal Six-Laning Road Project | 805 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18000 | No Information |  |  | Bawal | Haryana | 09 Sep 2010 | Date of announcement | 2010-09-09 | 18000 | 18000 | 0 | N
942 | National Highways Authority Of India | 155597 | Panipat-Shamli (NH-709AD) Four Lane Highway Project (Package 1 of Panipat-Nagina Highway) | 1540 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12530 | Completed | Engineering, Procurement & Construction | January 2023 | Panipat | Haryana | 10 Jun 2016 | Date of announcement | 2019-02-20 | 12530 | 7814.4 | 4715.6 | Y | 2023-01-25 | Completed | 2022-09-17 | Y | 130 | 2019-10-15 | Bids awarded
943 | National Highways Authority Of India | 155597 | Panitanki-Bagdogra-Fulbari (AH-2) Road Project | 988 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6020 | No Information |  |  | Bagdogra | West Bengal | 01 Jul 2013 | Date of announcement | 2014-06-04 | 6020 | 6020 | 0 | N
944 | National Highways Authority Of India | 155597 | Paniyala (Kotputli)-Mator-Baraodaneo (NH-148B) Six Lane Access Controlled Highway Project | 2086 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 37750 | Under Implementation | Engineering, Procurement & Construction |  | Baraodaneo | Rajasthan | 01 Sep 2020 | Date of announcement | 2023-02-12 | 37750 | 37750 | 0 | N | [5 empty] | 2023-01-30 | Bids awarded
945 | National Highways Authority Of India | 155597 | Panjim-Mangalore (NH-17) Highway Project | 27 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1400 | No Information |  |  | Mangalore | Karnataka | 12 Feb 1998 | Central Government approval received | 2002-04-01 | 1400 | 1560 | -160 | N
946 | National Highways Authority Of India | 155597 | Panvel-Indapur (NH-17) Four Laning Highway Project (Mumbai-Goa NH 66 Highway) (Package-1) | 1553 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13700 | Under Implementation | Build Operate Transfer Toll | December 2023 | Indapur | Maharashtra | 01 Dec 2003 | Date of announcement | 2018-06-30 | 13700 | 9426.9 | 4273.1 | Y | 2024-02-28 | Initial completion date | 2014-06-16 | Y | 3544 | 2011-01-21 | Bids awarded
947 | National Highways Authority Of India | 155597 | Paonta Sahib-Ballupur Chowk (Dehradun) Four Lane (NH-72) Highway Project | 1934 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17000 | Under Implementation |  |  | Ballupur chowk (dehradun) | Uttarakhand | 01 Apr 2016 | Date of announcement | 2021-12-04 | 17000 | 6000 | 11000 | Y | [5 empty] | 2022-05-30 | Bids awarded
948 | National Highways Authority Of India | 155597 | Paradip Port Road Project | 207 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4593.8 | Completed |  | June 2009 | Paradip | Odisha | 28 Feb 2004 | Construction commenced | 2009-04-01 | 4593.8 | 3500 | 1093.8 | Y
949 | National Highways Authority Of India | 155597 | Paramakudi-Ramanathapuram (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 1280 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Completed |  | March 2019 | Paramakudi | Tamil Nadu | 01 Nov 2010 | Date of announcement | 2017-03-28 | 2000 | 2000 | 0 | N | 2019-05-31 | Initial completion date | 2017-11-30 | Y | 547 | 2015-04-17 | Bids awarded
950 | National Highways Authority Of India | 155597 | Pararia-Mohania Four Lane Highway (NH-319) Project (Package 2 of Mohania-Arrah) (Bharatmala) | 1835 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8560 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Mohania | Bihar | 01 Jul 2011 | Date of announcement | 2020-09-22 | 8560 | 7277.4 | 1282.6 | Y | 2023-07-16 | Completion expected by | 2014-06-30 | Y | 3303 | 2011-08-11 | Bids awarded
951 | National Highways Authority Of India | 155597 | Paravoor-Kottunkulangara (NH-66) Six Lane Highway Project (Bharatmala) | 1881 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 35051.6 | Under Implementation | Engineering, Procurement & Construction |  | Kottankulangara | Kerala | 01 Dec 2020 | Date of announcement | 2022-12-15 | 35051.6 | 13105.2 | 21946.4 | Y | [5 empty] | 2022-03-22 | Bids awarded
952 | National Highways Authority Of India | 155597 | Pardi Flyover (NH-6) (on Urban Link to Nagpur-Raipur) Project | 995 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4970 | Under Implementation | Engineering, Procurement & Construction | June 2023 | Nagpur | Maharashtra | 31 Mar 2012 | Date of announcement | 2022-06-19 | 4970 | 650 | 4320 | Y | 2023-06-30 | Completion expected by | 2019-03-30 | Y | 1553 | 2015-12-28 | Bids awarded
953 | National Highways Authority Of India | 155597 | Parle-G Factory FOB Project | 831 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Parle-g factory | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N
954 | National Highways Authority Of India | 155597 | Parwanoo-Solan (NH-5) (Parwanoo-Shimla Package-I) Two/Four Lane Highway Project | 662 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13030 | Completed | Engineering, Procurement & Construction | June 2021 | Kumarhatti | Himachal Pradesh | 10 Feb 2009 | Date of announcement | 2021-06-24 | 13030 | 6905.6 | 6124.4 | Y | 2021-06-30 | Initial completion date | 2018-03-31 | Y | 1187 | 2015-03-30 | Bids awarded
955 | National Highways Authority Of India | 155597 | Pashchimi Singhbhum (NH-75) (between Jhinkpani-Talaburu) ROB Project | 3006 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 990 | Under Implementation |  |  | Pashchimi singhbhum | Jharkhand | 01 Mar 2023 | Date of announcement | 2023-03-19 | 990 | 990 | 0 | N
956 | National Highways Authority Of India | 155597 | Pashchimi Singhbhum-Simdega NH-320G Road Project | 3009 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5140 | Under Implementation |  |  | Pashchimi singhbhum | Jharkhand | 01 Mar 2023 | Date of announcement | 2023-03-19 | 5140 | 5140 | 0 | N
957 | National Highways Authority Of India | 155597 | Patan (Near Rajpur)-Gojariya (NH-68) Four/Six Lane Highway Project (Package-II) | 2004 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11520 | Under Implementation | Engineering, Procurement & Construction |  | Gojariya | Gujarat | 01 Jan 2021 | Date of announcement | 2023-02-16 | 11520 | 8758.3 | 2761.7 | Y | [5 empty] | 2022-03-28 | Bids awarded
959 | National Highways Authority Of India | 155597 | Patel Chowk (NH-33) Six Lane Underpass Project | 2101 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 240 | Completed |  | March 2023 | Patel chowk | Jharkhand | 01 Oct 2020 | Date of announcement | 2023-03-23 | 240 | 246.9 | -6.9 | N | 2023-03-23 | Completed | 2021-11-30 | Y | 478 | 2020-11-22 | Bids awarded
960 | National Highways Authority Of India | 155597 | Pathankot-Bhogpur (NH-1A) Highway Project | 307 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5130 | Completed | Engineering, Procurement & Construction | January 2014 | Bhogpur | Punjab | 01 Dec 2003 | Date of announcement | 2009-07-01 | 5130 | 5130 | 0 | N | 2014-01-31 | Completed | 2010-12-31 | Y | 1127
961 | National Highways Authority Of India | 155597 | Pathankot-Delhi(Ambala-Delhi) Highway Project | 70 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7316 | Completed |  | December 2001 | Ambala | Haryana | 01 Mar 1993 | Date of announcement | 2001-10-01 | 7316 | 3790.7 | 3525.3 | Y | 2001-12-14 | Completed | 1998-07-31 | Y | 1232
962 | National Highways Authority Of India | 155597 | Pathankot-Jammu & Kashmir Border (NS-36/J&K) Highways project | 739 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2450 | Completed | Engineering, Procurement & Construction | December 2014 | Jammu | Jammu & Kashmir | 31 Dec 2003 | Date of announcement | 2012-11-30 | 2450 | 977.3 | 1472.7 | Y | 2014-12-31 | Completed | 2010-12-31 | Y | 1461 | 2005-06-30 | Bids awarded
963 | National Highways Authority Of India | 155597 | Pathankot-Mandi (NH-154) Four Laning Highway Project | 1313 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 100000 | Under Implementation | Hybrid Annuity |  | Ahju | Himachal Pradesh | 01 Feb 2013 | Date of announcement | 2022-11-13 | 100000 | 16000 | 84000 | Y | [5 empty] | 2021-04-01 | Bids awarded
964 | National Highways Authority Of India | 155597 | Pathrapali-Kathghora (NH-130) Four Lane Highway Project (Package 2 of Bilaspur-Kathghora section) (Bharatmala) | 1783 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8600 | Under Implementation | Hybrid Annuity | May 2023 | Kathghora | Chhattisgarh | 06 Sep 2018 | Date of announcement | 2023-05-05 | 8600 | 5751 | 2849 | Y | 2023-05-31 | Completion expected by | 2022-09-30 | Y | 243 | 2020-03-18 | Bids awarded
965 | National Highways Authority Of India | 155597 | Patna Four/Six Laning Ring Road Project | 1132 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 40000 | Under Implementation | Engineering, Procurement & Construction |  | Astipur | Bihar | 15 Mar 2008 | Date of announcement | 2019-08-30 | 40000 | 15000 | 25000 | Y | [5 empty] | 2020-09-11 | Bids awarded
966 | National Highways Authority Of India | 155597 | Patna-Arrah-Sasaram (NH-119) Four/Six Lane Highway Project | 1926 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 29790 | Announced |  |  | Arrah | Bihar | 31 Mar 2002 | Date of announcement | 2022-09-28 | 29790 | 35000 | -5210 | N
967 | National Highways Authority Of India | 155597 | Patna-Gaya-Dobhi (NH-83) Four Lane Highway Project | 603 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 16104.7 | Under Implementation | Build Operate Transfer | June 2023 | Dobhi | Bihar | 30 Apr 2009 | Date of announcement | 2021-07-19 | 16104.7 | 4380 | 11724.7 | Y | 2023-06-30 | Completion expected by | 2015-06-01 | Y | 2951 | 2014-10-13 | Bids awarded
968 | National Highways Authority Of India | 155597 | Patna-Ghazipur Expressway Project (Patna Expressway) | 1412 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 20000 | No Information |  |  | Ghazipur | Uttar Pradesh | 10 Nov 2017 | Date of announcement | 2017-11-11 | 20000 | 20000 | 0 | N
969 | National Highways Authority Of India | 155597 | Patna-Koilwar (NH-30) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1010 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21000 | Under Implementation | Engineering, Procurement & Construction |  | Koilwar | Bihar | 12 Aug 2008 | Date of announcement | 2019-06-24 | 21000 | 4918.9 | 16081.1 | Y | [5 empty] | 2011-11-12 | Bids awarded
970 | National Highways Authority Of India | 155597 | Patradevi-Pollem Four/Six Laning Road Project | 809 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11580 | No Information | Design Build Finance Operate Transfer |  | Patradevi (Pernem) | Goa | 31 Jul 2003 | Date of announcement | 2008-10-01 | 11580 | 11580 | 0 | N | [5 empty] | 2010-06-17 | Bids awarded
971 | National Highways Authority Of India | 155597 | Payikulangara to Alappuzha Byass Road Project (Port Connectivity) | 1745 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3247 | No Information |  |  | Alappuzha byass | Kerala | 01 Dec 2016 | Date of announcement | 2018-05-15 | 3247 | 3247 | 0 | N
972 | National Highways Authority Of India | 155597 | Payyambalam-Azhikkal Road Widening Project (Bharatmala) | 1715 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1736.3 | Announced |  |  | Azhikkal | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 1736.3 | 1736.3 | 0 | N
973 | National Highways Authority Of India | 155597 | Pedestrian Underpass including Service Road Project (on Jabalpur-Nagpur NH-44 section) | 1760 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 108.4 | No Information | Engineering, Procurement & Construction |  | Jabalpur | Madhya Pradesh | 10 Jul 2019 | Date of announcement | 2019-07-10 | 108.4 | 108.4 | 0 | N
974 | National Highways Authority Of India | 155597 | Penchalakona-Yerpedu (NH-565) Two Lane Road Project | 971 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3613 | Completed | Engineering, Procurement & Construction | September 2016 | Penchalakona | Andhra Pradesh | 01 Jan 2014 | Date of announcement | 2014-11-27 | 3613 | 2902.5 | 710.5 | Y | [5 empty] | 2014-02-24 | Bids awarded
975 | National Highways Authority Of India | 155597 | Phagwara Junction (NH-1) Flyover Project | 960 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 197 | Completed | Engineering, Procurement & Construction | January 2008 | Phagwara | Punjab | 01 Aug 2005 | Date of announcement | 2005-08-01 | 197 | 197 | 0 | N | [5 empty] | 2005-11-09 | Bids awarded
976 | National Highways Authority Of India | 155597 | Phalodi-Jaisalmer (NH-15) Two/Four Lane Highway Project | 1030 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4280 | Completed | Engineering, Procurement & Construction | January 2019 | Jaisalmer | Rajasthan | 15 Nov 2011 | Date of announcement | 2017-10-31 | 4280 | 5675.1 | -1395.1 | N | 2019-01-05 | Completed | 2018-03-31 | Y | 280 | 2014-10-28 | Bids awarded
977 | National Highways Authority Of India | 155597 | Pimpalgaon-Nashik-Gonde (NH-3,60&160) Six-Laning Highway Project | 1396 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16910 | Completed | Engineering, Procurement & Construction | October 2021 | Gonde | Maharashtra | 31 Mar 2005 | Date of announcement | 2016-02-28 | 16910 | 7520 | 9390 | Y | 2021-10-30 | Completed | 2012-07-31 | Y | 3378 | 2009-01-15 | Bids awarded
978 | National Highways Authority Of India | 155597 | Pimpalkutti Two Lane ROB (on Nagpur-Hyderabad NH-44 & NH-7) Project | 1301 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 162 | Completed | Engineering, Procurement & Construction | August 2021 | Pimpalkutti | Maharashtra | 13 May 2017 | Date of announcement | 2021-02-09 | 162 | 141.5 | 20.5 | Y | 2021-08-05 | Completed | 2019-11-24 | Y | 620 | 2017-09-14 | Bids awarded
979 | National Highways Authority Of India | 155597 | Pimpri Sado-Gonde (NH-3) Six Lane Road Project | 2077 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8660 | Under Implementation |  |  | Gonde | Maharashtra | 01 Oct 2020 | Date of announcement | 2022-12-18 | 8660 | 6000 | 2660 | Y
980 | National Highways Authority Of India | 155597 | Pindari-Rawalganj Bypass (NH-31) Four Lane Greenfield Highway Project (Package-III of Ghazipur-Ballia-UP/Bihar State Border) | 2104 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8061.8 | Under Implementation | Engineering, Procurement & Construction |  | Pindari | Uttar Pradesh | 12 Apr 2017 | Date of announcement | 2022-08-02 | 8061.8 | 8061.8 | 0 | N | [5 empty] | 2022-11-30 | Bids awarded
981 | National Highways Authority Of India | 155597 | Pinjore Bypass connecting Surajpur-Baddi Project | 856 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1408.4 | Under Implementation |  |  | Pinjore | Haryana | 27 Apr 2010 | Date of announcement | 2021-03-25 | 1408.4 | 320 | 1088.4 | Y
982 | National Highways Authority Of India | 155597 | Pinjore Bypass-Baddi-Nalagarh (NH-21A) Four Laning Highway Project | 1609 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16920 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Nalagarh | Himachal Pradesh | 29 Apr 2009 | Date of announcement | 2022-10-05 | 16920 | 10700 | 6220 | Y | 2024-12-31 | Completion expected by | 2014-06-30 | Y | 3837 | 2021-09-30 | Bids awarded
983 | National Highways Authority Of India | 155597 | Pirpaiti-Gandhigram (NH-80 & 133) Four Lane Highway Project | 1334 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5134.4 | Under Implementation | Engineering, Procurement & Construction |  | Gandhigram | Jharkhand | 22 Aug 2017 | Date of announcement | 2017-08-22 | 5134.4 | 5134.4 | 0 | N
984 | National Highways Authority Of India | 155597 | Piska More-Palma (NH-23) Four Laning Highway Project | 1228 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2556.8 | Completed | Engineering, Procurement & Construction | April 2020 | Palma | Jharkhand | 09 Nov 2016 | Date of announcement | 2017-10-31 | 2556.8 | 1651 | 905.8 | Y | 2020-04-30 | Initial completion date | 2018-05-31 | Y | 700 | 2017-03-31 | Bids awarded
985 | National Highways Authority Of India | 155597 | Pollachi-Coimbatore (NH-209) Four Lane Road Project | 1197 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6560 | Under Implementation |  |  | Coimbatore | Tamil Nadu | 06 Jul 2015 | Date of announcement | 2020-04-21 | 6560 | 5000 | 1560 | Y
986 | National Highways Authority Of India | 155597 | Pondavakkam-Kannigaipair (NH-716B) Six Lane Road Project (Package-4 of Chittoor-Thatchur Expressway) | 2032 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9090 | Under Implementation | Hybrid Annuity |  | Kannur | Kerala | 01 Apr 2018 | Date of announcement | 2022-04-06 | 9090 | 9090 | 0 | N | [5 empty] | 2021-09-25 | Bids awarded
987 | National Highways Authority Of India | 155597 | Poovar-Chovvara Road Project | 1740 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1386.3 | No Information |  |  | Chovvara | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 1386.3 | 1386.3 | 0 | N
988 | National Highways Authority Of India | 155597 | Porbander-Bhiladi NH-8B (Package 1) Project | 111 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2760.7 | Completed | Engineering, Procurement & Construction | September 2007 | Bhiladi | Gujarat | 01 Dec 2002 | Date of announcement | 2002-12-01 | 2760.7 | 2760.7 | 0 | N | [5 empty] | 2005-02-01 | Bids awarded
989 | National Highways Authority Of India | 155597 | Prayagraj Four Lane Ring Road Project | 1312 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 70480 | Under Implementation |  | December 2025 | Allahabad | Uttar Pradesh | 08 Jun 2017 | Date of announcement | 2023-03-16 | 70480 | 37000 | 33480 | Y
990 | National Highways Authority Of India | 155597 | Puducherry-Kottakuppam Four lane Road Project | 815 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 110 | No Information |  |  | Kottakuppam | Tamil Nadu | 01 Nov 2007 | Date of announcement | 2007-11-01 | 110 | 110 | 0 | N
991 | National Highways Authority Of India | 155597 | Puducherry-Marakkanam-Kovalam-Coromandel-Chennai (NH-32) Two/Four Laning Highway Project (BM/17) | 1106 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14400 | No Information |  |  | Chennai | Tamil Nadu | 15 Apr 2015 | Date of announcement | 2016-07-31 | 14400 | 14400 | 0 | N
992 | National Highways Authority Of India | 155597 | Puintola-Tangi (NH-16) Six/Four Lane Highway Project | 1472 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7286 | Completed | Engineering, Procurement & Construction | April 2023 | Puintola | Odisha | 01 Jan 2018 | Date of announcement | 2020-08-09 | 7286 | 6169.9 | 1116.1 | Y | 2023-04-01 | Completed | 2020-03-31 | Y | 1096 | 2018-03-23 | Bids awarded
993 | National Highways Authority Of India | 155597 | Pune-Bangalore Eight Lane Expressway Project | 1790 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 492410 | Under Implementation |  |  | Bangalore | Karnataka | 01 Dec 2019 | Date of announcement | 2023-02-08 | 492410 | 492410 | 0 | N
994 | National Highways Authority Of India | 155597 | Pune-Khed (NH-50) Highway Project | 962 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1276 | Completed | Engineering, Procurement & Construction | December 2005 | Khed | Maharashtra | 01 Sep 2002 | Date of announcement | 2005-10-01 | 1276 | 834.2 | 441.8 | Y | [5 empty] | 2003-08-15 | Bids awarded
995 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj Realignment) Highway Project | 215 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1462.5 | Completed | Engineering, Procurement & Construction | June 2006 | Katraj | Maharashtra | 21 Mar 2000 | Date of announcement | 2000-03-31 | 1462.5 | 1462.5 | 0 | N | 2006-09-30 | Initial completion date | 2004-06-30 | Y | 822 | 2002-11-01 | Bids awarded
996 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj-Sarole) Highway Project | 214 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 979 | Completed | Engineering, Procurement & Construction | December 2005 | Katraj | Maharashtra | 01 Mar 2001 | Date of announcement | 2002-01-01 | 979 | 979 | 0 | N | [5 empty] | 2001-11-01 | Bids awarded
997 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1189.3 | Completed | Engineering, Procurement & Construction | December 2003 | Sarole | Maharashtra | 01 Mar 2001 | Date of announcement | 2001-12-01 | 1189.3 | 1189.3 | 0 | N | 2004-03-31 | Initial completion date | 2003-12-31 | Y | 91 | 2001-11-01 | Bids awarded
998 | National Highways Authority Of India | 155597 | Pune-Satara (Wathar-Satara) Highway Project | 217 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1390 | Completed | Engineering, Procurement & Construction | February 2004 | Satara | Maharashtra | 01 Mar 2001 | Date of announcement | 2001-12-01 | 1390 | 1390 | 0 | N | [5 empty] | 2001-07-01 | Bids awarded
999 | National Highways Authority Of India | 155597 | Pune-Solapur (NH-9) Section Six Laning Highway Project | 562 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9653 | No Information | Design Build Finance Operate Transfer |  | Pune | Maharashtra | 26 Dec 2008 | Date of announcement | 2008-12-26 | 9653 | 9653 | 0 | N
1000 | National Highways Authority Of India | 155597 | Punjab/Haryana Border-Jind (NH-71) Four Lane Road Project | 1211 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8570 | Completed | Engineering, Procurement & Construction | July 2020 | Jind | Haryana | 07 Dec 2010 | Date of announcement | 2020-07-13 | 8570 | 4387.5 | 4182.5 | Y | 2020-07-31 | Initial completion date | 2014-10-30 | Y | 2101 | 2012-04-03 | Bids awarded
1001 | National Highways Authority Of India | 155597 | Purmepada VUP on Dhule-Pimplegaon section of NH-3 Project | 1921 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 270 | Under Implementation |  |  | Purmepada | Maharashtra | 19 May 2020 | Date of announcement | 2021-10-05 | 270 | 270 | 0 | N | [5 empty] | 2020-11-03 | Bids awarded
1002 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-1) Road project | 708 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3600 | Completed |  | April 2010 | Forbesganj | Bihar | 01 Dec 2003 | Date of announcement | 2010-04-30 | 3600 | 3600 | 0 | N | 2010-04-30 | Completed | 2009-12-31 | Y | 120
1003 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-2) Highway Project | 709 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3922.6 | Completed |  | July 2010 | Forbesganj | Bihar | 01 Dec 2003 | Date of announcement | 2010-03-31 | 3922.6 | 3100 | 822.6 | Y | 2010-07-31 | Completed | 2009-12-31 | Y | 212
1004 | National Highways Authority Of India | 155597 | Purnea-Gayakota Section(EW-12/BR) Highway Project | 199 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2477 | Completed |  | June 2011 | Gayakota | Bihar | 01 Apr 2000 | Date of announcement | 2011-02-28 | 2477 | 2057.3 | 419.7 | Y | 2011-06-30 | Completed | 2010-06-30 | Y | 365
1005 | National Highways Authority Of India | 155597 | Purulia Bypass Four Lane Road (NH-32) Project | 2025 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1750 | Under Implementation | Engineering, Procurement & Construction | December 2023 | Purulia | West Bengal | 01 Nov 2020 | Date of announcement | 2022-11-17 | 1750 | 2358.3 | -608.3 | N | 2023-12-31 | Completion expected by | 2023-08-04 | Y | 149 | 2021-08-18 | Bids awarded
1006 | National Highways Authority Of India | 155597 | Puruliya (JHR Border)-Balrampur-Chandil (NH-18) Two Lane Highway Project | 1326 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7083 | Under Implementation | Engineering, Procurement & Construction |  | Balrampur (wb) | West Bengal | 30 Aug 2017 | Date of announcement | 2018-04-18 | 7083 | 5929.1 | 1153.9 | Y | [5 empty] | 2018-08-31 | Bids awarded
1007 | National Highways Authority Of India | 155597 | RJ/MP Border-Kota (RJ-11) Highway Project | 295 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3113.5 | Completed | Engineering, Procurement & Construction | October 2008 | Kota | Rajasthan | 25 Nov 2003 | Date of announcement | 2008-10-01 | 3113.5 | 3495.9 | -382.4 | N | 2008-10-31 | Completed | 2008-09-03 | Y | 58 | 2005-05-30 | Bids awarded
1008 | National Highways Authority Of India | 155597 | ROB between Piska-Chetar Railway Stations (Ranchi) Project | 1516 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 296 | No Information | Engineering, Procurement & Construction |  | Chetar | Jharkhand | 21 Jun 2018 | Date of announcement | 2018-06-21 | 296 | 296 | 0 | N
1009 | National Highways Authority Of India | 155597 | Radhanpur-Deesa NH-14 (Package 6) Project | 236 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4797.4 | Completed | Engineering, Procurement & Construction | December 2008 | Deesa | Rajasthan | 01 Dec 2002 | Date of announcement | 2002-12-01 | 4797.4 | 4797.4 | 0 | N | [5 empty] | 2005-02-01 | Bids awarded
1010 | National Highways Authority Of India | 155597 | Radhaswamy Ashram FOB Project | 834 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10 | No Information |  |  | Radhaswamy ashram | Karnataka | 01 Dec 2010 | Date of announcement | 2010-12-01 | 10 | 10 | 0 | N | [5 empty] | 2010-12-16 | Bids awarded
1011 | National Highways Authority Of India | 155597 | Rae Bareli-Banda Highway Widening Project | 765 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5587.7 | Completed | Engineering, Procurement & Construction | December 2018 | Banda | Uttar Pradesh | 19 Apr 2010 | Date of announcement | 2014-02-06 | 5587.7 | 5250 | 337.7 | Y | 2018-12-16 | Completed | 2016-01-31 | Y | 1050 | 2014-02-28 | Bids awarded
1012 | National Highways Authority Of India | 155597 | Raebareli-Jagdishpur Two Lane Highway including Jagdishpur Bypass (NH-330A) Project | 2023 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7200 | Under Implementation | Engineering, Procurement & Construction | June 2024 | Jagdishpur | Uttar Pradesh | 01 Apr 2020 | Date of announcement | 2021-07-14 | 7200 | 5183.7 | 2016.3 | Y | [5 empty] | 2021-08-02 | Bids awarded
1013 | National Highways Authority Of India | 155597 | Raebareli-Prayagraj (Allahabad) (NH-24B) Four lane Highway Upgradation Project | 1152 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14070 | Under Implementation | Hybrid Annuity | December 2024 | Allahabad | Uttar Pradesh | 15 Nov 2015 | Date of announcement | 2017-06-14 | 14070 | 14070 | 0 | N | 2024-12-31 | Completion expected by | 2024-10-31 | Y | 61 | 2023-03-20 | Bids awarded
1014 | National Highways Authority Of India | 155597 | Raiganj-Dalkola (NH-34) Four Laning Highway (Kolkata-Dalkola) Project | 1400 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9620 | Completed | Engineering, Procurement & Construction | November 2022 | Dalkola | West Bengal | 01 Jun 2003 | Date of announcement | 2022-11-17 | 9620 | 5804.3 | 3815.7 | Y | 2022-12-31 | Initial completion date | 2010-02-28 | Y | 4689 | 2010-02-10 | Bids awarded
1015 | National Highways Authority Of India | 155597 | Railway Over Bridge (ROB) at Saundad (NH-53) Project | 1754 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1229.8 | Under Implementation | Engineering, Procurement & Construction |  | Saundad | Maharashtra | 01 Aug 2016 | Date of announcement | 2021-02-09 | 1229.8 | 800 | 429.8 | Y | [5 empty] | 2018-10-24 | Bids awarded
1016 | National Highways Authority Of India | 155597 | Raipur-Jassa Khera (NH-458) Two Laning Highway Project | 953 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1493.4 | No Information | Engineering, Procurement & Construction |  | Jassa khera | Rajasthan | 01 Aug 2012 | Date of announcement | 2012-08-01 | 1493.4 | 1493.4 | 0 | N | [5 empty] | 2013-04-30 | Bids awarded
1017 | National Highways Authority Of India | 155597 | Raipur-Kodebad (NH-30) Four-Lane (NH-43) Highway Project | 812 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9878.8 | Under Implementation | Engineering, Procurement & Construction |  | Kodebad | Chhattisgarh | 13 Oct 2010 | Date of announcement | 2019-12-02 | 9878.8 | 4002.5 | 5876.3 | Y | [5 empty] | 2016-11-22 | Bids awarded
1018 | National Highways Authority Of India | 155597 | Raipur-Simga (NH-30) Four/Six Laning Highway (Package-I of Raipur-Bilaspur) Project | 980 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7667 | Completed | Engineering, Procurement & Construction | January 2022 | Bilaspur | Chhattisgarh | 14 Oct 2009 | Date of announcement | 2018-03-31 | 7667 | 19638.8 | -11971.8 | N | 2022-01-04 | Completed | 2015-01-30 | Y | 2531 | 2012-01-30 | Bids awarded
1019 | National Highways Authority Of India | 155597 | Raisinghnagar (Sri Ganganagar)-Anupgarh-Rojhri-Awa-Poogal Two/Four Laning Highway Project (BM/6) | 1098 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8107.3 | Completed | Engineering, Procurement & Construction | February 2021 | Anupgarh | Rajasthan | 05 Apr 2015 | Date of announcement | 2018-02-27 | 8107.3 | 8107.3 | 0 | N | [5 empty] | 2018-02-27 | Bids awarded
1020 | National Highways Authority Of India | 155597 | Raj/UP border-Mania (NS-19/UP/RJ) Highway Project | 188 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 760 | Completed | Engineering, Procurement & Construction | January 2005 | Mania | Rajasthan | 01 Mar 2001 | Date of announcement | 2001-09-01 | 760 | 760 | 0 | N | 2005-01-31 | Completed | 2003-05-31 | Y | 611 | 2001-08-01 | Bids awarded
1021 | National Highways Authority Of India | 155597 | Rajah-Eluru(Gowthami-Gundugolanu) Bridges AP-20 Project | 248 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1313.3 | Completed | Engineering, Procurement & Construction | May 2005 | Eluru | Andhra Pradesh | 31 Aug 2000 | Date of announcement | 2000-08-31 | 1313.3 | 1313.3 | 0 | N | [5 empty] | 2001-08-01 | Bids awarded
1022 | National Highways Authority Of India | 155597 | Rajahmu-Eluru(Divancheru-Gowthami) Bridges AP-19 Project | 247 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1364.5 | Completed |  | March 2005 | Eluru | Andhra Pradesh | 31 Aug 2001 | Construction commenced | 2003-03-01 | 1364.5 | 1364.5 | 0 | N
1023 | National Highways Authority Of India | 155597 | Rajahmundry-Eluru(Gowthami-Gundugolanu) Highway Project | 178 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3233.5 | Completed | Engineering, Procurement & Construction | February 2004 | Eluru | Andhra Pradesh | 01 Mar 2001 | Date of announcement | 2002-01-01 | 3233.5 | 3400 | -166.5 | N | 2004-02-29 | Completed | 2003-10-31 | Y | 121 | 2001-08-01 | Bids awarded
1024 | National Highways Authority Of India | 155597 | Rajamunda-Barkote (NH-23&143) Four Laning Highway Project (Birmitrapur-Barkote) | 1283 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6162.3 | Under Implementation | Engineering, Procurement & Construction |  | Barkote | Odisha | 25 Oct 2010 | Date of announcement | 2022-07-21 | 6162.3 | 4945 | 1217.3 | Y | [5 empty] | 2018-01-17 | Bids awarded
1025 | National Highways Authority Of India | 155597 | Rajasthan/MP Border To Kota (RJ-10) Highway Project | 773 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3650.5 | Completed |  | June 2009 | Kota | Rajasthan | 31 Oct 2005 | Date of announcement | 2005-10-31 | 3650.5 | 3650.5 | 0 | N
1026 | National Highways Authority Of India | 155597 | Rajasthan/MP Border To Kota (RJ-9) Highway Project | 774 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2898.8 | Completed |  | June 2009 | Kota | Rajasthan | 31 Oct 2005 | Date of announcement | 2005-10-31 | 2898.8 | 2898.8 | 0 | N
1027 | National Highways Authority Of India | 155597 | Rajasthan/MP Border to Jodmi village of Mandsaur Eight Lane Carriageway Project (Package 17 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1570 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8884.2 | Under Implementation | Engineering, Procurement & Construction |  | Jodmi village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2018-10-03 | 8884.2 | 8884.2 | 0 | N | [5 empty] | 2020-02-11 | Bids awarded
1028 | National Highways Authority Of India | 155597 | Rajauli-Bakhtiyarpur (NH-31) Four Laning Highway Project | 1416 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8471 | Under Implementation | Design Build Finance Operate Transfer |  | Bakhtiarpur | Bihar | 22 Aug 2011 | Date of announcement | 2016-03-02 | 8471 | 8590 | -119 | N | [5 empty] | 2012-05-01 | Bids awarded
1029 | National Highways Authority Of India | 155597 | Rajiv Chowk-Bhondsi (NH-248A) Six Laning Highway Project (Package-1 of Rajasthan Border-Nuh-Gurugram) | 1317 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10000 | Completed | Hybrid Annuity | July 2022 | Bhondsi | Haryana | 29 Jul 2016 | Date of announcement | 2022-07-07 | 10000 | 6955.8 | 3044.2 | Y | 2022-07-11 | Completed | 2021-07-31 | Y | 345 | 2018-03-06 | Bids awarded
1030 | National Highways Authority Of India | 155597 | Rajiv Gandhi Statue-OAR Theatre Flyover Project | 898 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 480 | No Information |  |  | Oar theatre | Tamil Nadu | 01 Sep 2010 | Date of announcement | 2012-07-17 | 480 | 350 | 130 | Y
1031 | National Highways Authority Of India | 155597 | Rajkot-Bamanbor-Bagodha Renovation Highway Project | 648 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 1040 | No Information | Public Private Partnership |  | Bagodha | Gujarat | 01 Jul 2009 | Date of announcement | 2009-07-01 | 1040 | 1040 | 0 | N
1032 | National Highways Authority Of India | 155597 | Rajkot-Gondal-Jetpur (NH-27) Six Lane Highway Project | 1669 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15804.9 | Under Implementation | Engineering, Procurement & Construction |  | Gondal | Gujarat | 07 Aug 2018 | Date of announcement | 2022-01-10 | 15804.9 | 10000 | 5804.9 | Y | [5 empty] | 2022-03-31 | Bids awarded
1033 | National Highways Authority Of India | 155597 | Rajkot-Porbandar Road Project | 391 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7350 | No Information |  |  | Porbandar | Gujarat | 20 Jul 2004 | Date of announcement | 2004-07-20 | 7350 | 7350 | 0 | N
1034 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-8) Highway Project | 748 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3850 | Completed | Engineering, Procurement & Construction | January 2015 | Lakhnadon | Madhya Pradesh | 31 Dec 2003 | Date of announcement | 2014-07-31 | 3850 | 2510.3 | 1339.7 | Y | 2015-01-31 | Completed | 2011-06-30 | Y | 1311 | 2005-12-01 | Bids awarded
1035 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-9) Highway Project | 294 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3120 | Completed |  | March 2013 | Lahknadon | Madhya Pradesh | 01 Dec 2003 | Date of announcement | 2012-08-31 | 3120 | 2299.1 | 820.9 | Y | 2013-03-31 | Completed | 2009-11-01 | Y | 1246 | 2005-12-01 | Bids awarded
1036 | National Highways Authority Of India | 155597 | Ramanathapura (SH-86)-Terakanambi - Paschima vahini (NH-275) Four Lane Highway Project (Package-3 of Mysuru-Kushalnagar Highway) | 2099 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6669.7 | Under Implementation | Hybrid Annuity |  | Paschima vahini | Karnataka | 01 Apr 2018 | Date of announcement | 2022-09-19 | 6669.7 | 6669.7 | 0 | N
1037 | National Highways Authority Of India | 155597 | Ramanathapura-Terakanambi Road/ KR Nagar Junction to Yelawala-KR Nagara Road Junction Four Lane Highway Project (Package IV of Mysuru-Kushalnagar (NH-275) Highway) | 2098 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8429.3 | Under Implementation | Hybrid Annuity |  | Kr nagara road | Karnataka | 01 Apr 2018 | Date of announcement | 2022-09-19 | 8429.3 | 8429.3 | 0 | N | [5 empty] | 2023-03-10 | Bids awarded
1038 | National Highways Authority Of India | 155597 | Ramanathapuram-Rameswaram Four Lane Highway Project | 969 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13661.3 | No Information | Engineering, Procurement & Construction |  | Ramanathapuram | Tamil Nadu | 01 Jan 2014 | Date of announcement | 2021-09-07 | 13661.3 | 1450 | 12211.3 | Y
1039 | National Highways Authority Of India | 155597 | Ramanattukara Junction-Start Of Valanchery Bypass Six Lane Highway (NH-66) Project | 1875 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 47080 | Under Implementation | Hybrid Annuity | July 2024 | Ramanattukara jn. | Kerala | 01 Aug 2020 | Date of announcement | 2022-12-15 | 47080 | 17950.8 | 29129.2 | Y | [5 empty] | 2021-03-30 | Bids awarded
1040 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21686.6 | Under Implementation | Engineering, Procurement & Construction |  | Banihal | Jammu & Kashmir | 15 Apr 2005 | Date of announcement | 2015-09-23 | 21686.6 | 9860 | 11826.6 | Y | [5 empty] | 2015-09-23 | Bids awarded
1041 | National Highways Authority Of India | 155597 | Ramban-Udhampur (NH-44) Section Four Laning Highway Project | 685 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 22730 | Under Implementation | Engineering, Procurement & Construction |  | Ramban | Jammu & Kashmir | 28 Feb 2009 | Date of announcement | 2018-06-30 | 22730 | 9860 | 12870 | Y | [5 empty] | 2015-09-23 | Bids awarded
1042 | National Highways Authority Of India | 155597 | Rampur Four Lane Bypass (NH-530) Project | 2008 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2750.2 | Under Implementation | Engineering, Procurement & Construction |  | Rampur | Uttar Pradesh | 01 Sep 2021 | Date of announcement | 2021-10-18 | 2750.2 | 2750.2 | 0 | N | [5 empty] | 2022-03-30 | Bids awarded
1043 | National Highways Authority Of India | 155597 | Rampur-Kathgodam (NH-87) Four Lane Highway (Package-II) Project | 1156 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7200 | Completed | Hybrid Annuity | September 2022 | Kathgodam | Uttarakhand | 15 Jul 2009 | Date of announcement | 2016-03-31 | 7200 | 5714.4 | 1485.6 | Y | 2022-09-01 | Completed | 2019-10-28 | Y | 1039 | 2011-12-19 | Bids awarded
1044 | National Highways Authority Of India | 155597 | Rampur-Khajuriya-Kesaria-end on NH-722 (NH-227A) Road Project | 1134 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1600 | Announced |  |  | Kesaria | Bihar | 15 May 2015 | Date of announcement | 2018-05-25 | 1600 | 1600 | 0 | N
1045 | National Highways Authority Of India | 155597 | Ranchi (NH-43) ROB Project (between Piska and Itki Railway Station) | 1996 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1083 | Under Implementation | Engineering, Procurement & Construction |  | Ranchi | Jharkhand | 01 Jan 2021 | Date of announcement | 2022-07-09 | 1083 | 1083 | 0 | N | [5 empty] | 2022-03-17 | Bids awarded
1046 | National Highways Authority Of India | 155597 | Ranchi (NH-75 & 23) Two Lane Elevated Corridor Project | 1492 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2920 | Under Implementation | Engineering, Procurement & Construction |  | Ranchi | Jharkhand | 01 May 2018 | Date of announcement | 2022-03-31 | 2920 | 2124.8 | 795.2 | Y | [5 empty] | 2022-03-30 | Bids awarded
1047 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16550 | Under Implementation | Build Operate Transfer Annuity |  | Jamshedpur | Jharkhand | 01 Dec 2003 | Date of announcement | 2018-01-31 | 16550 | 14364.9 | 2185.1 | Y | [5 empty] | 2011-03-18 | Bids awarded
1048 | National Highways Authority Of India | 155597 | Ranichak Four Lane ROB-cum-Flyover Project (Bharatmala) | 1142 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1280 | Completed | Engineering, Procurement & Construction | February 2021 | Ranichak | West Bengal | 15 Mar 2013 | Date of announcement | 2017-04-30 | 1280 | 1889.8 | -609.8 | N | 2021-02-07 | Completed | 2018-11-30 | Y | 800 | 2016-02-01 | Bids awarded
1049 | National Highways Authority Of India | 155597 | Raniganj-Panagarh Highway Project | 41 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2110 | Completed | Engineering, Procurement & Construction | November 2001 | Panagarh | West Bengal | 31 Mar 1995 | Date of announcement | 2001-11-30 | 2110 | 1870.5 | 239.5 | Y | 2001-11-30 | Completed | 1999-06-30 | Y | 884
1050 | National Highways Authority Of India | 155597 | Ranirbazar-Arambagh Four Lane Road (NH-116A) Project | 2054 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11357.2 | Announced |  | February 2024 | Arambagh | West Bengal | 01 Nov 2017 | Date of announcement | 2021-09-07 | 11357.2 | 11357.2 | 0 | N
1051 | National Highways Authority Of India | 155597 | Ranni Village-Miyati Village Eight Lane Carriageway Project (Package 24 of Delhi-Mumbai Expressway) | 1603 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8470 | Completed | Engineering, Procurement & Construction | November 2022 | Miyati village | Madhya Pradesh | 31 Mar 1998 | Date of announcement | 2022-03-17 | 8470 | 9216.3 | -746.3 | N | 2022-12-14 | Initial completion date | 2021-12-31 | Y | 348 | 2019-08-07 | Bids awarded
1052 | National Highways Authority Of India | 155597 | Rapti River Bridge (NH-8) Project | 261 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 165 | Completed |  | March 2006 | Rapti River | Uttar Pradesh | 01 Sep 2003 | Date of announcement | 2003-09-01 | 165 | 165 | 0 | N | 2006-03-31 | Initial completion date | 2006-03-31 | N
1053 | National Highways Authority Of India | 155597 | Ratanpur-Himatnagar NH-8 Four Lane Highway Project | 132 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1822.9 | Completed | Engineering, Procurement & Construction | December 2003 | Himatnagar | Gujarat | 01 Mar 2001 | Date of announcement | 2002-01-01 | 1822.9 | 2200 | -377.1 | N | 2004-04-30 | Initial completion date | 2003-12-31 | Y | 121 | 2001-11-01 | Bids awarded
1054 | National Highways Authority Of India | 155597 | Ratanpur-Satabhaya-Dharma-Basudevpur-Talapada-Chandipur-Chandaneshwar-Digha (NH-316A) Two/Four Laning Highway Project (BM/19) | 1108 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22305 | Under Implementation | Engineering, Procurement & Construction |  | Basudevpur | Odisha | 15 Apr 2015 | Date of announcement | 2021-02-08 | 22305 | 22305 | 0 | N
1055 | National Highways Authority Of India | 155597 | Rau junction (NH-52) Six Lane Flyover Project | 1667 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 470 | Under Implementation | Engineering, Procurement & Construction | December 2024 | Rau junction | Madhya Pradesh | 31 Oct 2010 | Date of announcement | 2022-07-26 | 470 | 800 | -330 | N | 2024-12-31 | Completion expected by | 2023-06-30 | Y | 550 | 2022-03-11 | Bids awarded
1056 | National Highways Authority Of India | 155597 | Raxaul (Indo-Nepal Border)-Haldia Four Lane Expressway Project | 2092 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 302330 | Announced |  |  | Haldia | West Bengal | 01 Jan 2021 | Date of announcement | 2023-02-03 | 302330 | 350000 | -47670 | N
1057 | National Highways Authority Of India | 155597 | Rayya Chowk Six Lane Flyover on Jalandhar-Amritsar Section (NH-03) Project | 2012 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 699 | Under Implementation | Engineering, Procurement & Construction |  | Rayya chowk | Punjab | 01 Dec 2020 | Date of announcement | 2020-12-30 | 699 | 699 | 0 | N | [5 empty] | 2021-04-16 | Bids awarded
1058 | National Highways Authority Of India | 155597 | Recherla Village to Gurvaygudem Village (NH-365BG) Four Lane Access Controlled Greenfield Highway Project (Package 4 of Khammam-Devarapalle NH) (Bharatmala) | 1713 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8174.8 | Under Implementation | Hybrid Annuity | September 2024 | Gurvaigudem | Andhra Pradesh | 28 Dec 2018 | Date of announcement | 2022-12-21 | 8174.8 | 5693.7 | 2481.1 | Y | [5 empty] | 2021-09-15 | Bids awarded
1059 | National Highways Authority Of India | 155597 | Reconstruction of Minor Bridges on Thirthahalli-Udupi Section (NH-169 A) Project | 1871 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 82 | Completed |  | March 2021 | Thirthahalli | Karnataka | 01 Aug 2020 | Date of announcement | 2020-12-19 | 82 | 82 | 0 | N
1060 | National Highways Authority Of India | 155597 | Rehabilitation & Up-gradation of Anantapur-Kalyandurg (NH-544DD) Highway Project | 1862 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2941.2 | Completed |  | October 2019 | Anantapur | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2019-10-17 | 2941.2 | 2941.2 | 0 | N
1061 | National Highways Authority Of India | 155597 | Rehabilitation & Upgradation of Hyderabad-Dindi (NH-765) Two Lane Highway Project | 1811 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3400 | Completed |  | January 2019 | Dindi | Andhra Pradesh | 15 Jan 2014 | Date of announcement | 2015-04-29 | 3400 | 3400 | 0 | N
1062 | National Highways Authority Of India | 155597 | Rehabilitation & up-gradation to 4-laning of Birmitrapur-Brahmani Bypass End of NH-23 (NH-143) Project | 1265 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6789.2 | Under Implementation | Engineering, Procurement & Construction |  | Birmitrapur | Odisha | 04 Apr 2014 | Date of announcement | 2022-07-21 | 6789.2 | 4765.6 | 2023.6 | Y | [5 empty] | 2017-07-19 | Bids awarded
1063 | National Highways Authority Of India | 155597 | Rehabilitation and Up-gradation of Ambala-Saha (NH-444A) Four Lane Highway Project (Package-1) | 1768 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1440 | Completed | Engineering, Procurement & Construction | August 2022 | Ambala | Haryana | 01 Jan 2017 | Date of announcement | 2019-07-24 | 1440 | 2200 | -760 | N | 2022-08-01 | Completed | 2021-11-30 | Y | 244 | 2019-03-08 | Bids awarded
1064 | National Highways Authority Of India | 155597 | Rehukaldhar-Aut(Tunnel) (NH-21) Highway Project (Package-IV of Nerchowk-Kullu stretch) | 1046 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5751.4 | Under Implementation | Hybrid Annuity |  | Aut section | Himachal Pradesh | 15 Nov 2014 | Date of announcement | 2014-12-05 | 5751.4 | 5751.4 | 0 | N | [5 empty] | 2017-06-19 | Bids awarded
1065 | National Highways Authority Of India | 155597 | Renigunta-Naidupeta (NH-71) Six Lane Highway Project (Bharatmala) | 1762 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 22250 | Under Implementation | Hybrid Annuity | January 2024 | Naidupeta | Andhra Pradesh | 01 Jan 2019 | Date of announcement | 2020-10-16 | 22250 | 22250 | 0 | N | [5 empty] | 2020-12-24 | Bids awarded
1066 | National Highways Authority Of India | 155597 | Residency road flyover at Sadar Project | 1018 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3000 | Completed |  | January 2020 | Nagpur | Maharashtra | 01 Dec 2007 | Date of announcement | 2016-02-23 | 3000 | 375.4 | 2624.6 | Y | 2020-01-31 | Initial completion date | 2019-01-31 | Y | 365
1067 | National Highways Authority Of India | 155597 | Rimuli-Roxy (Koida)-Rajamunda (NH-215 & 520) Two/Four Laning Highway Project | 1689 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 20047.6 | Under Implementation | Build Operate Transfer |  | Rajamunda | Odisha | 30 Oct 2008 | Date of announcement | 2019-01-05 | 20047.6 | 7850 | 12197.6 | Y | [5 empty] | 2010-04-30 | Bids awarded
1068 | National Highways Authority Of India | 155597 | Ring bunds to Jhanjharpur (BR-6) Road Project | 732 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5355 | Completed |  | November 2011 | Jhanjhapur | Bihar | 31 Dec 2003 | Date of announcement | 2011-04-30 | 5355 | 3400 | 1955 | Y | 2011-11-30 | Completed | 2010-06-30 | Y | 518
1069 | National Highways Authority Of India | 155597 | RoB near junction with NH-11A to Junction with MDR-1 (Baonli-Jhalai Road) Eight Lane Carriageway Project (Package 8 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1587 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11098.1 | Completed | Engineering, Procurement & Construction | February 2023 | Baonli-jhalai road | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-10-04 | 11098.1 | 11098.1 | 0 | N | 2023-02-12 | Completed | 2021-12-31 | Y | 408 | 2020-02-11 | Bids awarded
1070 | National Highways Authority Of India | 155597 | RoB near village Itawa to Major Bridge on Chakan River Eight Lane Carriageway Project (Package-10 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1561 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7580.8 | Under Implementation | Engineering, Procurement & Construction |  | Baonli-jhalai road | Rajasthan | 31 Mar 1998 | Date of announcement | 2018-09-28 | 7580.8 | 7580.8 | 0 | N | [5 empty] | 2020-06-30 | Bids awarded
1071 | National Highways Authority Of India | 155597 | Road approaches to Rail-cum Road Bridge across river Ganga on Munger Ghat (NH-333B) Project | 1242 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6960 | Completed | Engineering, Procurement & Construction | February 2022 | Munger ghat | Bihar | 01 Apr 2015 | Date of announcement | 2022-02-11 | 6960 | 1720 | 5240 | Y | 2022-02-11 | Completed | 2020-07-31 | Y | 560 | 2017-03-31 | Bids awarded
1072 | National Highways Authority Of India | 155597 | Road cum Flyover to Paradip Port Project (serving as 2nd exit) (near Atharbanki Chowk) | 1523 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 930 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Paradip | Odisha | 01 Apr 2018 | Date of announcement | 2020-12-30 | 930 | 1000 | -70 | N | 2024-03-16 | Completion expected by | 2022-11-30 | Y | 472 | 2020-12-30 | Bids awarded
1073 | National Highways Authority Of India | 155597 | Road from SH-Alappuzha Bypass Intersection Project (Port Connectivity) (Sagarmala) | 1750 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2281.1 | No Information |  |  | Alappuzha bypass | Kerala | 01 Dec 2016 | Date of announcement | 2018-05-15 | 2281.1 | 2281.1 | 0 | N
1074 | National Highways Authority Of India | 155597 | Rohna/Hassangarh-Jhajjar (NH-334B) Four Lane Highway Project (Package-II) (Meerut to Jhajjar) | 1433 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11830 | Completed | Hybrid Annuity | July 2020 | Hassangarh | Haryana | 01 May 2017 | Date of announcement | 2020-07-13 | 11830 | 5515.8 | 6314.2 | Y | [5 empty] | 2018-03-26 | Bids awarded
1075 | National Highways Authority Of India | 155597 | Rohtak Hissar Section Of NH-10 Project | 458 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5860 | Completed | Build Operate Transfer | July 2008 | Hissar | Haryana | 01 Jul 2007 | Date of announcement | 2008-07-01 | 5860 | 5430 | 430 | Y
1076 | National Highways Authority Of India | 155597 | Rohtak-Jind (NH-71) Four-Laning Highway Project (Bharatmala) | 1398 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5107.4 | Under Implementation | Engineering, Procurement & Construction |  | Jind | Haryana | 30 Apr 2009 | Date of announcement | 2020-08-04 | 5107.4 | 1840 | 3267.4 | Y | [5 empty] | 2011-12-01 | Bids awarded
1077 | National Highways Authority Of India | 155597 | Rohtak-Panipat Six Laning Road project | 655 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 6500 | No Information |  |  | Panipat | Haryana | 28 Jul 2009 | Date of announcement | 2009-07-28 | 6500 | 6500 | 0 | N
1078 | National Highways Authority Of India | 155597 | Rudrapur Four Lane Bypass Project | 2117 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6000 | Under Implementation | Hybrid Annuity |  | Rudrapur bypass | Uttarakhand | 01 May 2022 | Date of announcement | 2023-04-07 | 6000 | 6000 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
1079 | National Highways Authority Of India | 155597 | Saadiya-Fort Vypin Road Upgradation Project | 1744 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 387.2 | No Information |  |  | Fort vypin | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 387.2 | 387.2 | 0 | N
1080 | National Highways Authority Of India | 155597 | Sagar Bypass (NH-26) Road Project | 425 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1900 | Completed |  | October 2012 | Sagar | Madhya Pradesh | 31 Dec 2003 | Date of announcement | 2012-06-30 | 1900 | 1513 | 387 | Y | 2012-10-31 | Completed | 2009-11-30 | Y | 1066
1081 | National Highways Authority Of India | 155597 | Sagar-Mohari Four Lane Highway (NH-934) Project | 1914 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7910 | Under Implementation | Engineering, Procurement & Construction |  | Mohari | Madhya Pradesh | 01 Jan 2018 | Date of announcement | 2021-09-16 | 7910 | 5200 | 2710 | Y | [5 empty] | 2021-07-22 | Bids awarded
1082 | National Highways Authority Of India | 155597 | Sagar-Rajmarg Choraha (ADB-II/C-6) Highway Project | 747 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2450 | Completed |  | March 2013 | Rajmarg Choraha | Madhya Pradesh | 31 Dec 2003 | Date of announcement | 2012-08-30 | 2450 | 2034.3 | 415.7 | Y | 2013-03-31 | Completed | 2010-12-31 | Y | 821
1083 | National Highways Authority Of India | 155597 | Sagar-Rajmarg Choraha (ADB-II/C-7) Highway Project | 293 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2820 | Completed |  | December 2010 | Rajmarg Choraha | Madhya Pradesh | 01 Dec 2003 | Date of announcement | 2010-10-31 | 2820 | 1900 | 920 | Y | 2010-12-31 | Completed | 2008-12-31 | Y | 730
1084 | National Highways Authority Of India | 155597 | Saha Junction-Shahabad (NH-444A) Four Lane Highway Project (Bharatmala) | 1763 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1278.5 | Completed | Engineering, Procurement & Construction | August 2022 | Ambala | Haryana | 01 Jan 2017 | Date of announcement | 2021-03-25 | 1278.5 | 2620 | -1341.5 | N | [5 empty] | 2020-10-19 | Bids awarded
1085 | National Highways Authority Of India | 155597 | Sakoli (NH-53) Flyover Project | 1423 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2700 | Completed | Engineering, Procurement & Construction | May 2022 | Sakoli | Maharashtra | 30 Nov 2017 | Date of announcement | 2022-05-29 | 2700 | 2892.1 | -192.1 | N | 2022-05-29 | Completed | 2020-05-22 | Y | 737 | 2018-03-29 | Bids awarded
1086 | National Highways Authority Of India | 155597 | Salasar-Nagaur (NH-65) Two Lane Highway Project | 1198 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4800 | Completed | Hybrid Annuity | January 2019 | Deh | Rajasthan | 31 Jan 2016 | Date of announcement | 2019-01-27 | 4800 | 6371.8 | -1571.8 | N | 2019-09-30 | Initial completion date | 2019-01-28 | Y | 245 | 2016-06-30 | Bids awarded
1087 | National Highways Authority Of India | 155597 | Salem Bypass(NS/12) Highway Project | 53 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 269.4 | Completed | Engineering, Procurement & Construction | January 2003 | Salem | Tamil Nadu | 01 Mar 1999 | Date of announcement | 2002-03-31 | 269.4 | 330 | -60.6 | N | 2003-01-31 | Completed | 2001-06-30 | Y | 580 | 1999-12-01 | Bids awarded
1088 | National Highways Authority Of India | 155597 | Salem to Kerala Border (TN-7) Highway Project | 769 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4532 | Completed | Build Operate Transfer | August 2009 | Kerala | Kerala | 01 Jul 2006 | Date of announcement | 2006-07-01 | 4532 | 4532 | 0 | N
1089 | National Highways Authority Of India | 155597 | Salem-Chengapalli Eight Lane Highway Project (Bharatmala) | 1633 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17600.3 | Announced | Hybrid Annuity | February 2024 | Chengapali | Tamil Nadu | 19 Dec 2018 | Date of announcement | 2021-09-07 | 17600.3 | 19310 | -1709.7 | N
1090 | National Highways Authority Of India | 155597 | Salem-Coimbatore Highway Project | 337 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9350 | No Information |  |  | Coimbatore | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2003-12-01 | 9350 | 9350 | 0 | N
1091 | National Highways Authority Of India | 155597 | Salem-Karur (NS-2/TN-2) Highway Project | 771 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3333.4 | Completed | Build Operate Transfer | August 2009 | Karur | Tamil Nadu | 01 Aug 2006 | Date of announcement | 2006-08-01 | 3333.4 | 3333.4 | 0 | N
1092 | National Highways Authority Of India | 155597 | Salem-Karur (NS-2/TN-3) Highway Project | 772 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3239.4 | Completed | Build Operate Transfer | August 2009 | Karur | Tamil Nadu | 01 Jul 2006 | Date of announcement | 2006-07-01 | 3239.4 | 3239.4 | 0 | N
1093 | National Highways Authority Of India | 155597 | Salem-Namakkal Highway Project | 332 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2500 | Completed | Build Operate Transfer | August 2009 | Namakkal | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2009-07-01 | 2500 | 3800 | -1300 | N | 2009-08-31 | Completed | 2008-12-31 | Y | 243
1094 | National Highways Authority Of India | 155597 | Salur Town Bypass Road in Raipur-Vizag section of NH-26 Project | 1860 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 708.1 | Under Implementation |  |  | Raipur | Chhattisgarh | 01 Mar 2015 | Date of announcement | 2020-10-16 | 708.1 | 401 | 307.1 | Y | [5 empty] | 2020-10-16 | Bids awarded
1095 | National Highways Authority Of India | 155597 | Samakhiali-Gandhidham (Package I) Highway Project | 23 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 400 | Completed | Engineering, Procurement & Construction | September 2000 | Gandhidham | Gujarat | 01 Jun 1998 | Date of announcement | 1998-06-01 | 400 | 400 | 0 | N | 2001-05-31 | Initial completion date | 2000-09-30 | Y | 243 | 1998-09-01 | Bids awarded
1096 | National Highways Authority Of India | 155597 | Samakhiyali to Santalpur (NH-27) Six Lane Highway Project | 2087 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 21320 | Under Implementation | Build Operate Transfer Toll |  | Samakhiyali | Gujarat | 01 Apr 2022 | Date of announcement | 2023-02-21 | 21320 | 21320 | 0 | N | [5 empty] | 2023-02-24 | Bids awarded
1097 | National Highways Authority Of India | 155597 | Samakhiyali-Bhachau N H-8 A Project | 25 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 400 | No Information |  |  | Bhachau | Gujarat | 01 Dec 1997 | Date of announcement | 1997-12-01 | 400 | 400 | 0 | N
1098 | National Highways Authority Of India | 155597 | Samarlakota-Achampeta Junction Four Lane Road (NH-516F) (Part of Kakinada Port Connectivity to NH-16) Project | 2065 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6390 | Under Implementation | Engineering, Procurement & Construction |  | Achampeta junction (kakinada) | Andhra Pradesh | 01 Jul 2021 | Date of announcement | 2022-09-22 | 6390 | 4162.1 | 2227.9 | Y | [5 empty] | 2022-09-29 | Bids awarded
1099 | National Highways Authority Of India | 155597 | Samayapuram Service Road connecting Chennai-Tiruchi Highway project | 1550 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 127.7 | Completed |  | November 2019 | Samayapuram | Tamil Nadu | 01 Mar 2018 | Date of announcement | 2019-11-12 | 127.7 | 130 | -2.3 | N | 2019-11-12 | Completed | 2019-06-30 | Y | 135
1100 | National Highways Authority Of India | 155597 | Samrala Chowk-Ludhiana Municipal Limit (NH-95 & 5) Four Lane Highway Project | 1169 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8954.5 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Ludhiana municipal limit | Punjab | 30 Sep 2014 | Date of announcement | 2021-07-22 | 8954.5 | 8677.2 | 277.3 | Y | 2023-10-31 | Initial completion date | 2018-09-30 | Y | 1857 | 2017-03-31 | Bids awarded
1101 | National Highways Authority Of India | 155597 | Sanath Nagar Industrial Cluster (Hyderabad)-JNPT Expressway Project | 1743 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 220000 | No Information |  |  | Jnpt | Maharashtra | 01 Apr 2016 | Date of announcement | 2019-07-31 | 220000 | 220000 | 0 | N
1102 | National Highways Authority Of India | 155597 | Sanathnagar industrial cluster-Hyderabad to Vodarevu Expressway Project (Port Connectivity) | 1720 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 100000 | No Information |  |  | Sanathnagar industrial cluster | Telangana | 01 Dec 2016 | Date of announcement | 2020-08-09 | 100000 | 100000 | 0 | N
1103 | National Highways Authority Of India | 155597 | Sanchi-Sagar NH-86 (Extn) (New NH-146) Widening Highway Project | 781 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 2873.4 | Completed | Engineering, Procurement & Construction | August 2020 | Sagar | Madhya Pradesh | 19 May 2010 | Date of announcement | 2020-08-23 | 2873.4 | 1250 | 1623.4 | Y | 2020-08-25 | Completed | 2012-05-31 | Y | 3008 | 2011-01-05 | Bids awarded
1104 | National Highways Authority Of India | 155597 | Sanganur NH 209 Bridge Project | 448 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14.6 | No Information |  |  | Sanganur | Tamil Nadu | 05 Feb 2007 | Date of announcement | 2007-02-05 | 14.6 | 14.6 | 0 | N
1105 | National Highways Authority Of India | 155597 | Sangareddy-Nanded-Akola (NH-161) Four-Lane Highway Project | 1195 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 23000 | Under Implementation |  |  | Akola | Maharashtra | 31 May 2016 | Date of announcement | 2017-08-11 | 23000 | 23000 | 0 | N
1106 | National Highways Authority Of India | 155597 | Sankha-Khajuri (NH-75) Four Lane Highway project (Rehla/Garhwa Bypass) (Package 4 of Garhwa-UP Border) | 1676 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9034.7 | Under Implementation | Hybrid Annuity | October 2023 | Khajuri | Jharkhand | 01 Apr 2018 | Date of announcement | 2022-12-21 | 9034.7 | 5743.4 | 3291.3 | Y | [5 empty] | 2020-10-26 | Bids awarded
1107 | National Highways Authority Of India | 155597 | Sanquelim-Jamboti-Belagavi Two Lane Road (NH-748AA) Project | 1964 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2467.8 | Under Implementation | Engineering, Procurement & Construction |  | Belagavi | Karnataka | 01 Nov 2021 | Date of announcement | 2022-02-24 | 2467.8 | 2291.9 | 175.9 | Y | [5 empty] | 2022-03-16 | Bids awarded
1108 | National Highways Authority Of India | 155597 | Saoner (NH-547E) Four Laning bypass Project (on Saoner-Dhapewada Gondkhairi Road) | 1173 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1386.1 | No Information | Engineering, Procurement & Construction |  | Saoner | Maharashtra | 15 Jan 2015 | Date of announcement | 2015-01-15 | 1386.1 | 1386.1 | 0 | N
1109 | National Highways Authority Of India | 155597 | Saoner-Dhapewada-Kalmeshwar-Gondkhairi (NH-547E) Four Lane Highway Project | 1682 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7200 | Completed | Engineering, Procurement & Construction | January 2022 | Dhapewada | Maharashtra | 01 Apr 2016 | Date of announcement | 2022-01-15 | 7200 | 4800.6 | 2399.4 | Y | 2022-01-23 | Initial completion date | 2021-03-31 | Y | 298 | 2019-03-11 | Bids awarded
1110 | National Highways Authority Of India | 155597 | Sarai Cholla-Morena (NS-20/MP) Highway Project | 191 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 514.2 | Completed | Engineering, Procurement & Construction | August 2004 | Morena | Madhya Pradesh | 01 May 2001 | Date of announcement | 2004-04-01 | 514.2 | 600 | -85.8 | N | 2004-08-31 | Completed | 2003-04-30 | Y | 489 | 2001-09-01 | Bids awarded
1111 | National Highways Authority Of India | 155597 | Saraighat Double Decker Rail cum Road Bridge across Brahmaputra River (Near Existing Saraighat Bridge) Project | 2066 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9967.5 | Under Implementation |  |  | Brahmapurtra river, guwahati | Assam | 15 Apr 2017 | Date of announcement | 2022-09-28 | 9967.5 | 11266.7 | -1299.2 | N
1112 | National Highways Authority Of India | 155597 | Saraighat Second Bridge over Brahmhaputra Project | 1240 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4750 | Completed |  | January 2017 | Saraighat | Assam | 30 Jun 2006 | Date of announcement | 2017-01-28 | 4750 | 2383.4 | 2366.6 | Y | 2017-01-28 | Completed | 2017-01-01 | N |  | 2006-10-03 | Bids awarded
1113 | National Highways Authority Of India | 155597 | Sardar Patel Ring Road-Sindhrej Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 1) (Bharatmala) | 1704 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7935.4 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Sardar patel ring road | Gujarat | 20 Mar 2010 | Date of announcement | 2018-12-28 | 7935.4 | 7935.4 | 0 | N | 2024-03-31 | Completion expected by | 2013-12-31 | Y | 3743 | 2020-11-18 | Bids awarded
1114 | National Highways Authority Of India | 155597 | Sargaon-Bilaspur (NH-130) Four Laning Highway (Package-III of Raipur-Bilaspur) Project | 1136 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5350 | Completed | Engineering, Procurement & Construction | September 2018 | Bilaspur | Chhattisgarh | 14 Oct 2009 | Date of announcement | 2017-10-31 | 5350 | 4131.8 | 1218.2 | Y | 2018-09-22 | Completed | 2018-04-30 | Y | 145 | 2012-01-30 | Bids awarded
1115 | National Highways Authority Of India | 155597 | Sarkhej(Ahemdabad)-Mundra Expressway Project | 1734 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 100000 | No Information |  |  | Mundra | Gujarat | 01 Apr 2016 | Date of announcement | 2019-07-31 | 100000 | 100000 | 0 | N
1116 | National Highways Authority Of India | 155597 | Sarkhej-Ahmedabad-Pipavav Expressway Project (Port Connectivity) (Sagarmala) | 1717 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 90000 | Announced |  |  | Ahmedabad | Gujarat | 01 Apr 2016 | Date of announcement | 2016-06-03 | 90000 | 90000 | 0 | N
1117 | National Highways Authority Of India | 155597 | Sasaram-dehri-on-sone (GTRIP/IV-C) Highway Project | 691 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2218.7 | Completed | Engineering, Procurement & Construction | July 2008 | Dehri on sone | Bihar | 01 Mar 2002 | Date of announcement | 2002-03-01 | 2218.7 | 2218.7 | 0 | N | [5 empty] | 2002-03-31 | Bids awarded
1118 | National Highways Authority Of India | 155597 | Satai Ghat-Chauka (Chhatarpur) (NH-34&934) Four Lane Highway Project | 2084 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10710 | Under Implementation |  |  | Chauka | Madhya Pradesh | 01 Nov 2022 | Date of announcement | 2023-01-23 | 10710 | 10710 | 0 | N
1119 | National Highways Authority Of India | 155597 | Satna-Maihar Two Lane Highway (NH-135BG) Project | 1918 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6150 | Under Implementation | Engineering, Procurement & Construction |  | Maihar | Madhya Pradesh | 01 Apr 2019 | Date of announcement | 2021-09-17 | 6150 | 4408.1 | 1741.9 | Y | [5 empty] | 2021-09-14 | Bids awarded
1120 | National Highways Authority Of India | 155597 | Savali Vihir to start of Ahmednagar Bypass (NH-160) Four Lane Highway Project | 1892 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4301.1 | Under Implementation |  |  | Ahmednagar | Maharashtra | 01 Jan 2021 | Date of announcement | 2021-01-12 | 4301.1 | 4301.1 | 0 | N | [5 empty] | 2021-03-27 | Bids awarded
1121 | National Highways Authority Of India | 155597 | Sector 29/31 roundabout (Tribune Chowk) Flyover Project | 1509 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1580 | Under Implementation |  |  | Chandigarh | Chandigarh | 06 Jun 2016 | Date of announcement | 2019-07-27 | 1580 | 3000 | -1420 | N
1122 | National Highways Authority Of India | 155597 | Seelapadi Vehicular Underpass (VUP) Project | 1968 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 210 | Announced |  |  | Seelapadi | Tamil Nadu | 01 Jan 2022 | Date of announcement | 2022-03-02 | 210 | 210 | 0 | N
1123 | National Highways Authority Of India | 155597 | Seoni-MP/MH Border (NH-7) (Delinked Stretch) Four Laning Highway Project | 1329 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9602.4 | Completed | Engineering, Procurement & Construction | February 2021 | Seoni | Madhya Pradesh | 30 Apr 2016 | Date of announcement | 2019-08-31 | 9602.4 | 5668 | 3934.4 | Y | 2021-06-30 | Initial completion date | 2020-08-08 | Y | 326 | 2018-01-18 | Bids awarded
1124 | National Highways Authority Of India | 155597 | Service Road from Rau Circle-DPS School on Indore Bypass Project | 2053 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 425.8 | Under Implementation |  |  | Rau circle | Madhya Pradesh | 01 Jan 2022 | Date of announcement | 2022-07-25 | 425.8 | 425.8 | 0 | N
1125 | National Highways Authority Of India | 155597 | Service Road on Ahmadabad Bypass Section Project | 368 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 75 | No Information |  |  | Ahmedabad | Gujarat | 01 Dec 2003 | Date of announcement | 2003-12-01 | 75 | 75 | 0 | N
1126 | National Highways Authority Of India | 155597 | Sethiyahopu-Cholopuram (NH-45C) Four Laning Highway (Pkg-II of Vikravandi-Thanjavur) Project | 1243 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12278.7 | Under Implementation | Hybrid Annuity |  | Cholopuram | Tamil Nadu | 27 Dec 2016 | Date of announcement | 2018-12-31 | 12278.7 | 9562.3 | 2716.4 | Y | [5 empty] | 2017-09-29 | Bids awarded
1127 | National Highways Authority Of India | 155597 | Sevoke-Gangtok (NH-31A) Highway Project | 360 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9000 | No Information |  |  | Gangtok | Sikkim | 01 Dec 2003 | Date of announcement | 2007-04-01 | 9000 | 9000 | 0 | N
1128 | National Highways Authority Of India | 155597 | Shahapur-Pindari (NH-31) Four Lane Greenfield Highway Project (Package-II of Ghazipur-Ballia-UP/Bihar State Border) | 1646 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7839.2 | Under Implementation | Engineering, Procurement & Construction |  | Pindari | Uttar Pradesh | 12 Apr 2017 | Date of announcement | 2022-08-02 | 7839.2 | 4766.6 | 3072.6 | Y | [5 empty] | 2023-01-23 | Bids awarded
1129 | National Highways Authority Of India | 155597 | Shahganj Junction-Obedullaganj (NH-69) Four-Laning Highway Project | 806 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1780 | No Information | Design Build Finance Operate Transfer |  | Obedullaganj | Madhya Pradesh | 14 Sep 2010 | Date of announcement | 2010-09-15 | 1780 | 1780 | 0 | N
1130 | National Highways Authority Of India | 155597 | Shahpur Bypass-Muktainagar Four Lane Road (NH-753L) Project (Package-II of Boregaon Buzurg-Muktainagar Road) | 2078 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7843.5 | Under Implementation | Hybrid Annuity |  | Muktainagar | Maharashtra | 01 Jul 2022 | Date of announcement | 2022-12-20 | 7843.5 | 5641.6 | 2201.9 | Y | [5 empty] | 2023-03-23 | Bids awarded
1131 | National Highways Authority Of India | 155597 | Shahpura Tiraha Flyover Project | 1970 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 407.8 | Under Implementation |  |  | Shahpura tiraha | Rajasthan | 01 Apr 2009 | Date of announcement | 2022-03-09 | 407.8 | 407.8 | 0 | N
1132 | National Highways Authority Of India | 155597 | Shahpura-Gulabpura (NH-148D) Carriageway Improvement Project | 877 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 320.1 | No Information |  |  | Gulabpura | Rajasthan | 11 Oct 2011 | Date of announcement | 2011-10-11 | 320.1 | 320.1 | 0 | N
1133 | National Highways Authority Of India | 155597 | Shambu-Jalandhar Six laning Highway Project | 775 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18000 | No Information | Build Operate Transfer Toll |  | Jalandhar | Punjab | 23 Sep 2009 | Date of announcement | 2012-04-23 | 18000 | 15000 | 3000 | Y
1134 | National Highways Authority Of India | 155597 | Shamli-Ambala Six Lane Greenfield Expressway Project (Part of Bareilly-Ludhiana Expressway) | 1931 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 46000 | Announced | Engineering, Procurement & Construction | December 2024 | Ambala | Haryana | 01 Jan 2021 | Date of announcement | 2022-11-29 | 46000 | 36938 | 9062 | Y
1135 | National Highways Authority Of India | 155597 | Shamli-Muzaffarnagar (NH-709AD) Four Lane Highway Project (Package 2 of Panipat-Nagina Highway) | 1641 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 16220 | Under Implementation | Engineering, Procurement & Construction |  | Muzaffarnagar | Uttar Pradesh | 10 Jun 2016 | Date of announcement | 2019-02-20 | 16220 | 9419.9 | 6800.1 | Y | [5 empty] | 2019-10-15 | Bids awarded
1136 | National Highways Authority Of India | 155597 | Shamo-Matihani Six Lane Bridge (Begusarai Bridge) Project | 1846 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 60000 | Under Implementation |  |  | Begusarai | Bihar | 01 Apr 2006 | Date of announcement | 2022-10-19 | 60000 | 44123.4 | 15876.6 | Y
1137 | National Highways Authority Of India | 155597 | Shanti Chowk-Gentyal Chowk (NH-9) Four Lane Flyover Project | 1408 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1444.9 | No Information | Engineering, Procurement & Construction |  | Gentyal chowk | Maharashtra | 07 Nov 2017 | Date of announcement | 2017-11-07 | 1444.9 | 1444.9 | 0 | N
1138 | National Highways Authority Of India | 155597 | Shedgaon (NH-44) Four Lane VUP/Flyover Project | 1904 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 480 | Under Implementation | Engineering, Procurement & Construction |  | Shedgaon | Maharashtra | 01 Apr 2021 | Date of announcement | 2021-06-17 | 480 | 480 | 0 | N
1139 | National Highways Authority Of India | 155597 | Shikohabad-Etawah (GTRIP/I-B) Highway Project | 501 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2612.2 | Completed | Engineering, Procurement & Construction | September 2008 | Etawah | Uttar Pradesh | 01 Mar 2002 | Date of announcement | 2008-07-01 | 2612.2 | 2360 | 252.2 | Y | 2008-09-30 | Completed | 2008-08-31 | Y | 30 | 2002-03-12 | Bids awarded
1140 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 39150 | Under Implementation | Hybrid Annuity | April 2026 | Mdr junction | Himachal Pradesh | 10 Feb 2009 | Date of announcement | 2022-09-22 | 39150 | 6128.3 | 33021.7 | Y | 2026-04-20 | Completion expected by | 2020-09-30 | Y | 2028 | 2016-08-26 | Bids awarded
1141 | National Highways Authority Of India | 155597 | Shivpuri Bypass & upto MP/RJ Border (NH-76&25) Highway Project | 550 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3603.4 | Completed | Engineering, Procurement & Construction | October 2008 | Rajasthan | Rajasthan | 01 Mar 2005 | Date of announcement | 2005-03-01 | 3603.4 | 3603.4 | 0 | N | [5 empty] | 2005-04-01 | Bids awarded
1142 | National Highways Authority Of India | 155597 | Shiwrampur-Ramnagar Four Lane Highway (Package-II of Amas-Darbhanga Expressway) Project | 1890 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14943.1 | Under Implementation |  | September 2024 | Ramnagar | Bihar | 01 Mar 2021 | Date of announcement | 2022-04-06 | 14943.1 | 10754.1 | 4189 | Y | [5 empty] | 2022-03-22 | Bids awarded
1143 | National Highways Authority Of India | 155597 | Sikandara-Bhaunti (TNHP/II-A) Highway Project | 148 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3110.9 | Completed | Engineering, Procurement & Construction | March 2007 | Bara | Uttar Pradesh | 31 Jan 2001 | Date of announcement | 2007-01-01 | 3110.9 | 2890 | 220.9 | Y | 2007-03-31 | Completed | 2004-08-31 | Y | 942 | 2001-02-01 | Bids awarded
1144 | National Highways Authority Of India | 155597 | Silchar-Kolasib (NH-54) Highway Project | 353 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8220 | No Information |  |  | Kolasib | Mizoram | 01 Dec 2003 | Date of announcement | 2009-10-01 | 8220 | 8220 | 0 | N
1145 | National Highways Authority Of India | 155597 | Silchar-Udarband (NH-54) Four-Laning Highway Project | 274 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2700 | Completed | Engineering, Procurement & Construction | March 2015 | Silchar | Assam | 01 Dec 2003 | Date of announcement | 2014-10-30 | 2700 | 1545.7 | 1154.3 | Y | 2015-03-31 | Completed | 2007-09-30 | Y | 2739
1146 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-6) Four Lane Highway Project | 287 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1550 | Completed | Public Private Partnership | October 2008 | Islampore | West Bengal | 01 Dec 2003 | Date of announcement | 2003-12-01 | 1550 | 1550 | 0 | N | [5 empty] | 2005-04-15 | Bids awarded
1147 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-7) Four-Laning Highway Project | 701 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2250 | Completed | Engineering, Procurement & Construction | March 2014 | Islampore | West Bengal | 01 Dec 2003 | Date of announcement | 2003-12-01 | 2250 | 2250 | 0 | N | 2014-03-31 | Completed | 2008-07-30 | Y | 2070
1148 | National Highways Authority Of India | 155597 | Simaria-Khagaria (NH-31) Four Laning Highway Project (Package 3 of Khagaria-Bakhtiarpur Highway) | 1073 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7250 | Under Implementation | Engineering, Procurement & Construction |  | Khagaria | Bihar | 12 Aug 2008 | Date of announcement | 2019-02-13 | 7250 | 6072.5 | 1177.5 | Y | [5 empty] | 2011-12-03 | Bids awarded
1149 | National Highways Authority Of India | 155597 | Simariya Tekri-Haripur Tiraha (NH-75) Four Laning Road Project | 1424 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 497.5 | Completed | Engineering, Procurement & Construction | December 2019 | Haripur tiraha | Madhya Pradesh | 01 Dec 2017 | Date of announcement | 2019-12-05 | 497.5 | 672.7 | -175.2 | N | 2019-12-05 | Completed | 2019-11-30 | N
1150 | National Highways Authority Of India | 155597 | Simga-Sargaon (NH-130) Four Laning Highway (Package-II of Raipur-Bilaspur) Project | 1135 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5966.7 | Completed | Engineering, Procurement & Construction | February 2020 | Sargaon | Chhattisgarh | 14 Oct 2009 | Date of announcement | 2015-12-28 | 5966.7 | 4784.3 | 1182.4 | Y | 2020-03-31 | Initial completion date | 2018-05-31 | Y | 670 | 2012-01-30 | Bids awarded
1151 | National Highways Authority Of India | 155597 | Simrahi To Ring Bund Missing link (BR-4) Road Project | 710 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2160 | Completed |  | March 2012 | Ring bund | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2012-02-28 | 2160 | 1005 | 1155 | Y | 2012-04-30 | Initial completion date | 2009-12-31 | Y | 851 | 2005-12-31 | Bids awarded
1152 | National Highways Authority Of India | 155597 | Sindhrej Village-Vejalka Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 2) | 1705 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8946 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Sindhrej village | Gujarat | 20 Mar 2010 | Date of announcement | 2018-12-28 | 8946 | 8946 | 0 | N | 2024-03-31 | Completion expected by | 2013-12-31 | Y | 3743 | 2020-11-16 | Bids awarded
1153 | National Highways Authority Of India | 155597 | Singhara-Binjabahal (NH-6) (New NH-49) Four Laning Highway Project | 946 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14200 | Completed | Hybrid Annuity | March 2022 | Binjabahal | Odisha | 11 Nov 2013 | Date of announcement | 2022-02-28 | 14200 | 10780 | 3420 | Y | 2022-03-03 | Completed | 2020-03-31 | Y | 702 | 2017-03-29 | Bids awarded
1154 | National Highways Authority Of India | 155597 | Sinnar-Sirdi (NH-160) Four Lane Highway Project | 1422 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13307.2 | Under Implementation | Hybrid Annuity | June 2023 | Shirdi | Maharashtra | 30 Apr 2015 | Date of announcement | 2019-12-31 | 13307.2 | 9203.9 | 4103.3 | Y | [5 empty] | 2019-03-09 | Bids awarded
1155 | National Highways Authority Of India | 155597 | Sira Bypass Highway Project | 63 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 193.2 | Completed | Engineering, Procurement & Construction | April 2002 | Sira | Karnataka | 01 Nov 1999 | Date of announcement | 2002-01-01 | 193.2 | 209 | -15.8 | N | 2002-04-30 | Completed | 2002-03-31 | Y | 30 | 2000-07-01 | Bids awarded
1156 | National Highways Authority Of India | 155597 | Sirhind-Sehna Six Lane Access Controlled Highway Project | 1928 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 47335.8 | Announced | Engineering, Procurement & Construction |  | Sehna | Punjab | 15 Jun 2021 | Date of announcement | 2021-09-10 | 47335.8 | 47335.8 | 0 | N
1157 | National Highways Authority Of India | 155597 | Sitarganj-Pilibhit-Bareily (NH-74) Two/Four Laning Road Project | 1147 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 24372.7 | Under Implementation | Hybrid Annuity |  | Bareilly | Uttar Pradesh | 05 Feb 2013 | Date of announcement | 2021-08-02 | 24372.7 | 3014 | 21358.7 | Y | [5 empty] | 2013-10-10 | Bids awarded
1158 | National Highways Authority Of India | 155597 | Sitarganj-Tanakpur via Khatima (NH-125) Two Laning Highway Project | 1031 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3687.3 | Completed | Engineering, Procurement & Construction | November 2018 | Sitarganj | Uttarakhand | 15 Jan 2010 | Date of announcement | 2017-03-31 | 3687.3 | 2264.2 | 1423.1 | Y | 2018-11-20 | Completed | 2017-09-18 | Y | 428 | 2014-10-09 | Bids awarded
1159 | National Highways Authority Of India | 155597 | Siwan-Madhubani-Sitamarhi-Indo/Nepal border Road Project | 1133 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 40000 | No Information |  |  | Madhubani | Bihar | 15 May 2015 | Date of announcement | 2018-05-25 | 40000 | 40000 | 0 | N
1160 | National Highways Authority Of India | 155597 | Six Lane Bridge over Phalguni River at Kuloor (NH-66) Project | 1868 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 690.2 | Implementation Stalled | Engineering, Procurement & Construction |  | Kuloor (mangalore) | Karnataka | 24 Jul 2018 | Date of announcement | 2020-12-19 | 690.2 | 750 | -59.8 | N | [5 empty] | 2020-12-30 | Bids awarded
1161 | National Highways Authority Of India | 155597 | Six Lane Elevated Road Project (on Kona Expressway to connect Vidyasagar Setu) | 2033 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 8394 | Announced | Engineering, Procurement & Construction | March 2026 | Kolkata | West Bengal | 01 Jan 2016 | Date of announcement | 2023-04-04 | 8394 | 20000 | -11606 | N
1162 | National Highways Authority Of India | 155597 | Six Lane Flyover Near Tangra Town and Six Lane Vehicular Underpass (VUP) Near Mallian Town (NH-03) Project | 2027 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 536.4 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Mallian | Punjab | 01 Jan 2021 | Date of announcement | 2021-02-06 | 536.4 | 536.4 | 0 | N | [5 empty] | 2021-05-28 | Bids awarded
1163 | National Highways Authority Of India | 155597 | Six Lane Flyover and Six Lane Vehicular Underpass (VUP) on Jalandhar-Amritsar Section of NH-03 Project | 2026 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 437.8 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Amritsar | Punjab | 01 Jan 2021 | Date of announcement | 2021-02-17 | 437.8 | 437.8 | 0 | N | [5 empty] | 2021-05-31 | Bids awarded
1164 | National Highways Authority Of India | 155597 | Six Lane Grade Separator Project (Barhi-Hazaribagh NH-20 section) | 1994 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 442.6 | Under Implementation | Engineering, Procurement & Construction |  | Barhi | Jharkhand | 01 Jan 2021 | Date of announcement | 2022-12-21 | 442.6 | 442.6 | 0 | N | [5 empty] | 2021-04-20 | Bids awarded
1165 | National Highways Authority Of India | 155597 | Six Lane Jalandhar Bypass starting from Kahlwan (NH-3) ending at Kang Sahbu (NH-703) via Sarmastpur (NH-44)-Madara (NH-3)-Khajurla (NH-44) Project | 1990 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12633.4 | Under Implementation | Hybrid Annuity |  | Jalandhar | Punjab | 01 Nov 2020 | Date of announcement | 2021-02-01 | 12633.4 | 12080 | 553.4 | Y | [5 empty] | 2021-09-30 | Bids awarded
1166 | National Highways Authority Of India | 155597 | Six Lane Minor Bridge (Paloli Palam), Major Bridge (Moorad) and Carriageway (NH-66) Project | 1661 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2102.1 | Under Implementation | Engineering, Procurement & Construction |  | Moorad | Kerala | 06 Feb 2019 | Date of announcement | 2020-10-12 | 2102.1 | 516.6 | 1585.5 | Y | [5 empty] | 2020-09-17 | Bids awarded
1167 | National Highways Authority Of India | 155597 | Six Lane access controlled Highway from Junction with Jaitpur-Pushta Road-Junction with Sector-62/65 dividing Road on Faridabad-Ballabhgarh Bypass (NH-148NA) Project (Pkg-2) (Delhi-Mumbai Expressway) | 1678 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15458 | Under Implementation | Hybrid Annuity | March 2024 | Jaitpur (dl) | NCT of Delhi | 26 Dec 2018 | Date of announcement | 2019-02-28 | 15458 | 15458 | 0 | N | [5 empty] | 2020-03-05 | Bids awarded
1168 | National Highways Authority Of India | 155597 | Six Lane access controlled Highway from Junction with Sector-62/65 (on Faridabad -Ballabhgarh Bypass) to Junction near KMP E-way with NH-148N Project (Package-3) (Delhi-Mumbai Expressway) | 1679 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9082 | Completed | Hybrid Annuity | April 2023 | Sector-62/65 | Haryana | 26 Dec 2018 | Date of announcement | 2019-02-28 | 9082 | 9082 | 0 | N | 2024-03-31 | Initial completion date | 2023-04-01 | Y | 365 | 2020-03-05 | Bids awarded
1169 | National Highways Authority Of India | 155597 | Six Laning of Gajuwaka-Gangavaram Port (NH-16) & Four Laning of Gangavaram Port to Beach Road Highway Project (Package-II) (Bharatmala) | 1437 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2150 | Announced | Engineering, Procurement & Construction |  | Beach road | Andhra Pradesh | 29 Dec 2017 | Date of announcement | 2017-12-29 | 2150 | 2150 | 0 | N
1170 | National Highways Authority Of India | 155597 | Six Laning of Tuticorin Port Road (section of NH-7A New NH-138) Project | 3014 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1648.2 | Under Implementation | Hybrid Annuity |  | Tuticorin | Tamil Nadu | 01 Jan 2023 | Date of announcement | 2023-02-07 | 1648.2 | 1648.2 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
1171 | National Highways Authority Of India | 155597 | Six lane Capital Region Ring Road (Palatotapada (NH-16) to Kuspangi ( NH-42) | 1756 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 57440 | Under Implementation |  |  | Kuspangi | Odisha | 21 Jun 2019 | Date of announcement | 2022-04-07 | 57440 | 25000 | 32440 | Y
1172 | National Highways Authority Of India | 155597 | Six lane Greenfield connectivity from DND-Faridabad-Ballabhgarh bypass to Jewar International Airport Project | 1943 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 30000 | Under Implementation | Hybrid Annuity | June 2025 | Ballabhgarh | Haryana | 01 Jan 2021 | Date of announcement | 2023-05-19 | 30000 | 21000 | 9000 | Y | [5 empty] | 2022-08-01 | Bids awarded
1173 | National Highways Authority Of India | 155597 | Six-Lane Access-Controlled Spur to Haridwar from Delhi-Saharanpur-Dehradun Economic Corridor Project (Halgoya Village to Badheri Village) | 2024 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 23250 | Under Implementation | Hybrid Annuity |  | Badheri | Uttarakhand | 01 Apr 2021 | Date of announcement | 2021-05-11 | 23250 | 23250 | 0 | N | [5 empty] | 2021-12-24 | Bids awarded
1174 | National Highways Authority Of India | 155597 | Six-Laning of Aurangabad-Gorhar (Aurangabad-Barwa Adda) Road Project | 1231 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10370 | No Information | Build Operate Transfer |  | Aurangabad | Bihar | 01 Apr 2011 | Date of announcement | 2012-03-01 | 10370 | 10370 | 0 | N | [5 empty] | 2012-03-01 | Bids awarded
1175 | National Highways Authority Of India | 155597 | Sohna-Ballabhgarh-Tigaon-Gautam Buddh Nagar-Deota-Sikandrabad Four Laning Highway Project | 1026 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11000 | No Information | Engineering, Procurement & Construction |  | Ballabhgarh | Haryana | 01 Sep 2014 | Date of announcement | 2014-09-09 | 11000 | 11000 | 0 | N
1176 | National Highways Authority Of India | 155597 | Sohna-Gurugram Road near Alipur Village-KMP Expressway Eight Lane Carriageway Project (Package 1 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1612 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19945.2 | Completed | Engineering, Procurement & Construction | February 2023 | Alipur | Haryana | 31 Mar 1998 | Date of announcement | 2021-03-25 | 19945.2 | 11440 | 8505.2 | Y | 2023-02-12 | Completed | 2021-12-31 | Y | 408 | 2019-03-05 | Bids awarded
1177 | National Highways Authority Of India | 155597 | Solan-Kaithlighat (NH-5) (Parwanoo-Shimla Package-II) Two/Four Lane Highway Project | 1067 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11350.8 | Under Implementation | Engineering, Procurement & Construction | November 2023 | Kaithalghat | Himachal Pradesh | 10 Feb 2009 | Date of announcement | 2022-12-31 | 11350.8 | 5053.6 | 6297.2 | Y | 2023-11-30 | Completion expected by | 2021-05-30 | Y | 914 | 2018-03-28 | Bids awarded
1178 | National Highways Authority Of India | 155597 | Sonapur-Guwahati (AS-3) Four-Laning Highway Project | 713 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4920 | Completed | Engineering, Procurement & Construction | August 2019 | Guwahati | Assam | 01 Dec 2003 | Date of announcement | 2011-12-31 | 4920 | 2450 | 2470 | Y | 2019-09-30 | Initial completion date | 2010-12-31 | Y | 3195 | 2005-03-01 | Bids awarded
1179 | National Highways Authority Of India | 155597 | Sonepat-Baghpat Six Lane Expressway Project (Package 1 of Eastern Peripheral Expressway) | 438 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7920 | Completed | Engineering, Procurement & Construction | May 2018 | Baghpat | Uttar Pradesh | 31 Jan 1995 | Date of announcement | 2017-04-30 | 7920 | 7711.8 | 208.2 | Y | 2018-07-31 | Initial completion date | 2009-07-30 | Y | 3288 | 2015-08-30 | Bids awarded
1180 | National Highways Authority Of India | 155597 | Sonepurbigha Village to Junction with NH-22 (Chatra Bypass) near Chatra Four/Six Lane Greenfield Access Control Expressway Project (Package-8 of Varanasi-Kolkata Expressway) | 1981 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 17280 | Under Implementation | Engineering, Procurement & Construction |  | Chatra village | Jharkhand | 01 Aug 2021 | Date of announcement | 2023-05-18 | 17280 | 17280 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
1181 | National Highways Authority Of India | 155597 | Sonpur (Bakarpur)-Manikpur (NH-139 W) Four Lane Highway (Package 2 of Patna (AIIMS)-Bettiah Section) Project | 1901 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8677 | Under Implementation |  | December 2025 | Bakarpur | Bihar | 01 Mar 2021 | Date of announcement | 2023-02-03 | 8677 | 6054.6 | 2622.4 | Y
1182 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 791.4 | No Information |  |  | Icchapuram | Andhra Pradesh | 01 Jun 2001 | Date of announcement | 2003-07-01 | 791.4 | 1501.4 | -710 | N | [5 empty] | 2001-06-30 | Bids awarded
1183 | National Highways Authority Of India | 155597 | Srinagar Bypass (NS-30) Project | 237 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1680 | Completed |  | December 2013 | Srinagar | Jammu & Kashmir | 01 Dec 2002 | Date of announcement | 2002-12-01 | 1680 | 1680 | 0 | N | 2013-12-31 | Completed | 2008-09-30 | Y | 1918
1184 | National Highways Authority Of India | 155597 | Srinagar Four Lane Ring Road (Galander-Sumbel Road) Project | 924 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20126.1 | Under Implementation | Engineering, Procurement & Construction | February 2024 | Galander | Jammu & Kashmir | 01 Sep 2012 | Date of announcement | 2019-12-31 | 20126.1 | 9909.4 | 10216.7 | Y | 2024-02-28 | Completion expected by | 2021-02-28 | Y | 1095 | 2018-02-28 | Bids awarded
1185 | National Highways Authority Of India | 155597 | Srinagar Two Lane Ring Road (Narbal-Wayul Road) Project | 1460 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 6190 | Under Implementation |  | February 2024 | Narbal | Jammu & Kashmir | 01 Sep 2012 | Date of announcement | 2019-07-22 | 6190 | 4480 | 1710 | Y
1186 | National Highways Authority Of India | 155597 | Sriperumbudur-Karaipettai (NH-48) Six Lane Highway (Pkg-1) Project | 1220 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7775.2 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Karaipettai | Tamil Nadu | 22 Aug 2009 | Date of announcement | 2021-07-22 | 7775.2 | 10450 | -2674.8 | N | 2024-03-31 | Completion expected by | 2014-12-31 | Y | 3378 | 2012-06-01 | Bids awarded
1187 | National Highways Authority Of India | 155597 | Start of DSIR Zone-Adhelai Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-4) | 1707 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9646.8 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Adhelai village | Gujarat | 20 Mar 2010 | Date of announcement | 2019-02-25 | 9646.8 | 9646.8 | 0 | N | 2024-03-31 | Completion expected by | 2013-12-31 | Y | 3743 | 2020-10-29 | Bids awarded
1188 | National Highways Authority Of India | 155597 | Start of Kollam Bypass- Kadambattukonam (NH-66) (Old NH-47) Six Lane Highway Project (Bharatmala) | 1894 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30240 | Under Implementation | Hybrid Annuity |  | Kadambattukonam | Kerala | 01 Oct 2019 | Date of announcement | 2022-12-15 | 30240 | 12828.8 | 17411.2 | Y | [5 empty] | 2021-09-14 | Bids awarded
1189 | National Highways Authority Of India | 155597 | Start of Shahjahanpur Bypass to End of Hardoi Bypass (NH-731) Four Lane Highway Project (Package-II of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2067 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 23074.7 | Under Implementation | Hybrid Annuity |  | Hardoi | Uttar Pradesh | 01 Nov 2010 | Date of announcement | 2023-02-03 | 23074.7 | 23074.7 | 0 | N | [5 empty] | 2022-11-29 | Bids awarded
1190 | National Highways Authority Of India | 155597 | Subhash Square-Pardi Octroi Post Four Lane Cement Road Project (on Bhandara Road) | 1059 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 240 | No Information |  |  | Octroi post | Maharashtra | 15 Jan 2015 | Date of announcement | 2015-01-29 | 240 | 240 | 0 | N
1191 | National Highways Authority Of India | 155597 | Subway/LVUP at Adhegaon Junction and Mohol Junction on NH-65 (Pune-Solapur Section) Project | 2028 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 442.6 | Under Implementation | Engineering, Procurement & Construction |  | Adhegaon | Maharashtra | 01 Apr 2021 | Date of announcement | 2022-04-25 | 442.6 | 442.6 | 0 | N
1192 | National Highways Authority Of India | 155597 | Suhagada-Bardiya Amra (NH-148) Four Lane Highway Project (Package-3 of Ujjain-Garoth Section) | 1962 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9520 | Under Implementation | Hybrid Annuity |  | Bardiya amra | Madhya Pradesh | 01 Jan 2019 | Date of announcement | 2022-02-24 | 9520 | 6379.4 | 3140.6 | Y | [5 empty] | 2022-03-07 | Bids awarded
1193 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-I) | 895 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 26283.1 | Under Implementation | Engineering, Procurement & Construction |  | Sultanpur | Uttar Pradesh | 01 Jul 2011 | Date of announcement | 2022-11-14 | 26283.1 | 10275.3 | 16007.8 | Y | [5 empty] | 2015-08-26 | Bids awarded
1194 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-II) | 1074 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 26039.9 | Completed | Engineering, Procurement & Construction | February 2023 | Sultanpur | Uttar Pradesh | 01 Jul 2011 | Date of announcement | 2021-12-16 | 26039.9 | 8152.8 | 17887.1 | Y | 2023-02-01 | Completed | 2018-06-30 | Y | 1677 | 2015-08-26 | Bids awarded
1195 | National Highways Authority Of India | 155597 | Sumdoh-Kaza-Gramphu (NH-505) Two Lane Road Project | 1845 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2000 | Announced |  |  | Gramphu | Himachal Pradesh | 04 Mar 2014 | Date of announcement | 2020-06-14 | 2000 | 2000 | 0 | N
1196 | National Highways Authority Of India | 155597 | Sundar Nagar Four Lane (NH-21) Bypass Project (Part of Kiratpur-Nerchowk Highway) | 1995 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1561.6 | Under Implementation | Engineering, Procurement & Construction |  | Sundar nagar | Himachal Pradesh | 01 Jan 2022 | Date of announcement | 2022-01-13 | 1561.6 | 1561.6 | 0 | N | [5 empty] | 2022-03-31 | Bids awarded
1197 | National Highways Authority Of India | 155597 | Surat (Chalthan)-Atul Highway Project | 37 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4104 | Completed |  | June 2005 | Atul | Gujarat | 31 Oct 1998 | Date of announcement | 2005-04-01 | 4104 | 5046 | -942 | N | 2005-06-30 | Completed | 2003-04-30 | Y | 792
1198 | National Highways Authority Of India | 155597 | Swaroopganj-Bakaria (NH-76&14) Highway Project | 643 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2444.7 | Completed |  | June 2009 | Bakaria | Uttar Pradesh | 30 Dec 2003 | Date of announcement | 2003-12-30 | 2444.7 | 2444.7 | 0 | N
1199 | National Highways Authority Of India | 155597 | Takoli-Kullu Section (NH-21) Four Laning Highway Project (Package-VI of Nerchowk-Kullu stretch) | 1048 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7517.5 | Completed | Engineering, Procurement & Construction | September 2022 | Kullu | Himachal Pradesh | 15 Nov 2014 | Date of announcement | 2017-10-31 | 7517.5 | 4115.1 | 3402.4 | Y | 2022-09-01 | Completed | 2019-07-15 | Y | 1144 | 2016-11-08 | Bids awarded
1200 | National Highways Authority Of India | 155597 | Talaja-Mahuva (NH-8E) (Package-II Bhavnagar-Veraval Section) Four Lane Highway Project | 1927 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6984 | Under Implementation | Hybrid Annuity |  | Mahuva | Gujarat | 03 May 2012 | Date of announcement | 2022-12-17 | 6984 | 8290 | -1306 | N | [5 empty] | 2016-05-23 | Bids awarded
1201 | National Highways Authority Of India | 155597 | Talapady-Chengala (NH-66) Six Lane Highway Project | 1345 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12763.2 | Under Implementation | Hybrid Annuity |  | Chengala | Kerala | 01 Mar 2017 | Date of announcement | 2020-10-29 | 12763.2 | 16752.5 | -3989.3 | N | [5 empty] | 2021-02-24 | Bids awarded
1202 | National Highways Authority Of India | 155597 | Talapady-Karwar Two Lane Road Project | 453 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7800 | No Information |  |  | Karwar | Karnataka | 12 Jun 2007 | Date of announcement | 2020-02-11 | 7800 | 8000 | -200 | N
1203 | National Highways Authority Of India | 155597 | Talasari-Karvad Package-10 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1625 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 19097.4 | Under Implementation | Hybrid Annuity | March 2024 | Karvad | Gujarat | 31 Mar 1998 | Date of announcement | 2022-12-07 | 19097.4 | 11268 | 7829.4 | Y | 2024-03-21 | Completion expected by | 2021-12-31 | Y | 811 | 2021-03-30 | Bids awarded
1204 | National Highways Authority Of India | 155597 | Talcher-Kamakhyanagar Bypass (NH-149 & 53) Four Lane Road Project | 1403 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6144.8 | Under Implementation | Engineering, Procurement & Construction |  | Kamakhyanagar bypass | Odisha | 26 Oct 2017 | Date of announcement | 2019-12-31 | 6144.8 | 7951.8 | -1807 | N | [5 empty] | 2018-01-31 | Bids awarded
1205 | National Highways Authority Of India | 155597 | Talwandi Bhai-Firozpur (NH-05) Four Lane Highway Project | 1418 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3545.1 | Completed | Engineering, Procurement & Construction | February 2022 | Firozpur | Punjab | 01 Mar 2017 | Date of announcement | 2018-05-18 | 3545.1 | 3386.5 | 158.6 | Y | 2022-02-10 | Completed | 2021-01-14 | Y | 392 | 2018-02-28 | Bids awarded
1206 | National Highways Authority Of India | 155597 | Tamil Nadu/Karnataka Border-Bangalore (NH-209) Two/Four Laning Highway Project | 785 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 19583 | Under Implementation | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Bangalore | Karnataka | 19 May 2010 | Date of announcement | 2018-03-24 | 19583 | 6120 | 13463 | Y | [5 empty] | 2016-09-26 | Bids awarded
1207 | National Highways Authority Of India | 155597 | Tamilnadu/Karnataka Border-Hoskote (NH-648) Four/Six Laning Highway Project | 1200 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8000 | Under Implementation | Hybrid Annuity |  | Hoskote | Karnataka | 29 Jul 2016 | Date of announcement | 2020-08-09 | 8000 | 6250 | 1750 | Y | [5 empty] | 2022-03-31 | Bids awarded
1208 | National Highways Authority Of India | 155597 | Tanda-Raibareilly Two Lane Highway Project | 870 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8175.2 | Completed | Engineering, Procurement & Construction | December 2018 | Rae bareli | Uttar Pradesh | 05 Sep 2011 | Date of announcement | 2014-02-06 | 8175.2 | 6920 | 1255.2 | Y | 2018-12-14 | Completed | 2016-01-31 | Y | 1048 | 2014-02-28 | Bids awarded
1209 | National Highways Authority Of India | 155597 | Tangi-Bhubaneshwar (NH-16) Six Laning Highway Project | 1477 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11753 | Completed |  | February 2023 | Bhubaneshwar | Odisha | 01 Jul 2017 | Date of announcement | 2021-02-11 | 11753 | 9668.1 | 2084.9 | Y | 2023-02-01 | Completed | 2021-04-30 | Y | 642 | 2018-03-28 | Bids awarded
1210 | National Highways Authority Of India | 155597 | Tangi-Chhatarpur-Satapada and Konark-Astarang-Naugaon-Paradwip Port-Ratanpur Two/Four Laning Highway Project (BM/18) | 1107 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 27658 | Under Implementation |  |  | Astarang | Odisha | 15 Apr 2015 | Date of announcement | 2021-02-08 | 27658 | 21964.9 | 5693.1 | Y
1211 | National Highways Authority Of India | 155597 | Taran Taran Flyover to Golden Gate Stretch of Jalandhar-Amritsar Section (NH-03) Six Lane Road Project | 2016 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 933.2 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Golden gate | Punjab | 01 Dec 2020 | Date of announcement | 2020-12-26 | 933.2 | 933.2 | 0 | N | [5 empty] | 2021-04-16 | Bids awarded
1212 | National Highways Authority Of India | 155597 | Tatibandh Chowk (NH-6/53) Flyover Project | 1551 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1200 | Under Implementation | Engineering, Procurement & Construction | May 2023 | Tatibandh chowk | Chhattisgarh | 07 Sep 2018 | Date of announcement | 2021-12-13 | 1200 | 886.7 | 313.3 | Y | 2023-05-31 | Completion expected by | 2020-08-31 | Y | 1003 | 2019-10-15 | Bids awarded
1213 | National Highways Authority Of India | 155597 | Tejaji Nagar-Balwara (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package II) (Bharatmala) | 1851 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11628 | Under Implementation | Hybrid Annuity |  | Balwara | Madhya Pradesh | 27 Jul 2016 | Date of announcement | 2022-07-25 | 11628 | 7470 | 4158 | Y | [5 empty] | 2022-03-31 | Bids awarded
1214 | National Highways Authority Of India | 155597 | Telebani-Sambalpur (NH-6) Two/Four Lane Highway Project | 1022 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7128.2 | Completed | Engineering, Procurement & Construction | February 2023 | Sambalpur | Odisha | 15 Mar 2013 | Date of announcement | 2022-07-21 | 7128.2 | 6470 | 658.2 | Y | 2023-02-01 | Completed | 2019-11-30 | Y | 1159 | 2015-12-31 | Bids awarded
1215 | National Highways Authority Of India | 155597 | Tendesara Village to Khatti Village 4/6 Lane Highway Project (Package 1A of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1547 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6952.4 | Under Implementation | Engineering, Procurement & Construction |  | Khatti village | Chhattisgarh | 01 Apr 2017 | Date of announcement | 2018-08-30 | 6952.4 | 6952.4 | 0 | N | [5 empty] | 2022-12-27 | Bids awarded
1216 | National Highways Authority Of India | 155597 | Tetali Junction (NH-216A) Flyover Project | 2064 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 350 | Under Implementation |  | March 2024 | Tetali | Andhra Pradesh | 01 Oct 2021 | Date of announcement | 2022-09-22 | 350 | 350 | 0 | N | [5 empty] | 2022-09-19 | Bids awarded
1217 | National Highways Authority Of India | 155597 | Thalassery-Mahe Bypass (NH-66) Four Laning Highway Project | 1233 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 8830 | Under Implementation | Engineering, Procurement & Construction |  | Mahe bypass | Puducherry | 01 Nov 2011 | Date of announcement | 2022-12-13 | 8830 | 8136.6 | 693.4 | Y | [5 empty] | 2017-09-12 | Bids awarded
1218 | National Highways Authority Of India | 155597 | Thalikulam-Kodungallur (NH-66) Six Lane Highway Project | 1879 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 39950 | Under Implementation | Hybrid Annuity |  | Kodungallur | Kerala | 01 Nov 2020 | Date of announcement | 2022-12-15 | 39950 | 12317 | 27633 | Y | [5 empty] | 2021-09-24 | Bids awarded
1219 | National Highways Authority Of India | 155597 | Thaliparambha-Muzhapilangad (NH-66) Six Lane Highway Project (Bharatmala) | 1803 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 27370 | Under Implementation | Hybrid Annuity |  | Muzhapilangad | Kerala | 01 Jul 2019 | Date of announcement | 2021-07-19 | 27370 | 15183.9 | 12186.1 | Y | [5 empty] | 2021-02-08 | Bids awarded
1220 | National Highways Authority Of India | 155597 | Thanjavur-Pudukottai (NH-226) Two-Laning Highway Project | 667 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2832.7 | Completed | Engineering, Procurement & Construction | October 2017 | Manumadurai | Tamil Nadu | 28 Oct 2009 | Date of announcement | 2016-07-31 | 2832.7 | 1615.1 | 1217.6 | Y | 2017-10-31 | Completed | 2016-11-30 | Y | 335 | 2014-09-12 | Bids awarded
1221 | National Highways Authority Of India | 155597 | Thankassery-Neendakara Road Project | 1747 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4443.8 | No Information |  |  | Neendakara | Kerala | 12 Apr 2018 | Date of announcement | 2018-05-15 | 4443.8 | 4443.8 | 0 | N
1222 | National Highways Authority Of India | 155597 | Tharad-Ahmedabad Six/Eight Lane Greenfield Expressway Project | 2041 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 62000 | Announced | Engineering, Procurement & Construction |  | Ahmedabad | Gujarat | 01 Feb 2022 | Date of announcement | 2023-01-19 | 62000 | 135672.5 | -73672.5 | N
1223 | National Highways Authority Of India | 155597 | Thevara-Kundanoor Willingdon Bridge Project | 20 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 530 | Completed |  | June 1999 | Kundanoor | Kerala | 01 Mar 1997 | Date of announcement | 1999-04-01 | 530 | 355.8 | 174.2 | Y | 1999-06-15 | Completed | 1998-03-31 | Y | 441
1224 | National Highways Authority Of India | 155597 | Thirumayam-Manamadurai (NH-226) Two Laning Highway Project | 998 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 4011.1 | Completed | Engineering, Procurement & Construction | October 2017 | Manamadurai | Tamil Nadu | 01 Jan 2014 | Date of announcement | 2014-04-30 | 4011.1 | 2525.3 | 1485.8 | Y | 2017-10-31 | Completed | 2017-01-31 | Y | 273 | 2014-04-30 | Bids awarded
1225 | National Highways Authority Of India | 155597 | Thiruvananthapuram International Airport-NH-66 Bypass Connectivity Project | 1193 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11208 | Completed |  | October 2020 | Thiruvananthapuram | Kerala | 30 Jun 2016 | Date of announcement | 2020-10-13 | 11208 | 11208 | 0 | N | 2021-01-31 | Initial completion date | 2020-10-13 | Y | 110
1226 | National Highways Authority Of India | 155597 | Thondapalli to Farukhanagar (NS/9) Project | 227 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 280 | Completed | Engineering, Procurement & Construction | January 2003 | Farukhnagar | Telangana | 31 Jan 1999 | Date of announcement | 2002-01-01 | 280 | 280 | 0 | N | 2003-01-31 | Completed | 2001-06-30 | Y | 580 | 1999-05-18 | Bids awarded
1227 | National Highways Authority Of India | 155597 | Thondupally-Kothur (NH-44) Six Lane Highway Project (Hyderabad-Bangalore Section) | 1960 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5420 | Under Implementation | Engineering, Procurement & Construction |  | Kothur | Telangana | 01 Feb 2022 | Date of announcement | 2022-04-29 | 5420 | 3993.3 | 1426.7 | Y | [5 empty] | 2022-11-11 | Bids awarded
1228 | National Highways Authority Of India | 155597 | Thopurghar section (NS/14) Highway Project | 228 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 337.4 | Completed | Engineering, Procurement & Construction | April 2002 | Thoppur ghat | Tamil Nadu | 01 Nov 1999 | Date of announcement | 1999-11-01 | 337.4 | 337.4 | 0 | N | 2002-04-30 | Completed | 2001-09-30 | Y | 212 | 1999-12-15 | Bids awarded
1229 | National Highways Authority Of India | 155597 | Thopurghat to Thumpipadi (NS-25/TN) Road Project | 416 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 925.4 | Completed |  | January 2010 | Thoppur ghat | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2009-07-01 | 925.4 | 500 | 425.4 | Y | 2010-01-31 | Completed | 2009-03-31 | Y | 306
1230 | National Highways Authority Of India | 155597 | Thorapalli Agraharam-Jittandahalli section (NH-844) Four Lane Highway Project (Package 2 of Hosur-Dharmapuri) (Bharatmala) | 1688 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10810 | Under Implementation | Hybrid Annuity | December 2023 | Jittandahalli | Tamil Nadu | 11 Jul 2018 | Date of announcement | 2020-03-14 | 10810 | 6960.6 | 3849.4 | Y | [5 empty] | 2020-03-20 | Bids awarded
1231 | National Highways Authority Of India | 155597 | Three Lane Bridge Across River Tapi (NH-8) Project | 11 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 650 | No Information |  |  | Gujarat | Gujarat | 09 May 2002 | Bids invited | 2009-07-01 | 650 | 300 | 350 | Y
1232 | National Highways Authority Of India | 155597 | Thumpipadi-Salem Highway Project | 331 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 996.6 | Completed |  | March 2010 | Salem | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2008-07-31 | 996.6 | 824.9 | 171.7 | Y | 2010-06-30 | Initial completion date | 2004-10-31 | Y | 2068
1233 | National Highways Authority Of India | 155597 | Thuravoor Thekku-Paravoor (NH-66) Six Lane Highway Project (Bharatmala) | 1895 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 28880 | Under Implementation | Engineering, Procurement & Construction |  | Paravoor | Kerala | 01 Jan 2020 | Date of announcement | 2022-12-15 | 28880 | 12480.8 | 16399.2 | Y | [5 empty] | 2021-11-15 | Bids awarded
1234 | National Highways Authority Of India | 155597 | Tikamgarh-Orchha (NH-539) Two Lane Road Project | 2083 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7410 | Under Implementation |  |  | Orchha | Madhya Pradesh | 01 Apr 2022 | Date of announcement | 2022-12-02 | 7410 | 7410 | 0 | N
1235 | National Highways Authority Of India | 155597 | Tindivanam-Krishnagiri (NH-77) Two Laning Highway Project | 1613 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5620 | Under Implementation | Build Operate Transfer | June 2023 | Krishnagiri | Tamil Nadu | 28 Oct 2009 | Date of announcement | 2017-10-31 | 5620 | 7533.8 | -1913.8 | N | 2023-06-30 | Completion expected by | 2012-11-30 | Y | 3864 | 2011-05-31 | Bids awarded
1236 | National Highways Authority Of India | 155597 | Tindivanam-Krishnagiri(NH-66) Four-Laning Road Project | 570 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10750 | No Information | Build Operate Transfer |  | Krishnagiri | Tamil Nadu | 04 Mar 2009 | Date of announcement | 2009-03-04 | 10750 | 10750 | 0 | N
1237 | National Highways Authority Of India | 155597 | Tindivanam-Ulundurpet (Pkg -VI-A) Highway Project | 417 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11308 | Completed | Build Operate Transfer | June 2009 | Tindivanam | Tamil Nadu | 18 Oct 2006 | Financial closure achieved | 2009-06-30 | 11308 | 8280 | 3028 | Y | 2009-06-30 | Completed | 2009-03-31 | Y | 91
1238 | National Highways Authority Of India | 155597 | Tiruchi Road Stock Exchange Building To Narasimhanaicken Palayam Four Laning Project | 779 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 496.9 | Completed |  | January 2012 | Narashimanaickenpalayam | Tamil Nadu | 01 Apr 2010 | Date of announcement | 2010-04-01 | 496.9 | 496.9 | 0 | N | 2012-06-30 | Initial completion date | 2010-05-31 | Y | 761
1239 | National Highways Authority Of India | 155597 | Tiruchi-Karur (NH-67) Road Over Bridge Project | 526 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 277.9 | Completed |  | January 2009 | Karur | Tamil Nadu | 03 Dec 2008 | Date of announcement | 2009-01-01 | 277.9 | 241.9 | 36 | Y | 2009-01-30 | Initial completion date | 2009-01-09 | N
1240 | National Highways Authority Of India | 155597 | Tiruchy-Karur Four Lane Highway Project (Bharatmala) | 1604 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 5160 | Under Implementation |  |  | Karur | Tamil Nadu | 01 Oct 2018 | Date of announcement | 2020-08-09 | 5160 | 5160 | 0 | N
1241 | National Highways Authority Of India | 155597 | Tirupur Industrial Cluster (Coimbatore)-Enayam Expressway Project | 1738 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 130000 | No Information |  |  | Enayam | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2016-06-03 | 130000 | 130000 | 0 | N
1242 | National Highways Authority Of India | 155597 | Tirupur Road Widening Project | 14 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Renovation & Modernisation | 24.9 | No Information |  |  | Tirupur | Tamil Nadu | 01 Jun 1997 | Date of announcement | 1997-06-01 | 24.9 | 24.9 | 0 | N
1243 | National Highways Authority Of India | 155597 | Tonk-Sawaimadhopur (NH-116) Two-Laning Highway Project | 1491 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3203 | Completed | Engineering, Procurement & Construction | October 2019 | Sawai madhopur | Rajasthan | 01 Mar 2016 | Date of announcement | 2017-03-31 | 3203 | 3176 | 27 | Y | 2019-10-15 | Completed | 2019-01-31 | Y | 257 | 2016-08-19 | Bids awarded
1244 | National Highways Authority Of India | 155597 | Tori Level Crossing (NH-99) ROB Project | 1556 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 430 | Under Implementation |  |  | Tori railway station | Jharkhand | 21 Sep 2018 | Date of announcement | 2021-04-04 | 430 | 430 | 0 | N
1245 | National Highways Authority Of India | 155597 | Tovaramkurchi-Madurai (Package-VIIB) Highway Project | 495 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 3040 | Completed |  | December 2009 | Madurai | Tamil Nadu | 01 Apr 2000 | Date of announcement | 2009-12-31 | 3040 | 2630 | 410 | Y | 2009-12-31 | Initial completion date | 2009-03-31 | Y | 275
1246 | National Highways Authority Of India | 155597 | Trichy Bypass-Tovaramkurchi (Package-VII A) Highway Project | 407 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2863 | Completed |  | April 2010 | Tiruchi | Tamil Nadu | 31 Dec 2003 | Date of announcement | 2010-02-28 | 2863 | 2610 | 253 | Y | 2010-04-30 | Completed | 2009-06-30 | Y | 304
1247 | National Highways Authority Of India | 155597 | Trichy-Dindigul (NH-45) Highway Project | 446 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6000 | Completed | Build Operate Transfer | January 2012 | Dindigul | Tamil Nadu | 01 Feb 2007 | Cabinet Committee on Economic Affairs (CCEA) approval received | 2012-01-11 | 6000 | 5760 | 240 | Y | 2012-01-11 | Completed | 2010-07-31 | Y | 529
1248 | National Highways Authority Of India | 155597 | Tumakuru (NH-206)-Honnavar Port Two to Four Lane Road Project (Port Connectivity) | 1728 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5000 | No Information |  |  | Honnavar port | Karnataka | 01 Dec 2016 | Date of announcement | 2019-01-31 | 5000 | 5000 | 0 | N
1249 | National Highways Authority Of India | 155597 | Tumkur Bypass (NH-4) Highway Project | 117 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 830 | Completed |  | December 2010 | Tumkur | Karnataka | 01 Jun 2001 | Date of announcement | 2002-01-01 | 830 | 520 | 310 | Y | 2010-12-31 | Completed | 2004-03-31 | Y | 2466
1250 | National Highways Authority Of India | 155597 | Tumkur Road Six-Lane Elevated Expressway Project or Nelamangala Cross-Jalahalli Cross Highway Project | 429 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7500 | Completed |  | December 2010 | Tumkur | Karnataka | 09 Jun 2006 | Date of announcement | 2010-12-11 | 7500 | 7200 | 300 | Y | 2010-12-11 | Completed | 2010-08-31 | Y | 102
1251 | National Highways Authority Of India | 155597 | Tupudana-Itre Four Lane Road (NH-75E) (NH-20) Project (Package-1 of Ranchi-Jaintgarh-Paradip Economic Corridor) | 2124 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 17900 | Announced |  |  | Itre | Jharkhand | 01 Mar 2021 | Date of announcement | 2022-12-21 | 17900 | 17900 | 0 | N
1252 | National Highways Authority Of India | 155597 | Tuticorin-Palayamkottai Four Lane Road Project | 854 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2250 | Completed | Build Operate Transfer | April 2013 | Palayamkottai | Tamil Nadu | 01 Dec 2004 | Date of announcement | 2012-11-30 | 2250 | 2310 | -60 | N | 2013-04-30 | Completed | 2012-05-31 | Y | 334
1253 | National Highways Authority Of India | 155597 | Two Lane Bridge across Kosi River (NH-527 A) Project (Umagaon-Saharsa Package-IV) (Bharatmala) | 1637 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11010 | Under Implementation | Engineering, Procurement & Construction | August 2023 | Bakaur | Bihar | 21 Dec 2018 | Date of announcement | 2023-01-19 | 11010 | 9842.9 | 1167.1 | Y | 2025-07-31 | Initial completion date | 2022-11-30 | Y | 974 | 2019-10-01 | Bids awarded
1254 | National Highways Authority Of India | 155597 | Two Laning Parallel Road to Indo-Nepal Project | 1489 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 25027.2 | Under Implementation |  | December 2024 | Araria | Bihar | 10 Jan 2010 | Date of announcement | 2022-02-28 | 25027.2 | 26000 | -972.8 | N | 2024-12-31 | Completion expected by | 2016-03-30 | Y | 3198
1255 | National Highways Authority Of India | 155597 | Two lane composite ROB (NH 13) of Chitradurga Shimoga Section in Lieu of LC No.46 Project | 1869 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 439 | Under Implementation | Engineering, Procurement & Construction |  | Chitradurga | Karnataka | 01 Nov 2020 | Date of announcement | 2020-12-19 | 439 | 439 | 0 | N | [5 empty] | 2022-07-28 | Bids awarded
1256 | National Highways Authority Of India | 155597 | UP/Bihar Border-Kasia (LMNHP-8) Highway Project | 714 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3900 | Completed |  | May 2012 | Kasia | Uttar Pradesh | 01 Dec 2003 | Date of announcement | 2011-12-31 | 3900 | 2270 | 1630 | Y | 2012-05-30 | Completed | 2010-12-31 | Y | 516
1257 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-I) | 976 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6008.5 | Completed | Engineering, Procurement & Construction | July 2018 | Barwala | Haryana | 30 Apr 2009 | Date of announcement | 2015-05-19 | 6008.5 | 3890 | 2118.5 | Y | 2018-07-15 | Completed | 2014-09-30 | Y | 1384 | 2012-03-26 | Bids awarded
1258 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-II) | 1003 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5623.4 | Completed | Engineering, Procurement & Construction | June 2018 | Barwala | Haryana | 30 Apr 2009 | Date of announcement | 2015-05-19 | 5623.4 | 3377 | 2246.4 | Y | 2018-06-10 | Completed | 2014-09-30 | Y | 1349 | 2012-03-26 | Bids awarded
1259 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-III) | 1043 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2070 | Completed | Engineering, Procurement & Construction | June 2020 | Barwala | Haryana | 30 Apr 2009 | Date of announcement | 2017-10-31 | 2070 | 3010 | -940 | N | 2020-06-30 | Completed | 2014-09-30 | Y | 2100 | 2012-03-26 | Bids awarded
1260 | National Highways Authority Of India | 155597 | UP/Haryana Border-Rohna (Package-I) NH-334B Four Laning Highway Project (Meerut to Jhajjar) | 1286 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10200 | Completed | Hybrid Annuity | April 2022 | Bahalgarh | Haryana | 01 May 2017 | Date of announcement | 2021-03-25 | 10200 | 12636.5 | -2436.5 | N | 2022-04-04 | Completed | 2022-01-31 | Y | 63 | 2019-02-28 | Bids awarded
1261 | National Highways Authority Of India | 155597 | Udai Pole-Court Gate (NH-927A) Elevated Road Project | 1478 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1300 | Shelved | Engineering, Procurement & Construction |  | Court gate | Rajasthan | 01 Apr 2008 | Date of announcement | 2018-10-16 | 1300 | 1148.9 | 151.1 | Y
1262 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2260.5 | Completed | Engineering, Procurement & Construction | March 2005 | Kesariaji | Rajasthan | 01 Mar 2001 | Date of announcement | 2002-01-01 | 2260.5 | 1920 | 340.5 | Y | 2005-03-31 | Completed | 2004-03-31 | Y | 365 | 2001-10-20 | Bids awarded
1263 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Udaipur-Kesariaji (UG-I)) Highway Project | 130 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2459 | Completed | Engineering, Procurement & Construction | January 2004 | Kesariaji | Rajasthan | 01 Sep 2001 | Date of announcement | 2001-09-01 | 2459 | 2459 | 0 | N | 2004-03-31 | Initial completion date | 2004-01-31 | Y | 60 | 2001-10-15 | Bids awarded
1264 | National Highways Authority Of India | 155597 | Udaipura-Bhogu (NH-75) Four Lane Highway Project (Package-2) | 2050 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14370 | Under Implementation |  |  | Bhogu | Jharkhand | 01 Apr 2018 | Date of announcement | 2023-03-23 | 14370 | 14370 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
1265 | National Highways Authority Of India | 155597 | Udarband-Harangajo Highway Project | 275 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1550 | No Information |  |  | Harangajo | Assam | 01 Dec 2003 | Date of announcement | 2010-01-01 | 1550 | 1550 | 0 | N
1266 | National Highways Authority Of India | 155597 | Umagaon-Basopatti-Kalauhi-Saharghat-Benipatti-Rahika-Pokhrauni-Madubani-Rampatti-Bideshwarsthan-Awam-Loufa-Bheja-Supaul-Saharsa Two Lane Port Connectivity Project | 1558 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 50000 | Under Implementation | Build Operate Transfer |  | Awam | Bihar | 03 Feb 2016 | Date of announcement | 2018-05-25 | 50000 | 50000 | 0 | N | [5 empty] | 2022-03-29 | Bids awarded
1267 | National Highways Authority Of India | 155597 | Umred-Nagbhid-Bramhapur-Armori (NH-353D) Two Lane Highway Project | 1686 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4620.8 | Under Implementation |  |  | Armori | Maharashtra | 08 Jan 2016 | Date of announcement | 2016-01-08 | 4620.8 | 4620.8 | 0 | N
1268 | National Highways Authority Of India | 155597 | Una-Kodinar (NH-8E) (Package-V Bhavnagar-Veraval Section) Four Lane Highway Project | 1016 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7630.8 | Under Implementation | Hybrid Annuity |  | Kodinar | Gujarat | 03 May 2012 | Date of announcement | 2016-05-26 | 7630.8 | 8210 | -579.2 | N | [5 empty] | 2016-05-26 | Bids awarded
1269 | National Highways Authority Of India | 155597 | Uncha-Nagla-Khanuawa-Roppas-Dholpur (NH-123) Two Laning Highway Project | 1009 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2759 | Completed | Engineering, Procurement & Construction | October 2019 | Dholpur | Rajasthan | 15 Jul 2011 | Date of announcement | 2014-01-30 | 2759 | 2759 | 0 | N | 2019-10-01 | Completed | 2018-02-28 | Y | 580 | 2015-08-31 | Bids awarded
1270 | National Highways Authority Of India | 155597 | Uniara-Nainwa-Hindoli-Jahajpur-Shahpura-Gulabpura (NH-148D) Two Lane Road Project | 932 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7172 | Completed | Engineering, Procurement & Construction | June 2022 | Gulabpura | Rajasthan | 10 Sep 2012 | Date of announcement | 2018-02-28 | 7172 | 5707.4 | 1464.6 | Y | 2022-06-30 | Completed | 2017-10-30 | Y | 1704 | 2013-11-20 | Bids awarded
1271 | National Highways Authority Of India | 155597 | Up-gradation of B.T Road (Burmah Shell area to Security Gate at Kakinada Anchorage port) Project | 1378 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 150 | Completed |  | May 2018 | Kakinada | Andhra Pradesh | 01 Apr 2016 | Date of announcement | 2016-06-03 | 150 | 150 | 0 | N
1272 | National Highways Authority Of India | 155597 | Upgradation of Bhangbar-Kangra Bypass (NH-88) (New NH-303,503) Four Lane Highway Project (Package-VB of Shimla-Mataur Highway) | 1905 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13230 | Under Implementation |  |  | Bhangbar (ranital) | Himachal Pradesh | 01 Jan 2021 | Date of announcement | 2021-06-24 | 13230 | 12959.8 | 270.2 | Y | [5 empty] | 2021-04-12 | Bids awarded
1273 | National Highways Authority Of India | 155597 | Upgradation of Hinterland Road from Naidupeta-Krishnagiri Project | 1719 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30000 | No Information |  |  | Krishnagiri | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2016-07-01 | 30000 | 30000 | 0 | N
1274 | National Highways Authority Of India | 155597 | Upgradation of Multai-Seoni section & Narsinghpur-Saoner Section including Chhindwara Town Ring Road Project | 810 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15601.5 | Completed | Engineering, Procurement & Construction | March 2015 | Chhindwara | Madhya Pradesh | 07 Feb 2010 | Date of announcement | 2012-03-31 | 15601.5 | 14122.7 | 1478.8 | Y | 2015-03-31 | Completed | 2013-06-30 | Y | 639 | 2010-10-14 | Bids awarded
1275 | National Highways Authority Of India | 155597 | Upgradation of Old NH-6 (NH-53) Four Lane Highway Project (Khamgaon City) | 1449 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 522.5 | Completed | Engineering, Procurement & Construction | February 2021 | Khamgaon | Maharashtra | 18 Dec 2017 | Date of announcement | 2018-10-12 | 522.5 | 706.8 | -184.3 | N | 2021-02-18 | Completed | 2019-08-27 | Y | 541 | 2018-05-31 | Bids awarded
1276 | National Highways Authority Of India | 155597 | Upgradation of Two Laning of Sriganganagar to Raisinghnagar (NH-911) Highway Project | 1888 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 6703.8 | Under Implementation | Hybrid Annuity |  | Raisinghnagar | Rajasthan | 01 Jan 2021 | Date of announcement | 2022-06-27 | 6703.8 | 6446.1 | 257.7 | Y | [5 empty] | 2021-10-29 | Bids awarded
1277 | National Highways Authority Of India | 155597 | Urukunnu-Kadampattukonam Four/Six Lane Economic Corridor Project | 2040 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 27410 | Announced |  |  | Kadampattukonam | Kerala | 01 Jan 2022 | Date of announcement | 2022-03-16 | 27410 | 27410 | 0 | N
1278 | National Highways Authority Of India | 155597 | Vadape-Thane (NH-848) Six/Eight Laning Highway Project | 1941 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 11830 | Under Implementation | Hybrid Annuity | May 2023 | Thane | Maharashtra | 05 Aug 2016 | Date of announcement | 2018-03-29 | 11830 | 12437.5 | -607.5 | N | 2023-05-31 | Completion expected by | 2020-03-31 | Y | 1156 | 2018-03-29 | Bids awarded
1279 | National Highways Authority Of India | 155597 | Vadodara-Bharuch (NH-8) Six-Laning Highway Project | 430 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7898.4 | Completed | Build Operate Transfer | September 2009 | Bharuch | Gujarat | 19 Jun 2006 | Date of announcement | 2009-07-01 | 7898.4 | 7500 | 398.4 | Y | 2009-09-09 | Completed | 2009-07-30 | Y | 41
1280 | National Highways Authority Of India | 155597 | Vadodara-Surat (NH-8) Six-Laning Highway (Four-lane Bridge over Narmada River in Bharuch along with Six-Lane Approach Roads) Project (Extra Dosed Bridge) | 901 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5031.6 | Completed | Design, Build, Finance, Operate and Transfer (Toll) basis | February 2020 | Surat | Gujarat | 17 Oct 2009 | Date of announcement | 2013-12-26 | 5031.6 | 5092.9 | -61.3 | N | 2020-02-06 | Completed | 2014-12-31 | Y | 1863 | 2012-05-01 | Bids awarded
1281 | National Highways Authority Of India | 155597 | Vakalapudi Light House-Uppada-Annavaram (NH-516F) Four Lane Access controlled Highway Project | 2061 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13270 | Under Implementation | Hybrid Annuity |  | Annavaram | Andhra Pradesh | 01 Apr 2022 | Date of announcement | 2022-09-22 | 13270 | 13270 | 0 | N | [5 empty] | 2023-03-31 | Bids awarded
1282 | National Highways Authority Of India | 155597 | Vanavolu-Vankarakunta Four/Six Lane Greenfield Expressway Project (Package-2 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1974 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 60016 | Under Implementation | Hybrid Annuity | March 2026 | Vanavolu | Andhra Pradesh | 01 Aug 2021 | Date of announcement | 2022-01-25 | 60016 | 60016 | 0 | N | [5 empty] | 2023-01-31 | Bids awarded
1283 | National Highways Authority Of India | 155597 | Varadharajula-Kumarajapet (NH-716B) Six Laning Expressway Project (Package-I of Chittoor-Thatchur Expressway) | 1638 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 14848.3 | Under Implementation | Hybrid Annuity |  | Kumarajapet | Andhra Pradesh | 01 Apr 2018 | Date of announcement | 2022-02-17 | 14848.3 | 14848.3 | 0 | N | [5 empty] | 2021-08-31 | Bids awarded
1284 | National Highways Authority Of India | 155597 | Varanasi (Kashi) Intermodal Station Project | 1458 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 30000 | Announced | Hybrid Annuity |  | Varanasi | Uttar Pradesh | 01 Jan 2017 | Date of announcement | 2018-03-23 | 30000 | 30000 | 0 | N
1285 | National Highways Authority Of India | 155597 | Varanasi (NH-29) Four Laning Bypass (Phase 2) Project (Package-II) | 1327 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9727.7 | Completed | Hybrid Annuity | December 2022 | Varanasi | Uttar Pradesh | 20 Aug 2017 | Date of announcement | 2020-02-29 | 9727.7 | 10573.3 | -845.6 | N | 2023-03-31 | Initial completion date | 2022-12-31 | Y | 90 | 2018-06-11 | Bids awarded
1286 | National Highways Authority Of India | 155597 | Varanasi (NH-56) Four Laning Bypass (Phase 2) Project (Package-I) | 1328 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4523.5 | Completed | Hybrid Annuity | February 2019 | Varanasi | Uttar Pradesh | 20 Aug 2017 | Date of announcement | 2018-01-31 | 4523.5 | 4861.2 | -337.7 | N | [5 empty] | 2018-06-30 | Bids awarded
1287 | National Highways Authority Of India | 155597 | Varanasi Ring Road (NH-31) Project (Varanasi-Gorakhpur NH-29) | 910 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 15000 | Under Implementation | Engineering, Procurement & Construction | February 2024 | Varanasi | Uttar Pradesh | 15 Jan 2000 | Date of announcement | 2018-03-05 | 15000 | 10000 | 5000 | Y | 2024-02-28 | Completion expected by | 2018-05-31 | Y | 2099 | 2018-01-13 | Bids awarded
1288 | National Highways Authority Of India | 155597 | Varanasi Ring Road (Near Rewasa Village) to Chandauli-Chainpur Road (Near Khainti Village) Four/Six Lane Greenfield Access Control Expressway Project (Package-1 of Varanasi-Kolkata Expressway) | 1983 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 9940.3 | Under Implementation | Hybrid Annuity |  | Chainpur | Uttar Pradesh | 01 Oct 2021 | Date of announcement | 2023-03-29 | 9940.3 | 9940.3 | 0 | N | [5 empty] | 2023-03-29 | Bids awarded
1289 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Dehri on-sone--Aurangabad) Highway Project | 156 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2426.1 | Completed | Engineering, Procurement & Construction | November 2005 | Aurangabad | Bihar | 31 Jan 2001 | Date of announcement | 2003-01-01 | 2426.1 | 2850 | -423.9 | N | 2005-11-30 | Completed | 2004-06-30 | Y | 518 | 2001-02-16 | Bids awarded
1290 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Mohania-Sasaram) Highway Project | 154 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2305.5 | Completed | Engineering, Procurement & Construction | March 2006 | Mohania | Bihar | 31 Jan 2001 | Date of announcement | 2002-01-01 | 2305.5 | 2300 | 5.5 | Y | 2006-03-31 | Completed | 2004-12-31 | Y | 455 | 2001-02-07 | Bids awarded
1291 | National Highways Authority Of India | 155597 | Varanasi-Dagmagpur (NH-7) Four Lane Highway Project (Package-I) | 1414 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12482.6 | Completed | Engineering, Procurement & Construction | September 2022 | Dagmagpur | Uttar Pradesh | 01 Apr 2016 | Date of announcement | 2021-08-02 | 12482.6 | 8719.8 | 3762.8 | Y | 2022-09-29 | Completed | 2020-09-30 | Y | 729 | 2018-02-28 | Bids awarded
1292 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-24) Four Laning Highway (Package-IV Amilla Village-Gorakhpur) Project | 1051 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 30418.3 | Under Implementation | Engineering, Procurement & Construction |  | Amilla village | Uttar Pradesh | 15 Oct 2014 | Date of announcement | 2022-12-14 | 30418.3 | 13513.2 | 16905.1 | Y | [5 empty] | 2016-03-04 | Bids awarded
1293 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-II from Sandah-Birnon) Project | 1049 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 34218.4 | Completed | Engineering, Procurement & Construction | January 2022 | Birnon village | Uttar Pradesh | 15 Sep 2014 | Date of announcement | 2021-08-05 | 34218.4 | 17031.6 | 17186.8 | Y | 2022-01-04 | Completed | 2019-05-31 | Y | 949 | 2016-03-31 | Bids awarded
1294 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-III Birnon Village-Amilla Village) Project | 1050 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 38051.8 | Under Implementation | Engineering, Procurement & Construction |  | Amilla village | Uttar Pradesh | 15 Oct 2014 | Date of announcement | 2022-12-14 | 38051.8 | 13446 | 24605.8 | Y | [5 empty] | 2016-03-04 | Bids awarded
1295 | National Highways Authority Of India | 155597 | Varanasi-Mohania (GTRIP/IV-A) Highway Project | 153 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4679.3 | Completed |  | September 2010 | Mohania | Bihar | 01 Jun 2001 | Date of announcement | 2009-04-01 | 4679.3 | 3080 | 1599.3 | Y | 2010-10-31 | Initial completion date | 2004-11-30 | Y | 2161
1296 | National Highways Authority Of India | 155597 | Vashista River Bridge Project | 173 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1002.5 | No Information |  |  | Athili canal | Andhra Pradesh | 15 Aug 2001 | Date of announcement | 2001-09-01 | 1002.5 | 1002.5 | 0 | N | [5 empty] | 2001-08-20 | Bids awarded
1297 | National Highways Authority Of India | 155597 | Vehicular Underpasses at Kalabadia Chowk and Kuliana Village Road in Balasore-Baripada-Jharpokharia Section of NH-5 Project | 1840 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 255.2 | Under Implementation | Engineering, Procurement & Construction |  | Kalabadia chowk | Odisha | 01 May 2020 | Date of announcement | 2020-05-16 | 255.2 | 255.2 | 0 | N | [5 empty] | 2021-10-06 | Bids awarded
1298 | National Highways Authority Of India | 155597 | Vejalka Village-Start of DSIR Zone (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-3) | 1706 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 7443.8 | Under Implementation | Engineering, Procurement & Construction | March 2024 | Dsir zone | Gujarat | 20 Mar 2010 | Date of announcement | 2018-12-28 | 7443.8 | 7443.8 | 0 | N | 2024-03-31 | Completion expected by | 2013-12-31 | Y | 3743 | 2020-10-26 | Bids awarded
1299 | National Highways Authority Of India | 155597 | Vellora Square (Balasore and Kharagpur) (NH-60) Underpass Project | 1428 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 111.1 | Under Implementation | Engineering, Procurement & Construction |  | Balasore | Odisha | 01 Dec 2017 | Date of announcement | 2021-06-07 | 111.1 | 111.1 | 0 | N | [5 empty] | 2021-06-07 | Bids awarded
1300 | National Highways Authority Of India | 155597 | Vengalam-Kuttipuram (NH-66) Four Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 539 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 15785.9 | Under Implementation | Engineering, Procurement & Construction | December 2025 | Kuttipuram | Kerala | 21 Nov 2008 | Date of announcement | 2009-01-01 | 15785.9 | 11084.7 | 4701.2 | Y | 2025-12-31 | Completion expected by | 2018-08-30 | Y | 2680 | 2009-08-31 | Bids awarded
1301 | National Highways Authority Of India | 155597 | Verka Chowk to Attari-Wagha Border Four-Laning Road Project | 783 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2058.8 | Completed |  | June 2010 | Punjab | Punjab | 26 Oct 2006 | Date of announcement | 2006-10-26 | 2058.8 | 2058.8 | 0 | N | 2010-06-15 | Initial completion date | 2010-06-15 | N |  | 2007-12-18 | Bids awarded
1302 | National Highways Authority Of India | 155597 | Vijayapura Road (NH)-Anchatageri Bypass Road Project | 1315 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2480 | No Information |  |  | Anchatageri | Karnataka | 04 Jul 2017 | Date of announcement | 2017-07-04 | 2480 | 2480 | 0 | N
1304 | National Highways Authority Of India | 155597 | Vijayawada Six Lane Bypass Project (Chinna Autupalli-Gollapudi & Gollapudi-Chinnakakani Section) (Vijayawada-Gundugolanu section) | 1510 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 28250 | Under Implementation | Hybrid Annuity | April 2025 | Gundugolanu | Andhra Pradesh | 02 Jan 2018 | Date of announcement | 2020-10-04 | 28250 | 28250 | 0 | N | 2025-04-14 | Completion expected by | 2022-12-31 | Y | 835 | 2020-03-11 | Bids awarded
1305 | National Highways Authority Of India | 155597 | Vijayawada-Chilkaluripet (Package IV) Highway Project | 177 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 580 | Completed | Engineering, Procurement & Construction | May 2002 | Chilkaluripet | Andhra Pradesh | 01 Apr 1999 | Date of announcement | 2002-01-01 | 580 | 115.2 | 464.8 | Y | 2002-05-31 | Initial completion date | 2002-05-31 | N |  | 1999-05-15 | Bids awarded
1306 | National Highways Authority Of India | 155597 | Vijayawada-Elluru-Rajamundri NH-5 road project | 528 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 26580 | No Information | Build Operate Transfer Toll |  | Eluru | Andhra Pradesh | 21 Nov 2008 | Date of announcement | 2009-04-01 | 26580 | 24266.5 | 2313.5 | Y
1307 | National Highways Authority Of India | 155597 | Vijayawada-Machilipatnam (NH-65) Four-Laning Highway Project (Bharatmala) | 990 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 14620 | Completed | Engineering, Procurement & Construction | November 2019 | Machilipatnam | Andhra Pradesh | 09 Sep 2004 | Date of announcement | 2017-10-31 | 14620 | 3000 | 11620 | Y | 2019-11-13 | Completed | 2014-08-01 | Y | 1930 | 2012-01-27 | Bids awarded
1308 | National Highways Authority Of India | 155597 | Vijayawada-Rajamundry Section (near Eluru) HIghway Project | 46 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 190 | Completed | Engineering, Procurement & Construction | March 2002 | Rajahmundhry | Andhra Pradesh | 01 Dec 1998 | Date of announcement | 2002-01-01 | 190 | 200 | -10 | N | [5 empty] | 2000-06-01 | Bids awarded
1309 | National Highways Authority Of India | 155597 | Vijaypur-Pathankot Highway Project | 306 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 3593.6 | Completed | Engineering, Procurement & Construction | May 2014 | Pathankot | Punjab | 01 Dec 2003 | Date of announcement | 2009-04-01 | 3593.6 | 3593.6 | 0 | N | 2014-05-31 | Completed | 2009-06-30 | Y | 1796
1310 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageII) Highway Project | 175 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 800 | Completed | Engineering, Procurement & Construction | January 2003 | Chilkaluripet | Andhra Pradesh | 01 Mar 1999 | Date of announcement | 2002-01-01 | 800 | 1280 | -480 | N | 2003-01-31 | Completed | 2002-03-31 | Y | 306 | 1999-03-15 | Bids awarded
1311 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageIII) Highway Project | 176 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 680 | Completed | Engineering, Procurement & Construction | January 2003 | Chilkaluripet | Andhra Pradesh | 01 Mar 1999 | Date of announcement | 2002-01-01 | 680 | 951.2 | -271.2 | N | 2003-01-31 | Completed | 2002-03-31 | Y | 306 | 1999-03-15 | Bids awarded
1312 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet(Package I) Highway Project | 55 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 600 | Completed | Engineering, Procurement & Construction | January 2003 | Chilkaluripet | Andhra Pradesh | 01 Feb 1999 | Date of announcement | 2002-01-01 | 600 | 2270 | -1670 | N | 2003-01-31 | Completed | 2002-03-31 | Y | 306 | 1999-03-15 | Bids awarded
1313 | National Highways Authority Of India | 155597 | Vijaywada-Hyderabad(Vijay-Ibrahimpatnam & Hyderabad City) Highway Project | 10 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 720 | Completed | Build Operate Transfer | June 2001 | Hyderabad | Telangana | 01 Sep 1996 | Date of announcement | 2001-04-01 | 720 | 587.2 | 132.8 | Y | 2001-06-07 | Completed | 1999-03-31 | Y | 799
1314 | National Highways Authority Of India | 155597 | Vijaywada-Ranchi Highway Project | 435 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 13330 | No Information |  |  | Ranchi | Jharkhand | 19 Jul 2006 | Date of announcement | 2015-12-24 | 13330 | 1200 | 12130 | Y | [5 empty] | 2010-03-15 | Bids awarded
1315 | National Highways Authority Of India | 155597 | Vikkaravandi-Sethiyahopu (NH-45 C) Four Laning Highway (Pkg-I of Vikravandi-Thanjavur) Project | 890 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 12590 | Under Implementation | Design, Build, Finance, Operate and Transfer (Toll) basis |  | Thanjavur | Tamil Nadu | 17 Dec 2009 | Date of announcement | 2019-10-29 | 12590 | 11000 | 1590 | Y | [5 empty] | 2017-03-24 | Bids awarded
1316 | National Highways Authority Of India | 155597 | Village Kalyanpur to Village Balbhadrapur Four Lane Access Controlled Greenfield Highway (NH-119D) Project (Package-III of Amas-Darbhanga Expressway) | 1946 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 18577.8 | Under Implementation | Hybrid Annuity | September 2024 | Village balbhadrapur | Bihar | 01 Dec 2019 | Date of announcement | 2022-04-06 | 18577.8 | 11655.4 | 6922.4 | Y | 2024-12-31 | Initial completion date | 2024-09-30 | Y | 92 | 2022-03-30 | Bids awarded
1317 | National Highways Authority Of India | 155597 | Villukuri-Kanyakumari (NH-47 & NH-66) & Nagercoil-Kavalkinaru (NH-47B) Four Laning Highway Project | 351 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 13000 | Under Implementation | Engineering, Procurement & Construction | July 2023 | Kanyakumari | Tamil Nadu | 01 Dec 2003 | Date of announcement | 2021-07-09 | 13000 | 6411.7 | 6588.3 | Y | 2023-07-15 | Completion expected by | 2018-03-31 | Y | 1932 | 2016-02-25 | Bids awarded
1318 | National Highways Authority Of India | 155597 | Virnoda-Mopa Four/Six Lane (NH-166S) Highway Project | 1629 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 11830 | Under Implementation | Engineering, Procurement & Construction |  | Mopa | Goa | 01 Jul 2018 | Date of announcement | 2022-01-03 | 11830 | 12000 | -170 | N | [5 empty] | 2021-12-15 | Bids awarded
1319 | National Highways Authority Of India | 155597 | Visakhapatnam (NH-516C) Four Lane Port Road Connectivity Project (Sheelanagar to Sabbavaram) (Bharatmala) | 1826 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5490 | Under Implementation | Hybrid Annuity |  | Sabbavaram | Andhra Pradesh | 07 Dec 2017 | Date of announcement | 2018-03-21 | 5490 | 3926 | 1564 | Y | [5 empty] | 2018-03-21 | Bids awarded
1320 | National Highways Authority Of India | 155597 | Visakhapatnam Beach Road-Bhogapuram International Airport Six Lane Highway Project | 3001 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 63000 | Under Implementation |  |  | Bhogapuram | Andhra Pradesh | 01 Nov 2021 | Date of announcement | 2023-03-03 | 63000 | 63000 | 0 | N
1321 | National Highways Authority Of India | 155597 | Visakhapatnam Port-NH-5/NH-16 Balance Connectivity Four Lane Road Project | 1237 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1003.3 | Completed | Engineering, Procurement & Construction | July 2018 | Vishakhapatanam | Andhra Pradesh | 30 Sep 2015 | Date of announcement | 2016-01-18 | 1003.3 | 829.3 | 174 | Y | 2018-07-13 | Completed | 2017-09-30 | Y | 286 | 2016-01-18 | Bids awarded
1323 | National Highways Authority Of India | 155597 | Vizhinjam Bypass-Navaikulam (Kollam Border) Four/Six Lane Outer Ring Road Project (Thiruvananthpuram Outer Ring Road) | 1651 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 45000 | Under Implementation | Hybrid Annuity |  | Parippally | Kerala | 01 Jan 2018 | Date of announcement | 2022-03-11 | 45000 | 48680 | -3680 | N
1324 | National Highways Authority Of India | 155597 | Wadner-Devdhari (NS-60/MH) Highway Project | 949 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 2500 | Completed | Engineering, Procurement & Construction | October 2018 | Devdhari | Maharashtra | 01 Mar 2005 | Date of announcement | 2018-10-25 | 2500 | 1934.5 | 565.5 | Y | 2019-08-31 | Initial completion date | 2014-03-31 | Y | 1979 | 2005-04-01 | Bids awarded
1325 | National Highways Authority Of India | 155597 | Wadpe-Kasarghat N H-3 Project | 49 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2100 | Shelved |  |  | Kasarghat | Maharashtra | 01 Jan 1999 | Date of announcement | 1999-01-01 | 2100 | 2100 | 0 | N
1326 | National Highways Authority Of India | 155597 | Wakhri-Kudus (NH-965) Four Lane Highway Project (Package-II of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1439 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 9790 | Under Implementation | Engineering, Procurement & Construction |  | Kudus | Maharashtra | 29 Dec 2017 | Date of announcement | 2021-11-08 | 9790 | 5448.2 | 4341.8 | Y | [5 empty] | 2019-09-18 | Bids awarded
1327 | National Highways Authority Of India | 155597 | Warangal-Khammam Four Lane Access Controlled Greenfield Highway Project | 1930 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 140550 | Under Implementation | Hybrid Annuity |  | Khammam | Telangana | 01 Oct 2016 | Date of announcement | 2023-02-03 | 140550 | 28990 | 111560 | Y | [5 empty] | 2023-03-29 | Bids awarded
1328 | National Highways Authority Of India | 155597 | Warora-Wani (NH-930) Four Lane Highway Project | 1766 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 2798 | Under Implementation | Engineering, Procurement & Construction |  | Wani | Maharashtra | 01 Nov 2017 | Date of announcement | 2019-03-15 | 2798 | 2798 | 0 | N | [5 empty] | 2019-08-06 | Bids awarded
1329 | National Highways Authority Of India | 155597 | Washim-Pangare (NH-161) Four Lane Highway project (Package-III) | 1697 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10370.4 | Completed | Engineering, Procurement & Construction | July 2022 | Pangare | Maharashtra | 01 Apr 2018 | Date of announcement | 2022-07-05 | 10370.4 | 5733 | 4637.4 | Y | 2022-07-05 | Completed | 2021-05-14 | Y | 417 | 2019-02-25 | Bids awarded
1330 | National Highways Authority Of India | 155597 | Westerly Diversion Highway Project | 58 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 1515.6 | Completed | Engineering, Procurement & Construction | November 2003 | Pune | Maharashtra | 01 Jun 1999 | Date of announcement | 2003-07-01 | 1515.6 | 1200 | 315.6 | Y | 2003-11-15 | Completed | 2002-08-31 | Y | 441 | 2000-05-16 | Bids awarded
1331 | National Highways Authority Of India | 155597 | Whitefield industrial cluster-Bangalore to Enayam Expressway Project (Port Connectivity) | 1722 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 200000 | No Information |  |  | Enayam | Tamil Nadu | 01 Apr 2016 | Date of announcement | 2016-06-03 | 200000 | 200000 | 0 | N
1332 | National Highways Authority Of India | 155597 | Widening & Strengthening of Garhmukteshwar-Meerut (NH-709A) Highway Project | 1673 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 20689.9 | Under Implementation |  | December 2023 | Garhmukteshwar | Uttar Pradesh | 01 Dec 2018 | Date of announcement | 2021-08-02 | 20689.9 | 33670 | -12980.1 | N | [5 empty] | 2021-03-12 | Bids awarded
1333 | National Highways Authority Of India | 155597 | Widening and strengthening of Two to Four lane East West Corridor Project (Package AS 02) | 1757 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 59.6 | No Information |  |  | Assam | Assam | 21 Jun 2019 | Date of announcement | 2019-06-21 | 59.6 | 59.6 | 0 | N
1334 | National Highways Authority Of India | 155597 | Widening of Pashchimi Singhbhum NH-320G Road Project | 3005 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 4230 | Under Implementation |  |  | Pashchimi singhbhum | Jharkhand | 01 Mar 2023 | Date of announcement | 2023-03-19 | 4230 | 4230 | 0 | N
1335 | National Highways Authority Of India | 155597 | Yadgiri-Warangal (NH-163) Four Laning Highway Project | 992 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 18900 | Completed | Engineering, Procurement & Construction | December 2020 | Warangal | Telangana | 01 Sep 2010 | Date of announcement | 2020-12-21 | 18900 | 9570 | 9330 | Y | 2020-12-21 | Completed | 2018-11-30 | Y | 752 | 2015-12-10 | Bids awarded
1336 | National Highways Authority Of India | 155597 | Yalachahalli Near SH-117 Yelawala-KR Nagara Road to Srirangapatna Bypass Four Lane Highway Project (Package V of Mysuru-Kushalnagar (NH-275) Highway) | 2097 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 7622 | Under Implementation | Hybrid Annuity |  | Kr nagara road | Karnataka | 01 Apr 2018 | Date of announcement | 2022-09-19 | 7622 | 7622 | 0 | N | [5 empty] | 2023-03-10 | Bids awarded
1337 | National Highways Authority Of India | 155597 | Yanam ROB (Yanam-Yedurulanka) Project | 206 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1100 | Completed | Build Operate Transfer | October 2002 | Yanam | Puducherry | 01 Dec 2001 | Date of announcement | 2001-12-01 | 1100 | 1100 | 0 | N | 2002-10-01 | Completed | 2002-09-30 | N
1338 | National Highways Authority Of India | 155597 | Zero Mile to Kamptee-Kanhan Four Lane Cement Road Project (on Jabalpur Road) | 1055 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 10000 | No Information |  |  | Kamptee | Maharashtra | 15 Mar 2014 | Date of announcement | 2016-02-23 | 10000 | 1750 | 8250 | Y
1339 | National Highways Authority Of India | 155597 | Zero Mile-Khapri Four Lane Cement Road Project (on Wardha Road) | 1056 | Road transport infrastructure services | Central Govt. - Statutory Bodies | New Unit | 1250 | No Information |  |  | Khapri | Maharashtra | 15 Jan 2015 | Date of announcement | 2015-01-29 | 1250 | 1250 | 0 | N
1340 | National Highways Authority Of India | 155597 | Zirakpur-Solan Four Laning Highway Project | 436 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 10000 | No Information |  |  | Solan | Himachal Pradesh | 30 Sep 2006 | Date of announcement | 2006-09-30 | 10000 | 10000 | 0 | N
1341 | National Highways Authority Of India | 155597 | lchhapuram-Narasannapeta (NH-16) Six Laning Highway Project (Package-I) | 1277 | Road transport infrastructure services | Central Govt. - Statutory Bodies | Substantial Expansion | 5767.8 | Completed | Engineering, Procurement & Construction | May 2021 | Ichapuram | Andhra Pradesh | 01 Jan 2017 | Date of announcement | 2021-05-13 | 5767.8 | 5573 | 194.8 | Y | 2021-05-13 | Completed | 2020-11-01 | Y | 193 | 2018-03-23 | Bids awarded

## NHAI_Associate_Projects
| COMPANY | COMPANY_CODE | PROJECT_NAME | PROJECT_NUMBER | ASSOCIATE_TYPE | ASSOCIATE_COMPANY(AC) | AC_CODE | AC_COUNTRY | AC_ADDRESS | AC_PINCODE | AC_CITY | AC_STATE | AC_TEL_NO | AC_FAX | AC_EMAIL | AC_WEBSITE
23625 | National Highways Authority Of India | 155597 | Rajahmundry City (Morampudi Junction) (NH-216A) Flyover Project | 1599 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
23626 | National Highways Authority Of India | 155597 | 4 Laning of four stretches of Lakhnadon-Seoni (Chapara) ( leftout Stretches ) of NH-7 Project | 1229 | Contractor | Prakash Asphaltings & Toll Highways (india) Ltd. | 178735 | India | Registered Office:76, Mall Road, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-275001 | 91-7324-400318 | path@pathltd.com | www.pathltd.com
23627 | National Highways Authority Of India | 155597 | 4 Laning of four stretches of Lakhnadon-Seoni (Chapara) ( leftout Stretches ) of NH-7 Project | 1229 | Contractor | Udit Infraworld Pvt. Ltd. | 416257 | India | Registered Office:White House Arjun Nagar, | 486001 | Rewa | Madhya Pradesh |  |  | uditinfraworld@rediffmail.com
23628 | National Highways Authority Of India | 155597 | 84 Kosi Parikrama Marg (NH-227B) Project | 1665 | Co-promoter | Uttar Pradesh Public Works Department | 375252 | India | Registered Office:Nirman Bhawan, 96, Mahatma Gandhi Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2236496 |  | pwdgislko@gmail.com | www.uppwd.gov.in
23629 | National Highways Authority Of India | 155597 | Achhampeta Junction (NH-216)-Kakinada Anchorage Port Connecting Vakalpudi Light House (NH-516F) Four Laning Project | 1955 | Contractor | R K Infracorp Pvt. Ltd. | 406064 | India | Registered Office:1/712, Dwaraka Nagar, Kadapa, | 516001 | East Godavari | Andhra Pradesh |  |  | rkinfracorp@gmail.com
23630 | National Highways Authority Of India | 155597 | Achhampeta Junction (NH-216)-Kakinada Anchorage Port Connecting Vakalpudi Light House (NH-516F) Four Laning Project | 1955 | Contractor | Suryodaya Infra Projects (i) Pvt. Ltd. | 466751 | India | Registered Office:H No.7-1-644, 1st Floor, Sunder Nagar Colony, Sanath Nagar, | 500038 | Hyderabad | Telangana | 91-40-40123881 |  | rp@sipil.in | www.sipil.in
23631 | National Highways Authority Of India | 155597 | Addahole-Bantwal Cross (NH-75) Four Lane Highway Project (Hassan-B.C. Road Pkg-II) | 1144 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
23632 | National Highways Authority Of India | 155597 | Addahole-Bantwal Cross (NH-75) Four Lane Highway Project (Hassan-B.C. Road Pkg-II) | 1144 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
23633 | National Highways Authority Of India | 155597 | Adhelai village-Nari junction (NH-751) Four Lane Highway (Package-I of Pipli-Bhavnagar stretch) Project | 1339 | Contractor | Kalthia Engineering & Construction Ltd. | 114870 | India | Corporate Office:28, Rangin Park, Opp. Rajpath Club, S G Highway, Bodakdev, | 380059 | Ahmedabad | Gujarat | 91-79-26870501 | 91-79-26870501 | kecl@kathiagroup.com | www.kalthiagroup.com
23634 | National Highways Authority Of India | 155597 | Adhelai village-Nari junction (NH-751) Four Lane Highway (Package-I of Pipli-Bhavnagar stretch) Project | 1339 | Contractor | J P Iscon Pvt. Ltd. | 371610 | India | Registered Office:Iscon House, Opp. Associated Petrol- Pump, B/h R. Bldg. Off C G Road, Rembrand Building, | 380009 | Ahmedabad | Gujarat | 91-79-32919227 | 91-79-26464369 | cs@isocongroup.com | www.iscongroup.com
23635 | National Highways Authority Of India | 155597 | Adloor-Pochanpalli NH-7 Road Project | 546 | Contractor | G M R Airports Infrastructure Ltd. | 76718 | India | Corporate Office:Skip House, 25/1, Museum Road, | 560025 | Bengaluru | Karnataka | 91-80-2279949 | 91-80-2998118 |  | www.gmrgroup.in
23636 | National Highways Authority Of India | 155597 | Agra Bypass (NS-1/UP-1) Four-Laning Highway Project | 315 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23637 | National Highways Authority Of India | 155597 | Agra Bypass (NS-1/UP-1) Four-Laning Highway Project | 315 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
23638 | National Highways Authority Of India | 155597 | Agra Bypass (NS-1/UP-1) Four-Laning Highway Project | 315 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
23639 | National Highways Authority Of India | 155597 | Agra Six Lane Bypass (Northern) connecting NH-19 to Yamuna Expressway Six Lane Project | 2003 | Contractor | Hillways Construction Co. Pvt. Ltd. | 456827 | India | Registered Office:3/64, West Punjabi Bagh, | 110026 | New Delhi | Delhi
23640 | National Highways Authority Of India | 155597 | Agra Six Lane Bypass (Northern) connecting NH-19 to Yamuna Expressway Six Lane Project | 2003 | Contractor | Velji Ratna Sorathia Infra Pvt. Ltd. | 521163 | India | Registered Office:A-401, Kalpvrux Complex, Gotri Road, | 390021 | Vadodara | Gujarat | 91-265-2320970 |  | mail@vrs.co.in | www.vrs.co.in
23641 | National Highways Authority Of India | 155597 | Agra-Gwalior (NS/4) Four Lane Highway Project | 189 | Turnkey contractor | P N C Construction Pvt. Ltd. | 167138 | India |  | NA
23642 | National Highways Authority Of India | 155597 | Agra-Jalesar-Etah (NH-321-G) Two/Four Lane Highway Improvement & Upgradation Project | 1649 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
23643 | National Highways Authority Of India | 155597 | Agra-Shikohabad (GTRIP/I-A) Road Project | 145 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
23644 | National Highways Authority Of India | 155597 | Agra-Shikohabad (GTRIP/I-A) Road Project | 145 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
23645 | National Highways Authority Of India | 155597 | Agra-Shikohabad (GTRIP/I-A) Road Project | 145 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
23646 | National Highways Authority Of India | 155597 | Agra-Sikandara Highway Project | 146 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
23647 | National Highways Authority Of India | 155597 | Agra-Sikandara Highway Project | 146 | Turnkey contractor | China Coal Ltd. | 284671 | China |  | NA
23648 | National Highways Authority Of India | 155597 | Ahmadabad-Dandi Heritage Route Project | 470 | Promoter | Government Of India | 84845 | India | Registered Office:3rd Floor, National Informatics Centre, A-Block, CGO Complex, Lodhi Road, | 110003 | Central Delhi | NCT of Delhi |  |  | indiaportal@gov.in | www.india.gov.in
23649 | National Highways Authority Of India | 155597 | Ahmednagar Four Lane Bypass Project | 1420 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
23650 | National Highways Authority Of India | 155597 | Ahmednagar Four Lane Bypass Project | 1420 | Consultant | Infinite Civil Solutions Pvt. Ltd. | 594436 | India |  | NA
23651 | National Highways Authority Of India | 155597 | Ahmednagar Four Lane Bypass Project | 1420 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
23652 | National Highways Authority Of India | 155597 | Ahmednagar Four Lane Bypass Project | 1420 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23653 | National Highways Authority Of India | 155597 | Akola City (NH-53) Flyovers Project | 1450 | Contractor | Jandu Construction Co. | 585722 | India |  | NA
23654 | National Highways Authority Of India | 155597 | Akola City (NH-53) Flyovers Project | 1450 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
23655 | National Highways Authority Of India | 155597 | Akola City (NH-6) Bypass Project | 31 | Contractor | Rani Constructions Pvt. Ltd. | 193772 | India | Registered Office:407, Shiv Towers, 4th Floor, Patto Plaza, Panaji, | 403001 | Goa | Goa | 91-832-2438092
23656 | National Highways Authority Of India | 155597 | Akola-Medshi (NH-161) Four Lane Highway Project | 1814 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
23657 | National Highways Authority Of India | 155597 | Alappuzha Bypass Project | 782 | Co-promoter | Kerala Public Works Department | 426356 | India | Registered Office:PWD Road & Bridges & Administration, Public Office, Museum P.O., | 695033 | Thiruvananthapuram | Kerala | 91-471-2322346 |  | ceroads@pwd.kerala.gov.in | www.keralapwd.gov.in
23658 | National Highways Authority Of India | 155597 | Alappuzha Bypass Project | 782 | Contractor | R D S Project Ltd. | 185799 | India | Registered Office:427, Somdutt Chambers-II, 9, Bhikaji Cama Place, | 110066 | New Delhi | NCT of Delhi | 91-11-26170242 | 91-11-26168092 | agra@rdsproject.com | www.rdsproject.com
23659 | National Highways Authority Of India | 155597 | Alawalpur Chowk to Agra Chowk (NH-19) Elevated Corridor Project | 1264 | Contractor | Cube Highways & Infrastructure Pte. Ltd. | 529547 | Singapore |  | NA
23660 | National Highways Authority Of India | 155597 | Aligarh-Kanpur (NH-91) Four/Six Laning Highway Project (Bharatmala) | 1040 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23661 | National Highways Authority Of India | 155597 | Aligarh-Kanpur (NH-91) Four/Six Laning Highway Project (Bharatmala) | 1040 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23662 | National Highways Authority Of India | 155597 | Aligarh-Kanpur (NH-91) Four/Six Laning Highway Project (Bharatmala) | 1040 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
23663 | National Highways Authority Of India | 155597 | Aligarh-Kanpur (NH-91) Four/Six Laning Highway Project (Bharatmala) | 1040 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
23664 | National Highways Authority Of India | 155597 | Aligarh-Moradabad (NH-93) (New NH-509) Two Laning Road Project | 818 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
23665 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-I Highway Project | 151 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23666 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-I Highway Project | 151 | Supervision consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
23667 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-II Project | 721 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
23668 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-II Project | 721 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23669 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-III Project | 722 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
23670 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-III Project | 722 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
23671 | National Highways Authority Of India | 155597 | Allahabad Bypass (NH-2) Contract-III Project | 722 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
23672 | National Highways Authority Of India | 155597 | Aluva-Angamali(NS-28/KL) NH47 Highway Project | 164 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23673 | National Highways Authority Of India | 155597 | Aluva-Angamali(NS-28/KL) NH47 Highway Project | 164 | Contractor | Tantia Constructions Ltd. | 247502 | India | Corporate Office:DD-30, Sector-1, Salt Lake City, | 700064 | Kolkata | West Bengal | 91-33-40190000 | 91-33-40190001 | info@tantiagroup.com | www.tantiagroup.com
23674 | National Highways Authority Of India | 155597 | Aluva-Angamali(NS-28/KL) NH47 Highway Project | 164 | Contractor | Techni Bharathi Pvt. Ltd. | 248600 | India | Head Office:'Florance', No. 34/136-A, Bye-pass Road, Edappally, | 682024 | Kochi | Kerala | 91-484-2344906 | 91-484-2344908 | tsind@tsind.com
23675 | National Highways Authority Of India | 155597 | Amas-Shiwrampur Four Lane Highway (Package-I of Amas-Darbhanga Expressway) Project | 1891 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
23676 | National Highways Authority Of India | 155597 | Amas-Shiwrampur Four Lane Highway (Package-I of Amas-Darbhanga Expressway) Project | 1891 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
23677 | National Highways Authority Of India | 155597 | Ambala Four Lane Ring Road (NH-44) (Connecting Five NH) Project | 1825 | Consultant | Lion Engineering Consultants | 551358 | India | Registered Office:Plot No. 97, Lion Tower, Near Mother Teresa School, Kolar Road, | 462042 | Bhopal | Madhya Pradesh | 91-755-2879496 | 91-755-2879499 | info@liongroup.in | www.lionengineering.in
23678 | National Highways Authority Of India | 155597 | Ambala Four Lane Ring Road (NH-44) (Connecting Five NH) Project | 1825 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
23679 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-I) | 612 | Consultant | Meinhardt (singapore) Pte Ltd. | 286809 | Singapore | Registered Office:A - 8, Sector 16, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh | 91-120-2516165 | 91-120-2515745 | rajesh@meinhardtindia.com | www.meinhardtgroup.com
23680 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-I) | 612 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
23681 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-I) | 612 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
23682 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-II) | 1011 | Consultant | Meinhardt (singapore) Pte Ltd. | 286809 | Singapore | Registered Office:A - 8, Sector 16, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh | 91-120-2516165 | 91-120-2515745 | rajesh@meinhardtindia.com | www.meinhardtgroup.com
23683 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-II) | 1011 | Consultant | Antea India Pvt. Ltd. | 407588 | India | Registered Office:Unit No. 404, 4th Floor, IRIS Tech Park, Sector 48, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4518800 | 91-124-4518832 | ajaysingh@unihornidia.com | www.unihornindia.com
23684 | National Highways Authority Of India | 155597 | Ambala-Kaithal (Pehowa) (NH-65) Four Laning Highway Project (Package-II) | 1011 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
23685 | National Highways Authority Of India | 155597 | Ambala-Kala Amb section of NH-72 to Shahzadpur and Part of New NH-7 from Shahzadpur to Kala Amb Four Lane Highway Project | 2089 | Contractor | D C C Infra Projects Ltd. | 658629 | India |  | NA
23686 | National Highways Authority Of India | 155597 | Ambala-Zirakpur (NH-21 & 22) Highway Project | 767 | Contractor | G M R Airports Infrastructure Ltd. | 76718 | India | Corporate Office:Skip House, 25/1, Museum Road, | 560025 | Bengaluru | Karnataka | 91-80-2279949 | 91-80-2998118 |  | www.gmrgroup.in
23687 | National Highways Authority Of India | 155597 | Ambala-Zirakpur (NH-21 & 22) Highway Project | 767 | Contractor | G M R Energy Ltd. | 247422 | India | Registered Office:701, 7th Floor, Naman Centre, Plot No. C-31, Bandra Kurla Complex, Bandra East, | 400051 | Mumbai | Maharashtra | 91-11-49882200 | 91-11-49882227 | energy-secretarial@gmrgroup.in | www.gmrgroup.in
23688 | National Highways Authority Of India | 155597 | Ambience Mall & DLF Phase 2 (NH-48) Elevated U-Turns Project | 1539 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
23689 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Co-promoter | City & Industrial Devp. Corpn. Of Maharashtra Ltd. | 48094 | India | Corporate Office:Udyog Bhavan, Next To LIC Building, CIDCO, Jalgaon Road, | 431003 | Aurangabad (MAH) | Maharashtra | 91-240-2485321 | 91-240-2485324 | info@cidco.maharashtra.gov.in | www.cidconewtowns.gov.in
23690 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Co-promoter | Jawaharlal Nehru Port Trust | 108007 | India | Corporate Office:Jawaharlal Nehru Port Turst, 1107, Raheja Centre, F P J Marg, Nariman Point, | 400021 | Mumbai | Maharashtra | 91-22-66165600 | 91-22-67431116 |  | www.jnport.gov.in
23691 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23692 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
23693 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Contractor | J Kumar Infraprojects Ltd. | 104004 | India | Corporate Office:CTS No. 448, 448/1, 449, Subhash Road, Vile Parle East, | 400057 | Mumbai | Maharashtra | 91-22-68717900 |  | info@jkumar.com | www.jkumar.com
23694 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Contractor | Thakur Infra Projects Pvt. Ltd. | 407339 | India | Registered Office:House No 1221, At & Po : Jasai, Jasai Naka, Taluka Uran, Navi Mumbai, Raigad, | NA | Navi Mumbai | Maharashtra |  |  | thakurinfraprojects@gmail.com
23695 | National Highways Authority Of India | 155597 | Amra Marg-JNPT (NH-348A) Road Project (Bharatmala) | 1238 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
23696 | National Highways Authority Of India | 155597 | Amravati Bypass Highway Project | 13 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23697 | National Highways Authority Of India | 155597 | Amravati Bypass Highway Project | 13 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
23698 | National Highways Authority Of India | 155597 | Amravati Bypass Highway Project | 13 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
23699 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
23700 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Consultant | Louis Berger Consulting Pvt. Ltd. | 406754 | India | Registered Office:Regus Business Centre, Level-3, Vasant Square Mall Pocket V, Sector B, | 110070 | New Delhi | NCT of Delhi |  |  | neeraj.kumar2@wsp.com | www.wsp.com
23701 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
23702 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Contractor | Raj Path Infracon Pvt. Ltd. | 190016 | India | Registered Office:Office No. 403, 4th Floor, Pride House, 108, Ganesh Khind Road,Opp Pune University, | 411016 | Pune | Maharashtra | 91-20-25636060 | 91-20-25633344 | raj@rajgrouppune.net
23703 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Contractor | Kalyan Toll Infrastructure Ltd. | 386962 | India | Registered Office:Vidhya Deep, 15/3 Manorama Ganj, | 452001 | Indore | Madhya Pradesh | 91-731-2496931 | 91-731-4096457 | accounts@kalyangroup.in | www.kalyangroup.in
23704 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Contractor | Eagle Infra Pvt. Ltd. | 575135 | India |  | NA
23705 | National Highways Authority Of India | 155597 | Amravati-Chikli (NH-6 or New NH-53) Four Laning Highway Project | 1859 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
23706 | National Highways Authority Of India | 155597 | Amritsar Bypass (NH-354) Project (Package-III) | 2017 | Contractor | K R C Infraprojects Pvt. Ltd. | 514791 | India | Registered Office:101, K R Chambers, Rasulpur Road, | 121102 | Palwal | Haryana | 91-1275-247999 |  | info@krcinfraprojects.com | www.krcinfraprojects.com
23707 | National Highways Authority Of India | 155597 | Amritsar Bypass (NH-354) Project (Package-III) | 2017 | Contractor | S K S Infra Projects Pvt. Ltd. | 595556 | India | Registered Office:1/115-A/2, Babu Gulab Rai Marg Delhi Gate, | 282002 | Agra | Uttar Pradesh |  |  | sksharma.skcc@gmail.com
23708 | National Highways Authority Of India | 155597 | Amritsar Bypass Improvement (NH-1) Project | 1146 | Consultant | Antea India Pvt. Ltd. | 407588 | India | Registered Office:Unit No. 404, 4th Floor, IRIS Tech Park, Sector 48, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4518800 | 91-124-4518832 | ajaysingh@unihornidia.com | www.unihornindia.com
23709 | National Highways Authority Of India | 155597 | Amritsar Bypass Improvement (NH-1) Project | 1146 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
23710 | National Highways Authority Of India | 155597 | Amritsar-Bhatinda (NH-15) Four Laning Highway Project | 973 | Contractor | Brahmaputra Infrastructure Ltd. | 38163 | India | Registered Office:Brahmaputra House, A-7, Mahipalpur, (N H 8-Mahipalpur Crossing), | 110037 | New Delhi | NCT of Delhi | 91-11-42290200 | 91-11-41687880 | cs@brahmaputragroup.com | www.brahmaputragroup.com
23711 | National Highways Authority Of India | 155597 | Amritsar-Bhikhiwind-Khemkaran Two Laning Road project | 1761 | Contractor | Inderjit Mehta Constructions Pvt. Ltd. | 320786 | India | Registered Office:#13219/6, Gali No.9/1, Shiv Colony, Namdev Road, | 151001 | Bathinda | Punjab |  |  | shashibjindal@yahoo.com
23712 | National Highways Authority Of India | 155597 | Amritsar-Bhikhiwind-Khemkaran Two Laning Road project | 1761 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
23713 | National Highways Authority Of India | 155597 | Amritsar-Ghoman-Tanda-Una (NH-503A) Four Lane Highway Project | 1765 | Contractor | Chetak Enterprises Ltd. | 379365 | India | Registered Office:Petch Area, Opposite Dak Bunglow, Circuit House Road, | 312601 | Nimbahera | Rajasthan | 91-1477-220066 | 91-1477-223125 | chetak_nbh@hotmail.com | www.chetakenterprises.com/
23714 | National Highways Authority Of India | 155597 | Amritsar-Ghoman-Tanda-Una (NH-503A) Four Lane Highway Project | 1765 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
23715 | National Highways Authority Of India | 155597 | Amritsar-Wagha Border (NH-1) Highway Project | 464 | Contractor | I D F C Ltd. | 100709 | India | Corporate Office:906/907, 9th Floor, Embassy Centre, Jamnalal Bajaj Road, Nariman Point, | 400021 | Mumbai | Maharashtra | 91-22-22821549 | 91-22-24215052 | info@idfc.com | www.idfc.com
23716 | National Highways Authority Of India | 155597 | Amritsar-Wagha Border (NH-1) Highway Project | 464 | Contractor | Rohan Builders (india) Pvt. Ltd. | 199144 | India | Registered Office:1, Modibaug Commercial Building, CTS No 2254, Ganeshkhind Road, Road, Shivaji Nagar, | 411016 | Pune | Maharashtra | 91-20-71017301 |  | rohanpn@rohanbuilders.com | www.rohanbuilders.com
23717 | National Highways Authority Of India | 155597 | Amritsar-Wagha Border (NH-1) Highway Project | 464 | Contractor | Rajdeep Buildcon Pvt. Ltd. | 355389 | India | Registered Office:Rajdeep House, Opp. Swastik Apartments, Savedi Naka, Savedi, | 414003 | Ahmadnagar | Maharashtra | 91-241-2424072 | 91-241-2424101 | info@rajdeepgroup.com | www.rajdeepgroup.com
23718 | National Highways Authority Of India | 155597 | Anakapalli-Annavaram-Diwancheruvu Four/Six Lane Highway (NH-16) Project | 2069 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
23719 | National Highways Authority Of India | 155597 | Anakapalli-Annavaram-Diwancheruvu Four/Six Lane Highway (NH-16) Project | 2069 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
23720 | National Highways Authority Of India | 155597 | Anantapur-Muchukota (NH-544D) Four Lane Highway Project (Package-1) | 2045 | Contractor | S R C Infra Developers Pvt. Ltd. | 598980 | India | Registered Office:7-272, kakateeya Residency Court Road, | 515001 | Anantapur | Andhra Pradesh |  |  | sheema.src1@gmail.com
23721 | National Highways Authority Of India | 155597 | Anarbansalea village to Sagrampur village Four/Six Lane Greenfield Access Control Expressway Project (Package-7 of Varanasi-Kolkata Expressway) | 1982 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23722 | National Highways Authority Of India | 155597 | Anarbansalea village to Sagrampur village Four/Six Lane Greenfield Access Control Expressway Project (Package-7 of Varanasi-Kolkata Expressway) | 1982 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
23723 | National Highways Authority Of India | 155597 | Andhra NH-5 Project | 68 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
23724 | National Highways Authority Of India | 155597 | Angamaly-Kundanoor (Ernakulam Bypass) (NH-544&46) Four Lane Bypass Project | 1786 | Consultant | Louis Berger Group - Usa | 536211 | USA |  | NA
23725 | National Highways Authority Of India | 155597 | Angul-Sambalpur (NH-42) Highway Project | 820 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23726 | National Highways Authority Of India | 155597 | Angul-Sambalpur (NH-42) Highway Project | 820 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
23727 | National Highways Authority Of India | 155597 | Ankaleshwar-Netrang Highway Project | 1302 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
23728 | National Highways Authority Of India | 155597 | Armur-(K)adloor-Yellareddy (NH-7) Four-Laning Highway Project | 483 | Consultant | C D M Smith India Pvt. Ltd. | 390999 | India | Registered Office:No. 103 & 104, First Floor, Brigade Opus, Kodigehalli Main Road, Sanjeevini Nagar, | 560092 | Bengaluru | Karnataka | 91-80-67150300 |  | sumeshn@cdmsmith.com | www.cdmsmith.com
23729 | National Highways Authority Of India | 155597 | Armur-(K)adloor-Yellareddy (NH-7) Four-Laning Highway Project | 483 | Contractor | Adani Krishnapatnam Port Ltd. | 123565 | India | Registered Office:Adani Corporate House, Shantigram, Near Vaishnodevi Circle, S G Highway Khodiyar, | 382421 | Ahmedabad | Gujarat |  |  | cs@krishnapatnamport.com | www.krishnapatnamport.com
23730 | National Highways Authority Of India | 155597 | Armur-(K)adloor-Yellareddy (NH-7) Four-Laning Highway Project | 483 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
23731 | National Highways Authority Of India | 155597 | Aroor to Thuravoor Thekku Six Lane (NH-66) Elevated Corridor Project | 2074 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
23732 | National Highways Authority Of India | 155597 | Arrah-Pararia Four Lane Highway (NH-319) Project (Package 1 of Mohania-Arrah) (Bharatmala) | 1838 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
23733 | National Highways Authority Of India | 155597 | Assam/WB Border to Gairkata (WB-1) Highway Project | 285 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23734 | National Highways Authority Of India | 155597 | Atmakur-Dornala (NH-340C) Two Lane Highway Project (Kurnool-Dornala) | 1490 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
23735 | National Highways Authority Of India | 155597 | Atul-Kajali (NH-8) Highway Project | 52 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23736 | National Highways Authority Of India | 155597 | Atul-Kajali (NH-8) Highway Project | 52 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
23737 | National Highways Authority Of India | 155597 | Atul-Kajali (NH-8) Highway Project | 52 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
23738 | National Highways Authority Of India | 155597 | Atul-Kajali (NH-8) Highway Project | 52 | Contractor | L G Construction Co. Ltd. | 348696 | Korea Republic (South) |  | NA
23739 | National Highways Authority Of India | 155597 | Aurad-Bidar (NH-161A) Two Lane Highway Project | 1656 | Contractor | R M N Infrastructures Ltd. | 413951 | India | Head Office:H No.8-2-684/J/3/A, RMN House, 3rd Flr, Bhavani Nagar, Rd No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23322146 | 91-40-23322147 | rmnilbangalore@yahoo.com | www.rmninfra.com
23740 | National Highways Authority Of India | 155597 | Aurangabad-Barwa-Adda(Aurangabad-Barachatti) Highway Project | 157 | Consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
23741 | National Highways Authority Of India | 155597 | Aurangabad-Barwa-Adda(Aurangabad-Barachatti) Highway Project | 157 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
23742 | National Highways Authority Of India | 155597 | Aurangabad-Barwa-Adda(Aurangabad-Barachatti) Highway Project | 157 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
23743 | National Highways Authority Of India | 155597 | Aurangabad-Bihar/Jharkhand Border (Chordaha) (NH-2) Six Laning Highway Project (Package-I) | 897 | Consultant | C E S Ltd. | 216887 | India | Registered Office:7th Floor, Tower A, Ramky Selenium, Nanakramguda, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-42421122 | 91-40-66259444 | info@cesltd.com | www.cesltd.com
23744 | National Highways Authority Of India | 155597 | Aurangabad-Bihar/Jharkhand Border (Chordaha) (NH-2) Six Laning Highway Project (Package-I) | 897 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
23745 | National Highways Authority Of India | 155597 | Aurangabad-Bihar/Jharkhand Border (Chordaha) (NH-2) Six Laning Highway Project (Package-I) | 897 | Contractor | Barbrik Project Ltd. | 380698 | India | Corporate Office:15/198, Bramha Road, Ambikapur, | 497001 | Surguja | Chhattisgarh | 91-7774-220375 | 91-7774-220475 | apur@barbrik.in
23746 | National Highways Authority Of India | 155597 | Aurangabad-Paithan (NH-752E) Four Lane Highway Project | 1866 | Contractor | V P Sethi Constructions Pvt. Ltd. | 668851 | India |  | NA
23747 | National Highways Authority Of India | 155597 | Aurangabad-Paithan (NH-752E) Four Lane Highway Project | 1866 | Contractor | Courage Infra Pvt. Ltd. | 668852 | India |  | NA
23748 | National Highways Authority Of India | 155597 | Aurangabad-Telwadi (NH-52) Four-Laning Highway Project | 1006 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23749 | National Highways Authority Of India | 155597 | Aurangabad-Telwadi (NH-52) Four-Laning Highway Project | 1006 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
23750 | National Highways Authority Of India | 155597 | Aut-Takoli (Tunnel) (NH-21) Highway Project (Package-V of Nerchowk-Kullu stretch) | 1047 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23751 | National Highways Authority Of India | 155597 | Aut-Takoli (Tunnel) (NH-21) Highway Project (Package-V of Nerchowk-Kullu stretch) | 1047 | Contractor | Shapoorji Pallonji Pandoh Takoli Highway Pvt. Ltd. | 576634 | India | Registered Office:Shapoorji Pallonji Centre 41/44, Minoo Desai Marg, Colaba, | 400005 | Mumbai | Maharashtra | 91-22-67490000 | 91-22-66338176 | secretarial.infra@shapoorji.com | www.shapoorji.in
23752 | National Highways Authority Of India | 155597 | Avathi village-Nandi Hills cross & Devanhalli-Meenukunte (NS-10) Six Lane Project | 957 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
23753 | National Highways Authority Of India | 155597 | Avathi village-Nandi Hills cross & Devanhalli-Meenukunte (NS-10) Six Lane Project | 957 | Contractor | Bhagheeratha Engineering Ltd. | 33012 | India | Head Office:3rd Flr, Bhagheeratha Residency, Opp. Bank Of Baroda, (Ernakulam North Br.), Banerji Road, | 682018 | Ernakulam | Kerala | 91-484-2397906 | 91-484-2397983 | info@belkochi.com | www.belkochi.com
23754 | National Highways Authority Of India | 155597 | Ayodhya Four Lane Ring Road project | 1662 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23755 | National Highways Authority Of India | 155597 | Ayodhya-Gorakhpur (Lucknow-Muzaffarpur) Highway Project | 270 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
23756 | National Highways Authority Of India | 155597 | Ayodhya-Gorakhpur (Lucknow-Muzaffarpur) Highway Project | 270 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23757 | National Highways Authority Of India | 155597 | Ayodhya-Gorakhpur (Lucknow-Muzaffarpur) Highway Project | 270 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
23758 | National Highways Authority Of India | 155597 | Ayodhya-Lucknow (LMNHP) Highway Project | 513 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
23759 | National Highways Authority Of India | 155597 | Ayodhya-Lucknow (LMNHP) Highway Project | 513 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23760 | National Highways Authority Of India | 155597 | Ayodhya-Varanasi (NH-135A) Four Lane Highway Project | 1663 | Consultant | Holtec Consulting Pvt. Ltd. | 94858 | India | Corporate Office:Holtec Centre, A Block, Sushant Lok, | 122001 | Gurgaon | Haryana | 91-124-2385095 | 91-124-2385114 | dkj@holtecnet.com | www.holtecnet.com
23761 | National Highways Authority Of India | 155597 | Azhiyur-Vengalam (NH-66) Six Lane Highway Project | 1880 | Contractor | Adani Enterprises Ltd. | 5747 | India | Registered Office:Adani Corporate House, Shantigram, Near Vaishno Devi Circle,S. G. Highway, Khodiyar, | 382421 | Ahmedabad | Gujarat | 91-79-26565555 |  | customercare.irm@adani.com | www.adanienterprises.com
23762 | National Highways Authority Of India | 155597 | Badarpur Elevated Highway Project | 405 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23763 | National Highways Authority Of India | 155597 | Badarpur Elevated Highway Project | 405 | Promoter | Badarpur Faridabad Tollway Ltd. | 384905 | India | Registered Office:Hincon House, 11th Floor, 247 Park, Lal Bahadur Shastri Marg, Vikhroli-W | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25794767 |  | www.hccinfrastructure.com
23764 | National Highways Authority Of India | 155597 | Baghpat-Ghaziabad Six Lane Expressway Project (Package 2 of Eastern Peripheral Expressway) | 1122 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
23765 | National Highways Authority Of India | 155597 | Baghpat-Ghaziabad Six Lane Expressway Project (Package 2 of Eastern Peripheral Expressway) | 1122 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
23766 | National Highways Authority Of India | 155597 | Bahalgarh Chowk (NH-1) Flyover Project | 1001 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
23767 | National Highways Authority Of India | 155597 | Baharagora-Singhara (NH-6 & 49) Four Laning Highway Project | 1064 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
23768 | National Highways Authority Of India | 155597 | Baharagora-Singhara (NH-6 & 49) Four Laning Highway Project | 1064 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23769 | National Highways Authority Of India | 155597 | Bakaria-Gogunda NH-76 Highway Project | 644 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
23770 | National Highways Authority Of India | 155597 | Bakaria-Gogunda NH-76 Highway Project | 644 | Contractor | Soma Enterprise Ltd. | 230660 | India | Corporate Office:2 Avenue, 4, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-66538899 | 91-40-23321286 | info@soma.co.in | www.soma.co.in
23771 | National Highways Authority Of India | 155597 | Bakhtiyarpur-Mokama (NH-31) Four Laning Highway Project (Package 1 of Khagaria-Bakhtiarpur Highway) | 478 | Consultant | Craphts Consultants India Pvt. Ltd. | 51920 | India | Head Office:14/3 Mathura Road, | 121003 | Faridabad | Haryana | 91-129-2278813 | 91-129-2256392 | info@craphts.com
23772 | National Highways Authority Of India | 155597 | Bakhtiyarpur-Mokama (NH-31) Four Laning Highway Project (Package 1 of Khagaria-Bakhtiarpur Highway) | 478 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
23773 | National Highways Authority Of India | 155597 | Balance work of Four Laning of Nagpur - Hyderbad Section of NH-7 (NS-62) (Package-II) (Kelapur-Pimpalkhatti) Project | 1180 | Contractor | Raj Path Infracon Pvt. Ltd. | 190016 | India | Registered Office:Office No. 403, 4th Floor, Pride House, 108, Ganesh Khind Road,Opp Pune University, | 411016 | Pune | Maharashtra | 91-20-25636060 | 91-20-25633344 | raj@rajgrouppune.net
23774 | National Highways Authority Of India | 155597 | Balance work of Four Laning of Nagpur-Hyderabad Section of NH-7 (NS-60) (Package-I) Project (Wadner-Devdhari Highway) | 1179 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23775 | National Highways Authority Of India | 155597 | Balance works on Hapur Bypass-Moradabad section (NH-24) Road Project | 1255 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
23776 | National Highways Authority Of India | 155597 | Balasore-Bhadrak (NH-5) Highway Project | 136 | Consultant | Sheladia Associates Inc. | 287104 | USA | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
23777 | National Highways Authority Of India | 155597 | Balasore-Chandikhole (Bridges section OR-V) Highway Project | 138 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23778 | National Highways Authority Of India | 155597 | Balasore-Chandikhole (Bridges section OR-V) Highway Project | 138 | Turnkey contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
23779 | National Highways Authority Of India | 155597 | Balbhadrapur (Tal Dasraha)-Bela Nawada Four Lane Access Controlled Greenfield Highway (NH-119D) Project (Package-IV of Amas-Darbhanga Expressway) | 1952 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
23780 | National Highways Authority Of India | 155597 | Baleshwar-Laxmannath Road Project | 162 | Consultant | Louis Berger Intl. Inc. | 287149 | India | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23781 | National Highways Authority Of India | 155597 | Baleshwar-Laxmannath Road Project | 162 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23782 | National Highways Authority Of India | 155597 | Baletiya village-Nani Bhadol village Eight Lane Access-Controlled Expressway Project (Package 30 of Delhi-Mumbai Expressway) | 1634 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
23783 | National Highways Authority Of India | 155597 | Baletiya village-Nani Bhadol village Eight Lane Access-Controlled Expressway Project (Package 30 of Delhi-Mumbai Expressway) | 1634 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
23784 | National Highways Authority Of India | 155597 | Baletiya village-Nani Bhadol village Eight Lane Access-Controlled Expressway Project (Package 30 of Delhi-Mumbai Expressway) | 1634 | Contractor | Patel Infrastructure Ltd. | 372691 | India | Corporate Office:Patcon House, 80 Ft. Road, Near Indira Gandhi Statue, | 388001 | Anand | Gujarat | 91-2692-245801 | 91-2692-245804 | anand@patelinfra.com | www.patelinfra.com
23785 | National Highways Authority Of India | 155597 | Balongi-Khanpur Flyover Project (Mohali-Kharar) | 1194 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23786 | National Highways Authority Of India | 155597 | Balwara-Dhangaon (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package III) (Bharatmala) | 1852 | Consultant | Lion Engineering Consultants | 551358 | India | Registered Office:Plot No. 97, Lion Tower, Near Mother Teresa School, Kolar Road, | 462042 | Bhopal | Madhya Pradesh | 91-755-2879496 | 91-755-2879499 | info@liongroup.in | www.lionengineering.in
23787 | National Highways Authority Of India | 155597 | Balwara-Dhangaon (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package III) (Bharatmala) | 1852 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23788 | National Highways Authority Of India | 155597 | Bamitha-Khajuraho (NH-339B) Four Lane Highway Project | 1435 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23789 | National Highways Authority Of India | 155597 | Bamni-Rajura-Warur-Devada MH/TG Border Four Lane Road (NH-930D) Project | 1987 | Consultant | Mukesh & Associates | 150152 | India | Registered Office:5/3, Ragavan Street, Swarnapuri, | 636004 | Salem | Tamil Nadu | 91-427-330395 | 91-427-330209 | mukeshassociates@vsnl.com | www.mukeshassociates.com
23790 | National Highways Authority Of India | 155597 | Bamni-Rajura-Warur-Devada MH/TG Border Four Lane Road (NH-930D) Project | 1987 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23791 | National Highways Authority Of India | 155597 | Bangalore Satellite Town Six Lane Ring Road (STRR) Project (Bharatmala) | 1610 | Co-promoter | Karnataka State Highways Improvement Project (k Ship) | 425807 | India | Registered Office:1st Floor, PWD Annexe Building, Project Implementation UNit, K R Circle, | 560001 | Bengaluru | Karnataka | 91-80-22226262 | 91-80-2229666 |  | www.kship.in
23792 | National Highways Authority Of India | 155597 | Bangalore Satellite Town Six Lane Ring Road (STRR) Project (Bharatmala) | 1610 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
23793 | National Highways Authority Of India | 155597 | Bangalore Satellite Town Six Lane Ring Road (STRR) Project (Bharatmala) | 1610 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
23794 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
23795 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Consultant | Egis International Sa | 417585 | India |  | NA
23796 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Consultant | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
23797 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
23798 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
23799 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
23800 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Contractor | Ramalingam Construction Co. Pvt. Ltd. | 398843 | India | Registered Office:Nr. Tower, No.175/2, South State Bank Nagar Chettipalayam, | 638002 | Erode | Tamil Nadu | 91-424-2282389 |  | vignesh@ramalingam.in
23801 | National Highways Authority Of India | 155597 | Bangalore-Chennai-Chitradurga Expressway Project (Bharatmala) | 508 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
23802 | National Highways Authority Of India | 155597 | Bangalore-Hoskote-Mulbagal (NH-4) Highway Project | 395 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
23803 | National Highways Authority Of India | 155597 | Bangalore-Hoskote-Mulbagal (NH-4) Highway Project | 395 | Contractor | Lanco Hoskote Highway Ltd. | 375031 | India | Registered Office:Plot No.4, Software Units Layout, Hitec City, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-40090400 | 91-40-23118444 | naveen.kumar@lancogroup.com | www.lancogroup.com
23804 | National Highways Authority Of India | 155597 | Bangalore-Hosur (NH-7) Six Laning Highway Project | 408 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23805 | National Highways Authority Of India | 155597 | Bangalore-Hosur (NH-7) Six Laning Highway Project | 408 | Contractor | G V R Infra Projects Ltd. | 352897 | India | Corporate Office:VBS Solitaire, No.47&49, 9th&10th Floor, Bazullah Road, T Nagar, | 600017 | Chennai | Tamil Nadu | 91-44-49099999 | 91-44-49099998 | gvrchennai@gvrinfra.com | www.gvrinfra.com
23806 | National Highways Authority Of India | 155597 | Bangalore-Nelamangala (NH-4) Highway Project | 397 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
23807 | National Highways Authority Of India | 155597 | Bangalore-Nelamangala (NH-4) Highway Project | 397 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
23808 | National Highways Authority Of India | 155597 | Bangalore-Salem-Madurai (NS-27/TN) Highway Project | 54 | Consultant | Nag Infrastructure Consulting Engineers Pvt. Ltd. | 153259 | India | Registered Office:2nd Floor, Ravula Residency, 8-2-5-12, Srinagar Colony Main Road, | 500082 | Hyderabad | Andhra Pradesh
23809 | National Highways Authority Of India | 155597 | Bangalore-Salem-Madurai (NS-27/TN) Highway Project | 54 | Turnkey contractor | Vijay Engineering Enterprises Pvt. Ltd. | 336118 | India | Registered Office:25, Pragati Colony, Rajiv Nagar, Wardha Road, Shricon House, Somalwada, | 440025 | Nagpur | Maharashtra | 91-712-2285033 | 91-712-2290700 | legalpoint2010@gmail.com | www.veepl.in
23810 | National Highways Authority Of India | 155597 | Bani village to Bardawadi village of Mandsaur Eight Lane Carriageway Project (Package 19 of Delhi-Mumbai Expressway) | 1572 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
23811 | National Highways Authority Of India | 155597 | Bani village to Bardawadi village of Mandsaur Eight Lane Carriageway Project (Package 19 of Delhi-Mumbai Expressway) | 1572 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
23812 | National Highways Authority Of India | 155597 | Banjhula (Chakia)-Shivhar-Bairgania (NH-227F) Two Laning Highway project (Bharatmala) | 1653 | Contractor | J K M Infra Projects Ltd. | 388063 | India | Registered Office:C-84, Greater Kailash-1, | 110048 | New Delhi | NCT of Delhi | 91-11-4624555 | 91-11-4624545 | roc@jkminfra.com
23813 | National Highways Authority Of India | 155597 | Banwara-Bettadahalli (NH-206) Four Lane Highway Project (section of Tumkur-Shimoga Package-3) (Bharatmala) | 1788 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
23814 | National Highways Authority Of India | 155597 | Baonli-Jhalai Road to Start of RoB near village Itawa Eight Lane Carriageway Project (Package 9 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1559 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
23815 | National Highways Authority Of India | 155597 | Bar-Bilara-Jodhpur (NH-112) (New NH-25) Four Lane Highway Project | 1155 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
23816 | National Highways Authority Of India | 155597 | Bar-Bilara-Jodhpur (NH-112) (New NH-25) Four Lane Highway Project | 1155 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23817 | National Highways Authority Of India | 155597 | Bar-Bilara-Jodhpur (NH-112) (New NH-25) Four Lane Highway Project | 1155 | Contractor | E S Infraserve Pvt. Ltd. | 581118 | India |  | NA
23818 | National Highways Authority Of India | 155597 | Barabanki-Bahraich (NH-28C) Highway Widening Project | 945 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
23819 | National Highways Authority Of India | 155597 | Barachatti-Gorhar (GTRIP/V-B) Highway Project | 158 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
23820 | National Highways Authority Of India | 155597 | Barachatti-Gorhar (GTRIP/V-B) Highway Project | 158 | Consultant | Halcrow Int'l Ltd. | 324261 | UK | Registered Office:UK | NA
23821 | National Highways Authority Of India | 155597 | Barachatti-Gorhar (GTRIP/V-B) Highway Project | 158 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23822 | National Highways Authority Of India | 155597 | Barachatti-Gorhar (GTRIP/V-B) Highway Project | 158 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23823 | National Highways Authority Of India | 155597 | Baraja-Kandili (NH-130 CD) Six Lane Greenfield Highway Project (Package OD-7) (Part of Raipur-Visakhapatnam Economic Corridor) | 2015 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
23824 | National Highways Authority Of India | 155597 | Baramati-Indapur Four Lane Highway (NH-965G) (Package-II of Sant Tukaram Maharaj Palkhi Marg) Project | 1897 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
23825 | National Highways Authority Of India | 155597 | Baramati-Indapur Four Lane Highway (NH-965G) (Package-II of Sant Tukaram Maharaj Palkhi Marg) Project | 1897 | Contractor | Vijay Nirman Co. Pvt. Ltd. | 387009 | India | Registered Office:D No.11-9-16, Dasapalla Hills, | 530003 | Visakhapatnam | Andhra Pradesh | 91-891-2575755 | 91-891-2754046 | vijay@vijaynirman.com | www.vijaynirman.com
23826 | National Highways Authority Of India | 155597 | Baramati-Indapur Four Lane Highway (NH-965G) (Package-II of Sant Tukaram Maharaj Palkhi Marg) Project | 1897 | Contractor | R K Chavan Infrastructure Pvt. Ltd. | 560853 | India | Registered Office:Flat No 202, Rahul Enclave,S No, 116/7/1,Plot No A, Warje, | 411058 | Pune | Maharashtra | 91-20-25204294 |  | info@rkcipl.com | www.rkcipl.com
23827 | National Highways Authority Of India | 155597 | Barasat-Krishnanagar (NH-34) Four-Laning Highway Project (Bharatmala) | 1399 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
23828 | National Highways Authority Of India | 155597 | Barasat-Krishnanagar (NH-34) Four-Laning Highway Project (Bharatmala) | 1399 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
23829 | National Highways Authority Of India | 155597 | Barasat-Krishnanagar (NH-34) Four-Laning Highway Project (Bharatmala) | 1399 | EPC contractor | Supreme Infrastructure India Ltd. | 241950 | India | Registered Office:Supreme House, Plot No.94/C, Pratap Gad, Opp IIT Main Gate, Powai, | 400076 | Mumbai | Maharashtra | 91-22-61289700 | 91-22-61289711 | vijayj@supremeinfra.com | www.supremeinfra.com
23830 | National Highways Authority Of India | 155597 | Barasat-Raiganj (NH-34) Highway Project | 239 | Co-promoter | Government Of West Bengal | 84873 | India | Registered Office:4, Camac Street, | 700016 | Kolkata | West Bengal | 91-33-22821952 | 91-33-22821944 |  | www.wb.gov.in
23831 | National Highways Authority Of India | 155597 | Barasat-Raiganj (NH-34) Highway Project | 239 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23832 | National Highways Authority Of India | 155597 | Barasat-Raiganj (NH-34) Highway Project | 239 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23833 | National Highways Authority Of India | 155597 | Barasat-Raiganj (NH-34) Highway Project | 239 | Consultant | Halcrow Int'l Ltd. | 324261 | UK | Registered Office:UK | NA
23834 | National Highways Authority Of India | 155597 | Bardawadi village of Mandsaur to Kamliya village of Ratlam Eight Lane Carriageway Project (Package 20 of Delhi-Mumbai Expressway) | 1573 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
23835 | National Highways Authority Of India | 155597 | Bardawadi village of Mandsaur to Kamliya village of Ratlam Eight Lane Carriageway Project (Package 20 of Delhi-Mumbai Expressway) | 1573 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23836 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23837 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Contractor | P R L Projects & Infrastructure Ltd. | 167393 | India | Registered Office:34/1, Vikas Apartment, Punjabi Bagh East, | 110026 | New Delhi | NCT of Delhi | 91-11-45540701 |  | prlprojects_infraltd@yahoo.co.in
23838 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Contractor | Jagdish Saran | 464383 | India |  | NA
23839 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Contractor | Raj Corporation Ltd. | 482680 | India | Registered Office:Gali No. 3 Punjabi Colony, | 205001 | Mainpuri | Uttar Pradesh |  |  | rcllko @gmail.com
23840 | National Highways Authority Of India | 155597 | Bareily-Sitapur (NH-24) Four-Laning Highway Project | 1701 | Contractor | Siddhartha Construction | 531311 | India |  | NA
23841 | National Highways Authority Of India | 155597 | Barhi-Hazaribagh (NH-33) Four-Laning Highway Project | 1090 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23842 | National Highways Authority Of India | 155597 | Barhi-Hazaribagh (NH-33) Four-Laning Highway Project | 1090 | Consultant | Upham International Corpn. Pvt. Ltd. | 580929 | India | Registered Office:298, Pocket, D Mayur Vihar - II, | 110091 | New Delhi | NCT of Delhi |  |  | uicpl13@gmail.com | www.uphaminternational.com
23843 | National Highways Authority Of India | 155597 | Barhi-Hazaribagh (NH-33) Four-Laning Highway Project | 1090 | Contractor | Ramky Infrastructure Ltd. | 347143 | India | Registered Office:Ramky Grandiose, 15th Floor, Sy No. 136/2 & 4, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-23015000 | 91-40-23015444 | investors@ramky.com | www.ramkyinfrastructure.com
23844 | National Highways Authority Of India | 155597 | Barhi-Koderma (NH-31) Four Laning Highway Project | 1239 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
23845 | National Highways Authority Of India | 155597 | Barmer-Sanchore-Gujarat Border (upto Gandhav Bridge) (NH-15) Two/Four Lane Highway Project | 1025 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
23846 | National Highways Authority Of India | 155597 | Barmer-Sanchore-Gujarat Border (upto Gandhav Bridge) (NH-15) Two/Four Lane Highway Project | 1025 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
23847 | National Highways Authority Of India | 155597 | Barwa-Adda--Barakar Highway Project | 160 | Consultant | Symonds Travers Morgan Ltd. | 245358 | UK |  | NA
23848 | National Highways Authority Of India | 155597 | Barwa-Adda--Barakar Highway Project | 160 | Contractor | B S C-r B M Pati | 27713 | India |  | NA
23849 | National Highways Authority Of India | 155597 | Barwa-Adda--Barakar Highway Project | 160 | Financial collaborator | Asian Development Bank | 22786 | Philippines | Registered Office:4, San Martin Marg, Chanakyapuri, | 110021 | South West Delhi | NCT of Delhi | 91-11-24107200 | 91-11-26870945 |  | www.adb.org
23850 | National Highways Authority Of India | 155597 | Basanwahi-Marangpuri Six Lane Highway (Package CG3) (NH-130CD) Project (Section of Raipur-Visakhapatnam Economic Corridor) | 1947 | Contractor | K M V Projects Ltd. | 387233 | India | Registered Office:Plot No. 8-3-948&949, 4th Floor, Solitaire Plaza, Beside Image, Hospital, Ameerpet, | 500073 | Hyderabad | Telangana | 91-40-30171111 | 91-40-23735293 | abr@kmvprojects.com | www.kmvprojects.com
23851 | National Highways Authority Of India | 155597 | Basukinath-Jarmundi-Deoghar (NH-114A) Four Lane Highway Project | 1311 | Contractor | Grover Construction Co. Pvt. Ltd. | 598671 | India | Registered Office:5/9, Old Rajinder Nagar, | 110060 | New Delhi | NCT of Delhi |  |  | groverrajendra@yahoo.co.in
23852 | National Highways Authority Of India | 155597 | Bata-Rehukaldhar (Tunnel) (NH-21) Highway Project (Package-III of Nerchowk-Kullu stretch) | 1045 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23853 | National Highways Authority Of India | 155597 | Bata-Rehukaldhar (Tunnel) (NH-21) Highway Project (Package-III of Nerchowk-Kullu stretch) | 1045 | Contractor | Shapoorji Pallonji Pandoh Takoli Highway Pvt. Ltd. | 576634 | India | Registered Office:Shapoorji Pallonji Centre 41/44, Minoo Desai Marg, Colaba, | 400005 | Mumbai | Maharashtra | 91-22-67490000 | 91-22-66338176 | secretarial.infra@shapoorji.com | www.shapoorji.in
23854 | National Highways Authority Of India | 155597 | Bathinda-Malout intersection (NH-7) Four Lane Highway Project | 1771 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
23855 | National Highways Authority Of India | 155597 | Bawadi village (Shivgarh)-Ranni Village Eight Lane Carriageway Project (Package 23 of Delhi-Vadodara Expressway (Delhi-Mumbai Expressway) (Bharatmala) | 1600 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
23856 | National Highways Authority Of India | 155597 | Bawadi village (Shivgarh)-Ranni Village Eight Lane Carriageway Project (Package 23 of Delhi-Vadodara Expressway (Delhi-Mumbai Expressway) (Bharatmala) | 1600 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23857 | National Highways Authority Of India | 155597 | Bawana (Delhi)-Sonepat-Panipat-Uchana-Indri-Yamunanagar Expressway Project | 1340 | Financial collaborator | National Capital Region Planning Board | 155552 | India | Registered Office:Core IV-B, India Habitat Centre, 1st Floor, Lodhi Road, | 110003 | New Delhi | NCT of Delhi | 91-11-24642285 |  | ncrpb-ms@nic.in | www.ncrpb.nic.in
23858 | National Highways Authority Of India | 155597 | Bawana Industrial Area (Delhi)-Barwasani Bypass (Sonipat) (NH-352A) Link Road Project (Package 4 of Delhi 3rd Ring Road or UER-2) | 1683 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
23859 | National Highways Authority Of India | 155597 | Bawana Industrial Area (Delhi)-Barwasani Bypass (Sonipat) (NH-352A) Link Road Project (Package 4 of Delhi 3rd Ring Road or UER-2) | 1683 | Consultant | Aecom India Pvt. Ltd. | 462940 | India | Registered Office:9th Floor, Infinity Tower C, DLF Cyber City, DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-2818000 | 91-124-2816008 | pradeep.khurana@aecom.com | www.aecom.com
23860 | National Highways Authority Of India | 155597 | Bawana Industrial Area (Delhi)-Barwasani Bypass (Sonipat) (NH-352A) Link Road Project (Package 4 of Delhi 3rd Ring Road or UER-2) | 1683 | Contractor | Bharat Construction | 390638 | India |  | NA
23861 | National Highways Authority Of India | 155597 | Bawana Industrial Area (Delhi)-Barwasani Bypass (Sonipat) (NH-352A) Link Road Project (Package 4 of Delhi 3rd Ring Road or UER-2) | 1683 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
23862 | National Highways Authority Of India | 155597 | Beas-Baba Bakala-Dera Baba Nanak (NH-503D) Four Lane Highway Project (Section from start of Batala Bypass till intersection with Ajnala Gurdaspur Highway (NH 354) (Package-II) | 2022 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
23863 | National Highways Authority Of India | 155597 | Beas-Mehta-Batala-Dera Baba Nanak (NH-3) Four Lane Highway Project (Jalandhar-Amritsar Highway) (Package-1) | 2021 | Contractor | Ganeshgarhia Construction Co. | 457406 | India |  | NA
23864 | National Highways Authority Of India | 155597 | Belekeri Port-Kumta-Sirsi (SH-69) Two Lane Highway Project | 1759 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
23865 | National Highways Authority Of India | 155597 | Belekeri Port-Kumta-Sirsi (SH-69) Two Lane Highway Project | 1759 | Contractor | R N S Infrastructure Ltd. | 377885 | India | Corporate Office:7th Floor, Naveen Complex #14, M G Road, | 560001 | Bengaluru | Karnataka | 91-80-25584181 | 91-80-25584017 |  | www.rnsil.com
23866 | National Highways Authority Of India | 155597 | Belgaum Bypass Project | 112 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
23867 | National Highways Authority Of India | 155597 | Belgaum Bypass Project | 112 | Contractor | Sunway Construction Bhd | 282631 | Malaysia | Registered Office:Level 8, Menara Sunway, Jalan Lagoon Timur, Bandar Sunway, 46150 Petaling Jaya, Selangor Darul Ehsan, Malaysia | NA
23868 | National Highways Authority Of India | 155597 | Belgaum Bypass Project | 112 | Contractor | R N Shetty & Co. | 332162 | India |  | NA
23869 | National Highways Authority Of India | 155597 | Belgaum Western & Eastern (NH-4,4A&SH-54) Bypass Project | 1324 | Consultant | Antea India Pvt. Ltd. | 407588 | India | Registered Office:Unit No. 404, 4th Floor, IRIS Tech Park, Sector 48, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4518800 | 91-124-4518832 | ajaysingh@unihornidia.com | www.unihornindia.com
23870 | National Highways Authority Of India | 155597 | Belgaum Western & Eastern (NH-4,4A&SH-54) Bypass Project | 1324 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23871 | National Highways Authority Of India | 155597 | Belgaum-Hungund-Raichur Four Lane Highway (NH-748A) Project (Part of Hyderabad-Panaji Economic Corridor) | 2103 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23872 | National Highways Authority Of India | 155597 | Belghoria Expressway Project | 931 | Promoter | Government Of West Bengal | 84873 | India | Registered Office:4, Camac Street, | 700016 | Kolkata | West Bengal | 91-33-22821952 | 91-33-22821944 |  | www.wb.gov.in
23873 | National Highways Authority Of India | 155597 | Beypore-Malapparamba Four-Lane Road Project (Bharatmala) | 1488 | Promoter | Government Of Kerala | 84856 | India | Registered Office:ICT Campus, Vellayambalam, K G Camp, | 695033 | Thiruvananthapuram | Kerala | 91-471-2726881 | 91-471-2314284 | admin.ksitm@kerala.gov.in | www.kerala.gov.in
23874 | National Highways Authority Of India | 155597 | Bhadohi-Mariahu-Jaunpur (NH-135A) Highway Project | 1936 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23875 | National Highways Authority Of India | 155597 | Bhadohi-Mariahu-Jaunpur (NH-135A) Highway Project | 1936 | Co-promoter | Uttar Pradesh Public Works Department | 375252 | India | Registered Office:Nirman Bhawan, 96, Mahatma Gandhi Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2236496 |  | pwdgislko@gmail.com | www.uppwd.gov.in
23876 | National Highways Authority Of India | 155597 | Bhadrak-Baleshwar (NH-16) Six Lane Highway Project (Package-II) | 1023 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
23877 | National Highways Authority Of India | 155597 | Bhadrak-Chandikhole (OR-II) Highway Project | 137 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23878 | National Highways Authority Of India | 155597 | Bhadrak-Chandikhole (OR-II) Highway Project | 137 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23879 | National Highways Authority Of India | 155597 | Bhamaiya village-Baletiya village Eight Lane Access-Controlled Expressway Project (Package 29 of Delhi-Mumbai Expressway) | 1635 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
23880 | National Highways Authority Of India | 155597 | Bhamaiya village-Baletiya village Eight Lane Access-Controlled Expressway Project (Package 29 of Delhi-Mumbai Expressway) | 1635 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
23881 | National Highways Authority Of India | 155597 | Bhamaiya village-Baletiya village Eight Lane Access-Controlled Expressway Project (Package 29 of Delhi-Mumbai Expressway) | 1635 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
23882 | National Highways Authority Of India | 155597 | Bhandara (Wainganga)-Durg Highway Project | 441 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
23883 | National Highways Authority Of India | 155597 | Bhandara (Wainganga)-Durg Highway Project | 441 | Contractor | Prafful (india) Pvt. Ltd. | 348643 | India | Registered Office:No. 37-A, Avardan House, Kashmiri Gate, | 110001 | New Delhi | Delhi
23884 | National Highways Authority Of India | 155597 | Bhaniyawala-Jollygrant-Rishikesh (NH-07) Four Lane Highway Project | 2123 | Consultant | Yongma Engineering Co. Ltd. | 585553 | India | Registered Office:Unit 301, 302, Time Centre, Golf Course Road, Sector 54, | 122002 | Gurgaon | Haryana |  |  | vba1981mca@gmail.com | www.ymeng.co.kr
23885 | National Highways Authority Of India | 155597 | Bharauli (Buxar)-Haidariya (NH-31) Four Lane Greenfield Link Road Project (connecting Purvanchal Expressway) | 2070 | Consultant | Voyants Solutions Pvt. Ltd. | 436055 | India | Registered Office:403, 4th Floor, Park Centra, Sector 30, Opp. 32nd Milestone, NH-8, | 122001 | Gurgaon | Haryana | 91-124-4598200 | 91-124-4019051 | arunkumar@adrasl.com | www.voyants.in
23886 | National Highways Authority Of India | 155597 | Bharuch Logistics Park Project | 1371 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23887 | National Highways Authority Of India | 155597 | Bharuch to Surat Package BOT- II Highway Project | 213 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23888 | National Highways Authority Of India | 155597 | Bharuch to Surat Package BOT- II Highway Project | 213 | Contractor | I R B Infrastructure Pvt. Ltd. | 96911 | India | Registered Office:I R B Complex, Chandivi Farm, Chandivli Village, Andheri (E), | 400072 | Mumbai | Maharashtra | 91-22-66404200 | 91-22-66751024 | grievances@irb.co.in | www.irb.co.in
23889 | National Highways Authority Of India | 155597 | Bhatinda Logistics Park Project | 1347 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23890 | National Highways Authority Of India | 155597 | Bhavnagar-Sosiya-Alang Ship Recycling Yard Alternative Road Project (Bharatmala) | 1359 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23891 | National Highways Authority Of India | 155597 | Bhavnagar-Talaja (NH-8E) (Package-I Bhavnagar-Veraval Section) Four/Six Lane Highway Project | 927 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
23892 | National Highways Authority Of India | 155597 | Bhavnagar-Talaja (NH-8E) (Package-I Bhavnagar-Veraval Section) Four/Six Lane Highway Project | 927 | Contractor | Sadbhav Infrastructure Project Ltd. | 385775 | India | Registered Office:Sadbhav House, Ellibridge, Opp Law Garden Police Chowki, | 380006 | Ahmedabad | Gujarat | 91-79-26463384 | 91-79-26400210 | gaurav.vesasi@sadbhav.co.in | www.sadbhavinfra.co.in
23893 | National Highways Authority Of India | 155597 | Bhavnagar-Talaja (NH-8E) (Package-I Bhavnagar-Veraval Section) Four/Six Lane Highway Project | 927 | EPC contractor | Sadbhav Bhavnagar Highway Ltd. | 549006 | India | Registered Office:Sadbav House, Opp Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat |  |  | hardik.modi@sadbhav.co.in
23894 | National Highways Authority Of India | 155597 | Bheem-Parsoli (NH-148 D) Two Lane Highway Project (Phase 2) | 1013 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23895 | National Highways Authority Of India | 155597 | Bheem-Parsoli Two Lane (Phase 1) Highway Widening Project | 1012 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23896 | National Highways Authority Of India | 155597 | Bhilwara-Ladpura (NH-758) Two Lane Road Project | 916 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
23897 | National Highways Authority Of India | 155597 | Bhilwara-Ladpura (NH-758) Two Lane Road Project | 916 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23898 | National Highways Authority Of India | 155597 | Bhilwara-Ladpura (NH-758) Two Lane Road Project | 916 | Contractor | Zignego Company Inc. | 482693 | USA |  | NA
23899 | National Highways Authority Of India | 155597 | Bhiwani-Hansi (NH-148B) Four Lane Highway Project | 2073 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
23900 | National Highways Authority Of India | 155597 | Bhogpur to Jalandhar (NS-16/PB) Highway Project | 197 | Turnkey contractor | Bhumi Highway D D B L | 35111 | Malaysia |  | NA
23901 | National Highways Authority Of India | 155597 | Bhogpur-Mukerian (NH-1A) Four Laning Highway project | 768 | Consultant | Nag Infrastructure Consulting Engineers Pvt. Ltd. | 153259 | India | Registered Office:2nd Floor, Ravula Residency, 8-2-5-12, Srinagar Colony Main Road, | 500082 | Hyderabad | Andhra Pradesh
23902 | National Highways Authority Of India | 155597 | Bhogpur-Mukerian (NH-1A) Four Laning Highway project | 768 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
23903 | National Highways Authority Of India | 155597 | Bhogu-Sankha (NH-75) Four Lane Highway Project (Package-3) | 2048 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
23904 | National Highways Authority Of India | 155597 | Bhogu-Sankha (NH-75) Four Lane Highway Project (Package-3) | 2048 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
23905 | National Highways Authority Of India | 155597 | Bhojpur-Buxar (NH-84 & NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1088 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
23906 | National Highways Authority Of India | 155597 | Bhojpur-Buxar (NH-84 & NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1088 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
23907 | National Highways Authority Of India | 155597 | Bhopal (Mandideep) Logistics Park Project | 1351 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23908 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23909 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Consultant | L R P Consultants Consortium Pvt. Ltd. | 293646 | India | Registered Office:No. L-384-A, Mahipal Pur Extension, National Highway No. 8, | 110037 | New Delhi | Delhi |  |  | LRPCC79@GMAIL.COM | www.lrpcc.com
23910 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Consultant | East Consultancy Services Pvt. Ltd. | 580872 | India | Registered Office:320-1/1, Raheja Arcade Koramangala Inds. Layout, Koramangala, | 560095 | Bengaluru | Karnataka |  |  | accounts@eastcs.com
23911 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Contractor | Iron Triangle Ltd. | 384589 | India | Corporate Office:209, Akik Tower, Opp Rajpath Club, S G Highway, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-26840710 | 91-79-40040710 |  | www.irontriangle.in
23912 | National Highways Authority Of India | 155597 | Bhopal-Sanchi (NH-86 Extn.) (New NH-146) Highway Project | 1062 | Contractor | Ashish Infracon Pvt. Ltd. | 414537 | India | Registered Office:602, Indraprasth Corp. Opp. Venus Atlantis, Prahladnagar, | 380015 | Ahmedabad | Gujarat | 91-79-66172925 |  | account@ashishinfracon.com | www.ashishinfracon.com
23913 | National Highways Authority Of India | 155597 | Bhubaneshwar-Khurda (OR-I) Highway Project | 139 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23914 | National Highways Authority Of India | 155597 | Bhubaneshwar-Khurda (OR-I) Highway Project | 139 | Contractor | Atlanta Construction Co. (i) Ltd. | 24021 | India | Registered Office:Atlanta B-22-A, V.M. Road Vile Parle, | 400049 | Mumbai | Maharashtra | 91-22-26141048 | 91-22-26113792
23915 | National Highways Authority Of India | 155597 | Bhubaneshwar-Khurda (OR-I) Highway Project | 139 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
23916 | National Highways Authority Of India | 155597 | Bhubaneshwar-Puri (NH-203) Four-Laning Highway Project | 1402 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
23917 | National Highways Authority Of India | 155597 | Bhubaneshwar-Puri (NH-203) Four-Laning Highway Project | 1402 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
23918 | National Highways Authority Of India | 155597 | Bihar/Jharkhand Border (Chordaha)-Gorhar (NH-2) Six Laning Highway Project (Package-II) | 1113 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23919 | National Highways Authority Of India | 155597 | Bihar/Jharkhand Border (Chordaha)-Gorhar (NH-2) Six Laning Highway Project (Package-II) | 1113 | Contractor | Reliance Infrastructure Ltd. | 27747 | India | Registered Office:Reliance Centre, Ground Floor 19, Walchand Hirachand Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-43031000 | 91-22-43033664 | rinfra.investor@relianceada.com | www.rinfra.com
23920 | National Highways Authority Of India | 155597 | Biharsharif-Barbigha-Mokama (NH-82) Two Laning Road Project | 821 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
23921 | National Highways Authority Of India | 155597 | Biharsharif-Barbigha-Mokama (NH-82) Two Laning Road Project | 821 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
23922 | National Highways Authority Of India | 155597 | Bijapur-Gulbarga-Humnabad (NH-218) Two lane Highway Project | 934 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
23923 | National Highways Authority Of India | 155597 | Bijapur-Gulbarga-Humnabad (NH-218) Two lane Highway Project | 934 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23924 | National Highways Authority Of India | 155597 | Bijni-Assam/WB Border (NH-31C) Four-Laning Highway Project | 284 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
23925 | National Highways Authority Of India | 155597 | Bijni-Assam/WB Border (NH-31C) Four-Laning Highway Project | 284 | Contractor | Simplex Infrastructures Ltd. | 227710 | India | Registered Office:Simplex House, 27, Shakespeare Sarani, | 700017 | Kolkata | West Bengal | 91-33-23011600 | 91-33-22835964 | secretarial.legal@simplexinfra.com | www.simplexinfra.com
23926 | National Highways Authority Of India | 155597 | Bijni-Assam/WB Border (NH-31C) Four-Laning Highway Project | 284 | Supervision consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23927 | National Highways Authority Of India | 155597 | Bijnor-Kotawali (Nagina) (NH-709AD) Four Lane Highway Project (Package 4 of Panipat-Nagina Highway) | 1643 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
23928 | National Highways Authority Of India | 155597 | Bijnor-Kotawali (Nagina) (NH-709AD) Four Lane Highway Project (Package 4 of Panipat-Nagina Highway) | 1643 | Contractor | Mathiyan Construction Pvt. Ltd. | 419088 | India |  | NA
23929 | National Highways Authority Of India | 155597 | Bijnor-Kotawali (Nagina) (NH-709AD) Four Lane Highway Project (Package 4 of Panipat-Nagina Highway) | 1643 | Contractor | A P S Hydro Pvt. Ltd. | 483858 | India | Registered Office:House No. 58, Floor 1st, Block 10 Landmark Opp. Old Police Station Kirti Nagar Ind. Area, | 110015 | New Delhi | NCT of Delhi |  |  | apshydro@gmail.com
23930 | National Highways Authority Of India | 155597 | Biju Para-Kuru (NH-75) Four Laning Highway Project (Package-II) | 1227 | Contractor | Jaiprakash Associates Ltd. | 108841 | India | Corporate Office:JA House', 63, Basant Lok Vasant Vihar, | 110057 | New Delhi | NCT of Delhi | 91-11-4982500 | 91-11-26145389 | jalinvestor@jalindia.co.in | www.jalindia.com
23931 | National Highways Authority Of India | 155597 | Binjhabahal-Telebani (NH-49) Four Laning Highway Project | 1021 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
23932 | National Highways Authority Of India | 155597 | Binjhabahal-Telebani (NH-49) Four Laning Highway Project | 1021 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
23933 | National Highways Authority Of India | 155597 | Bodare-Dhule (NH-52) Four/Six Laning Highway Project | 1149 | Contractor | Kalthia Engineering & Construction Ltd. | 114870 | India | Corporate Office:28, Rangin Park, Opp. Rajpath Club, S G Highway, Bodakdev, | 380059 | Ahmedabad | Gujarat | 91-79-26870501 | 91-79-26870501 | kecl@kathiagroup.com | www.kalthiagroup.com
23934 | National Highways Authority Of India | 155597 | Bodare-Dhule (NH-52) Four/Six Laning Highway Project | 1149 | Contractor | Sunil Hitech Engineers Ltd. | 326027 | India | Corporate Office:MET Educational Complex, 6th Floor, C WIng, A K Vaidya Marg, Bandra Reclamation, Bandra (W), | 400050 | Mumbai | Maharashtra | 91-22-61872400 | 91-22-61872455 | cs@sunilhitech.com | www.sunilhitech.com
23935 | National Highways Authority Of India | 155597 | Bodare-Dhule (NH-52) Four/Six Laning Highway Project | 1149 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
23936 | National Highways Authority Of India | 155597 | Bokaro-Chas (NH-23) bridge over Garga river Project | 987 | Contractor | Hindustan Steelworks Construction Ltd. | 94142 | India | Registered Office:P-34 A, Gariahat Road (South), | 700031 | Kolkata | West Bengal | 91-33-22230663 | 91-33-24737546 | cshscl@nbccindia.com | www.hscl.co.in
23937 | National Highways Authority Of India | 155597 | Boregaon Buzurg to Shahpur Four Lane Road (NH-753L) Project (Package-I of Boregaon Buzurg-Muktainagar Road) | 2079 | Contractor | Kalyan Toll Infrastructure Ltd. | 386962 | India | Registered Office:Vidhya Deep, 15/3 Manorama Ganj, | 452001 | Indore | Madhya Pradesh | 91-731-2496931 | 91-731-4096457 | accounts@kalyangroup.in | www.kalyangroup.in
23938 | National Highways Authority Of India | 155597 | Borkhedi-Jam (NS-22/MH) Highway Project | 258 | Consultant | S O W I L Ltd. | 228409 | India | Registered Office:Flat No. 2, Esha Ekta Apt., Worli, Campacola Compound, B G Kher Road, | 400018 | Mumbai | Maharashtra | 91-22-24941743 | 91-22-4936970 | corporate@sowillimited.com
23939 | National Highways Authority Of India | 155597 | Borkhedi-Jam (NS-22/MH) Highway Project | 258 | Contractor | J S R Constructions Pvt. Ltd. | 104773 | India | Registered Office:No. 3415, IInd Stage, Indiranagar, | 560038 | Bengaluru | Karnataka
23940 | National Highways Authority Of India | 155597 | Borkhedi-Jam (NS-22/MH) Highway Project | 258 | Contractor | Ketan Construction Ltd. | 390601 | India | Corporate Office:209, Sumel-II, Near Gurudwara, S G Highway, | 380054 | Ahmedabad | Gujarat | 91-79-26857701 | 91-79-26851773 | kcl@kclindia.com | www.kclindia.com
23941 | National Highways Authority Of India | 155597 | Brahmani Bypass (End of NH-23)-Rajamunda (NH-143) Four Laning Highway Project (Birmitrapur-Barkote) | 981 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
23942 | National Highways Authority Of India | 155597 | Brahmani Bypass (End of NH-23)-Rajamunda (NH-143) Four Laning Highway Project (Birmitrapur-Barkote) | 981 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
23943 | National Highways Authority Of India | 155597 | Brahmani Bypass (End of NH-23)-Rajamunda (NH-143) Four Laning Highway Project (Birmitrapur-Barkote) | 981 | Contractor | Vijay Kumar Sahu Infrastructure Pvt. Ltd. | 576107 | India |  | NA
23944 | National Highways Authority Of India | 155597 | Brahmaputra Express Highway Project | 1279 | Co-promoter | Government Of Assam | 84837 | India | Registered Office:Assam Sachivalaya Complex, Dispur, | 781006 | Guwahati | Assam | 91-361-2724222 | 91-361-22883105 | gad.assam@gov.in | www.assam.gov.in
23945 | National Highways Authority Of India | 155597 | Brahmaputra Express Highway Project | 1279 | Co-promoter | Inland Waterways Authority Of India | 100848 | India | Head Office:A-13, Sector-1, | 201301 | Noida | Uttar Pradesh | 91-120-2544036 | 91-120-4543973 | iwainoi@nic.in | www.iwai.nic.in
23946 | National Highways Authority Of India | 155597 | Brahmaputra Express Highway Project | 1279 | Consultant | Wapcos Ltd. | 270852 | India | Head Office:Ground Floor, APGENCO Building, G T S Colony, Erragadda, | 500045 | Hyderabad | Telangana | 91-40-23840268 | 91-40-23840267 | ho@wapcos.gov.in | www.wapcos.gov.in
23947 | National Highways Authority Of India | 155597 | Brahmputra Bridge (AS-28) Project | 281 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
23948 | National Highways Authority Of India | 155597 | Brahmputra Bridge (AS-28) Project | 281 | Supervision consultant | Mott Mac Donald Pvt. Ltd. | 375482 | India | Registered Office:101, Nomura Hiranandani Gardens, Powai, | 400076 | Mumbai | Maharashtra |  |  | alkesh.parikh@mottmac.com | www.mottmac.com
23949 | National Highways Authority Of India | 155597 | Bridge over Rapti River at Gorakhpur (Addl. 2 Lane) Project | 956 | Consultant | S O W I L Ltd. | 228409 | India | Registered Office:Flat No. 2, Esha Ekta Apt., Worli, Campacola Compound, B G Kher Road, | 400018 | Mumbai | Maharashtra | 91-22-24941743 | 91-22-4936970 | corporate@sowillimited.com
23950 | National Highways Authority Of India | 155597 | Bridge over Rapti River at Gorakhpur (Addl. 2 Lane) Project | 956 | Contractor | Uttar Pradesh State Bridge Corpn. Ltd. | 255951 | India | Registered Office:Setu Bhawan, 16, Madan Mohan Malviya Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2209702 | 91-522-2209798 | upsbcltd@gmail.com | www.bridgecorporationltd.com
23951 | National Highways Authority Of India | 155597 | Bridge Over River Jia Bharali (NH-715) Project | 487 | Co-promoter | National Highways & Infrastructure Development Corporation Ltd. | 518179 | India | Registered Office:PTI Building, 3rd Floor, 4 Parliment Street, | 110001 | New Delhi | NCT of Delhi |  |  | info@nhidcl.com | www.nhidcl.com
23952 | National Highways Authority Of India | 155597 | Bridge Over River Jia Bharali (NH-715) Project | 487 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
23953 | National Highways Authority Of India | 155597 | Bridge Over River Jia Bharali (NH-715) Project | 487 | Contractor | R S M Infra (maharashtra) | 631348 | India |  | NA
23954 | National Highways Authority Of India | 155597 | BRT Tiger Reserve-Bangalore (NH-209) Two/Four-Laning Highway Project | 1172 | Contractor | Sadbhav Infrastructure Project Ltd. | 385775 | India | Registered Office:Sadbhav House, Ellibridge, Opp Law Garden Police Chowki, | 380006 | Ahmedabad | Gujarat | 91-79-26463384 | 91-79-26400210 | gaurav.vesasi@sadbhav.co.in | www.sadbhavinfra.co.in
23955 | National Highways Authority Of India | 155597 | BRT Tiger Reserve-Bangalore (NH-209) Two/Four-Laning Highway Project | 1172 | Sub contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
23956 | National Highways Authority Of India | 155597 | Budhel Junction-Nari Circle (NH-51) Four Lane Road (Missing Link) Project | 1805 | Consultant | Sheladia Associates Inc. | 287104 | India | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
23957 | National Highways Authority Of India | 155597 | Butibori ROB (NS-29/MH) Project | 44 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
23958 | National Highways Authority Of India | 155597 | Butibori ROB (NS-29/MH) Project | 44 | Contractor | J S R Constructions Pvt. Ltd. | 104773 | India | Registered Office:No. 3415, IInd Stage, Indiranagar, | 560038 | Bengaluru | Karnataka
23959 | National Highways Authority Of India | 155597 | Butibori-MIDC T-Junction (NH-44) Flyover Project | 1276 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
23960 | National Highways Authority Of India | 155597 | Butibori-MIDC T-Junction (NH-44) Flyover Project | 1276 | Contractor | T & T Infra Ltd. | 543147 | India | Registered Office:Office No.1 To 5, A1, Visnu Vihar, Bibwewadi Kondhwa Road, Marketyard, | 411037 | Pune | Maharashtra | 91-20-24275945 |  | groupt_t@yahoo.co.in | www.tandtinfra.com
23961 | National Highways Authority Of India | 155597 | Chambal Bridge (RJ-5) Project | 738 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
23962 | National Highways Authority Of India | 155597 | Chambal Bridge (RJ-5) Project | 738 | Contractor | Hyundai Engg. & Construction Co. | 96226 | Korea Republic (South) | Registered Office:140-2,Kye Dong Chongro-Ku Seoul South Korea | NA
23963 | National Highways Authority Of India | 155597 | Chambal Four/Six/Eight Lane Expressway Project (Chambal Progressway or Atal Progressway) | 1532 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
23964 | National Highways Authority Of India | 155597 | Chambal Four/Six/Eight Lane Expressway Project (Chambal Progressway or Atal Progressway) | 1532 | Promoter | Madhya Pradesh Road Devp. Corpn. Ltd. | 352545 | India | Head Office:16-A, Arera Hills, | 462001 | Bhopal | Madhya Pradesh | 91-755-2765196 | 91-755-2572643 | mismprdc@mp.nic.in | www.mprdc.nic.in
23965 | National Highways Authority Of India | 155597 | Champawati-Vishakhapatnam (AP-3) Highway Project | 103 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
23966 | National Highways Authority Of India | 155597 | Champawati-Vishakhapatnam (AP-3) Highway Project | 103 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
23967 | National Highways Authority Of India | 155597 | Champawati-Vishakhapatnam (AP-3) Highway Project | 103 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
23968 | National Highways Authority Of India | 155597 | Champawati-Vishakhapatnam (AP-3) Highway Project | 103 | Contractor | Unitech Ltd. | 257777 | India | Corporate Office:1306-1308, 13 th Floor, Tower B, Signature Towers, South City-1, | 122007 | Gurgaon | Haryana | 91-124-4726860 | 91-124-2383332 | share.dept@unitechgroup.com | www.unitechgroup.com
23969 | National Highways Authority Of India | 155597 | Chandesari-Khedakhajuria (NH-148) Four Lane Highway Project (Package 1 of Ujjain-Garoth Section) | 1883 | Consultant | Wolkem India Ltd. | 321676 | India | Registered Office:E-101, Mewar Industrial Area, Madri, Post Box No.21, | 313003 | Udaipur | Rajasthan | 91-294-2494600 | 91-294-2494608 | mktg@wolkem.com | www.wolkem.com
23970 | National Highways Authority Of India | 155597 | Chandesari-Khedakhajuria (NH-148) Four Lane Highway Project (Package 1 of Ujjain-Garoth Section) | 1883 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
23971 | National Highways Authority Of India | 155597 | Chandigarh (Balongi)-Kharar Section (NH-21), (NH-205 & 05) Four Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1032 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23972 | National Highways Authority Of India | 155597 | Chandigarh (Balongi)-Kharar Section (NH-21), (NH-205 & 05) Four Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1032 | Consultant | J P S Associates Pvt. Ltd. | 603350 | India | Registered Office:R-16, Hauz Khas Enclave, | 110016 | New Delhi | NCT of Delhi | 91-11-26862487 | 91-11-26864547 | info@jps-india.com | www.jps-india.com
23973 | National Highways Authority Of India | 155597 | Chandigarh (Balongi)-Kharar Section (NH-21), (NH-205 & 05) Four Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1032 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
23974 | National Highways Authority Of India | 155597 | Chandigarh-Manali (NH-21) Four Laning Highway Project | 1295 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
23975 | National Highways Authority Of India | 155597 | Chandikhol-Jagatpur Highway Project | 34 | Consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
23976 | National Highways Authority Of India | 155597 | Chandikhol-Jagatpur Highway Project | 34 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
23977 | National Highways Authority Of India | 155597 | Chandikhol-Jagatpur Highway Project | 34 | Turnkey contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
23978 | National Highways Authority Of India | 155597 | Chandikhole-Paradeep (NH-5A) Six Laning Road Project (Part of Paradip-Kalinganagar Highway) | 893 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
23979 | National Highways Authority Of India | 155597 | Chandikhole-Paradeep (NH-5A) Six Laning Road Project (Part of Paradip-Kalinganagar Highway) | 893 | Consultant | Meinhardt (singapore) Pte Ltd. | 286809 | Singapore | Registered Office:A - 8, Sector 16, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh | 91-120-2516165 | 91-120-2515745 | rajesh@meinhardtindia.com | www.meinhardtgroup.com
23980 | National Highways Authority Of India | 155597 | Chandikhole-Paradeep (NH-5A) Six Laning Road Project (Part of Paradip-Kalinganagar Highway) | 893 | Consultant | C M E C Engineering-consultancy & Surveyors Pvt. Ltd. | 306924 | India | Registered Office:182/A, Sahid Nagar, | 751007 | Bhubaneswar | Orissa
23981 | National Highways Authority Of India | 155597 | Chandikhole-Paradeep (NH-5A) Six Laning Road Project (Part of Paradip-Kalinganagar Highway) | 893 | Consultant | Agnitio Infrastructure Projects Pvt. Ltd. | 550455 | India | Registered Office:9B, Bharat Apartment 31, I P Extension, Patparganj, | 110092 | New Delhi | NCT of Delhi |  |  | 05rahulmishra@gmail.com
23982 | National Highways Authority Of India | 155597 | Chandikhole-Paradip Four lane Highway Project | 369 | Co-promoter | Paradip Port Trust | 170233 | India | Registered Office:Paradip Port Trust, Paradip Port, | 754142 | Jagatsinghapur | Orissa | 91-6722-222046 | 91-6722-222256 | chmppt@paradipport.gov.in | www.paradipport.gov.in
23983 | National Highways Authority Of India | 155597 | Chandikhole-Paradip Four lane Highway Project | 369 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23984 | National Highways Authority Of India | 155597 | Chandni Chowk Multi-Level Bridge Project | 1555 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
23985 | National Highways Authority Of India | 155597 | Chandni Chowk Multi-Level Bridge Project | 1555 | Promoter | Pune Municipal Corpn. | 183660 | India | Registered Office:P M C Main Building, Near Mangla Theatre, Shivajinagar, | 411005 | Pune | Maharashtra | 91-20-25501000 | 91-20-25501104 | info@punecorporation.org | www.pmc.gov.in
23986 | National Highways Authority Of India | 155597 | Chandrasekharapuram-Polavaram (NH-544G) Six Lane Greenfield Expressway Project (Package-11 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1976 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
23987 | National Highways Authority Of India | 155597 | Channarayanpatna (NH-75) Four Lane Bypass Project | 1652 | Contractor | Power Mech Projects Ltd. | 177768 | India | Corporate Office:Plot No.77, Jubilee Enclave, Opp. Hitex, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-30444444 | 91-40-30444400 | info@powermech.net | www.powermechprojects.in
23988 | National Highways Authority Of India | 155597 | Channarayanpatna (NH-75) Four Lane Bypass Project | 1652 | Contractor | S R C Infra Developers Pvt. Ltd. | 598980 | India | Registered Office:7-272, kakateeya Residency Court Road, | 515001 | Anantapur | Andhra Pradesh |  |  | sheema.src1@gmail.com
23989 | National Highways Authority Of India | 155597 | Chas-Bokaro-Gola-Ramgarh (NH-23) Two/Four Laning Road Project | 823 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
23990 | National Highways Authority Of India | 155597 | Chatra to Junc with NH-100 in Deoria Village Four/Six Lane Access Controlled Greenfield Highway Project (Package-9 of Varanasi-Kolkata Expressway) | 2119 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
23991 | National Highways Authority Of India | 155597 | Chengala-Neleshwaram-Kalikadavu Town (NH-66) Six Laning Highway Project | 1407 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
23992 | National Highways Authority Of India | 155597 | Chengala-Neleshwaram-Kalikadavu Town (NH-66) Six Laning Highway Project | 1407 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
23993 | National Highways Authority Of India | 155597 | Chengala-Neleshwaram-Kalikadavu Town (NH-66) Six Laning Highway Project | 1407 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
23994 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 1 Project | 32 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
23995 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 1 Project | 32 | Contractor | Satyam Constructions Ltd. | 214300 | India | Registered Office:Mayfair Centre, 1-8-303/34/1, Sardar Patel Road, | 500003 | Secunderabad | Andhra Pradesh | 91-40-840671 | 91-40-840058
23996 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 1 Project | 32 | Contractor | I J M (india) Infrastructure Ltd. | 312743 | India | Registered Office:H.No.3-71/NR, Plot No.71, Kavuri Hills-II, Madhapur, | 500033 | Hyderabad | Telangana |  |  | venkareddy@ijm.com | www.ijm.com
23997 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 2 Project | 390 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
23998 | National Highways Authority Of India | 155597 | Chennai Bypass Phase 2 Project | 390 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
23999 | National Highways Authority Of India | 155597 | Chennai Dedicated Container Corridor to NHAI Road Project | 1660 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24000 | National Highways Authority Of India | 155597 | Chennai Port -Maduravoyal Double Decker Elevated Corridor Project (Bharatmala) | 1397 | Co-promoter | Chennai Port Trust | 46012 | India | Registered Office:Rajaji Salai, Chennai, Tamil Nadu | 600001 |  |  | 91-44-25362201 | 91-44-25361228 | cprochpt@md4.vsnl.net.in/mmschpt@md3.vsnl.net.in | www.chennaiport.gov.in
24001 | National Highways Authority Of India | 155597 | Chennai Port -Maduravoyal Double Decker Elevated Corridor Project (Bharatmala) | 1397 | Consultant | L & T Infrastructure Engg. Ltd. | 125145 | India | Corporate Office:339/340, Anna Salai, Nandanam, | 600035 | Chennai | Tamil Nadu | 91-44-24331181 | 91-44-24331183 | lntielchm@lntiel.com | www.lntiel.com
24002 | National Highways Authority Of India | 155597 | Chennai Port -Maduravoyal Double Decker Elevated Corridor Project (Bharatmala) | 1397 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
24003 | National Highways Authority Of India | 155597 | Chennai Port -Maduravoyal Double Decker Elevated Corridor Project (Bharatmala) | 1397 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24004 | National Highways Authority Of India | 155597 | Chennai-Tada (NH-16) Six laning Highway Project | 1314 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | Canada | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24005 | National Highways Authority Of India | 155597 | Chennai-Tada (NH-16) Six laning Highway Project | 1314 | Contractor | S P L Infrastructure Pvt. Ltd. | 516118 | India | Registered Office:No. 24 , Crescent Part Street, 1st Floor, T Nagar, | 600018 | Chennai | Tamil Nadu | 91-44-48674770 | 91-44-2364787 | info@splinfra.com | www.splinfra.com
24006 | National Highways Authority Of India | 155597 | Chennai-Trichy-Tuticorin Four/Six Lane Expressway Project | 2091 | Consultant | E G I S India Consulting Engineers Pvt. Ltd. | 534570 | India | Registered Office:T-305, TF, Tirupati Plaza, Sector XI (MLU) Pkt-4, Plot No. 11, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-45704300 | 91-11-4050892 | egise_india@egis_india.com | www.egis_india.com
24007 | National Highways Authority Of India | 155597 | Cherlopalli-Pileru (NH-71) Four Lane Highway Project (Part of Tirupati-Cherlopalli-Pileru-Madanapalle Economic Corridor) | 1694 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24008 | National Highways Authority Of India | 155597 | Cherthalai-Ochira (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 542 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24009 | National Highways Authority Of India | 155597 | Cherthalai-Ochira (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 542 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24010 | National Highways Authority Of India | 155597 | Chettikulam (Madurai)-Natham (NH-785) Four Lane Highway Project (Bharatmala) | 1484 | Contractor | Ksheeraabd Constructions Pvt. Ltd. | 393689 | India |  | NA
24011 | National Highways Authority Of India | 155597 | Chettikulam (Madurai)-Natham (NH-785) Four Lane Highway Project (Bharatmala) | 1484 | Contractor | Om Sakthi Constructions | 466079 | India | Registered Office:M 13/11 Navabarath Colony, Kalakshetra Colony, Besant Nagar, | 600090 | Chennai | Tamil Nadu
24012 | National Highways Authority Of India | 155597 | Chhapra-Rewaghat-Muzaffarpur (NH-102) Two Lane Road Project | 827 | Consultant | Scott Wilson Ltd. | 547252 | India |  | NA
24013 | National Highways Authority Of India | 155597 | Chhapra-Rewaghat-Muzaffarpur (NH-102) Two Lane Road Project | 827 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24014 | National Highways Authority Of India | 155597 | Chhattisgarh/Maharashtra Border-Wainganga Bridge Highway Project | 594 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
24015 | National Highways Authority Of India | 155597 | Chhattisgarh/Maharashtra Border-Wainganga Bridge Highway Project | 594 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24016 | National Highways Authority Of India | 155597 | Chhattisgarh/Maharashtra Border-Wainganga Bridge Highway Project | 594 | Contractor | I D F C Ltd. | 100709 | India | Corporate Office:906/907, 9th Floor, Embassy Centre, Jamnalal Bajaj Road, Nariman Point, | 400021 | Mumbai | Maharashtra | 91-22-22821549 | 91-22-24215052 | info@idfc.com | www.idfc.com
24017 | National Highways Authority Of India | 155597 | Chicholi-Betul (NH-47) Four Lane Highway Project (Package 3 of Harda-Betul) (Bharatmala) | 1703 | Contractor | Bansal Construction Works Pvt. Ltd. | 470219 | India | Corporate Office:3rd Floor, Tawa Cplx, E-5, Bittan Market Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2423736 | 91-755-4224036 | sunilbcw@rediffmail.com
24018 | National Highways Authority Of India | 155597 | Chicholi-Temagaon (NH-47) Four Lane Highway Project (Package 2 of Harda-Betul) | 1822 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24019 | National Highways Authority Of India | 155597 | Chicholi-Temagaon (NH-47) Four Lane Highway Project (Package 2 of Harda-Betul) | 1822 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
24020 | National Highways Authority Of India | 155597 | Chicholi-Temagaon (NH-47) Four Lane Highway Project (Package 2 of Harda-Betul) | 1822 | Contractor | Skylark Infra Engg. Pvt. Ltd. | 534566 | India |  | NA
24021 | National Highways Authority Of India | 155597 | Chichra-Kharagpur (NH-6) Four Laning Highway Project | 1091 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
24022 | National Highways Authority Of India | 155597 | Chichra-Kharagpur (NH-6) Four Laning Highway Project | 1091 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24023 | National Highways Authority Of India | 155597 | Chilakaluripet (NH-16) Six Lane Bypass Project (Bharatmala) | 1528 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24024 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Chilkaluripet-Ongole) Highway Project | 105 | Consultant | K M International Ltd. | 112487 | India |  | NA
24025 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Chilkaluripet-Ongole) Highway Project | 105 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24026 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Chilkaluripet-Ongole) Highway Project | 105 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24027 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Chilkaluripet-Ongole) Highway Project | 105 | Contractor | I J M Constructions Sdn Bhd | 324217 | Malaysia | Registered Office:Malaysia | NA
24028 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Ongole-Kavali) Highway Project | 106 | Consultant | K M International Ltd. | 112487 | India |  | NA
24029 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Ongole-Kavali) Highway Project | 106 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24030 | National Highways Authority Of India | 155597 | Chilkaluripet-Nellore(Ongole-Kavali) Highway Project | 106 | Contractor | Simplex Construction Pvt. Ltd. | 227713 | India | Registered Office:24, C-Block Community Centre, Janak Puri, | 110058 | New Delhi | Delhi | 91-11-5515086
24031 | National Highways Authority Of India | 155597 | Chillakuru Cross Road-Turpu Kanupur (NH-516W) Four Lane Highway Project | 2057 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24032 | National Highways Authority Of India | 155597 | Chilodha-Naroda Six Laning Highway Project (Package-VII) (Kishangarh-Ahmadabad) | 1244 | Consultant | Louis Berger Consulting Pvt. Ltd. | 406754 | India | Registered Office:Regus Business Centre, Level-3, Vasant Square Mall Pocket V, Sector B, | 110070 | New Delhi | NCT of Delhi |  |  | neeraj.kumar2@wsp.com | www.wsp.com
24033 | National Highways Authority Of India | 155597 | Chilodha-Naroda Six Laning Highway Project (Package-VII) (Kishangarh-Ahmadabad) | 1244 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24034 | National Highways Authority Of India | 155597 | Chinchbhuvan-Khapri Four Lane Railway Over Bridge Project (on Wardha Road) | 1058 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24035 | National Highways Authority Of India | 155597 | Chinchbhuvan-Khapri Four Lane Railway Over Bridge Project (on Wardha Road) | 1058 | Contractor | D P Jain & Co Infrastructure Pvt. Ltd. | 409463 | India | Registered Office:U/6, Himalaya Accord Apartment Opp. Law College Amravati Road, | 440010 | Nagpur | Maharashtra | 91-712-2535357 | 91-712-2560836 | dpjain.company@dpjaingroup.com | www.dpjaingroup.com
24036 | National Highways Authority Of India | 155597 | Chinchbhuvan-Khapri Four Lane Railway Over Bridge Project (on Wardha Road) | 1058 | Contractor | Khalatkar Construction | 479186 | India |  | NA
24037 | National Highways Authority Of India | 155597 | Chinna Orampadu-Renigunta (NH-716) Four Lane Highway Project (Package-2 of Kadapa-Renigunta section) | 2106 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
24038 | National Highways Authority Of India | 155597 | Chintagudem Village to Recherla Village Four Lane Access Controlled Greenfield Highway Project (Package 3 of Khammam-Devarapalle NH) (Bharatmala) | 1712 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24039 | National Highways Authority Of India | 155597 | Chintagudem Village to Recherla Village Four Lane Access Controlled Greenfield Highway Project (Package 3 of Khammam-Devarapalle NH) (Bharatmala) | 1712 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24040 | National Highways Authority Of India | 155597 | Chitoor-Kurnool N H-18 Road Project | 15 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24041 | National Highways Authority Of India | 155597 | Chittorgarh Bypass (RJ-6) Project | 959 | Consultant | Stanley Consultants Inc. | 380296 | USA | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
24042 | National Highways Authority Of India | 155597 | Chittorgarh Bypass Project | 220 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24043 | National Highways Authority Of India | 155597 | Chittorgarh Bypass Project | 220 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
24044 | National Highways Authority Of India | 155597 | Cochin Port Road Project | 211 | Consultant | Dalal Mott Macdonald Pvt. Ltd. | 55303 | India | Corporate Office:86, Annie Besant Road, Worli, | 400018 | Mumbai | Maharashtra | 91-22-24934891
24045 | National Highways Authority Of India | 155597 | Cochin Port Road Project | 211 | Contractor | R D S Project Ltd. | 185799 | India | Registered Office:427, Somdutt Chambers-II, 9, Bhikaji Cama Place, | 110066 | New Delhi | NCT of Delhi | 91-11-26170242 | 91-11-26168092 | agra@rdsproject.com | www.rdsproject.com
24046 | National Highways Authority Of India | 155597 | Coimbatore Logistics Park Project | 1363 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24047 | National Highways Authority Of India | 155597 | Connectivity to Enayam through Nagarcoil Port Road Project (Bharatmala) | 1615 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24048 | National Highways Authority Of India | 155597 | Connectivity to Katupalli through Ponnani Port Road Project | 1616 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24049 | National Highways Authority Of India | 155597 | Convent Junction-Sheela Nagar Junction Four/Six Lane Road Project | 2072 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
24050 | National Highways Authority Of India | 155597 | Cuttack-Angul (NH-55) Highway Project | 1035 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24051 | National Highways Authority Of India | 155597 | Cuttack-Angul (NH-55) Highway Project | 1035 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24052 | National Highways Authority Of India | 155597 | Cuttack-Chandbali-Dhamra-Bhadrak-Anandapur National Highway Project | 1117 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
24053 | National Highways Authority Of India | 155597 | Daboka-Nagaon (NH-36) Highway Project | 243 | Contractor | Maytas Infrastructure Co. Ltd. | 365513 | India |  | NA
24054 | National Highways Authority Of India | 155597 | Dabwali Railway Over Bridge Project or Bhatinda-Suratgarh (ROB) Project | 912 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24055 | National Highways Authority Of India | 155597 | Dagmagpur-Lalganj (NH-35) Four Lane Highway Project (Package-II) | 1429 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24056 | National Highways Authority Of India | 155597 | Dahisar-Mumbai Highway Project | 93 | Contractor | Maharashtra Public Works Department | 414179 | India | Registered Office:Opposite Godrej, Showroom, Fort, | 400001 | Mumbai | Maharashtra | 91-22-22078627 |  | diritcc@mahapwd.gov.in | www.mahapwd.com
24057 | National Highways Authority Of India | 155597 | Dahod-Padhi (NH-113) Two Laning Highway Project | 878 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24058 | National Highways Authority Of India | 155597 | Dahod-Padhi (NH-113) Two Laning Highway Project | 878 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24059 | National Highways Authority Of India | 155597 | Dakshin Mechgram-Ranirbazar Four Lane Road (NH-116A) Project | 1912 | Consultant | C E Testing Co. Pvt. Ltd. | 285272 | India | Corporate Office:124 A, N S C Bose Road, | 700092 | Kolkata | West Bengal | 91-33-24286221 | 91-33-24286220 | marketing@cetestindia.com | www.cetestindia.com
24060 | National Highways Authority Of India | 155597 | Dalkhola Four Lane Bypass Project | 422 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24061 | National Highways Authority Of India | 155597 | Dalkhola Four Lane Bypass Project | 422 | Contractor | A B C I Infrastructures Pvt. Ltd. | 322707 | India | Head Office:Knowledge Hub, D N 23, 2nd Floor, Sector V, Salt Lake, | 700091 | Kolkata | West Bengal | 91-33-40044119 |  | kolkata@abciinfra.com | www.abciinfra.com
24062 | National Highways Authority Of India | 155597 | Dalkhola-Islampore Subsection 2 (EW/6) Highway Project | 181 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24063 | National Highways Authority Of India | 155597 | Dalkhola-Islampore Subsection 2 (EW/6) Highway Project | 181 | Turnkey contractor | Lanco Infratech Ltd. | 126872 | India | Corporate Office:Lanco House, Plot No.397, Udyog Vihar, Phase-III, | 122016 | Gurgaon | Haryana | 91-124-4741000 | 91-124-4741878 | complianceofficer.litl@lancogroup.com | www.lancogroup.com
24064 | National Highways Authority Of India | 155597 | Dalkhola-Islampur (EW/5) Highway Project | 223 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24065 | National Highways Authority Of India | 155597 | Dalkhola-Islampur (EW/5) Highway Project | 223 | Turnkey contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24066 | National Highways Authority Of India | 155597 | Damanganga Bridge (Surat-Manor) Project | 260 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24067 | National Highways Authority Of India | 155597 | Dankuni-Kharagpur (Bridge Section WB III) Highway Project | 109 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24068 | National Highways Authority Of India | 155597 | Dankuni-Kharagpur (Bridge Section WB III) Highway Project | 109 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24069 | National Highways Authority Of India | 155597 | Dankuni-Kharagpur (Bridge Section WB III) Highway Project | 109 | Turnkey contractor | Bhagheeratha Engineering Ltd. | 33012 | India | Head Office:3rd Flr, Bhagheeratha Residency, Opp. Bank Of Baroda, (Ernakulam North Br.), Banerji Road, | 682018 | Ernakulam | Kerala | 91-484-2397906 | 91-484-2397983 | info@belkochi.com | www.belkochi.com
24070 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-8) Road Project | 736 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
24071 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-8) Road Project | 736 | Contractor | C & C Constructions Ltd. | 39807 | India | Corporate Office:Plot No.70, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-4536666 | 91-124-4536799 | candc@candcinfrastructure.com | www.candcinfrastructure.com
24072 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-9) Road Project | 737 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | UK | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
24073 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-9) Road Project | 737 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24074 | National Highways Authority Of India | 155597 | Darbanga-Muzaffarpur (BR-9) Road Project | 737 | Contractor | C & C Constructions Ltd. | 39807 | India | Corporate Office:Plot No.70, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-4536666 | 91-124-4536799 | candc@candcinfrastructure.com | www.candcinfrastructure.com
24075 | National Highways Authority Of India | 155597 | Dasna-Hapur Road Project | 123 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24076 | National Highways Authority Of India | 155597 | Dasna-Meerut Expressway (NH-58) (Package-4 of Delhi-Meerut Expressway) Project (Bharatmala) | 1157 | Consultant | S N C Lavalin | 460429 | India | Registered Office:8th & 19th Floor, Tower C, D L F Cyber Greens, D L F Cyber City, D L F Phase-III, | 122002 | Gurgaon | Haryana | 91-124-5000147 |  |  | www.snclavalin.com
24077 | National Highways Authority Of India | 155597 | Dasna-Meerut Expressway (NH-58) (Package-4 of Delhi-Meerut Expressway) Project (Bharatmala) | 1157 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24078 | National Highways Authority Of India | 155597 | Davanagere-Haveri Six Laning Highway (NH-48) Project | 1234 | Consultant | Egis India Pvt. Ltd. | 66149 | India | Registered Office:K-4, 2nd Floor South Extension, Part II | 110049 | New Delhi | NCT of Delhi | 91-11-45704300 |  | bhaskar.m@egis-india.com | www.egis-india.com
24079 | National Highways Authority Of India | 155597 | Davanagere-Haveri Six Laning Highway (NH-48) Project | 1234 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24080 | National Highways Authority Of India | 155597 | Davanagere-Haveri Six Laning Highway (NH-48) Project | 1234 | Sub contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24081 | National Highways Authority Of India | 155597 | Dehradun Ring Road Project | 2056 | Consultant | M S V International Consultants Ltd. | 133047 | India | Registered Office:2654, Bank Street, Karol Bagh, | 110005 | New Delhi | Delhi
24082 | National Highways Authority Of India | 155597 | Delhi Logistics Park Project | 1384 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24083 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24084 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24085 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Vasishta Constructions Pvt. Ltd. | 263166 | India | Registered Office:Plot No.23, Rao & Raju Colony, Road No.2, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23546138 | 91-40-23546137 | info@vasishta.in | www.vasishta.in
24086 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24087 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Krishna Constructions | 419976 | India | Registered Office:784-J, Baghambari Gaddi Road, Allahpur, | 211006 | Allahabad | Uttar Pradesh |  |  | kcindia100@gmail.com | www.krishnaconstructions.org
24088 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Bharat Construction Co. | 450941 | India |  | NA
24089 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Shiv Buildindia Pvt. Ltd. | 457770 | India | Registered Office:401/2, 4th Floor, Siddhraj Zavod, Sargasan, | 382421 | Gandhinagar | Gujarat | 91-79-29750425 |  | contact@shivbuildindia.com | www.shivbuildindia.com
24090 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | K R C Infraprojects Pvt. Ltd. | 514791 | India | Registered Office:101, K R Chambers, Rasulpur Road, | 121102 | Palwal | Haryana | 91-1275-247999 |  | info@krcinfraprojects.com | www.krcinfraprojects.com
24091 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
24092 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Jandu Construction India Pvt. Ltd. | 646179 | India | Registered Office:H. No. 323 Aggarsain Colony, SBI Street, | 125055 | Sirsa | Haryana |  |  | janduconstco@yahoo.com
24093 | National Highways Authority Of India | 155597 | Delhi-Dehradun Six Lane (NH-709B) Greenfield Access Controlled Expressway Project | 1834 | Contractor | Shri Krishna & Co. | 662754 | India |  | NA
24094 | National Highways Authority Of India | 155597 | Delhi-Saharanpur (NH-709B) Six Lane Highway Project (Bharatmala) | 1659 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24095 | National Highways Authority Of India | 155597 | Delhi-Saharanpur (NH-709B) Six Lane Highway Project (Bharatmala) | 1659 | Contractor | Krishna Construction Pvt. Ltd. | 123264 | India | Registered Office:Shop No. 1, Basera Apartment, Upnagar, | 422007 | Nashik | Maharashtra
24096 | National Highways Authority Of India | 155597 | Delhi-Saharanpur (NH-709B) Six Lane Highway Project (Bharatmala) | 1659 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24097 | National Highways Authority Of India | 155597 | Delhi-Saharanpur (NH-709B) Six Lane Highway Project (Bharatmala) | 1659 | Contractor | E5 Infrastructure Pvt. Ltd. | 613495 | India | Registered Office:SCO-105 Pocket A, Sec-14, | 125001 | Hisar | Haryana |  |  |  | www.e5infra.com
24098 | National Highways Authority Of India | 155597 | Dera Baba Nanak(Gurdaspur)-Gurudwara Darbar Sahib (Indo/Pak Border) Road Project (Kartarpur Corridor) | 1702 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24099 | National Highways Authority Of India | 155597 | Derabassi Flyover Project (on Ambala-Chandigarh section) | 940 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24100 | National Highways Authority Of India | 155597 | Devdhari-Kelapur (NS-61/MH) Highway Project | 730 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24101 | National Highways Authority Of India | 155597 | Devdhari-Kelapur (NS-61/MH) Highway Project | 730 | Contractor | Ideal Road Builders Pvt. Ltd. | 97432 | India | Corporate Office:I R B Complex, Chandivli Farm, Chandivli, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | mhaiskar@bom2.vsnl.net.in
24102 | National Highways Authority Of India | 155597 | Dewas-Ujjain Four Lane (NH-148NG) Highway Project | 1821 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24103 | National Highways Authority Of India | 155597 | Dewas-Ujjain Four Lane (NH-148NG) Highway Project | 1821 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24104 | National Highways Authority Of India | 155597 | Dhanara Village-Tumbigura Highway Project (Phase 2) | 1810 | Consultant | Yongma Engineering Co. Ltd. | 585553 | India | Registered Office:Unit 301, 302, Time Centre, Golf Course Road, Sector 54, | 122002 | Gurgaon | Haryana |  |  | vba1981mca@gmail.com | www.ymeng.co.kr
24105 | National Highways Authority Of India | 155597 | Dhanara Village-Tumbigura Highway Project (Phase 2) | 1810 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
24106 | National Highways Authority Of India | 155597 | Dhanara-Hatibena Six Lane Road (Package-OD-1) (NH-130 CD) Project (Part of Raipur-Visakhapatnam Economic Corridor) | 1917 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
24107 | National Highways Authority Of India | 155597 | Dhangaon-Borgaon (NH-347BG and 753L) Four Lane Highway Project (Package IV) | 1711 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24108 | National Highways Authority Of India | 155597 | Dhankuni-Kolaghat (WB-1) Four Lane Highway Project | 82 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24109 | National Highways Authority Of India | 155597 | Dhankuni-Kolaghat (WB-1) Four Lane Highway Project | 82 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24110 | National Highways Authority Of India | 155597 | Dharamkot-Dyalpura Bhaika Package-2 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1908 | Contractor | Krishna Constructions | 419976 | India | Registered Office:784-J, Baghambari Gaddi Road, Allahpur, | 211006 | Allahabad | Uttar Pradesh |  |  | kcindia100@gmail.com | www.krishnaconstructions.org
24111 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-19) Highway Project | 711 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24112 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-19) Highway Project | 711 | Contractor | I L & F S Engg. & Construction Co. Ltd. | 142276 | India | Registered Office:Door No.8-2-120/113/3/4F, Sanali Info Park, Cyber Towers, Road No.2, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-40409333 | 91-40-40409444 | cs@ilfsengg.com | www.ilfsengg.com
24113 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-20) Four-Laning Highway Project | 712 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
24114 | National Highways Authority Of India | 155597 | Dharamtul-Sonapur (AS-20) Four-Laning Highway Project | 712 | Supervision consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24115 | National Highways Authority Of India | 155597 | Dharmapuri-Lonand (NH-965) Four Lane Highway Project (Package-IV of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1874 | Consultant | Technocrats Advisory Services Pvt. Ltd. | 566226 | India | Registered Office:68, Ajanta Apartments, 36, I P Extension Patparganj, | 110092 | New Delhi | NCT of Delhi |  |  | kamleshkumar.77@gmail.com
24116 | National Highways Authority Of India | 155597 | Dharmapuri-Lonand (NH-965) Four Lane Highway Project (Package-IV of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1874 | Contractor | Vijay Nirman Co. Pvt. Ltd. | 387009 | India | Registered Office:D No.11-9-16, Dasapalla Hills, | 530003 | Visakhapatnam | Andhra Pradesh | 91-891-2575755 | 91-891-2754046 | vijay@vijaynirman.com | www.vijaynirman.com
24117 | National Highways Authority Of India | 155597 | Dharmapuri-Lonand (NH-965) Four Lane Highway Project (Package-IV of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1874 | Contractor | R K Chavan Infrastructure Pvt. Ltd. | 560853 | India | Registered Office:Flat No 202, Rahul Enclave,S No, 116/7/1,Plot No A, Warje, | 411058 | Pune | Maharashtra | 91-20-25204294 |  | info@rkcipl.com | www.rkcipl.com
24118 | National Highways Authority Of India | 155597 | Dharuhera-Bhiwadi Four Lane Link Road (NH-919) Project | 1973 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
24119 | National Highways Authority Of India | 155597 | Dharwad-Hubli Four Lane Bypass Highway Project | 113 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24120 | National Highways Authority Of India | 155597 | Dhillon Nagar (Moga) to Bajakhana (Lambwali) (NH-105B) Four Lane Highway (Greenfield Alignment) Project | 1733 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
24121 | National Highways Authority Of India | 155597 | Dholpur-Morena Section (including chambal bridge) Project | 742 | Consultant | C D M Smith India Pvt. Ltd. | 390999 | India | Registered Office:No. 103 & 104, First Floor, Brigade Opus, Kodigehalli Main Road, Sanjeevini Nagar, | 560092 | Bengaluru | Karnataka | 91-80-67150300 |  | sumeshn@cdmsmith.com | www.cdmsmith.com
24122 | National Highways Authority Of India | 155597 | Dholpur-Morena Section (including chambal bridge) Project | 742 | Contractor | T R Gupta Construction Pvt. Ltd. | 246348 | India | Registered Office:19/1, Manoramaganj Indoreday Ower Plasia, | 452001 | Indore | Madhya Pradesh |  |  | amitsurana_co@yahoo.com
24123 | National Highways Authority Of India | 155597 | Dholpur-Morena Section (including chambal bridge) Project | 742 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
24124 | National Highways Authority Of India | 155597 | Dichaon Kalan-Bahadurgarh Bypass Six Lane Link Road (NH-344N) Project ( Package-5 of Delhi 3rd Ring Road Project or UER-2) | 1800 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
24125 | National Highways Authority Of India | 155597 | Dichaon Kalan-Bahadurgarh Bypass Six Lane Link Road (NH-344N) Project ( Package-5 of Delhi 3rd Ring Road Project or UER-2) | 1800 | Consultant | Aecom India Pvt. Ltd. | 462940 | India | Registered Office:9th Floor, Infinity Tower C, DLF Cyber City, DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-2818000 | 91-124-2816008 | pradeep.khurana@aecom.com | www.aecom.com
24126 | National Highways Authority Of India | 155597 | Dichaon Kalan-Bahadurgarh Bypass Six Lane Link Road (NH-344N) Project ( Package-5 of Delhi 3rd Ring Road Project or UER-2) | 1800 | Contractor | Diamond Construction Co. | 509680 | India |  | NA
24127 | National Highways Authority Of India | 155597 | Dichaon Kalan-Bahadurgarh Bypass Six Lane Link Road (NH-344N) Project ( Package-5 of Delhi 3rd Ring Road Project or UER-2) | 1800 | Contractor | S S Builders (maharashtra) | 631458 | India |  | NA
24128 | National Highways Authority Of India | 155597 | Divancheru (near Rajahmundry)-Gowthami (AP-17) Four Lane Highway Project | 144 | Consultant | S N C-lavalin Capital Inc. | 204139 | India | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24129 | National Highways Authority Of India | 155597 | Divancheru (near Rajahmundry)-Gowthami (AP-17) Four Lane Highway Project | 144 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24130 | National Highways Authority Of India | 155597 | Divancheru (near Rajahmundry)-Gowthami (AP-17) Four Lane Highway Project | 144 | Turnkey contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24131 | National Highways Authority Of India | 155597 | DND Maharani Bagh-Junction with Jaitpur-Pushta Road (section of NH-148NA) Six Lane access controlled Highway Project (Package 1) (Delhi-Mumbai Expressway) | 1677 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24132 | National Highways Authority Of India | 155597 | Dobbaspet-Dodaballapur Bypass (NH-648) Four/Six Lane Highway Project (Package 1) (Bharatmala) | 1657 | Contractor | Shankaranarayana Constructions Pvt. Ltd. | 571330 | India | Registered Office:No.7, S N C House, Residency Road (Old No.9), Raja Ram Mohan Roy Road, | 560025 | Bengaluru | Karnataka | 91-80-22109541 |  | sncbgr@ssncindia.com | www.ssncindia.co.in
24133 | National Highways Authority Of India | 155597 | Dodaballapur Bypass-Hoskote (NH-648) Four/Six Lane Highway Project (Package 2) (Banglore Ring Road) | 1658 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24134 | National Highways Authority Of India | 155597 | Donoreshan Village to Junction with NH20 in Bongabar Village Four/Six Lane Greenfield Access Control Expressway Project (Package-11 of Varanasi-Kolkata Expressway) | 2120 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24135 | National Highways Authority Of India | 155597 | Duburi-Chandikhole (NH-53) Four Lane Road Project | 1405 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24136 | National Highways Authority Of India | 155597 | Duburi-Chandikhole (NH-53) Four Lane Road Project | 1405 | Contractor | Gammon Engineers & Contractors Pvt. Ltd. | 542071 | India | Registered Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61114000 | 91-22-24300221 | marketing@gammonengineers.com | www.gammonengineers.com
24137 | National Highways Authority Of India | 155597 | Dudhadhari Elevated Four Lane (NH-34) Flyover Project (Muzaffarnagar-Haridwar Section) | 2020 | Contractor | S E C Buildtech Pvt. Ltd. | 487171 | India |  | NA
24138 | National Highways Authority Of India | 155597 | Dumad Chowkdi Underpass (NH-48) Project | 2126 | Contractor | Apex Tarmac Pvt. Ltd. | 452444 | India |  | NA
24139 | National Highways Authority Of India | 155597 | Dushehra Village-Arnia Khurd Village (NH-91) Four/Six Lane Divided Carriageway (THDCIL Bypass) Project | 1769 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24140 | National Highways Authority Of India | 155597 | Dwarka (NH-51)-Khambalia-Dewaria Section & Jamnanagar-Dhrol-Amram-Maliya Two/Four Laning Highway (BM/2) Project (Bharatmala) | 1094 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24141 | National Highways Authority Of India | 155597 | Dwarka NHAI Staff Residential Complex Project | 884 | Contractor | M B L Infrastructure Ltd. | 136291 | India | Corporate Office:Banani Corporate One Tower, Suite #303-308, 3rd Floor, Jasola, Plot No.5, Commercial Centre, | 110025 | New Delhi | NCT of Delhi | 91-11-49593300 | 91-11-48593320 | delhi@mblinfra.com | www.mblinfra.com
24142 | National Highways Authority Of India | 155597 | Dyalpura Bhaika-Sangat Kalan Package-3 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1909 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24143 | National Highways Authority Of India | 155597 | Dyalpura Bhaika-Sangat Kalan Package-3 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1909 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
24144 | National Highways Authority Of India | 155597 | Dyalpura Bhaika-Sangat Kalan Package-3 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1909 | Contractor | Krishna Construction | 547990 | India | Registered Office:Kamla Nehru Nagar, Ajmer Road, | 302024 | Jaipur | Rajasthan
24145 | National Highways Authority Of India | 155597 | East break water to Convent Junction Four Lane Road (Port Connectivity) Project | 1954 | Contractor | Sudharma Infratech Pvt. Ltd. | 434577 | India |  | NA
24146 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Co-promoter | Roads & Bridges Devp. Corpn. Of Kerala Ltd. | 198830 | India | Corporate Office:2nd Floor, Preethi Building, M V Road, Palarivattom, | 682025 | Ernakulam | Kerala | 91-484-2338205 | 91-484-2533294 | mail@rbdck.com | www.rbdck.com
24147 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Consultant | Kitco Ltd. | 121500 | India | Head Office:M M Gardens, Church Landing Road, Near Fine Arts Hall, Pallimukku, | 682016 | Kochi | Kerala | 91-484-4129000 | 91-484-2805066 | mail@kitco.in | www.kitco.in
24148 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Contractor | Delhi Metro Rail Corpn. Ltd. | 57888 | India | Registered Office:Metro Bhawan, Fire Brigade Lane, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-23417910 | 91-11-23417921 | sksakhuja@gmail.com | www.delhimetrorail.com
24149 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24150 | National Highways Authority Of India | 155597 | Edappally-Kundanoor Elevated Highway Project | 761 | Contractor | R D S Project Ltd. | 185799 | India | Registered Office:427, Somdutt Chambers-II, 9, Bhikaji Cama Place, | 110066 | New Delhi | NCT of Delhi | 91-11-26170242 | 91-11-26168092 | agra@rdsproject.com | www.rdsproject.com
24151 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting after End of Bridge over Hadaf River near Hathiyavan Village with SH-152 near Matariya Vadi Project (Package 27 of Delhi-Mumbai Expressway) | 1817 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24152 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting after End of Bridge over Hadaf River near Hathiyavan Village with SH-152 near Matariya Vadi Project (Package 27 of Delhi-Mumbai Expressway) | 1817 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24153 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting after End of Bridge over Hadaf River near Hathiyavan Village with SH-152 near Matariya Vadi Project (Package 27 of Delhi-Mumbai Expressway) | 1817 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
24154 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting from Junction with SH-152 near Matariya Vadi and near Bhamaiya village Project (Package 28 of Delhi-Mumbai Expressway) | 1816 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24155 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting from Junction with SH-152 near Matariya Vadi and near Bhamaiya village Project (Package 28 of Delhi-Mumbai Expressway) | 1816 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24156 | National Highways Authority Of India | 155597 | Eight Lane Excess Controlled Expressway Starting from Junction with SH-152 near Matariya Vadi and near Bhamaiya village Project (Package 28 of Delhi-Mumbai Expressway) | 1816 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
24157 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Contractor | J Kumar Infraprojects Ltd. | 104004 | India | Corporate Office:CTS No. 448, 448/1, 449, Subhash Road, Vile Parle East, | 400057 | Mumbai | Maharashtra | 91-22-68717900 |  | info@jkumar.com | www.jkumar.com
24158 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24159 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Contractor | Indiabulls Real Estate Ltd. | 369628 | India | Corporate Office:Indiabulls House, 448-451, Udyog Vihar, Phase-V, | 122016 | Gurgaon | Haryana | 91-124-3082249 | 91-124-3081680 | rtelkar@indiabulls.com | www.indiabullsrealestate.com
24160 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
24161 | National Highways Authority Of India | 155597 | Eight Lane Northern Peripheral Road Project or Dwarka Expressway NH-48&(NH 248-BB) Project (Bharatmala) | 1208 | Promoter | Haryana Urban Devp. Authority | 91331 | India | Registered Office:H U D A Office Complex, C-3, Sector-6, | NA | Panchkula | Haryana | 91-172-2567857 |  | huda@hry.nic.in | www.huda.org.in
24162 | National Highways Authority Of India | 155597 | Eluru-Vijaywada Highway including Eluru bypass Project | 22 | Consultant | Kampsax | 115611 | Denmark |  | NA
24163 | National Highways Authority Of India | 155597 | Eluru-Vijaywada Highway including Eluru bypass Project | 22 | Turnkey contractor | Madhucon Binapuri | 134107 | India |  | NA
24164 | National Highways Authority Of India | 155597 | Ena-Kim Package-6 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1626 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24165 | National Highways Authority Of India | 155597 | Ena-Kim Package-6 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1626 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24166 | National Highways Authority Of India | 155597 | End of Hardoi District to Lucknow Ring Road (NH-731) Four Lane Highway Project (Package-IV of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2068 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
24167 | National Highways Authority Of India | 155597 | End of Hardoi District to Lucknow Ring Road (NH-731) Four Lane Highway Project (Package-IV of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2068 | Contractor | Sobti Infratech Ltd. | 94313 | India | Registered Office:E-196, Naraina Vihar, | 110053 | New Delhi | NCT of Delhi |  |  | csmanoj_bly@rediffmail.com
24168 | National Highways Authority Of India | 155597 | End of Hardoi District to Lucknow Ring Road (NH-731) Four Lane Highway Project (Package-IV of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2068 | Contractor | R P Infraventure Pvt. Ltd. | 553264 | India |  | NA
24169 | National Highways Authority Of India | 155597 | End of Hardoi District to Lucknow Ring Road (NH-731) Four Lane Highway Project (Package-IV of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2068 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
24170 | National Highways Authority Of India | 155597 | Etawah Bypass Highway Project | 73 | Consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24171 | National Highways Authority Of India | 155597 | Etawah Bypass Highway Project | 73 | Contractor | Bhagheeratha Engineering Ltd. | 33012 | India | Head Office:3rd Flr, Bhagheeratha Residency, Opp. Bank Of Baroda, (Ernakulam North Br.), Banerji Road, | 682018 | Ernakulam | Kerala | 91-484-2397906 | 91-484-2397983 | info@belkochi.com | www.belkochi.com
24172 | National Highways Authority Of India | 155597 | Etawah Bypass Highway Project | 73 | Contractor | P N C Construction Pvt. Ltd. | 167138 | India |  | NA
24173 | National Highways Authority Of India | 155597 | Etawah Bypass Highway Project | 73 | Contractor | Ashwini Construction & Contractors Pvt. Ltd. | 335881 | India |  | NA
24174 | National Highways Authority Of India | 155597 | Etawah-Rajpur (GTRIP/IC) Highway Project | 693 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24175 | National Highways Authority Of India | 155597 | Etawah-Rajpur (GTRIP/IC) Highway Project | 693 | Contractor | Bharat Electronics Ltd. | 33727 | India | Corporate Office:Outer Ring Road, Nagavara, | 560045 | Bengaluru | Karnataka | 91-80-25039300 | 91-80-25039233 | secretary@bel.co.in | www.bel-india.in
24176 | National Highways Authority Of India | 155597 | Expressway from Dighi Industrial Cluster to JNPT Project | 1724 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24177 | National Highways Authority Of India | 155597 | Fagne-Maharashtra/Gujarat Border (Songarh) (NH-6) Four Laning Highway Project (Bharatmala) | 1801 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
24178 | National Highways Authority Of India | 155597 | Faridabad Logistic Park Project | 1379 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24179 | National Highways Authority Of India | 155597 | Faridabad-Palwal Six Lane Expressway Project (Package 6 of Eastern Peripheral Expressway) | 1124 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24180 | National Highways Authority Of India | 155597 | Faridabad-Palwal Six Lane Expressway Project (Package 6 of Eastern Peripheral Expressway) | 1124 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
24181 | National Highways Authority Of India | 155597 | Farukhanagar-Kottakata(NH-7) Highway Project | 323 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24182 | National Highways Authority Of India | 155597 | Farukhanagar-Kottakata(NH-7) Highway Project | 323 | Contractor | Jadcherla Expressways Pvt. Ltd. | 371352 | India | Registered Office:3rd Floor, C Block TSR Towers, 6-3-1090, Rajbhavan Road, | 500082 | Hyderabad | Telangana | 91-40-40062583 | 91-40-23326198 | balaji.gupta@jadcherlaexpressways.com
24183 | National Highways Authority Of India | 155597 | Farukhnagar-Jadcheria Four Laning Highway Project | 566 | Contractor | Jadcherla Expressways Pvt. Ltd. | 371352 | India | Registered Office:3rd Floor, C Block TSR Towers, 6-3-1090, Rajbhavan Road, | 500082 | Hyderabad | Telangana | 91-40-40062583 | 91-40-23326198 | balaji.gupta@jadcherlaexpressways.com
24184 | National Highways Authority Of India | 155597 | Fatehpur-Khaga (TNHP/II-C) Highway Project | 149 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24185 | National Highways Authority Of India | 155597 | Fatehpur-Khaga (TNHP/II-C) Highway Project | 149 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24186 | National Highways Authority Of India | 155597 | Fatehpur-Khaga (TNHP/II-C) Highway Project | 149 | Turnkey contractor | Centrodorstroy | 43595 | Russia |  | NA
24187 | National Highways Authority Of India | 155597 | Fazilka-Abohar (NH-07) Four Lane Highway Project | 3012 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24188 | National Highways Authority Of India | 155597 | Flyover/Underpass at Vizag Airport Junction Project | 1751 | Contractor | S V S Mookambika Constructions Pvt. Ltd. | 412923 | India |  | NA
24189 | National Highways Authority Of India | 155597 | FOBs on Gurgaon-Kotputli-Jaipur (NH-8 & 48) Project | 1390 | Contractor | E S Infraserve Pvt. Ltd. | 581118 | India |  | NA
24190 | National Highways Authority Of India | 155597 | Forbesganj-Jogbani (NH-57A) Four Laning Highway Project | 978 | Consultant | Antea India Pvt. Ltd. | 407588 | India | Registered Office:Unit No. 404, 4th Floor, IRIS Tech Park, Sector 48, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4518800 | 91-124-4518832 | ajaysingh@unihornidia.com | www.unihornindia.com
24191 | National Highways Authority Of India | 155597 | Forbesganj-Jogbani (NH-57A) Four Laning Highway Project | 978 | Consultant | Transtek Engineers & Services Pvt. Ltd. | 580821 | India |  | NA
24192 | National Highways Authority Of India | 155597 | Forbesganj-Jogbani (NH-57A) Four Laning Highway Project | 978 | Contractor | J K M Infra Projects Ltd. | 388063 | India | Registered Office:C-84, Greater Kailash-1, | 110048 | New Delhi | NCT of Delhi | 91-11-4624555 | 91-11-4624545 | roc@jkminfra.com
24193 | National Highways Authority Of India | 155597 | Forbesganj-Simrahi (BR-3) Four-Laning Highway Project | 735 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24194 | National Highways Authority Of India | 155597 | Forbesganj-Simrahi (BR-3) Four-Laning Highway Project | 735 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24195 | National Highways Authority Of India | 155597 | Fort Vypin to Matsyafed Tourist Office Road Upgradation Project (Bharatmala) | 1742 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24196 | National Highways Authority Of India | 155597 | Four Lane Bridge across River Ganga at Farakka (including approaches connecting Farraka-Raiganj (NH-34) section) Project | 1246 | Contractor | R K E C Projects Ltd. | 475933 | India | Registered Office:Door No 10-12-1, Rednam Alcazar, 3rd Floor, Opp. S B I Main Branch, Old Jail Road, Rednam Gardens, | 530002 | Visakhapatnam | Andhra Pradesh | 91-891-2574517 | 91-891-2574703 | info@rkecprojects.com | www.rkecprojects.com
24197 | National Highways Authority Of India | 155597 | Four Lane Bridge Parallel to Vikramshila Setu over Ganga River near Barari Ghat (Connecting Naugachia with Bhagalpur) Project | 1639 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
24198 | National Highways Authority Of India | 155597 | Four Lane Bridge Parallel to Vikramshila Setu over Ganga River near Barari Ghat (Connecting Naugachia with Bhagalpur) Project | 1639 | Promoter | Bihar Rajya Pul Nirman Nigam Ltd. | 35527 | India | Registered Office:7, Sardar Patel Marg, | 800015 | Patna | Bihar | 91-612-2226562 | 91-612-2223316 | info@brpnnl.co.in | www.brapnn.bih.nic.in
24199 | National Highways Authority Of India | 155597 | Four Lane Bypass on Western side of Gwalior Project (Rairu Nirwali-Girwai) | 1675 | Consultant | Lion Engineering Consultants | 551358 | India | Registered Office:Plot No. 97, Lion Tower, Near Mother Teresa School, Kolar Road, | 462042 | Bhopal | Madhya Pradesh | 91-755-2879496 | 91-755-2879499 | info@liongroup.in | www.lionengineering.in
24200 | National Highways Authority Of India | 155597 | Four Lane Connector from Delhi-Meerut Expressway to NH-235 (Package 5 of Delhi-Meerut Expressway) Project | 2013 | Contractor | Mathiyan Construction Pvt. Ltd. | 419088 | India |  | NA
24201 | National Highways Authority Of India | 155597 | Four Lane Connector from Delhi-Meerut Expressway to NH-235 (Package 5 of Delhi-Meerut Expressway) Project | 2013 | Contractor | A P S Hydro Pvt. Ltd. | 483858 | India | Registered Office:House No. 58, Floor 1st, Block 10 Landmark Opp. Old Police Station Kirti Nagar Ind. Area, | 110015 | New Delhi | NCT of Delhi |  |  | apshydro@gmail.com
24202 | National Highways Authority Of India | 155597 | Four Lane Elevated Highway at Gopalganj Town (NH-27) Project | 2001 | Contractor | A S C Infratech Pvt. Ltd. | 599981 | India | Registered Office:H - 37, Sector 63, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh |  |  | asc29032010@gmail.com | www.ascinfratech.com
24203 | National Highways Authority Of India | 155597 | Four Lane Greenfield Jabalpur City Bypass/Outer Ring Road Project | 1718 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24204 | National Highways Authority Of India | 155597 | Four Lane Greenfield Jabalpur City Bypass/Outer Ring Road Project | 1718 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
24205 | National Highways Authority Of India | 155597 | Four Lane Greenfield Jabalpur City Bypass/Outer Ring Road Project | 1718 | Contractor | I S C Projects Pvt. Ltd. | 445366 | India | Registered Office:S-2, The Metropole, Adjacent To Inox, Bund Garden Road, | 411001 | Pune | Maharashtra | 91-20-41299000 | 91-20-41299004 | info@iscprojects.co.in | www.iscprojects.co.in
24206 | National Highways Authority Of India | 155597 | Four Lane Greenfield Jabalpur City Bypass/Outer Ring Road Project | 1718 | Contractor | Vijai Construction (india) Pvt. Ltd. | 530179 | India |  | NA
24207 | National Highways Authority Of India | 155597 | Four Lane Kumta Bypass (NH-66) Project | 1203 | Consultant | Indian Technocrat Ltd. | 99026 | India | Registered Office:Plot No.8, Sector B-7, Local Shopping Complex, Vasant Kunj, | 110070 | New Delhi | NCT of Delhi | 91-11-49531100 | 91-11-49531166 | info@itl.net.in | www.itl.net.in
24208 | National Highways Authority Of India | 155597 | Four Lane ROB near Neleshwaram (NH-66) Project | 1409 | Consultant | Aecom Asia Co. Ltd. | 453427 | Hong Kong | Registered Office:9th Floor, Infinity Tower-C, DLF Cyber City DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-4830100 | 91-124-4830108 | sunil2.kumar@aecom.com | www.aecom.com
24209 | National Highways Authority Of India | 155597 | Four Lane ROB near Neleshwaram (NH-66) Project | 1409 | Contractor | E K K Infrastructure Ltd. | 536863 | India | Corporate Office:IInd Floor, Municipal Building, A M Road, Perumbavoor, | 683542 | Ernakulam | Kerala | 91-484-2523603 | 91-484-2523603 | info@ekk.co.in | www.ekk.co.in
24210 | National Highways Authority Of India | 155597 | Four Lane Spur of Panipat-Shamli connecting NH-709AD (Panipat-Shamli-Muzaffarnagar) and NH709A (Karnal-Meerut) bypassing Shamli Project | 2010 | Contractor | Ramky Infrastructure Ltd. | 347143 | India | Registered Office:Ramky Grandiose, 15th Floor, Sy No. 136/2 & 4, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-23015000 | 91-40-23015444 | investors@ramky.com | www.ramkyinfrastructure.com
24211 | National Highways Authority Of India | 155597 | Four Lane Spur of Panipat-Shamli connecting NH-709AD (Panipat-Shamli-Muzaffarnagar) and NH709A (Karnal-Meerut) bypassing Shamli Project | 2010 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
24212 | National Highways Authority Of India | 155597 | Four Lane Vehicular Underpass (VUP) at Aler-Jeedikal Cross Road on Hyderabad-Warangal Section of NH-163 Project | 2006 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
24213 | National Highways Authority Of India | 155597 | Four Lane Vehicular Underpass (VUP) at Aler-Jeedikal Cross Road on Hyderabad-Warangal Section of NH-163 Project | 2006 | Contractor | Rockeira Engineering L L P | 588717 | India |  | NA
24214 | National Highways Authority Of India | 155597 | Four Lane Western Side Spur of Rampur-Rudrapur Section connecting NH-24 to NH-87 bypassing Rampur Town Project | 2019 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24215 | National Highways Authority Of India | 155597 | Four Lane Western Side Spur of Rampur-Rudrapur Section connecting NH-24 to NH-87 bypassing Rampur Town Project | 2019 | Contractor | Dev Yash Projects & Infrastructure Pvt. Ltd. | 604509 | India |  | NA
24216 | National Highways Authority Of India | 155597 | Four/Six-Lane Access Controlled Highway (NH-152D) starting from Junction with Rewari-Kanina road (SH-24) near Kanina to Narnaul Project (Package 8 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1619 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24217 | National Highways Authority Of India | 155597 | Four/Six-Lane Access Controlled Highway (NH-152D) starting from Junction with Rewari-Kanina road (SH-24) near Kanina to Narnaul Project (Package 8 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1619 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24218 | National Highways Authority Of India | 155597 | Four/Six-Lane Access Controlled Highway (NH-152D) starting from Junction with Rewari-Kanina road (SH-24) near Kanina to Narnaul Project (Package 8 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1619 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24219 | National Highways Authority Of India | 155597 | Gadu-Porbandar (NH-8E) Two/Four lane Highway Project | 943 | Contractor | Kalthia Engineering & Construction Ltd. | 114870 | India | Corporate Office:28, Rangin Park, Opp. Rajpath Club, S G Highway, Bodakdev, | 380059 | Ahmedabad | Gujarat | 91-79-26870501 | 91-79-26870501 | kecl@kathiagroup.com | www.kalthiagroup.com
24220 | National Highways Authority Of India | 155597 | Gagaria (NH-25)-Baori Kalan-Serwa-Lakdassar-Bakhasar section (NH-925) & Sata-Gandhav section (NH-925 A) Two Lane Highway Project | 1110 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
24221 | National Highways Authority Of India | 155597 | Gagodhar-Radhanpur NH-15 (Package 5) Project | 235 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24222 | National Highways Authority Of India | 155597 | Gagodhar-Radhanpur NH-15 (Package 5) Project | 235 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24223 | National Highways Authority Of India | 155597 | Gandhidham-Samakhiali (PackII) Port Connectivity Highway Project | 200 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24224 | National Highways Authority Of India | 155597 | Gandhidham-Samakhiali (PackII) Port Connectivity Highway Project | 200 | Contractor | P B A Infrastructure Ltd. | 165960 | India | Registered Office:611/3, V N Purav Marg, Chembur (East), | 400071 | Mumbai | Maharashtra | 91-22-61277200 | 91-22-61277203 | pbamumbai@gmail.com | www.pbainfra.in
24225 | National Highways Authority Of India | 155597 | Gandhidham-Samakhiali(PackIII)Port Connectivity Project | 201 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24226 | National Highways Authority Of India | 155597 | Ganga Bridge to Rama Devi Crossing (Jajmau-Ramadevi) NH-25 Section Highway Project | 588 | Consultant | Feedback Turnkey Engineers Pvt. Ltd. | 72650 | India | Registered Office:10/6 Sarvapriya Vihar, New Delhi | 110016 |  | Delhi
24227 | National Highways Authority Of India | 155597 | Ganga Bridge to Rama Devi Crossing (Jajmau-Ramadevi) NH-25 Section Highway Project | 588 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24228 | National Highways Authority Of India | 155597 | Garamore to Bamanbore (NH-8A) Highway Project | 233 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24229 | National Highways Authority Of India | 155597 | Garamore-Gagodhar NH-8A (Package 4) Project | 234 | Contractor | Daelim E & C India Ltd. | 54969 | India | Registered Office:28, Najafgarh Road, | 110001 | New Delhi | Delhi
24230 | National Highways Authority Of India | 155597 | Garamore-Gagodhar NH-8A (Package 4) Project | 234 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24231 | National Highways Authority Of India | 155597 | Garhmukteshwar-Moradabad (NH-24) Highway Project | 343 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24232 | National Highways Authority Of India | 155597 | Garhmukteshwar-Moradabad (NH-24) Highway Project | 343 | Contractor | Bharat Electronics Ltd. | 33727 | India | Corporate Office:Outer Ring Road, Nagavara, | 560045 | Bengaluru | Karnataka | 91-80-25039300 | 91-80-25039233 | secretary@bel.co.in | www.bel-india.in
24233 | National Highways Authority Of India | 155597 | Garhmukteshwar-Moradabad (NH-24) Highway Project | 343 | Contractor | P N C Construction Pvt. Ltd. | 167138 | India |  | NA
24234 | National Highways Authority Of India | 155597 | GB Nagar Six Lane Expressway Project (Package 4 of Eastern Peripheral Expressway) | 1123 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24235 | National Highways Authority Of India | 155597 | GB Nagar Six Lane Expressway Project (Package 4 of Eastern Peripheral Expressway) | 1123 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
24236 | National Highways Authority Of India | 155597 | GB Nagar-Faridabad Six Lane Expressway Project (Package 5 of Eastern Peripheral Expressway) | 997 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
24237 | National Highways Authority Of India | 155597 | GB Nagar-Faridabad Six Lane Expressway Project (Package 5 of Eastern Peripheral Expressway) | 997 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
24238 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project | 892 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24239 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project | 892 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24240 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project (Package-I) | 1081 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24241 | National Highways Authority Of India | 155597 | Ghaghar Bridge (Indo Nepal Border)-Varanasi NH-233 Four Laning Road Project (Package-I) | 1081 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
24242 | National Highways Authority Of India | 155597 | Ghaziabad Logistics Park Project | 1382 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24243 | National Highways Authority Of India | 155597 | Ghaziabad-GB Nagar Six Lane Expressway Project (Package 3 of Eastern Peripheral Expressway) | 996 | Contractor | Jaiprakash Associates Ltd. | 108841 | India | Corporate Office:JA House', 63, Basant Lok Vasant Vihar, | 110057 | New Delhi | NCT of Delhi | 91-11-4982500 | 91-11-26145389 | jalinvestor@jalindia.co.in | www.jalindia.com
24244 | National Highways Authority Of India | 155597 | Ghaziabad-GB Nagar Six Lane Expressway Project (Package 3 of Eastern Peripheral Expressway) | 996 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
24245 | National Highways Authority Of India | 155597 | Ghaziabad-Hapur Highway & Hapur Bypass Project | 56 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24246 | National Highways Authority Of India | 155597 | Ghaziabad-Hapur Highway & Hapur Bypass Project | 56 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24247 | National Highways Authority Of India | 155597 | Ghaziabad-Hapur Highway & Hapur Bypass Project | 56 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24248 | National Highways Authority Of India | 155597 | Ghoshpukur (Dhupguri)-Salsalabari (NH-31D) Four Lane Highway Project (Package-II) | 1121 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24249 | National Highways Authority Of India | 155597 | Ghoshpukur (Dhupguri)-Salsalabari (NH-31D) Four Lane Highway Project (Package-II) | 1121 | Contractor | Simplex Infrastructures Ltd. | 227710 | India | Registered Office:Simplex House, 27, Shakespeare Sarani, | 700017 | Kolkata | West Bengal | 91-33-23011600 | 91-33-22835964 | secretarial.legal@simplexinfra.com | www.simplexinfra.com
24250 | National Highways Authority Of India | 155597 | Ghoshpukur-Salsalabari (Dhupguri) (NH-31D) Four Lane Highway Project (Package-I) | 717 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24251 | National Highways Authority Of India | 155597 | Ghoshpukur-Salsalabari (Dhupguri) (NH-31D) Four Lane Highway Project (Package-I) | 717 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24252 | National Highways Authority Of India | 155597 | Giddalur-Vinukonda (NH-544D) Two Lane Highway Project (Bharatmala) | 1444 | Contractor | B V S R Constructions Pvt. Ltd. | 387344 | India |  | NA
24253 | National Highways Authority Of India | 155597 | Gogunda-Udaipur NH-76 Highway Project | 642 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24254 | National Highways Authority Of India | 155597 | Gogunda-Udaipur NH-76 Highway Project | 642 | Contractor | Ranjit Construction Co. | 286134 | India | Registered Office:Near Newrang Bagh, Baipura Road, Hatkeshawar, Khokhar, Maninagar East, Ahmedabad, Gujarat | 380008 |  | Gujarat | 91-79-5854163
24255 | National Highways Authority Of India | 155597 | Gohana-Sonepat (NH-352A) Four Lane Highway Project (Package 2) (Bharatmala) | 1632 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
24256 | National Highways Authority Of India | 155597 | Gola-Bokaro (Jaina More) (NH-320) Four Lane Greenfield Highway Project (Package-I) (Bharatmala) | 1992 | Contractor | N G Projects Ltd. | 363366 | India | Registered Office:N G Circle, Mehtapura, Himatnagar, | 383001 | Sabar Kantha | Gujarat | 91-2772-222404 | 91-2772-223950 | ngpl_hmt@rediffmail.com
24257 | National Highways Authority Of India | 155597 | Gondal Chowkdi (NH-27) Six Lane Elevated Flyover (Bridge) Project | 1522 | Contractor | Vidya Infrabuilt Pvt. Ltd. | 594476 | India | Registered Office:K-120, Kirti Nagar, | 110015 | New Delhi | NCT of Delhi |  |  | rocdak1@gmail.com
24258 | National Highways Authority Of India | 155597 | Gondal-Ribda Section(EW-10/GJ) Highway Project | 195 | Contractor | Backbone Infrastructure Pvt. Ltd. | 289461 | India | Registered Office:BIPL Building Jalaram 2NR Shreepath Tower University Road, | 360001 | Rajkot | Gujarat |  |  | tenderbpl@yahoo.co.in
24259 | National Highways Authority Of India | 155597 | Gopalganj-Chhapra Two-Laning Highway Project | 540 | Consultant | Span Consultant Pvt. Ltd. | 586307 | India | Registered Office:92-C, Gurudwara Road, Madangir, | 110062 | New Delhi | NCT of Delhi | 91-11-29955645
24260 | National Highways Authority Of India | 155597 | Gopalganj-Chhapra Two-Laning Highway Project | 540 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24261 | National Highways Authority Of India | 155597 | Gopalganj-Muzaffarpur (Lucknow-Muzaffarpur) Road Project | 273 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24262 | National Highways Authority Of India | 155597 | Gorakhpur - Gopalganj (Lucknow-Muzaffarpur) Road Project | 272 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24263 | National Highways Authority Of India | 155597 | Gorakhpur-Bareilly Road Corridor Project | 2090 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24264 | National Highways Authority Of India | 155597 | Gorakhpur-Gopalganj (NH-28) Four Laning Highway Project | 1085 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24265 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | Consultant - Project management | Dorsch Consult Ingenieru Gesellschaft M B H. | 62671 | Germany |  | NA
24266 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | Consultant - Project management | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
24267 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | Contractor | Sunway Construction Bhd | 282631 | Malaysia | Registered Office:Level 8, Menara Sunway, Jalan Lagoon Timur, Bandar Sunway, 46150 Petaling Jaya, Selangor Darul Ehsan, Malaysia | NA
24268 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | EPC contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24269 | National Highways Authority Of India | 155597 | Gorhar-Barwa Adda Highway Project | 159 | Supervision consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24270 | National Highways Authority Of India | 155597 | Govindpur (Rajgunj)-Chas-West Bengal Border (NH-32) Two/Four Laning Highway Project | 824 | Consultant | Rodic Consultants Pvt. Ltd. | 307240 | India | Corporate Office:1, Jai Singh Road, | 110001 | New Delhi | NCT of Delhi | 91-11-49434500 | 91-11-49434501 | contact@rodicconsultants.com | www.rodicconsultants.com
24271 | National Highways Authority Of India | 155597 | Govindpur (Rajgunj)-Chas-West Bengal Border (NH-32) Two/Four Laning Highway Project | 824 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
24272 | National Highways Authority Of India | 155597 | Govindpur (Rajgunj)-Chas-West Bengal Border (NH-32) Two/Four Laning Highway Project | 824 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24273 | National Highways Authority Of India | 155597 | Govindsar Village-Talwara Village (NH-44) Four Lane Greenfield connectivity Project (Pathankot Bypass) | 2037 | Consultant | S M E C International Pty. Ltd. | 203789 | India | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24274 | National Highways Authority Of India | 155597 | Govindsar Village-Talwara Village (NH-44) Four Lane Greenfield connectivity Project (Pathankot Bypass) | 2037 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
24275 | National Highways Authority Of India | 155597 | Gowthami River Bridge Project | 172 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24276 | National Highways Authority Of India | 155597 | Grand Trunk Road Improvement Project | 218 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
24277 | National Highways Authority Of India | 155597 | Grand Trunk Road Improvement Project | 218 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24278 | National Highways Authority Of India | 155597 | Greenfield Road Connecting North & South Industrial Cluster of Khandaleru Creek near Krishnapatnam Port Project | 1716 | Contractor | Rithwik Projects Pvt. Ltd. | 198549 | India | Registered Office:Plot No. 37 & 39, Navodaya Colony, Banjara Hills, Road No. 2, # 8-2-268/K/37 & 39, | 500034 | Hyderabad | Telangana | 91-40-49113333 | 91-40-49113444 | rplhyd@rithwikprojects.com | www.rithwikprojects.com
24279 | National Highways Authority Of India | 155597 | Greenfield Road Connecting North & South Industrial Cluster of Khandaleru Creek near Krishnapatnam Port Project | 1716 | Contractor | A M R India Ltd. | 369454 | India | Corporate Office:Sri Krupa, D No 8-3-833, Plot No 37 & 38, Phase-1, Kamalapuri Colony, | 500073 | Hyderabad | Telangana | 91-40-30570009 | 91-40-30570012 | info@amrgroup.in | www.amrgroup.in
24280 | National Highways Authority Of India | 155597 | Guddehosur to Start of Ramanathapura Terakanambi Road Junction (NH-275) Four Lane Highway Project (Package-2 of Mysuru-Kushalnagar Highway) | 1985 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
24281 | National Highways Authority Of India | 155597 | Guna Bypass Project | 883 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24282 | National Highways Authority Of India | 155597 | Guna Bypass Project | 883 | Contractor | Guna Infrastructure Ltd. | 395257 | India | Registered Office:501, Heritage Plaza, J P Rd, Opp Indian Oil Colony, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-30688000 | 91-22-66790535 | compliance@kalyangroup.in
24283 | National Highways Authority Of India | 155597 | Gundla Pochampalli to Bowenpalli, Shivarampalli to Thondapalli Highway Project | 322 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24284 | National Highways Authority Of India | 155597 | Gundlapochampally-Bowenpally Six Lane Highway (NH-44) Project | 2002 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
24285 | National Highways Authority Of India | 155597 | Gundugolanu-Kalaparru (NH-5) (New NH-16) Six Lane Highway Project (Bharatmala) | 1828 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
24286 | National Highways Authority Of India | 155597 | Gurdaspur Logistic Park Project | 1370 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24287 | National Highways Authority Of India | 155597 | Gurgaon Logistics Park Project | 1383 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24288 | National Highways Authority Of India | 155597 | Gurgaon-Kotputli Highway Project | 40 | Consultant | Showy Mountains Engg. Corpn. Ltd. | 222008 | Australia |  | NA
24289 | National Highways Authority Of India | 155597 | Gurgaon-Kotputli Highway Project | 40 | Turnkey contractor | B S C-r B M Pati | 27713 | India |  | NA
24290 | National Highways Authority Of India | 155597 | Gurgaon-Pataudi-Rewari (NH-352W) Four-Laning Highway Project | 1815 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24291 | National Highways Authority Of India | 155597 | Gurvaygudem Village-Devarapalle Village Four Lane Access Controlled Greenfield Highway Project (Package 5 of Khammam-Devarapalle NH-365BG) | 1886 | Contractor | Bekem Infra Projects Pvt. Ltd. | 389845 | India | Corporate Office:Plot No. 289, Avenue 1, Road No.6, Kakatiya Hills, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-48587234 |  | info@bekemprojects.com | www.bekem.com
24292 | National Highways Authority Of India | 155597 | Gurvaygudem Village-Devarapalle Village Four Lane Access Controlled Greenfield Highway Project (Package 5 of Khammam-Devarapalle NH-365BG) | 1886 | Contractor | Sri Avantika Contractors (i) Ltd. | 395603 | India | Registered Office:7/1/618, 610-B, Nilgiri Block, Aditya Enclave, Ameerpet, | 500016 | Hyderabad | Telangana | 91-40-23747332 |  | avantika62@yahoo.com
24293 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW-14/AS) Highway Project | 198 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24294 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW-14/AS) Highway Project | 198 | Contractor | C & C Constructions Ltd. | 39807 | India | Corporate Office:Plot No.70, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-4536666 | 91-124-4536799 | candc@candcinfrastructure.com | www.candcinfrastructure.com
24295 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW/7) Highway Project__ | 224 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24296 | National Highways Authority Of India | 155597 | Guwahati Bypass(EW/7) Highway Project__ | 224 | Turnkey contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
24297 | National Highways Authority Of India | 155597 | Guwahati Six Lane Bypass (NH-37) (section of Jalukbari-Koinadhora Highway) Project | 1319 | Contractor | Dhariwal Buildtech Ltd. | 604954 | India |  | NA
24298 | National Highways Authority Of India | 155597 | Guwahati-Nalbari (NH-31) Highway Project | 282 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24299 | National Highways Authority Of India | 155597 | Guwahati-Nalbari (NH-31) Highway Project | 282 | Supervision consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24300 | National Highways Authority Of India | 155597 | Guwahati-Nalbari (NH-31) Highway Project | 282 | Supervision consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24301 | National Highways Authority Of India | 155597 | Hadapsar-Jejuri (NH-965) Four Lane Highway Project (Package-VI of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1939 | Consultant | Technocrats Advisory Services Pvt. Ltd. | 566226 | India | Registered Office:68, Ajanta Apartments, 36, I P Extension Patparganj, | 110092 | New Delhi | NCT of Delhi |  |  | kamleshkumar.77@gmail.com
24302 | National Highways Authority Of India | 155597 | Hadapsar-Jejuri (NH-965) Four Lane Highway Project (Package-VI of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1939 | Contractor | Thakur Infra Projects Pvt. Ltd. | 407339 | India | Registered Office:House No 1221, At & Po : Jasai, Jasai Naka, Taluka Uran, Navi Mumbai, Raigad, | NA | Navi Mumbai | Maharashtra |  |  | thakurinfraprojects@gmail.com
24303 | National Highways Authority Of India | 155597 | Hadapsar-Jejuri (NH-965) Four Lane Highway Project (Package-VI of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1939 | Contractor | T & T Infra Ltd. | 543147 | India | Registered Office:Office No.1 To 5, A1, Visnu Vihar, Bibwewadi Kondhwa Road, Marketyard, | 411037 | Pune | Maharashtra | 91-20-24275945 |  | groupt_t@yahoo.co.in | www.tandtinfra.com
24304 | National Highways Authority Of India | 155597 | Hadapsar-Jejuri (NH-965) Four Lane Highway Project (Package-VI of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1939 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
24305 | National Highways Authority Of India | 155597 | Hajipur-Muzaffarpur (NH-77) Eight Lane Road Project | 1789 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
24306 | National Highways Authority Of India | 155597 | Hajipur-Muzaffarpur (NH-77) Eight Lane Road Project | 1789 | Contractor | S R S C Infra Pvt. Ltd. | 611760 | India |  | NA
24307 | National Highways Authority Of India | 155597 | Halvad Cross Road (NH-8A) Flyover Project with approaches (on Bamanbore-Garamore section) | 1254 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24308 | National Highways Authority Of India | 155597 | Handia-Varanasi (TNHP/III-C) Highway Project | 690 | Consultant | Meinhardt (singapore) Pte Ltd. | 286809 | Singapore | Registered Office:A - 8, Sector 16, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh | 91-120-2516165 | 91-120-2515745 | rajesh@meinhardtindia.com | www.meinhardtgroup.com
24309 | National Highways Authority Of India | 155597 | Handia-Varanasi (TNHP/III-C) Highway Project | 690 | Contractor | Centrodorstroy | 43595 | Russia |  | NA
24310 | National Highways Authority Of India | 155597 | Hapur-Garhmukteshwar (NH-24) Highway Project | 342 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24311 | National Highways Authority Of India | 155597 | Hapur-Garhmukteshwar (NH-24) Highway Project | 342 | Contractor | Uttar Pradesh State Bridge Corpn. Ltd. | 255951 | India | Registered Office:Setu Bhawan, 16, Madan Mohan Malviya Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2209702 | 91-522-2209798 | upsbcltd@gmail.com | www.bridgecorporationltd.com
24312 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24313 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Consultant | Almondz Global Infra-consultant Ltd. | 492419 | India | Corporate Office:F-33/3, Okhla Industrial Area, Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-43500700 | 91-11-4350073 | delhi@almondz.com | www.almondzglobalinfra.com
24314 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Consultant | Thoughts Consultants Jaipur Pvt. Ltd. | 580546 | India | Registered Office:1 DA, 15, Jawahar Nagar, | 302004 | Jaipur | Rajasthan | 91-141-2653232 |  | thoughts.jaipur@gmail.com | www.thoughtsjaipur.com
24315 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24316 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
24317 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | EPC contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24318 | National Highways Authority Of India | 155597 | Harangaj-Maibang-Lumding Highway Project | 276 | EPC contractor | Continental Engineering Corpn. | 370689 | Taiwan (Taipei) | Head Office:Suite 4A, Plaza M-6, Jasola, | 110025 | South Delhi | NCT of Delhi | 91-11-47371000 | 91-11-47371010 | nangia@nangia.com | www.nangia.com
24319 | National Highways Authority Of India | 155597 | Harda-Temagaon (NH-47) Four Lane Highway Project (Package 1 of Harda-Betul) (Bharatmala) | 1796 | Contractor | Prakash Asphaltings & Toll Highways (india) Ltd. | 178735 | India | Registered Office:76, Mall Road, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-275001 | 91-7324-400318 | path@pathltd.com | www.pathltd.com
24320 | National Highways Authority Of India | 155597 | Haridwar Ring Road Project | 1451 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24321 | National Highways Authority Of India | 155597 | Haridwar-Nagina (NH-34&734) Four Lane Highway Project | 1024 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24322 | National Highways Authority Of India | 155597 | Haridwar-Nagina (NH-34&734) Four Lane Highway Project | 1024 | Contractor | Corsan Corviam Constructions Sa | 439998 | Spain |  | NA
24323 | National Highways Authority Of India | 155597 | Hariharganj-Rudwa (Near Parwa More) (NH-98) Four Lane Highway project | 1455 | Consultant | Shweta Technophile Consultants Pvt. Ltd. | 568348 | India | Registered Office:222, Rajhans Plaza, Ahinsa Khand - 1, Indrapuram, | 201014 | Ghaziabad | Uttar Pradesh |  |  | shwetatechnophile@gmail.com
24324 | National Highways Authority Of India | 155597 | Hariharganj-Rudwa (Near Parwa More) (NH-98) Four Lane Highway project | 1455 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
24325 | National Highways Authority Of India | 155597 | Harmu Road Flyover (LPN Nath Shahdeo Chowk-Kartik Oraon Chowk) Project | 1764 | Co-promoter | Jharkhand Urban Infrastructure Devp. Co. Ltd. | 535437 | India | Registered Office:Pragati Sadan (RRDA Building), 3rd Floor, Kutchary Chowk, | 834001 | Ranchi | Jharkhand | 91-651-2400962 |  | juidcolimited@gmail.com | www.juidco.jharkhand.gov.in
24326 | National Highways Authority Of India | 155597 | Haryana-Rajasthan border and ends at Junction with SH44 Eight Lane Carriageway Project (Package 4 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1541 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24327 | National Highways Authority Of India | 155597 | Haryana-Rajasthan border and ends at Junction with SH44 Eight Lane Carriageway Project (Package 4 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1541 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24328 | National Highways Authority Of India | 155597 | Hasapur-Badadal Six Lane Highway Project (Package-14 of Surat-Solapur Economic Corridor) | 2102 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24329 | National Highways Authority Of India | 155597 | Hassan (NH-75) Four Lane Bypass Project | 1650 | Contractor | Power Mech Projects Ltd. | 177768 | India | Corporate Office:Plot No.77, Jubilee Enclave, Opp. Hitex, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-30444444 | 91-40-30444400 | info@powermech.net | www.powermechprojects.in
24330 | National Highways Authority Of India | 155597 | Hassan (NH-75) Four Lane Bypass Project | 1650 | Contractor | S R C Infra Developers Pvt. Ltd. | 598980 | India | Registered Office:7-272, kakateeya Residency Court Road, | 515001 | Anantapur | Andhra Pradesh |  |  | sheema.src1@gmail.com
24331 | National Highways Authority Of India | 155597 | Hassan-Huliyar-Hiriyur (NH-150A) Four Lane Road Project | 1920 | Consultant | T P F Engineering Pvt. Ltd. | 578734 | India | Registered Office:Unit No 10, Banking Complex, No II, Plot No 9 & 10m Sector 19 A, Vashi, | 400705 | Mumbai | Maharashtra | 91-22-41273303 | 91-22-41273306 | tenders@tpfepl.com | www.tpfepl.com
24332 | National Highways Authority Of India | 155597 | Hassan-Huliyar-Hiriyur (NH-150A) Four Lane Road Project | 1920 | Consultant | T P F Getinsa Euroestudios | 586015 | Spain |  | NA
24333 | National Highways Authority Of India | 155597 | Hassan-Maranahalli (NH-75) Four Lane Highway Project (Hassan-B.C. Road Pkg-I) | 784 | Contractor | Rajkamal Builders Pvt. Ltd. | 443699 | India |  | NA
24334 | National Highways Authority Of India | 155597 | Hathipali-Hosur(NS/11) Highway Project | 45 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24335 | National Highways Authority Of India | 155597 | Hathipali-Hosur(NS/11) Highway Project | 45 | Turnkey contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24336 | National Highways Authority Of India | 155597 | Haveri-Harihar (NH-4) Highway Project | 749 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24337 | National Highways Authority Of India | 155597 | Haveri-Harihar (NH-4) Highway Project | 749 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24338 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga Bypass) Highway Project | 115 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24339 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga Bypass) Highway Project | 115 | Contractor | M B L Infrastructure Ltd. | 136291 | India | Corporate Office:Banani Corporate One Tower, Suite #303-308, 3rd Floor, Jasola, Plot No.5, Commercial Centre, | 110025 | New Delhi | NCT of Delhi | 91-11-49593300 | 91-11-48593320 | delhi@mblinfra.com | www.mblinfra.com
24340 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga Bypass) Highway Project | 115 | Contractor | Supreme Infrastructure India Ltd. | 241950 | India | Registered Office:Supreme House, Plot No.94/C, Pratap Gad, Opp IIT Main Gate, Powai, | 400076 | Mumbai | Maharashtra | 91-22-61289700 | 91-22-61289711 | vijayj@supremeinfra.com | www.supremeinfra.com
24341 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga-Sira) Highway Project | 116 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24342 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Chitradurga-Sira) Highway Project | 116 | Contractor | United Engineers International Inc. | 257913 | Malaysia |  | NA
24343 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Harihar-Chitradurga) Highway Project | 81 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24344 | National Highways Authority Of India | 155597 | Haveri-Tumkur (Harihar-Chitradurga) Highway Project | 81 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24345 | National Highways Authority Of India | 155597 | Haveri-Tumkur(Sira-Tumkur) Highway Project | 75 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24346 | National Highways Authority Of India | 155597 | Haveri-Tumkur(Sira-Tumkur) Highway Project | 75 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24347 | National Highways Authority Of India | 155597 | Hebbal flyover to Bengaluru International Airport Road Project | 801 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
24348 | National Highways Authority Of India | 155597 | Hebbal-Kempapura Junction Skywalk Project | 1065 | Financial collaborator | Manipal Hospitals Pvt. Ltd. | 385319 | USA | Registered Office:The Annexe, No. 98/2, Rustom Bagh, Off Hal Airport Road, | 560017 | Bengaluru | Karnataka |  |  | jagannath.ms@columbiaasia.com | www.columbiaasia.com
24349 | National Highways Authority Of India | 155597 | Hebbal-Kempapura Junction Skywalk Project | 1065 | Promoter | Bruhat Bangalore Mahanagar Palike | 379062 | India | Registered Office:Old Madras Road, Near Govt. Stand K R Puram, | 560036 | Bengaluru | Karnataka | 91-80-2239044 |  | contactusbbmp@gmail.com | www.bbmp.gov.in
24350 | National Highways Authority Of India | 155597 | Hero Honda Chowk Eight Lane Flyover & Underpass Project | 972 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
24351 | National Highways Authority Of India | 155597 | Himatnagar-Chiloda (Near Ahmedabad) (UG-IV) Highway Project | 133 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24352 | National Highways Authority Of India | 155597 | Hinganghat-Nandgaon Junction (NH-44) Flyover Project | 1640 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24353 | National Highways Authority Of India | 155597 | Hinganghat-Nandgaon Junction (NH-44) Flyover Project | 1640 | Contractor | Vidya Infrabuilt Pvt. Ltd. | 594476 | India | Registered Office:K-120, Kirti Nagar, | 110015 | New Delhi | NCT of Delhi |  |  | rocdak1@gmail.com
24354 | National Highways Authority Of India | 155597 | Hisar-Dabwali (NH-10) Four Lane Highway Project (Package-I) | 911 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24355 | National Highways Authority Of India | 155597 | Hisar-Dabwali (NH-10) Four Lane Highway Project (Package-II) | 1005 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24356 | National Highways Authority Of India | 155597 | Hoshiarpur-Una (NH-503A) Two/Four Lane Highway Project | 3013 | Contractor | Amar Infrastructure Ltd. | 399085 | India | Registered Office:Near Jain Palace, G E Road, Pulgaon, | 491001 | Durg | Chhattisgarh | 91-788-2210721 | 91-788-2320665 | amarbuilders_84@yahoo.co.in | www.amarinfra.com
24357 | National Highways Authority Of India | 155597 | Hoshiarpur-Una (NH-503A) Two/Four Lane Highway Project | 3013 | Contractor | P S Constructions (maharashtra) | 629893 | India |  | NA
24358 | National Highways Authority Of India | 155597 | Hoskote-Dobbaspet (NH-648) Four/Six Laning Highway Project (Banglore Ring Road) | 1406 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
24359 | National Highways Authority Of India | 155597 | Hoskote-Dobbaspet (NH-648) Four/Six Laning Highway Project (Banglore Ring Road) | 1406 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
24360 | National Highways Authority Of India | 155597 | Hoskote-Dobbaspet (NH-648) Four/Six Laning Highway Project (Banglore Ring Road) | 1406 | Consultant | Louis Berger Intl. Inc. | 287149 | India | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24361 | National Highways Authority Of India | 155597 | Hospet-Bellary-Karnataka/AP Border Four Lane Highway Project | 1037 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
24362 | National Highways Authority Of India | 155597 | Hospet-Bellary-Karnataka/AP Border Four Lane Highway Project | 1037 | Contractor | S R C Infra Developers Pvt. Ltd. | 598980 | India | Registered Office:7-272, kakateeya Residency Court Road, | 515001 | Anantapur | Andhra Pradesh |  |  | sheema.src1@gmail.com
24363 | National Highways Authority Of India | 155597 | Hospet-Bellary-Karnataka/AP Border Four Lane Highway Project | 1037 | EPC contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24364 | National Highways Authority Of India | 155597 | Hosur-Krishnagiri Four Lane Highway Project | 17 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24365 | National Highways Authority Of India | 155597 | Hosur-Krishnagiri Four Lane Highway Project | 17 | Contractor | S M S Ltd. | 218106 | India | Corporate Office:20, I T Park, Parsodi, | 440022 | Nagpur | Maharashtra | 91-712-6665000 | 91-712-6665100 | info@smsl.co.in | www.smsl.co.in
24366 | National Highways Authority Of India | 155597 | Hridaipur-Shahapur (NH-31) Four Lane Greenfield Highway Project (Package-I of Ghazipur-Ballia-UP/Bihar State Border) | 1284 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
24367 | National Highways Authority Of India | 155597 | Hubli-Ankola Six lane Road Project (Port Connectivity) | 1726 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24368 | National Highways Authority Of India | 155597 | Hubli-Dharwad (NH-4) Six Lane Bypass Project (Bangalore-Pune Section) | 1849 | Contractor | Mathiyan Construction Pvt. Ltd. | 419088 | India |  | NA
24369 | National Highways Authority Of India | 155597 | Hubli-Dharwad (NH-4) Six Lane Bypass Project (Bangalore-Pune Section) | 1849 | Contractor | A P S Hydro Pvt. Ltd. | 483858 | India | Registered Office:House No. 58, Floor 1st, Block 10 Landmark Opp. Old Police Station Kirti Nagar Ind. Area, | 110015 | New Delhi | NCT of Delhi |  |  | apshydro@gmail.com
24370 | National Highways Authority Of India | 155597 | Hubli-Hospet NH-67 (Old NH-63) Four Laning Highway Project | 902 | Consultant | Stanley Consultants Inc. | 380296 | India | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
24371 | National Highways Authority Of India | 155597 | Hubli-Hospet NH-67 (Old NH-63) Four Laning Highway Project | 902 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24372 | National Highways Authority Of India | 155597 | Hubli-Hospet NH-67 (Old NH-63) Four Laning Highway Project | 902 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24373 | National Highways Authority Of India | 155597 | Hyderabad (ORR Appa Junction)- Manneguda Four Lane Road (NH-163) Project | 1853 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
24374 | National Highways Authority Of India | 155597 | Hyderabad (ORR Appa Junction)- Manneguda Four Lane Road (NH-163) Project | 1853 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24375 | National Highways Authority Of India | 155597 | Hyderabad-Bangalore (NH-7,NS Corridor) Highway Project | 442 | Contractor | Soma Enterprise Ltd. | 230660 | India | Corporate Office:2 Avenue, 4, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-66538899 | 91-40-23321286 | info@soma.co.in | www.soma.co.in
24376 | National Highways Authority Of India | 155597 | Hyderabad-Bangalore (NH-7,NS Corridor) Highway Project | 442 | Supervision consultant | C E S Pvt. Ltd. [merged] | 372391 | India |  | NA
24377 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Icchapuram-Korlam) Highway Project | 99 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24378 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Icchapuram-Korlam) Highway Project | 99 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24379 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Icchapuram-Korlam) Highway Project | 99 | Turnkey contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
24380 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Srikakulam-Champawati) Highway Project | 102 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24381 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Srikakulam-Champawati) Highway Project | 102 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24382 | National Highways Authority Of India | 155597 | Iccha-Vishakha(Srikakulam-Champawati) Highway Project | 102 | Contractor | Sew Infrastructure Ltd. | 217307 | India | Head Office:6-3-871, Snehalata, 1st Floor, Greenlands Road, Begumpet, | 500016 | Hyderabad | Telangana | 91-40-23402153 | 91-40-23405016 | mail@sewconstructions.com | www.sewinfrastructure.com
24383 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Korlam-Palasa AP-4A) Highway Project | 100 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24384 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Korlam-Palasa AP-4A) Highway Project | 100 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24385 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Korlam-Palasa AP-4A) Highway Project | 100 | Turnkey contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
24386 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Palasa-Srikakulam) Highway Project | 101 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24387 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Palasa-Srikakulam) Highway Project | 101 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24388 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Palasa-Srikakulam) Highway Project | 101 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
24389 | National Highways Authority Of India | 155597 | Icchapuram-Vishakhapatnam(Palasa-Srikakulam) Highway Project | 101 | Contractor | Shapoorji Pallonji & Co. Pvt. Ltd. | 219012 | India | Head Office:S P Centre, 41/44, Minoo Desai Marg,Colaba, | 400005 | Mumbai | Maharashtra | 91-22-67490000 |  | comsec@shapoorji.com | www.shapoorji.com
24390 | National Highways Authority Of India | 155597 | Improvement & Development to Multi Lane Carriageway (NH-211) from Nagarnaka Junction-Cambridge School Road (Aurangabad) | 1670 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
24391 | National Highways Authority Of India | 155597 | Improvement of Khambataki Ghat section (with tunnel) on Pune-Satara section (NH-48) Project | 1298 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24392 | National Highways Authority Of India | 155597 | Improvement of Khambataki Ghat section (with tunnel) on Pune-Satara section (NH-48) Project | 1298 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24393 | National Highways Authority Of India | 155597 | Improvement of Khambataki Ghat section (with tunnel) on Pune-Satara section (NH-48) Project | 1298 | Contractor | Crescent E P C Projects & Technical Services Ltd. | 413241 | India | Registered Office:IDA Phase-II, Patancheru, | 502319 | Hyderabad | Telangana |  |  | mabubasha.d@gvk.com
24394 | National Highways Authority Of India | 155597 | Improvement of T-Junction near Dhaula Kuan Metro Station Project (Bharatmala) | 1321 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
24395 | National Highways Authority Of India | 155597 | Indapur-Tondale (NH-965G) Four Lane Road Project (Package-III of Sant Tukaram Maharaj Palkhi Marg) | 1899 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24396 | National Highways Authority Of India | 155597 | Indapur-Tondale (NH-965G) Four Lane Road Project (Package-III of Sant Tukaram Maharaj Palkhi Marg) | 1899 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
24397 | National Highways Authority Of India | 155597 | Indore (Pithampur) Logistic Park Project | 1360 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24398 | National Highways Authority Of India | 155597 | Indore (Pithampur) Logistic Park Project | 1360 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24399 | National Highways Authority Of India | 155597 | Indore-Khalghat (NH-3) Highway Project | 656 | Consultant | Feedback Turnkey Engineers Pvt. Ltd. | 72650 | India | Registered Office:10/6 Sarvapriya Vihar, New Delhi | 110016 |  | Delhi
24400 | National Highways Authority Of India | 155597 | Indore-Khalghat (NH-3) Highway Project | 656 | Consultant | Sheladia Associates Inc. | 287104 | USA | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
24401 | National Highways Authority Of India | 155597 | Indore-Khalghat (NH-3) Highway Project | 656 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
24402 | National Highways Authority Of India | 155597 | Indore-Raghav Garh (NH-59) Four Lane Highway Project (Package-I of Indore-Harda Economic Corridor) | 1951 | Contractor | P D Agrawal Infrastructure Ltd. | 389098 | India | Registered Office:No. 6, Joy Builders Colony, Near Rani Sati Mandir, | 452003 | Indore | Madhya Pradesh | 91-731-2544370 | 91-731-2538023 | pdagrawal_indore@yahoo.com
24403 | National Highways Authority Of India | 155597 | Intermodal Stations Project | 1459 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24404 | National Highways Authority Of India | 155597 | Islam Nagar to Kadtal (NS-2/BOT/AP-7) Highway Project | 503 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24405 | National Highways Authority Of India | 155597 | Islam Nagar to Kadtal (NS-2/BOT/AP-7) Highway Project | 503 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24406 | National Highways Authority Of India | 155597 | Islam Nagar to Kadtal (NS-2/BOT/AP-7) Highway Project | 503 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24407 | National Highways Authority Of India | 155597 | Islampur Four Lane Bypass (NH-31) Project | 1052 | Consultant | Archtech Consultants Pvt. Ltd. | 19112 | India | Registered Office:No. 11, Shakespeare Sarani, | 700071 | Kolkata | West Bengal | 91-33-2827255 | 91-33-2825377 | acplcal@cal3.vsnl.net.in | www.archtechconsultants.com
24408 | National Highways Authority Of India | 155597 | Islampur Four Lane Bypass (NH-31) Project | 1052 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24409 | National Highways Authority Of India | 155597 | Ismailabad on NH-152 to Junction with Karnal-Pehowa Road Four/Six Lane Access Controlled Highway Project (Package 1 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1533 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24410 | National Highways Authority Of India | 155597 | Ismailabad on NH-152 to Junction with Karnal-Pehowa Road Four/Six Lane Access Controlled Highway Project (Package 1 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1533 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24411 | National Highways Authority Of India | 155597 | Ismailabad on NH-152 to Junction with Karnal-Pehowa Road Four/Six Lane Access Controlled Highway Project (Package 1 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1533 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24412 | National Highways Authority Of India | 155597 | Ismailabad on NH-152 to Junction with Karnal-Pehowa Road Four/Six Lane Access Controlled Highway Project (Package 1 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1533 | Contractor | Shiv Buildindia Pvt. Ltd. | 457770 | India | Registered Office:401/2, 4th Floor, Siddhraj Zavod, Sargasan, | 382421 | Gandhinagar | Gujarat | 91-79-29750425 |  | contact@shivbuildindia.com | www.shivbuildindia.com
24413 | National Highways Authority Of India | 155597 | Ismailabad to Ambala (NH152) Four Lane Access Controlled Highway Project (Part of Ambala-Kotputli Corridor) | 2118 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24414 | National Highways Authority Of India | 155597 | Ismailabad to Ambala (NH152) Four Lane Access Controlled Highway Project (Part of Ambala-Kotputli Corridor) | 2118 | Contractor | P S Construction Pvt. Ltd. | 366387 | India | Registered Office:No. 11, Damodharan Street, Kellys, | 600010 | Chennai | Tamil Nadu
24415 | National Highways Authority Of India | 155597 | Ismailabad to Ambala (NH152) Four Lane Access Controlled Highway Project (Part of Ambala-Kotputli Corridor) | 2118 | Contractor | Amar Infrastructure Ltd. | 399085 | India | Registered Office:Near Jain Palace, G E Road, Pulgaon, | 491001 | Durg | Chhattisgarh | 91-788-2210721 | 91-788-2320665 | amarbuilders_84@yahoo.co.in | www.amarinfra.com
24416 | National Highways Authority Of India | 155597 | Itanagar-Banderdewa (NH-415) Four Laning Highway Project | 1217 | Contractor | A R S S Infrastructure Projects Ltd. | 370768 | India | Corporate Office:A R S S Mail, Plot No.40, Community Centre, Block-A, Paschim Vihar, Opp. To Jwalaheri Market, | 110063 | New Delhi | NCT of Delhi | 91-11-25252024 | 91-11-48636339 | delhi@arssgroup.in | www.arssgroup.in
24417 | National Highways Authority Of India | 155597 | Itanagar-Banderdewa (NH-415) Four Laning Highway Project | 1217 | Contractor | T K Engineering Consortium Pvt. Ltd. | 439979 | India | Registered Office:Model Village, Naharlagun, | 791110 | Naharlagun | Arunachal Pradesh | 91-360-2244014 |  | tkeconltd@gmail.com | www.tkeecon.com
24418 | National Highways Authority Of India | 155597 | Jabalpur-Katni-Rewa (NH-7) Four Laning Highway Project | 1019 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24419 | National Highways Authority Of India | 155597 | Jabalpur-Katni-Rewa (NH-7) Four Laning Highway Project | 1019 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24420 | National Highways Authority Of India | 155597 | Jabalpur-Lakhnadon Four Lane Highway (NH-30 and NH-34) Project | 859 | Consultant | Wilbur Smith Associates Inc. | 272295 | USA | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
24421 | National Highways Authority Of India | 155597 | Jabalpur-Lakhnadon Four Lane Highway (NH-30 and NH-34) Project | 859 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24422 | National Highways Authority Of India | 155597 | Jagadhari-HR/HP Border (Ponta Sahib) Four Lane Highway (NH-344) Project | 1856 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24423 | National Highways Authority Of India | 155597 | Jaigaon-Changrabandha (AH-48) Road Project | 989 | Co-promoter | West Bengal Public Works Department | 437735 | India | Registered Office:Main Block, 2nd Floor, Writers, Buildings, | 700001 | Kolkata | West Bengal | 91-33-22143161 | 91-33-22144788 |  | www.pwdwb.in
24424 | National Highways Authority Of India | 155597 | Jaigaon-Changrabandha (AH-48) Road Project | 989 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24425 | National Highways Authority Of India | 155597 | Jaigaon-Changrabandha (AH-48) Road Project | 989 | Financial collaborator | Asian Development Bank | 22786 | India | Registered Office:4, San Martin Marg, Chanakyapuri, | 110021 | South West Delhi | NCT of Delhi | 91-11-24107200 | 91-11-26870945 |  | www.adb.org
24426 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 1 Project | 24 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24427 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 1 Project | 24 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24428 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Consultant | Mahendra Raj Consultants Pvt. Ltd. | 136095 | India | Head Office:Q-24, Jangpura Extension, | 110014 | New Delhi | Delhi | 91-11-24312724 | 91-11-24312183 | mrc@giasdl01.vsnl.net.in
24429 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Consultant | Meritech Ltd. | 331064 | New Zealand | Registered Office: | NA | [5 empty] | www.meritechsolutions.com
24430 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24431 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24432 | National Highways Authority Of India | 155597 | Jaipur Bypass Phase 2 Project | 74 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24433 | National Highways Authority Of India | 155597 | Jaipur Logistic Park Project | 1365 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24434 | National Highways Authority Of India | 155597 | Jaipur Ring Road (South) Project (Bharatmala) | 1322 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24435 | National Highways Authority Of India | 155597 | Jaipur Ring Road (South) Project (Bharatmala) | 1322 | Contractor | Sona Builders | 485994 | India |  | NA
24436 | National Highways Authority Of India | 155597 | Jaipur Ring Road (South) Project (Bharatmala) | 1322 | Contractor | Bharat Spun Pipe & Construction Co. | 518138 | India |  | NA
24437 | National Highways Authority Of India | 155597 | Jaipur Ring Road (South) Project (Bharatmala) | 1322 | Promoter | Jaipur Development Authority | 106601 | India | Registered Office:Ram Kishor Vyas Bhawan, Indra Circle, Jawaharlal Nehru Marg, | 302004 | Jaipur | Rajasthan | 91-141-2569696 |  | jda@rajasthan.gov.in | www.jda.urban.rajasthan.gov.in
24438 | National Highways Authority Of India | 155597 | Jaipur Six Lane Ring Road (North) Project (Phase III) (Bharatmala) | 1655 | Co-promoter | Jaipur Development Authority | 106601 | India | Registered Office:Ram Kishor Vyas Bhawan, Indra Circle, Jawaharlal Nehru Marg, | 302004 | Jaipur | Rajasthan | 91-141-2569696 |  | jda@rajasthan.gov.in | www.jda.urban.rajasthan.gov.in
24439 | National Highways Authority Of India | 155597 | Jaipur Six Lane Ring Road (North) Project (Phase III) (Bharatmala) | 1655 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24440 | National Highways Authority Of India | 155597 | Jaipur Six Lane Ring Road (North) Project (Phase III) (Bharatmala) | 1655 | Consultant | Upham International Corpn. Pvt. Ltd. | 580929 | India | Registered Office:298, Pocket, D Mayur Vihar - II, | 110091 | New Delhi | NCT of Delhi |  |  | uicpl13@gmail.com | www.uphaminternational.com
24441 | National Highways Authority Of India | 155597 | Jaisalmer (NH-11)-Bhadasar-Ramgarh-Tanot and Bhadasar-Sarkaritala-upto Pakistan Border Two/Four Laning Highway Project (BM/5) | 1097 | Contractor | Ramky Infrastructure Ltd. | 347143 | India | Registered Office:Ramky Grandiose, 15th Floor, Sy No. 136/2 & 4, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-23015000 | 91-40-23015444 | investors@ramky.com | www.ramkyinfrastructure.com
24442 | National Highways Authority Of India | 155597 | Jaisalmer (NH-11)-Bhadasar-Ramgarh-Tanot and Bhadasar-Sarkaritala-upto Pakistan Border Two/Four Laning Highway Project (BM/5) | 1097 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
24443 | National Highways Authority Of India | 155597 | Jaisalmer-Barmer (NH-15) Two/Four Laning Highway Project | 999 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24444 | National Highways Authority Of India | 155597 | Jaitia (Patna) Logistic Park Project | 1357 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24445 | National Highways Authority Of India | 155597 | Jalandhar Bypass(NS/1) Project | 225 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24446 | National Highways Authority Of India | 155597 | Jalandhar Bypass(NS/1) Project | 225 | Turnkey contractor | Birla G T M Entrepose Pvt. Ltd. | 36324 | India | Registered Office:Birla Building, 9/1, R N Mukherjee Road, | 700001 | Kolkata | West Bengal | 91-33-22430383 | 91-33-22101912 | neical@nbcbearings.in
24447 | National Highways Authority Of India | 155597 | Jalandhar Logistic Park Project | 1369 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24448 | National Highways Authority Of India | 155597 | Jalandhar-Ambala Highway Project | 3 | Contractor | Afcons Infrastructure Ltd. | 7231 | India | Registered Office:Afcons House, 16, Shah Industrial Estate, Veera Desai Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-67191000 | 91-22-26730047 | rajendran@afcons.com | www.afcons.com
24449 | National Highways Authority Of India | 155597 | Jalandhar-Ambala Highway Project | 3 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24450 | National Highways Authority Of India | 155597 | Jalandhar-Ambala Highway Project | 3 | Contractor | Unitech Ltd. | 257777 | India | Corporate Office:1306-1308, 13 th Floor, Tower B, Signature Towers, South City-1, | 122007 | Gurgaon | Haryana | 91-124-4726860 | 91-124-2383332 | share.dept@unitechgroup.com | www.unitechgroup.com
24451 | National Highways Authority Of India | 155597 | Jalandhar-Amritsar (NH-1) Six Lane Highway Project (Bidhipur-Dhilwan) | 939 | Consultant | Bloom Engineering (europa) Gmbh. | 36744 | USA |  | NA
24452 | National Highways Authority Of India | 155597 | Jalandhar-Amritsar (NH-1) Six Lane Highway Project (Bidhipur-Dhilwan) | 939 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24453 | National Highways Authority Of India | 155597 | Jalandhar-Amritsar (NH-1) Six Lane Highway Project (Bidhipur-Dhilwan) | 939 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24454 | National Highways Authority Of India | 155597 | Jalbehra-near Ismailabad-Patti Kankra near Shahbad Four/Six Lane Highway Project | 2043 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24455 | National Highways Authority Of India | 155597 | Jalbehra-near Ismailabad-Patti Kankra near Shahbad Four/Six Lane Highway Project | 2043 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24456 | National Highways Authority Of India | 155597 | Jam-Wadner (NS-59/MH) Highway project | 744 | Consultant | Feedback Consultants Pvt. Ltd. | 72648 | India | Registered Office:Flat No.3, A I I M S Apts., Near Chilla Regulator, Vasundhra Enclave, | 110096 |  | Delhi
24457 | National Highways Authority Of India | 155597 | Jam-Wadner (NS-59/MH) Highway project | 744 | Contractor | Ideal Road Builders Pvt. Ltd. | 97432 | India | Corporate Office:I R B Complex, Chandivli Farm, Chandivli, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | mhaiskar@bom2.vsnl.net.in
24458 | National Highways Authority Of India | 155597 | Jammu Four lane Ring Road Project | 923 | Consultant | Louis Berger Consulting Pvt. Ltd. | 406754 | India | Registered Office:Regus Business Centre, Level-3, Vasant Square Mall Pocket V, Sector B, | 110070 | New Delhi | NCT of Delhi |  |  | neeraj.kumar2@wsp.com | www.wsp.com
24459 | National Highways Authority Of India | 155597 | Jammu Four lane Ring Road Project | 923 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
24460 | National Highways Authority Of India | 155597 | Jammu Four lane Ring Road Project | 923 | Contractor | Kyivmetrobud P J S C | 553882 | Ukraine |  | NA
24461 | National Highways Authority Of India | 155597 | Jammu Logistic Park Project | 1350 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24462 | National Highways Authority Of India | 155597 | Jammu-Kunjwani (incl. Jammu Bypass) Highway Project | 304 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24463 | National Highways Authority Of India | 155597 | Jammu-Kunjwani (incl. Jammu Bypass) Highway Project | 304 | Contractor | M Venkata Rao Infra Projects Pvt. Ltd. | 384435 | India | Registered Office:D. No. 48-19-6, 2nd Floor M V R Complex, Srinagar, | 530016 | Visakhapatnam | Andhra Pradesh |  |  | mvr999act@yahoo.com
24464 | National Highways Authority Of India | 155597 | Jammu-Pathankot(NS-15/JK) Expressway Project | 180 | Consultant | Lee Associates | 127813 | Canada | Registered Office: | NA | [5 empty] | www.leeassociates.ca
24465 | National Highways Authority Of India | 155597 | Jammu-Pathankot(NS-15/JK) Expressway Project | 180 | Turnkey contractor | Border Roads Organisation | 37884 | India | Registered Office:Seema Sadak Bhawan, Ring Road, Delhi Cantt. | 110010 | New Delhi | NCT of Delhi | 91-11-25686914 | 91-11-25699618 | bro-adg@nic.in | http://www.bro.nic.in
24466 | National Highways Authority Of India | 155597 | Jamujhadi-Basudevpur-Dhamara (NH-316A) Four Lane Highway Project | 1503 | Consultant | Indian Technocrat Ltd. | 99026 | India | Registered Office:Plot No.8, Sector B-7, Local Shopping Complex, Vasant Kunj, | 110070 | New Delhi | NCT of Delhi | 91-11-49531100 | 91-11-49531166 | info@itl.net.in | www.itl.net.in
24467 | National Highways Authority Of India | 155597 | Jatinga-Bara Narayanpur (Harangajo) (NH-54) (New NH-27) Four Lane Highway Project | 1268 | Consultant | Almondz Global Infra-consultant Ltd. | 492419 | India | Corporate Office:F-33/3, Okhla Industrial Area, Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-43500700 | 91-11-4350073 | delhi@almondz.com | www.almondzglobalinfra.com
24468 | National Highways Authority Of India | 155597 | Jatinga-Bara Narayanpur (Harangajo) (NH-54) (New NH-27) Four Lane Highway Project | 1268 | Consultant | Thoughts Consultants Jaipur Pvt. Ltd. | 580546 | India | Registered Office:1 DA, 15, Jawahar Nagar, | 302004 | Jaipur | Rajasthan | 91-141-2653232 |  | thoughts.jaipur@gmail.com | www.thoughtsjaipur.com
24469 | National Highways Authority Of India | 155597 | Jatinga-Bara Narayanpur (Harangajo) (NH-54) (New NH-27) Four Lane Highway Project | 1268 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24470 | National Highways Authority Of India | 155597 | Jawaharlal Nehru Port Road Project(Phase 2) | 582 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24471 | National Highways Authority Of India | 155597 | Jawaharlal Nehru Port Road Project(Phase 2) | 582 | Contractor | Jog Engineering Ltd. | 110207 | India | Registered Office:Jog Center, 28/1, Mumbai-Pune Road, Wakdewadi, | 411003 | Pune | Maharashtra | 91-20-25815931 | 91-20-25814690 | jelhopune@yahoo.com | www.jogengineering.com
24472 | National Highways Authority Of India | 155597 | Jetpur-Somnath (NH-151) Four-Laning Highway Project | 1401 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24473 | National Highways Authority Of India | 155597 | Jetpur-Somnath (NH-151) Four-Laning Highway Project | 1401 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24474 | National Highways Authority Of India | 155597 | Jhalawar-MP/Rajasthan Border Section Two Laning Road Project | 849 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24475 | National Highways Authority Of India | 155597 | Jhanjhapur-Darbanga (BR-7) Highway Project | 715 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | UK | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
24476 | National Highways Authority Of India | 155597 | Jhanjhapur-Darbanga (BR-7) Highway Project | 715 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24477 | National Highways Authority Of India | 155597 | Jhanki Village-Sargi Village (NH-130CD) Six Lane Highway Project (Package CG-1) (Section of Raipur-Visakhapatnam Economic Corridor) | 1809 | Consultant | Yongma Engineering Co. Ltd. | 585553 | India | Registered Office:Unit 301, 302, Time Centre, Golf Course Road, Sector 54, | 122002 | Gurgaon | Haryana |  |  | vba1981mca@gmail.com | www.ymeng.co.kr
24478 | National Highways Authority Of India | 155597 | Jhanki Village-Sargi Village (NH-130CD) Six Lane Highway Project (Package CG-1) (Section of Raipur-Visakhapatnam Economic Corridor) | 1809 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
24479 | National Highways Authority Of India | 155597 | Jhanki Village-Sargi Village (NH-130CD) Six Lane Highway Project (Package CG-1) (Section of Raipur-Visakhapatnam Economic Corridor) | 1809 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
24480 | National Highways Authority Of India | 155597 | Jhanki Village-Sargi Village (NH-130CD) Six Lane Highway Project (Package CG-1) (Section of Raipur-Visakhapatnam Economic Corridor) | 1809 | Contractor | Shalimar Corp Ltd. | 457175 | India | Corporate Office:11th Floor, Titanium, Shalimar Corporate Park, Vibhuti Khand, Gomti Nagar | 226010 | Lucknow | Uttar Pradesh | 91-522-4030444 | 91-522-4030413 | shalimar@shalimar.org | www.shalimarcorp.com
24481 | National Highways Authority Of India | 155597 | Jhansi Bypass (NH-25) Highway Project | 551 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
24482 | National Highways Authority Of India | 155597 | Jhansi-Lakhnadaon (NH 26) Road Project | 426 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24483 | National Highways Authority Of India | 155597 | Jhansi-Shivpuri (NH-25) Highway Project | 549 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
24484 | National Highways Authority Of India | 155597 | Jharpokharia-Baripada-Baleshwar (NH-5) Four Laning Highway Project | 964 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24485 | National Highways Authority Of India | 155597 | Jharpokharia-Baripada-Baleshwar (NH-5) Four Laning Highway Project | 964 | Contractor | Iron Triangle Ltd. | 384589 | India | Corporate Office:209, Akik Tower, Opp Rajpath Club, S G Highway, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-26840710 | 91-79-40040710 |  | www.irontriangle.in
24486 | National Highways Authority Of India | 155597 | Jind-Gohana (NH-352A) Four Lane Highway Project (Package 1) | 1481 | Contractor | Brij Gopal Construction Co. Pvt. Ltd. | 408202 | India | Registered Office:A-7/2, Shivaji Apptt., Sector-14, Rohini, | 110085 | Delhi | NCT of Delhi | 91-11-25818656 |  | raman010@yahoo.com
24487 | National Highways Authority Of India | 155597 | Jind-Karnal (NH-709A) Two Lane Highway Project | 1847 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24488 | National Highways Authority Of India | 155597 | Jind-Mundhal-Bhiwani (NH-709A) Two Lane Highway Project | 1480 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24489 | National Highways Authority Of India | 155597 | Jittandahalli-Dharmapuri section (NH-844) Four Lane Highway Project (Package 3 of Hosur-Dharmapuri) (Bharatmala) | 1690 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24490 | National Highways Authority Of India | 155597 | Jn with NH20 in Bongabar Village to Jn with NH320 in Lepo Village Six Lane Greenfield Access Control Expressway Project (Package-12 of Varanasi-Kolkata Expressway) | 2121 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24491 | National Highways Authority Of India | 155597 | Jn with NH20 in Bongabar Village to Jn with NH320 in Lepo Village Six Lane Greenfield Access Control Expressway Project (Package-12 of Varanasi-Kolkata Expressway) | 2121 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24492 | National Highways Authority Of India | 155597 | JNPT Logistics Park Project | 1387 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24493 | National Highways Authority Of India | 155597 | Jodhpur Ring Road Project (Phase 1) | 2042 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
24494 | National Highways Authority Of India | 155597 | Jodhpur Ring Road Project (Phase 1) | 2042 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24495 | National Highways Authority Of India | 155597 | Jodhpur Romana (Bathinda)-Mandi Dabwali Highway (Punjab/Haryana border) (NH-54) Six Lane Highway Project | 1839 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24496 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Bagundi-Barmer Pkg-II) | 1000 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | Canada | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24497 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Bagundi-Barmer Pkg-II) | 1000 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24498 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Jodhpur-Pachpadra Pkg-I) | 979 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24499 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Jodhpur-Pachpadra Pkg-I) | 979 | Consultant | Shri Kushalsuri Engg. Services Pvt. Ltd. | 536774 | India |  | NA
24500 | National Highways Authority Of India | 155597 | Jodhpur-Barmer (NH-112) Two/Four Lane Highway Project (Jodhpur-Pachpadra Pkg-I) | 979 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24501 | National Highways Authority Of India | 155597 | Jodhpur-Pokaran (NH-114) Two Lane Highway Project | 985 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
24502 | National Highways Authority Of India | 155597 | Jodhpur-Pokaran (NH-114) Two Lane Highway Project | 985 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24503 | National Highways Authority Of India | 155597 | Jodmi village to Bani village of Mandsaur Eight Lane Carriageway Project (Package 18 of Delhi-Mumbai Expressway) | 1571 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24504 | National Highways Authority Of India | 155597 | Jodmi village to Bani village of Mandsaur Eight Lane Carriageway Project (Package 18 of Delhi-Mumbai Expressway) | 1571 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24505 | National Highways Authority Of India | 155597 | Jonnada Junction (NH-216A) Four Lane Flyover Project | 2063 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
24506 | National Highways Authority Of India | 155597 | Jowai-Meghalaya/Assam Border (Ratacherra) (NH-6) Two Lane Highway Project | 950 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24507 | National Highways Authority Of India | 155597 | Jowai-Meghalaya/Assam Border (Ratacherra) (NH-6) Two Lane Highway Project | 950 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24508 | National Highways Authority Of India | 155597 | Jujuwa to Gandeva Package-8 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1628 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24509 | National Highways Authority Of India | 155597 | Jujuwa to Gandeva Package-8 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1628 | Contractor | Roadway Solutions India Infra Ltd. | 606355 | India | Registered Office:S N-29, H N-20, Nr. Kubex Soc., Nr. Shera School, Kondhwa (KD), | 411048 | Pune | Maharashtra |  |  | info@rsipl.net | www.rsipl.net
24510 | National Highways Authority Of India | 155597 | Junction at SH44 to Junction with Keshopura Road Eight Lane Carriageway Project (Package 5 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1542 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24511 | National Highways Authority Of India | 155597 | Junction with Amritsar-Bathinda Greenfield Road (NH-754A) near Rampura Phul to Junction with Moga-Barnala Road near Tallewal Six Lane Highway Project (Package 1 of Ludhiana-Bhatinda Expressway) | 1997 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
24512 | National Highways Authority Of India | 155597 | Junction with Jind-Safidon Road (SH-14) near Kheri village to Junction with NH-352 (Jind-Gohana section) near Julana Six Lane Access Controlled Highway Project (Package 4 of Ismailabad-Narnaul) | 1623 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24513 | National Highways Authority Of India | 155597 | Junction with Jind-Safidon Road (SH-14) near Kheri village to Junction with NH-352 (Jind-Gohana section) near Julana Six Lane Access Controlled Highway Project (Package 4 of Ismailabad-Narnaul) | 1623 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24514 | National Highways Authority Of India | 155597 | Junction with Jind-Safidon Road (SH-14) near Kheri village to Junction with NH-352 (Jind-Gohana section) near Julana Six Lane Access Controlled Highway Project (Package 4 of Ismailabad-Narnaul) | 1623 | Contractor | Shiv Buildindia Pvt. Ltd. | 457770 | India | Registered Office:401/2, 4th Floor, Siddhraj Zavod, Sargasan, | 382421 | Gandhinagar | Gujarat | 91-79-29750425 |  | contact@shivbuildindia.com | www.shivbuildindia.com
24515 | National Highways Authority Of India | 155597 | Junction with Jind-Safidon Road (SH-14) near Kheri village to Junction with NH-352 (Jind-Gohana section) near Julana Six Lane Access Controlled Highway Project (Package 4 of Ismailabad-Narnaul) | 1623 | Contractor | Jiangxi Construction Engg. (group) Corpn. Ltd. | 665334 | China |  | NA
24516 | National Highways Authority Of India | 155597 | Junction with Kaithal-Safidon Road (SH-11) near Rajound to Junction with Jind-Safidon Road near Kheri village Four/Six Lane Access Control Highway Project (Pkg 3 Ismailabad-Narnaul) (Bharatmala) | 1622 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24517 | National Highways Authority Of India | 155597 | Junction with Kaithal-Safidon Road (SH-11) near Rajound to Junction with Jind-Safidon Road near Kheri village Four/Six Lane Access Control Highway Project (Pkg 3 Ismailabad-Narnaul) (Bharatmala) | 1622 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24518 | National Highways Authority Of India | 155597 | Junction with Kaithal-Safidon Road (SH-11) near Rajound to Junction with Jind-Safidon Road near Kheri village Four/Six Lane Access Control Highway Project (Pkg 3 Ismailabad-Narnaul) (Bharatmala) | 1622 | Contractor | Galfar Engineering & Contracting (india) Pvt. Ltd. | 453269 | India | Registered Office:Unit No.6 & 7, 15th Floor, Tower-B, The Digital Greens, Sector-61, Golf Course Extension Road, | 122011 | Gurgaon | Haryana | 91-124-4971330 |  | saurabh.misra@galfar-india.com
24519 | National Highways Authority Of India | 155597 | Junction with Karnal-Pehowa Road (SH-9) near Dhand village to Junction with Kaithal-Safidon (SH-11) Road near Rajound Four/Six Lane Access Control Highway Project (Package 2 Ismailabad-Narnaul) | 1617 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24520 | National Highways Authority Of India | 155597 | Junction with Karnal-Pehowa Road (SH-9) near Dhand village to Junction with Kaithal-Safidon (SH-11) Road near Rajound Four/Six Lane Access Control Highway Project (Package 2 Ismailabad-Narnaul) | 1617 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24521 | National Highways Authority Of India | 155597 | Junction with Karnal-Pehowa Road (SH-9) near Dhand village to Junction with Kaithal-Safidon (SH-11) Road near Rajound Four/Six Lane Access Control Highway Project (Package 2 Ismailabad-Narnaul) | 1617 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24522 | National Highways Authority Of India | 155597 | Junction with Keshopura Road to Junction with NH-11 Road Eight Lane Carriageway Project (Package 6 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1543 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24523 | National Highways Authority Of India | 155597 | Junction with Moga-Barnala Road near Tallewal to Delhi-Katra Expressway (NE-5) at Ballowal (Ludhiana) Six Lane Highway Project (Package 2 of Ludhiana-Bhatinda Expressway) | 1998 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24524 | National Highways Authority Of India | 155597 | Junction with Moga-Barnala Road near Tallewal to Delhi-Katra Expressway (NE-5) at Ballowal (Ludhiana) Six Lane Highway Project (Package 2 of Ludhiana-Bhatinda Expressway) | 1998 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24525 | National Highways Authority Of India | 155597 | Junction with Moga-Barnala Road near Tallewal to Delhi-Katra Expressway (NE-5) at Ballowal (Ludhiana) Six Lane Highway Project (Package 2 of Ludhiana-Bhatinda Expressway) | 1998 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24526 | National Highways Authority Of India | 155597 | Junction with NH-11 to Start of RoB near junction with NH-11A Eight Lane Carriageway Project (Package 7 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1560 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24527 | National Highways Authority Of India | 155597 | Junction with NH-12 near village Ummedpura to Major bridge over Takli river near Nayagaon Jageer village Eight Lane Carriageway Project (Package 15) (Delhi-Mumbai Expressway) | 1568 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24528 | National Highways Authority Of India | 155597 | Junction with NH-334B (Charkhi Dadri-Jhajjar section) to Junction with Rewari-Kanina Road (SH-24) Four/Six Lane Access Controlled Highway Project (Package 7 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1618 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24529 | National Highways Authority Of India | 155597 | Junction with NH-334B (Charkhi Dadri-Jhajjar section) to Junction with Rewari-Kanina Road (SH-24) Four/Six Lane Access Controlled Highway Project (Package 7 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1618 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24530 | National Highways Authority Of India | 155597 | Junction with NH-334B (Charkhi Dadri-Jhajjar section) to Junction with Rewari-Kanina Road (SH-24) Four/Six Lane Access Controlled Highway Project (Package 7 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1618 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
24531 | National Highways Authority Of India | 155597 | Junction with NH-334B (Charkhi Dadri-Jhajjar section) to Junction with Rewari-Kanina Road (SH-24) Four/Six Lane Access Controlled Highway Project (Package 7 of Ismailabad-Narnaul NH-152D) (Bharatmala) | 1618 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24532 | National Highways Authority Of India | 155597 | Junction with NH-352 (Jind-Gohana) near Julana to Junction with NH-9 (Rohtak-Jind) near Kharkara Four/Six Lane Access Controlled Highway Project (Package 5 of Ismailabad-Narnaul) (Bharatmala) | 1620 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24533 | National Highways Authority Of India | 155597 | Junction with NH-352 (Jind-Gohana) near Julana to Junction with NH-9 (Rohtak-Jind) near Kharkara Four/Six Lane Access Controlled Highway Project (Package 5 of Ismailabad-Narnaul) (Bharatmala) | 1620 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24534 | National Highways Authority Of India | 155597 | Junction with NH-352 (Jind-Gohana) near Julana to Junction with NH-9 (Rohtak-Jind) near Kharkara Four/Six Lane Access Controlled Highway Project (Package 5 of Ismailabad-Narnaul) (Bharatmala) | 1620 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24535 | National Highways Authority Of India | 155597 | Junction with NH-65 near Patas-Vasunde Phata-Baramati (NH965G) & Baramati Bypass Four Lane Highway Project (Package-I of Sant Tukaram Maharaj Palkhi Marg) | 1896 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24536 | National Highways Authority Of India | 155597 | Junction with NH-65 near Patas-Vasunde Phata-Baramati (NH965G) & Baramati Bypass Four Lane Highway Project (Package-I of Sant Tukaram Maharaj Palkhi Marg) | 1896 | Contractor | Kalyan Toll Infrastructure Ltd. | 386962 | India | Registered Office:Vidhya Deep, 15/3 Manorama Ganj, | 452001 | Indore | Madhya Pradesh | 91-731-2496931 | 91-731-4096457 | accounts@kalyangroup.in | www.kalyangroup.in
24537 | National Highways Authority Of India | 155597 | Junction with NH-65 near Patas-Vasunde Phata-Baramati (NH965G) & Baramati Bypass Four Lane Highway Project (Package-I of Sant Tukaram Maharaj Palkhi Marg) | 1896 | Contractor | Shelke Construction | 479882 | India |  | NA
24538 | National Highways Authority Of India | 155597 | Junction with NH-76 to Junction with NH-12 (near Ummedpura village) Eight Lane Carriageway Project (Package 14 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1566 | Contractor | Crescent E P C Projects & Technical Services Ltd. | 413241 | India | Registered Office:IDA Phase-II, Patancheru, | 502319 | Hyderabad | Telangana |  |  | mabubasha.d@gvk.com
24539 | National Highways Authority Of India | 155597 | Junction with NH-76 to Junction with NH-12 (near Ummedpura village) Eight Lane Carriageway Project (Package 14 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1566 | Contractor | Dhaya Maju Infrastructure (asia) Sdn Bhd | 639703 | Malaysia |  | NA
24540 | National Highways Authority Of India | 155597 | Junction with NH-9 (Rohtak-Jind section) near Kharkara to Junction with NH-334B (Charkhi Dadri Jhajjar section) Four/Six Lane Access Controlled Highway Project (Pkg 6 of Ismailabad-Narnaul NH-152D) | 1621 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24541 | National Highways Authority Of India | 155597 | Junction with NH-9 (Rohtak-Jind section) near Kharkara to Junction with NH-334B (Charkhi Dadri Jhajjar section) Four/Six Lane Access Controlled Highway Project (Pkg 6 of Ismailabad-Narnaul NH-152D) | 1621 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
24542 | National Highways Authority Of India | 155597 | Junction with NH-9 (Rohtak-Jind section) near Kharkara to Junction with NH-334B (Charkhi Dadri Jhajjar section) Four/Six Lane Access Controlled Highway Project (Pkg 6 of Ismailabad-Narnaul NH-152D) | 1621 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24543 | National Highways Authority Of India | 155597 | Kadambattukonam-Kazhakuttom (NH-66) Four/Six Highway Project | 2005 | Contractor | R D S Project Ltd. | 185799 | India | Registered Office:427, Somdutt Chambers-II, 9, Bhikaji Cama Place, | 110066 | New Delhi | NCT of Delhi | 91-11-26170242 | 91-11-26168092 | agra@rdsproject.com | www.rdsproject.com
24544 | National Highways Authority Of India | 155597 | Kadapa-Chinna Orampadu (NH-716) Four Lane Highway Project | 2075 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
24545 | National Highways Authority Of India | 155597 | Kadloor Yellareddy to Gundla Pochampalli Highway Project | 504 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24546 | National Highways Authority Of India | 155597 | Kadloor Yellareddy to Gundla Pochampalli Highway Project | 504 | Contractor | G M R Airports Infrastructure Ltd. | 76718 | India | Corporate Office:Skip House, 25/1, Museum Road, | 560025 | Bengaluru | Karnataka | 91-80-2279949 | 91-80-2998118 |  | www.gmrgroup.in
24547 | National Highways Authority Of India | 155597 | Kadloor Yellareddy to Gundla Pochampalli Highway Project | 504 | Contractor | G M R Energy Ltd. | 247422 | India | Registered Office:701, 7th Floor, Naman Centre, Plot No. C-31, Bandra Kurla Complex, Bandra East, | 400051 | Mumbai | Maharashtra | 91-11-49882200 | 91-11-49882227 | energy-secretarial@gmrgroup.in | www.gmrgroup.in
24548 | National Highways Authority Of India | 155597 | Kagal-Satara (NH-4 & 48) Six-Laning Highway Project | 556 | Consultant | Ernst & Young Global Ltd. | 69006 | India | Registered Office: | NA | [5 empty] | www.ey.com
24549 | National Highways Authority Of India | 155597 | Kagal-Satara (NH-4 & 48) Six-Laning Highway Project | 556 | Consultant | Louis Berger Intl. Inc. | 287149 | India | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24550 | National Highways Authority Of India | 155597 | Kagal-Satara (NH-4 & 48) Six-Laning Highway Project | 556 | Contractor | Adani Enterprises Ltd. | 5747 | India | Registered Office:Adani Corporate House, Shantigram, Near Vaishno Devi Circle,S. G. Highway, Khodiyar, | 382421 | Ahmedabad | Gujarat | 91-79-26565555 |  | customercare.irm@adani.com | www.adanienterprises.com
24551 | National Highways Authority Of India | 155597 | Kagal-Satara (NH-4 & 48) Six-Laning Highway Project | 556 | Contractor | Roadway Solutions India Infra Ltd. | 606355 | India | Registered Office:S N-29, H N-20, Nr. Kubex Soc., Nr. Shera School, Kondhwa (KD), | 411048 | Pune | Maharashtra |  |  | info@rsipl.net | www.rsipl.net
24552 | National Highways Authority Of India | 155597 | Kagavadar-Una (NH-8E) (Package-IV Bhavnagar-Veraval Section) Four Lane Highway Project | 1164 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
24553 | National Highways Authority Of India | 155597 | Kagavadar-Una (NH-8E) (Package-IV Bhavnagar-Veraval Section) Four Lane Highway Project | 1164 | Contractor | Agroh Infrastructure Developers Pvt. Ltd. | 389210 | India | Registered Office:Bunglow No. 74, Infront of Govt. Girls School, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-271225 |  | aidplindore@gmail.com | www.agrohinfra.com
24554 | National Highways Authority Of India | 155597 | Kaikaram Junction (NH-216A) Flyover Project | 2060 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
24555 | National Highways Authority Of India | 155597 | Kajali-Manor (NH-8) Highway Project | 77 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24556 | National Highways Authority Of India | 155597 | Kajali-Manor (NH-8) Highway Project | 77 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24557 | National Highways Authority Of India | 155597 | Kajali-Manor (NH-8) Highway Project | 77 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24558 | National Highways Authority Of India | 155597 | Kakinada Anchorage Port-Uppada Beach (NH-16) Four Laning Road Project (Bharatmala) | 1535 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
24559 | National Highways Authority Of India | 155597 | Kakinada port-Rajanagaram (NH-16) Four Lane Road Connectivity Project | 1614 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24560 | National Highways Authority Of India | 155597 | Kalamassery-Vallarpadam (NH-47C) Four laning Highway Project | 454 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24561 | National Highways Authority Of India | 155597 | Kalamassery-Vallarpadam (NH-47C) Four laning Highway Project | 454 | Contractor | Soma Enterprise Ltd. | 230660 | India | Corporate Office:2 Avenue, 4, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-66538899 | 91-40-23321286 | info@soma.co.in | www.soma.co.in
24562 | National Highways Authority Of India | 155597 | Kalaparru-Chinna Avutapalli Six Lane Highway (NH-16) including Hanuman Junction bypass Project | 1956 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
24563 | National Highways Authority Of India | 155597 | Kalika Mata Mandir to Khote Nagar (Jalgaon City) (NH-53) Four Lane Road Project | 1700 | Contractor | Jandu Construction Co. | 585722 | India |  | NA
24564 | National Highways Authority Of India | 155597 | Kalkallu village-Gundla Pochampali (NS-8) Four Lane Highway Project | 226 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
24565 | National Highways Authority Of India | 155597 | Kalkallu village-Gundla Pochampali (NS-8) Four Lane Highway Project | 226 | Contractor | A L Sudershan Construction Co. Ltd. | 1740 | India | Registered Office:7-3-720, 3rd Floor, R P Road, | 500003 | Secunderabad | Telangana | 91-40-27802984 |  | alscol2498@gmail.com
24566 | National Highways Authority Of India | 155597 | Kalkallu-Gundla Pochanpally (NH-44) Six Lane Highway Project (Nagpur-Hyderabad section) | 1959 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
24567 | National Highways Authority Of India | 155597 | Kamakhyanagar Bypass-Duburi (NH-53) Four Lane Road Project | 1404 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24568 | National Highways Authority Of India | 155597 | Kamalapuram-Oddanchatram (NH-209, New NH-83) Four Lane Highway Project (Bharatmala) | 1848 | Contractor | D R N Infrastructure Pvt. Ltd. | 609586 | India | Registered Office:#110, Nayak House Dollars Colony, Gokul Road, Hubli, | 580030 | Dharwad | Karnataka
24569 | National Highways Authority Of India | 155597 | Kamalpur village (Jharkhand/WB Border)-Near Uluberia Four/Six Lane Greenfield Access Control Expressway (Part of Varanasi-Kolkata Expressway) Project | 1984 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24570 | National Highways Authority Of India | 155597 | Kamaspur-Haryana/Delhi Border (NS/2) Six Lane Highway Project | 186 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24571 | National Highways Authority Of India | 155597 | Kamaspur-Haryana/Delhi Border (NS/2) Six Lane Highway Project | 186 | Turnkey contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24572 | National Highways Authority Of India | 155597 | Kamliya Village-Kandarwasa Village Eight Lane Carriageway Project (Package 21 of Delhi-Mumbai Expressway) | 1602 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24573 | National Highways Authority Of India | 155597 | Kamliya Village-Kandarwasa Village Eight Lane Carriageway Project (Package 21 of Delhi-Mumbai Expressway) | 1602 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24574 | National Highways Authority Of India | 155597 | Kamrej-Chaltan (NH-8) Six Laning Highway Project | 1092 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
24575 | National Highways Authority Of India | 155597 | Kamrej-Chaltan (NH-8) Six Laning Highway Project | 1092 | Contractor | Unique Constructions | 445378 | India | Registered Office:Gali No 4, Near Pratap Nagar, P V T Bus Stand, Kamla Nehru Nagar, 1st Pulia, | 342008 | Jodhpur | Rajasthan |  |  |  | www.uniqueconstructions.com.au
24576 | National Highways Authority Of India | 155597 | Kamrej-Chaltan (NH-8) Six Laning Highway Project | 1092 | Contractor | Verkhovna Rada Of Ukraine | 540272 | Ukraine |  | NA
24577 | National Highways Authority Of India | 155597 | Kandarwasa village to Bawadi village (Shivgarh) Eight Lane Carriageway Project (Package 22 of Delhi-Mumbai Expressway) | 1601 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24578 | National Highways Authority Of India | 155597 | Kandarwasa village to Bawadi village (Shivgarh) Eight Lane Carriageway Project (Package 22 of Delhi-Mumbai Expressway) | 1601 | Contractor | L & T Construction | 560291 | India | Registered Office:Mount Poonamallee Road, Manapakkam, P B No.979, | 600089 | Chennai | Tamil Nadu | 91-44-22526000 | 91-44-22493317 | info@lntecc.com | www.lntecc.com
24579 | National Highways Authority Of India | 155597 | Kandili-Aluru (NH-130 CD) Six Lane Highway Project (Package OD-8) (Part of Raipur-Visakhapatnam Economic Corridor) | 2014 | Contractor | Max Infra (i) Pvt. Ltd. | 255661 | India | Registered Office:4th Floor, Plot No. 319 & 320, Ayyappa Society, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-66248240 | 91-40-66248242 | cfo@maxinfra.in | www.maxinfra.in
24580 | National Highways Authority Of India | 155597 | Kandili-Aluru (NH-130 CD) Six Lane Highway Project (Package OD-8) (Part of Raipur-Visakhapatnam Economic Corridor) | 2014 | Contractor | Bekem Infra Projects Pvt. Ltd. | 389845 | India | Corporate Office:Plot No. 289, Avenue 1, Road No.6, Kakatiya Hills, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-48587234 |  | info@bekemprojects.com | www.bekem.com
24581 | National Highways Authority Of India | 155597 | Kandla Logistic Park Project | 1348 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24582 | National Highways Authority Of India | 155597 | Kanniyakumari-Panagudi Highway Project | 370 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24583 | National Highways Authority Of India | 155597 | Kanniyakumari-Panagudi Highway Project | 370 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24584 | National Highways Authority Of India | 155597 | Kannur-Vengalam (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 538 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24585 | National Highways Authority Of India | 155597 | Kanpur Bypass Project | 298 | Consultant | A F Ferguson & Co. | 916 | India | Registered Office:Allahabad Bank Building, Bombay Samachar Marg, | 400023 | Mumbai | Maharashtra |  |  |  | www.afferguson.com
24586 | National Highways Authority Of India | 155597 | Kanpur Bypass Project | 298 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
24587 | National Highways Authority Of India | 155597 | Kanpur Bypass Project | 298 | Consultant | L & T Infrastructure Engg. Ltd. | 125145 | India | Corporate Office:339/340, Anna Salai, Nandanam, | 600035 | Chennai | Tamil Nadu | 91-44-24331181 | 91-44-24331183 | lntielchm@lntiel.com | www.lntiel.com
24588 | National Highways Authority Of India | 155597 | Kanpur Six Lane Outer Ring Road Project | 840 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24589 | National Highways Authority Of India | 155597 | Kanpur Six Lane Outer Ring Road Project | 840 | Contractor | Raj Corporation Ltd. | 482680 | India | Registered Office:Gali No. 3 Punjabi Colony, | 205001 | Mainpuri | Uttar Pradesh |  |  | rcllko @gmail.com
24590 | National Highways Authority Of India | 155597 | Kanpur-Fatehpur (GTRIP/II-B) Highway Project | 695 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24591 | National Highways Authority Of India | 155597 | Kanpur-Fatehpur (GTRIP/II-B) Highway Project | 695 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24592 | National Highways Authority Of India | 155597 | Kanpur-Fatehpur (GTRIP/II-B) Highway Project | 695 | Contractor | Som Datt Builders Pvt. Ltd. | 457240 | India | Registered Office:Gajraj Chambers, 2B, 2nd Floor, 86 B/2 Topsia Road (South), | 700046 | Kolkata | West Bengal |  |  | sdbhoaccounts@rediffmail.com
24593 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Consultant | Global Infrasolutions Ltd. | 500285 | India | Registered Office:C-57, Basant Vihar Delhi Road, | 247001 | Saharanpur | Uttar Pradesh |  |  | pankaj4361@gmail.com | www.globalinfrasolutions.org
24594 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24595 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Consultant | Yongma Engineering Co. Ltd. | 585553 | India | Registered Office:Unit 301, 302, Time Centre, Golf Course Road, Sector 54, | 122002 | Gurgaon | Haryana |  |  | vba1981mca@gmail.com | www.ymeng.co.kr
24596 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
24597 | National Highways Authority Of India | 155597 | Kantakapalle-Sabbavaram (NH-130CD) Six Lane Road Project (Package-4 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 1808 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
24598 | National Highways Authority Of India | 155597 | Kapasia Chowk-Begusarai Jail Area (NH-31) Four Lane Elevated Road Project | 1999 | Contractor | Transrail Lighting Ltd. | 387140 | India | Registered Office:501 A,B,C,E Fortune 2000, Block G Bandra Kurla Complex, Bandra East, | 400051 | Mumbai | Maharashtra |  | 91-7104-265765 | contact@transrailltd.com
24599 | National Highways Authority Of India | 155597 | Kappirikkad-Thalikulam (NH-66) Six Lane Highway Project | 1877 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
24600 | National Highways Authority Of India | 155597 | Kappirikkad-Thalikulam (NH-66) Six Lane Highway Project | 1877 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
24601 | National Highways Authority Of India | 155597 | Karaikudi-Ramanathapuram (NH-210) Two-Laning Road Project | 557 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24602 | National Highways Authority Of India | 155597 | Karaikudi-Ramanathapuram (NH-210) Two-Laning Road Project | 557 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24603 | National Highways Authority Of India | 155597 | Karaipettai-Walajapet (NH-48) Six Lane Highway Project (Package-2) | 1505 | Contractor | S P K & Co. | 515978 | India | Registered Office:2/67, R C Middil Street, Killamudimannarkottai, | 623603 | Madurai | Tamil Nadu
24604 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Road-Nangloi Najafgarh Six Lane Road (NH-344M) Project ( Package-2 of Delhi 3rd Ring Road Project or UER-2) | 1798 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
24605 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Road-Nangloi Najafgarh Six Lane Road (NH-344M) Project ( Package-2 of Delhi 3rd Ring Road Project or UER-2) | 1798 | Consultant | Aecom India Pvt. Ltd. | 462940 | India | Registered Office:9th Floor, Infinity Tower C, DLF Cyber City, DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-2818000 | 91-124-2816008 | pradeep.khurana@aecom.com | www.aecom.com
24606 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Road-Nangloi Najafgarh Six Lane Road (NH-344M) Project ( Package-2 of Delhi 3rd Ring Road Project or UER-2) | 1798 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24607 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Road-Nangloi Najafgarh Six Lane Road (NH-344M) Project ( Package-2 of Delhi 3rd Ring Road Project or UER-2) | 1798 | Contractor | Krishna Construction | 547990 | India | Registered Office:Kamla Nehru Nagar, Ajmer Road, | 302024 | Jaipur | Rajasthan
24608 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Six Lane (NH-344M) Road Project (Package 1 of Delhi 3rd Ring Road or UER-2) | 1797 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
24609 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Six Lane (NH-344M) Road Project (Package 1 of Delhi 3rd Ring Road or UER-2) | 1797 | Consultant | Aecom India Pvt. Ltd. | 462940 | India | Registered Office:9th Floor, Infinity Tower C, DLF Cyber City, DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-2818000 | 91-124-2816008 | pradeep.khurana@aecom.com | www.aecom.com
24610 | National Highways Authority Of India | 155597 | Karala-Kanjhawala Six Lane (NH-344M) Road Project (Package 1 of Delhi 3rd Ring Road or UER-2) | 1797 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24611 | National Highways Authority Of India | 155597 | Karanja Flyover (on NH-53) Project | 1645 | Contractor | Jandu Construction Co. | 585722 | India |  | NA
24612 | National Highways Authority Of India | 155597 | Karanodai Bridge Project | 857 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24613 | National Highways Authority Of India | 155597 | Karauli-Dholpur (NH-11B) Two Laning Highway Project | 1034 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24614 | National Highways Authority Of India | 155597 | Karimnagar-Telangana/Maharashtra Border Four Lane Highway Project | 1950 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24615 | National Highways Authority Of India | 155597 | Karnal Eastern Bypass (Part of Karnal Ring Road starting from NH44 near Village Shamgarh and terminating at Karnal-Munak Road) Project | 1864 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24616 | National Highways Authority Of India | 155597 | Karnataka/Kerala Border (Talapady)-Kannur (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 1515 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24617 | National Highways Authority Of India | 155597 | Karur Bypass including additional bridge across river Amrawati Project | 38 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24618 | National Highways Authority Of India | 155597 | Karur Bypass including additional bridge across river Amrawati Project | 38 | Contractor | Techni Bharathi Pvt. Ltd. | 248600 | India | Head Office:'Florance', No. 34/136-A, Bye-pass Road, Edappally, | 682024 | Kochi | Kerala | 91-484-2344906 | 91-484-2344908 | tsind@tsind.com
24619 | National Highways Authority Of India | 155597 | Karur ROB Project | 182 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24620 | National Highways Authority Of India | 155597 | Karur ROB Project | 182 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24621 | National Highways Authority Of India | 155597 | Karur-Kangeyam-Coimbatore (NH-67) Highway Project | 443 | Contractor | S R C Projects Pvt. Ltd. | 364856 | India | Registered Office:No. 4-B, Lakshmipuram, | 636007 | Salem | Tamil Nadu
24622 | National Highways Authority Of India | 155597 | Karur-Madurai (TN-4) or Karur-Dindigul Highway Project | 428 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24623 | National Highways Authority Of India | 155597 | Karur-Madurai (TN-4) or Karur-Dindigul Highway Project | 428 | Contractor | S R E I Infrastructure Finance Ltd. | 204843 | India | Registered Office:'Vishwakarma', 86-C, Topsia Road (South), | 700046 | Kolkata | West Bengal | 91-33-61607734 | 91-33-22857542 | corporate@srei.com | www.srei.com
24624 | National Highways Authority Of India | 155597 | Karvad-Jujuwa Package-9 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1624 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24625 | National Highways Authority Of India | 155597 | Karvad-Jujuwa Package-9 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1624 | Contractor | Roadway Solutions India Infra Ltd. | 606355 | India | Registered Office:S N-29, H N-20, Nr. Kubex Soc., Nr. Shera School, Kondhwa (KD), | 411048 | Pune | Maharashtra |  |  | info@rsipl.net | www.rsipl.net
24626 | National Highways Authority Of India | 155597 | Kasarkad Side of Honnavar Port to NH-66 Four Lane Road Connectivity Project | 1731 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24627 | National Highways Authority Of India | 155597 | Kasarkad Side of Honnavar Port to NH-66 Four Lane Road Connectivity Project | 1731 | Contractor | Viva Infraventure Pvt. Ltd. | 537014 | India |  | NA
24628 | National Highways Authority Of India | 155597 | Kashi Four Lane Signature Rail cum Road Bridge across River Ganga Project (on NH-19 Old Gt Road) | 2035 | Consultant | Technogem Consultants Pvt. Ltd. | 248830 | India | Registered Office:No. 101-A/B, Devmilan Building, Opposite Johnson Tiles, L B S Marg, | 400604 | Thane | Maharashtra
24629 | National Highways Authority Of India | 155597 | Kashi Four Lane Signature Rail cum Road Bridge across River Ganga Project (on NH-19 Old Gt Road) | 2035 | Consultant | Spectrum Techno-consultants Pvt. Ltd. | 661098 | India |  | NA
24630 | National Highways Authority Of India | 155597 | Kasia-Gorakhpur (LMNHP-7) Highway Project | 502 | Consultant | F P India Project Mgmt. Consultancy Services Pvt. Ltd. | 75309 | India | Registered Office:No. 3/5, Balgovindwadi, New Prabhadevi Road, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-22001530 | 91-22-22017915
24631 | National Highways Authority Of India | 155597 | Kasia-Gorakhpur (LMNHP-7) Highway Project | 502 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24632 | National Highways Authority Of India | 155597 | Katni (NH-30) Four Lane Bypass Project | 1778 | Contractor | P R L Projects & Infrastructure Ltd. | 167393 | India | Registered Office:34/1, Vikas Apartment, Punjabi Bagh East, | 110026 | New Delhi | NCT of Delhi | 91-11-45540701 |  | prlprojects_infraltd@yahoo.co.in
24633 | National Highways Authority Of India | 155597 | Katni (NH-30) Four Lane Bypass Project | 1778 | Contractor | Shreeji Infrastructure India Pvt. Ltd. | 224014 | India | Registered Office:513, 5th Floor, Shubham Corporate Ring Road No. 1, Near Railway Crossing, Telibandha, | 492001 | Raipur | Chhattisgarh | 91-771-4022430 |  | shreejiinfrajbp@gmail.com | www.siipl.net
24634 | National Highways Authority Of India | 155597 | Katraj Junction Multi -Level Flyover Project | 1785 | Co-promoter | Pune Municipal Corpn. | 183660 | India | Registered Office:P M C Main Building, Near Mangla Theatre, Shivajinagar, | 411005 | Pune | Maharashtra | 91-20-25501000 | 91-20-25501104 | info@punecorporation.org | www.pmc.gov.in
24635 | National Highways Authority Of India | 155597 | Kavali-Nellore (AP-11) Four/Six Lane Highway Project | 107 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24636 | National Highways Authority Of India | 155597 | Kavali-Nellore (AP-11) Four/Six Lane Highway Project | 107 | Consultant | K M International Ab | 476631 | Sweden |  | NA
24637 | National Highways Authority Of India | 155597 | Kavali-Nellore (AP-11) Four/Six Lane Highway Project | 107 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24638 | National Highways Authority Of India | 155597 | Kavali-Nellore (AP-11) Four/Six Lane Highway Project | 107 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24639 | National Highways Authority Of India | 155597 | Kavulakuntla-Narayanmpet Six Lane Access Controlled Highway (NH-544G) Project (Package-9 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2114 | Contractor | Max Infra (i) Pvt. Ltd. | 255661 | India | Registered Office:4th Floor, Plot No. 319 & 320, Ayyappa Society, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-66248240 | 91-40-66248242 | cfo@maxinfra.in | www.maxinfra.in
24640 | National Highways Authority Of India | 155597 | Kavulakuntla-Narayanmpet Six Lane Access Controlled Highway (NH-544G) Project (Package-9 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2114 | Contractor | Bekem Infra Projects Pvt. Ltd. | 389845 | India | Corporate Office:Plot No. 289, Avenue 1, Road No.6, Kakatiya Hills, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-48587234 |  | info@bekemprojects.com | www.bekem.com
24641 | National Highways Authority Of India | 155597 | Kavungal-Pallikuth Four Lane Highway (NH-966) Project | 1915 | Consultant | T P F Engineering Pvt. Ltd. | 578734 | India | Registered Office:Unit No 10, Banking Complex, No II, Plot No 9 & 10m Sector 19 A, Vashi, | 400705 | Mumbai | Maharashtra | 91-22-41273303 | 91-22-41273306 | tenders@tpfepl.com | www.tpfepl.com
24642 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24643 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Consultant | Almondz Global Infra-consultant Ltd. | 492419 | India | Corporate Office:F-33/3, Okhla Industrial Area, Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-43500700 | 91-11-4350073 | delhi@almondz.com | www.almondzglobalinfra.com
24644 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24645 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Contractor | Cherian Varkey Construction Co. Pvt. Ltd. | 287023 | India | Registered Office:5th Floor, Alpha Plaza, K P Vallon Road, Kadavanthra, | 682020 | Kochi | Kerala | 91-484-4120666 | 91-484-2312461 | mail@cherianvarkey.com | www.cherianvarkey.com
24646 | National Highways Authority Of India | 155597 | Kazhakuttam-Mukkola (NH-47 or new NH-66) Four Lane Highway Project (Phase 1 of Kazhakuttam-Karode Highway) (Bharatmala) | 937 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24647 | National Highways Authority Of India | 155597 | Kelapur-Pimpalkhatti (NS-62) Highway Project | 733 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24648 | National Highways Authority Of India | 155597 | Kelapur-Pimpalkhatti (NS-62) Highway Project | 733 | Contractor | Devi Enterprises Ltd. | 306303 | India | Registered Office:14/30, Near Arya Samaj Mandir, Obra, | 231219 | Sonbhadra | Uttar Pradesh |  |  | opslaw_1962@rediffmail.com
24649 | National Highways Authority Of India | 155597 | Ken Metal Factory FOB Project | 829 | Contractor | Navyug Construction Pvt. Ltd. | 156615 | India | Registered Office:Plot No.379, Road No.10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.navayuga.com
24650 | National Highways Authority Of India | 155597 | Kerala Border-Kollegal (NH-212) Two/Four Lane Highway Project | 935 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24651 | National Highways Authority Of India | 155597 | Kerala/Tamil Nadu Border-Villukuri (NH-47) Four Laning Highway Project | 1150 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24652 | National Highways Authority Of India | 155597 | Kerala/Tamil Nadu Border-Villukuri (NH-47) Four Laning Highway Project | 1150 | Contractor | L & T Transportation Infrastructure Ltd. | 125136 | India | Registered Office:Mount Poonamalli Road, P O Box 979, Manapakkam, | 600089 | Chennai | Tamil Nadu | 91-44-22526666 | 91-44-22528724 | rstt@lntidpl.com | www.lntidpl.com
24653 | National Highways Authority Of India | 155597 | Kerala/Tamil Nadu Border-Villukuri (NH-47) Four Laning Highway Project | 1150 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24654 | National Highways Authority Of India | 155597 | Kerle-Paijarwadi Four Lane Highway (Package-II of Ratnagiri-Kolhapur section of NH-166) Project | 1446 | Contractor | Thakur Infra Projects Pvt. Ltd. | 407339 | India | Registered Office:House No 1221, At & Po : Jasai, Jasai Naka, Taluka Uran, Navi Mumbai, Raigad, | NA | Navi Mumbai | Maharashtra |  |  | thakurinfraprojects@gmail.com
24655 | National Highways Authority Of India | 155597 | Kerle-Paijarwadi Four Lane Highway (Package-II of Ratnagiri-Kolhapur section of NH-166) Project | 1446 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
24656 | National Highways Authority Of India | 155597 | KGP Expressway to Aligarh-Palwal Highway Six Lane New Link Road Project | 1506 | Contractor | Raja Infraconstruction Pvt. Ltd. | 538648 | India | Registered Office:R-14/98, Raj Nagar, | 201002 | Ghaziabad | Uttar Pradesh
24657 | National Highways Authority Of India | 155597 | Khaga-Varanasi(Khaga-Kokhraj) Highway Project | 150 | Consultant | Meinhardt (singapore) Pte Ltd. | 286809 | Singapore | Registered Office:A - 8, Sector 16, Gautam Buddha Nagar, | 201301 | Noida | Uttar Pradesh | 91-120-2516165 | 91-120-2515745 | rajesh@meinhardtindia.com | www.meinhardtgroup.com
24658 | National Highways Authority Of India | 155597 | Khaga-Varanasi(Khaga-Kokhraj) Highway Project | 150 | Turnkey contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24659 | National Highways Authority Of India | 155597 | Khajuri-Wyndhamganj (NH-75) Four Lane Highway Project (Package 5) | 1958 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24660 | National Highways Authority Of India | 155597 | Khajuri-Wyndhamganj (NH-75) Four Lane Highway Project (Package 5) | 1958 | Contractor | M G Contractors Pvt. Ltd. | 131217 | India | Registered Office:603, RIng Road Mall, Near Depali Chowk, Rohini, | 110085 | New Delhi | NCT of Delhi |  |  | mgcpl@mgcpl.com | www.mgcpl.com
24661 | National Highways Authority Of India | 155597 | Khajuwala-Poogal section and Poogal-Dantour-Jaggasar-Gokul-Goddu-Ranjeetpura-Charanwala-Naukh-Bap section of (NH-911) Two/Four Lane Highway Project | 1485 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24662 | National Highways Authority Of India | 155597 | Khammam-TL/AP Border-Vijaywada (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Venkatayapalem village to Jakkampudi village) | 1953 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24663 | National Highways Authority Of India | 155597 | Khammam-TL/AP Border-Vijaywada (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Venkatayapalem village to Jakkampudi village) | 1953 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24664 | National Highways Authority Of India | 155597 | Khammam-TL/AP Border-Vijaywada (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Venkatayapalem village to Jakkampudi village) | 1953 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24665 | National Highways Authority Of India | 155597 | Khanapur-Karnataka-Goa Border (NH-4A) Two Lane Highway Project (Package-II) (section of Belgaum-KNT/Goa Border) (Bharatmala) | 1554 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24666 | National Highways Authority Of India | 155597 | Khanapur-Karnataka-Goa Border (NH-4A) Two Lane Highway Project (Package-II) (section of Belgaum-KNT/Goa Border) (Bharatmala) | 1554 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24667 | National Highways Authority Of India | 155597 | Khanapur-Karnataka-Goa Border (NH-4A) Two Lane Highway Project (Package-II) (section of Belgaum-KNT/Goa Border) (Bharatmala) | 1554 | Contractor | V M Matere Infrastructures (india) Pvt. Ltd. | 406445 | India | Registered Office:Matere House, Sector No.14, Pradhikaran, Gat No.62, Boradewadi, Moshi, | 412105 | Pune | Maharashtra |  |  | info@vmmatere.com | www.vmmatere.com
24668 | National Highways Authority Of India | 155597 | Khandagiri Chowk (NH-16) Grade Separator Project | 1223 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
24669 | National Highways Authority Of India | 155597 | Khanpur Ghati to Haryana/Rajasthan Border Eight Lane Carriageway Project (Package 3 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1545 | Contractor | C D S Infra Projects Ltd. | 393833 | India | Registered Office:B -94, Okhla Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-26389595 | 91-11-41709590 | finance@cdsipl.com | www.cdsipl.com
24670 | National Highways Authority Of India | 155597 | Kharagpur-Balasore (Bridges Section OR/WB-I) Highway Project | 135 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24671 | National Highways Authority Of India | 155597 | Kharagpur-Balasore (Bridges Section OR/WB-I) Highway Project | 135 | Turnkey contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24672 | National Highways Authority Of India | 155597 | Kharagpur-Laxmanath (WB-IV) Highway Project | 110 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24673 | National Highways Authority Of India | 155597 | Kharagpur-Laxmanath (WB-IV) Highway Project | 110 | Turnkey contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24674 | National Highways Authority Of India | 155597 | Kharar-Kurali (NH-21) Four Lane Highway Project | 975 | Contractor | Arvind Techno Engineers Pvt. Ltd. | 21082 | India | Corporate Office:A-4, 1st Flr, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-26866381 |  | info@arvindtechno.com | www.arvindtechno.com
24675 | National Highways Authority Of India | 155597 | Kharar-Kurali (NH-21) Four Lane Highway Project | 975 | Contractor | M G Contractors Pvt. Ltd. | 131217 | India | Registered Office:603, RIng Road Mall, Near Depali Chowk, Rohini, | 110085 | New Delhi | NCT of Delhi |  |  | mgcpl@mgcpl.com | www.mgcpl.com
24676 | National Highways Authority Of India | 155597 | Kharar-Ludhiana (NH-5) Four/Six Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1162 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24677 | National Highways Authority Of India | 155597 | Kharar-Ludhiana (NH-5) Four/Six Laning Highway Project (Part of Chandigarh-Ludhiana Highway) | 1162 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24678 | National Highways Authority Of India | 155597 | Khatima Two Lane Bypass (Sitarganj-Tanakpur Section on NH-125) Project | 1942 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24679 | National Highways Authority Of India | 155597 | Khatima Two Lane Bypass (Sitarganj-Tanakpur Section on NH-125) Project | 1942 | Contractor | A P S Infra Engineers Pvt. Ltd. | 658426 | India | Registered Office:D-138, Sector-51, | 201301 | Noida | Uttar Pradesh |  |  | info@apsinfra.com | www.apsinfra.com
24680 | National Highways Authority Of India | 155597 | Khatti Village to Arang Village 4/6 Lane Highway Project (Package 1B of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1548 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24681 | National Highways Authority Of India | 155597 | Khatti Village to Arang Village 4/6 Lane Highway Project (Package 1B of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1548 | Consultant | Transys Consulting Pvt. Ltd. | 541410 | India | Registered Office:12th Floor, J M D Regent Square, M G Road, | 122002 | Gurgaon | Haryana | 91-124-4195950 |  | info@transysconsulting.co.in | www.transys.in
24682 | National Highways Authority Of India | 155597 | Khatti Village to Arang Village 4/6 Lane Highway Project (Package 1B of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1548 | Contractor | Kalyan Toll Infrastructure Ltd. | 386962 | India | Registered Office:Vidhya Deep, 15/3 Manorama Ganj, | 452001 | Indore | Madhya Pradesh | 91-731-2496931 | 91-731-4096457 | accounts@kalyangroup.in | www.kalyangroup.in
24683 | National Highways Authority Of India | 155597 | Khatti Village to Arang Village 4/6 Lane Highway Project (Package 1B of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1548 | Contractor | Shelke Construction | 479882 | India |  | NA
24684 | National Highways Authority Of India | 155597 | Khed-Sinnar (NH-50) Four Laning Highway Project | 1824 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24685 | National Highways Authority Of India | 155597 | Khed-Sinnar (NH-50) Four Laning Highway Project | 1824 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24686 | National Highways Authority Of India | 155597 | Khed-Sinnar (NH-50) Four Laning Highway Project | 1824 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24687 | National Highways Authority Of India | 155597 | Khed-Sinnar (NH-50) Four Laning Highway Project | 1824 | Contractor | T & T Infra Ltd. | 543147 | India | Registered Office:Office No.1 To 5, A1, Visnu Vihar, Bibwewadi Kondhwa Road, Marketyard, | 411037 | Pune | Maharashtra | 91-20-24275945 |  | groupt_t@yahoo.co.in | www.tandtinfra.com
24688 | National Highways Authority Of India | 155597 | Khedakhajuria-Suhagadi (NH-148) Four Lane Highway Project (Package-2 of Ujjain-Garoth) | 1963 | Consultant | Wolkem India Ltd. | 321676 | India | Registered Office:E-101, Mewar Industrial Area, Madri, Post Box No.21, | 313003 | Udaipur | Rajasthan | 91-294-2494600 | 91-294-2494608 | mktg@wolkem.com | www.wolkem.com
24689 | National Highways Authority Of India | 155597 | Khedakhajuria-Suhagadi (NH-148) Four Lane Highway Project (Package-2 of Ujjain-Garoth) | 1963 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
24690 | National Highways Authority Of India | 155597 | Khema Karan (Indo-Pak Border)-Bhikhiwind-Chabal Kalan-Amritsar-Ajnala-Ramdas-Dera Baba Nanak-Gurdaspur & Fazilka(NH-7)-Jalalabad-Mamdor-Firozpur Two/Four Lane Highway Project (Bharatmala) | 1095 | Contractor | Inderjit Mehta Constructions Pvt. Ltd. | 320786 | India | Registered Office:#13219/6, Gali No.9/1, Shiv Colony, Namdev Road, | 151001 | Bathinda | Punjab |  |  | shashibjindal@yahoo.com
24691 | National Highways Authority Of India | 155597 | Khema Karan (Indo-Pak Border)-Bhikhiwind-Chabal Kalan-Amritsar-Ajnala-Ramdas-Dera Baba Nanak-Gurdaspur & Fazilka(NH-7)-Jalalabad-Mamdor-Firozpur Two/Four Lane Highway Project (Bharatmala) | 1095 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24692 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram (Ganjam-Icchapuram) Highway Project | 142 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
24693 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Khurda-Sunakhala) Highway Project | 140 | Consultant | D H V Consultants B V. | 53738 | Netherlands |  | NA
24694 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Khurda-Sunakhala) Highway Project | 140 | Contractor | Sri Durga Construction | 348697 | India |  | NA
24695 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Sunakhala-Ganjam) Highway Project | 141 | Consultant | D H V Consultants B V. | 53738 | Netherlands |  | NA
24696 | National Highways Authority Of India | 155597 | Khurda Town-Icchapuram(Sunakhala-Ganjam) Highway Project | 141 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24697 | National Highways Authority Of India | 155597 | Kiratpur-Ner Chowk Four-Laning (NH-3,154&205) Highway Project | 1819 | Consultant | Getinsa Ingenieria S L | 471808 | Spain |  | NA
24698 | National Highways Authority Of India | 155597 | Kiratpur-Ner Chowk Four-Laning (NH-3,154&205) Highway Project | 1819 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24699 | National Highways Authority Of India | 155597 | Kiratpur-Ner Chowk Four-Laning (NH-3,154&205) Highway Project | 1819 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24700 | National Highways Authority Of India | 155597 | Kishanganj Flyover (NH-31) Project | 1514 | Consultant | Construma Consultancy Pvt. Ltd. | 50566 | India | Registered Office:2nd Floor, Pinky Plaza, 5th Road, Khar West, | 400052 | Mumbai | Maharashtra | 91-22-26487415 | 91-22-26463181 | info@construma.in
24701 | National Highways Authority Of India | 155597 | Kishanganj Flyover (NH-31) Project | 1514 | Contractor | Bihar Rajya Pul Nirman Nigam Ltd. | 35527 | India | Registered Office:7, Sardar Patel Marg, | 800015 | Patna | Bihar | 91-612-2226562 | 91-612-2223316 | info@brpnnl.co.in | www.brapnn.bih.nic.in
24702 | National Highways Authority Of India | 155597 | Kishangarh ROB Project | 124 | Contractor | Welspun Enterprises Ltd. | 318534 | India | Corporate Office:Welspun House, 4th Flr, Kamala City, Senapati Bapat Marg, Lower Parel-W, | 400013 | Mumbai | Maharashtra | 91-22-66136000 | 91-22-24908020 | companysecretary_wpl@welspun.com | www.welspunenterprises.com
24703 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Bhilwara Bypass-Chittorgarh) High. Project | 127 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24704 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Bhilwara Bypass-Chittorgarh) High. Project | 127 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24705 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Bhilwara Bypass-Chittorgarh) High. Project | 127 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24706 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Bhilwara Bypass-Chittorgarh) High. Project | 127 | Turnkey contractor | S Seemiah & Co. Projects Ltd. | 205660 | India |  | NA
24707 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Chittorgarh-Mangalwar) Highway Project | 128 | Consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24708 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Chittorgarh-Mangalwar) Highway Project | 128 | Consultant | Sverdrup Civil India Ltd. | 244114 | USA | Registered Office:242, Okhla Industrial Estate Phase III | 110020 | New Delhi | Delhi
24709 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Chittorgarh-Mangalwar) Highway Project | 128 | Contractor | Binapuri Holdings Berhad | 35848 | Malaysia |  | NA
24710 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Chittorgarh-Mangalwar) Highway Project | 128 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24711 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24712 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Consultant | Sverdrup Civil India Ltd. | 244114 | USA | Registered Office:242, Okhla Industrial Estate Phase III | 110020 | New Delhi | Delhi
24713 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24714 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Contractor | J S R Constructions Pvt. Ltd. | 104773 | India | Registered Office:No. 3415, IInd Stage, Indiranagar, | 560038 | Bengaluru | Karnataka
24715 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Gulabpura-Bhilwara Bypass) Highway Project | 170 | Contractor | Ecovest Construction Sdn. Bhd. | 332159 | Malaysia |  | NA
24716 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Kishangarh-Nasirabad KU-I) Highway Project | 125 | Consultant | Dorsch Consult Ingenieru Gesellschaft M B H. | 62671 | Germany |  | NA
24717 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Kishangarh-Nasirabad KU-I) Highway Project | 125 | Consultant | Sverdrup Civil India Ltd. | 244114 | USA | Registered Office:242, Okhla Industrial Estate Phase III | 110020 | New Delhi | Delhi
24718 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Kishangarh-Nasirabad KU-I) Highway Project | 125 | Turnkey contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24719 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Nasirabad-Gulabpura) Highway Project | 126 | Consultant | Dorsch Consult Ingenieru Gesellschaft M B H. | 62671 | Germany |  | NA
24720 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Nasirabad-Gulabpura) Highway Project | 126 | Consultant | Sverdrup Civil India Ltd. | 244114 | USA | Registered Office:242, Okhla Industrial Estate Phase III | 110020 | New Delhi | Delhi
24721 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Nasirabad-Gulabpura) Highway Project | 126 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24722 | National Highways Authority Of India | 155597 | Kishangarh-Udaipur(Nasirabad-Gulabpura) Highway Project | 126 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24723 | National Highways Authority Of India | 155597 | KMP Expressway to Khanpur Ghati Eight Lane Carriageway Project (Package 2 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1544 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
24724 | National Highways Authority Of India | 155597 | KN/TS Border near Nandinne village-Kurnool Six Lane Greenfield Highway Project | 1889 | Consultant | S M Consultancy Pvt. Ltd. | 203764 | India | Registered Office:Hemakapada Chhak, Sunhat, | 756002 | Balasore | Odisha | 91-6782-251981 | 91-6782-251982 | smcbls@smcindia.com | www.smcindia.com
24725 | National Highways Authority Of India | 155597 | KN/TS Border near Nandinne village-Kurnool Six Lane Greenfield Highway Project | 1889 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24726 | National Highways Authority Of India | 155597 | Kodad-Khammam (NH 365-A) Four-Lane Highway Project (Bharatmala) | 1196 | Contractor | Adani Road Transport Ltd. | 595357 | India | Registered Office:Adani House, Nr. Mithakhali Six Road, | 380009 | Ahmedabad | Gujarat | 91-79-26565555 |  | deepak.pandya@adani.com | www.adanienterprises.com
24727 | National Highways Authority Of India | 155597 | Kodebad-Dhamtari Four Laning (NH-30) Highway Project | 1245 | Contractor | G K C Projects Ltd. | 384672 | India | Registered Office:Sy. No. 9 (P), Hitec City, Cii Green Building Lane, Kandapur, | 500084 | Hyderabad | Telangana | 91-40-44554545 |  | info@gkcpl.com | www.gkcpl.com
24728 | National Highways Authority Of India | 155597 | Kodinar-Veraval (NH-8E) (Package-VI Bhavnagar-Veraval Section) Four Lane Highway Project | 1080 | Contractor | Agroh Infrastructure Developers Pvt. Ltd. | 389210 | India | Registered Office:Bunglow No. 74, Infront of Govt. Girls School, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-271225 |  | aidplindore@gmail.com | www.agrohinfra.com
24729 | National Highways Authority Of India | 155597 | Kodungallur-Edapally (NH-66) Six Lane Highway Project | 1906 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
24730 | National Highways Authority Of India | 155597 | Koilwar-Bhojpur (NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) (Bharatmala) | 1087 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
24731 | National Highways Authority Of India | 155597 | Koilwar-Bhojpur (NH-922) Four-Laning Highway Project (Section of Patna-Buxar Highway) (Bharatmala) | 1087 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
24732 | National Highways Authority Of India | 155597 | Kolaghat-Kharagpur (WB-II) Highway Project | 108 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
24733 | National Highways Authority Of India | 155597 | Kolaghat-Kharagpur (WB-II) Highway Project | 108 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24734 | National Highways Authority Of India | 155597 | Kolaghat-Kharagpur (WB-II) Highway Project | 108 | Turnkey contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
24735 | National Highways Authority Of India | 155597 | Kolkata Logistics Park Project | 1368 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24736 | National Highways Authority Of India | 155597 | Kollam Bypass NH-66 Project | 204 | Co-promoter | Kerala Public Works Department | 426356 | India | Registered Office:PWD Road & Bridges & Administration, Public Office, Museum P.O., | 695033 | Thiruvananthapuram | Kerala | 91-471-2322346 |  | ceroads@pwd.kerala.gov.in | www.keralapwd.gov.in
24737 | National Highways Authority Of India | 155597 | Korappuzha Bridge Project | 1878 | Co-promoter | Kerala Road Fund Board | 591353 | India | Registered Office:Kerala Road Fund Board, TC 4/1654, Mayooram, Belhaven Gardens, Kowdiar Post, | 695003 | Thiruvananthapuram | Kerala | 91-471-2726080 | 91-471-2726080 | info@krfb.org | www.krfb.org
24738 | National Highways Authority Of India | 155597 | Korappuzha Bridge Project | 1878 | Contractor | Uralungal Labourcontract Co-op. Society Ltd. | 387892 | India | Head Office:PO Madappally Collage, Vatakara, | 673102 | Kozhikode | Kerala | 91-496-2514042 | 91-496-2516402 | uralungal@ulccsltd.com | www.ulccsltd.com
24739 | National Highways Authority Of India | 155597 | Korappuzha Bridge Project | 1878 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24740 | National Highways Authority Of India | 155597 | Korlam-Kantakapalle (NH-130CD) Six Lane Road Project (Package-3 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 2000 | Consultant | Global Infrasolutions Ltd. | 500285 | India | Registered Office:C-57, Basant Vihar Delhi Road, | 247001 | Saharanpur | Uttar Pradesh |  |  | pankaj4361@gmail.com | www.globalinfrasolutions.org
24741 | National Highways Authority Of India | 155597 | Korlam-Kantakapalle (NH-130CD) Six Lane Road Project (Package-3 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 2000 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
24742 | National Highways Authority Of India | 155597 | Korlam-Kantakapalle (NH-130CD) Six Lane Road Project (Package-3 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 2000 | Consultant | Kaius Consulting Pvt. Ltd. | 660643 | India |  | NA
24743 | National Highways Authority Of India | 155597 | Korlam-Kantakapalle (NH-130CD) Six Lane Road Project (Package-3 of Aluru-Sabbavaram Section) (Raipur Visakhapatnam Economic Corridor) | 2000 | Contractor | P S K Infrastructures & Projects Pvt. Ltd. | 395514 | India | Registered Office:8-2-248/1/7/51, Plot No. 51, Nagarjuna Hills, Punjagutta, | 500082 | Hyderabad | Telangana |  |  | pskhyd@yahoo.co.in
24744 | National Highways Authority Of India | 155597 | Kota Bypass (RJ-4) Project | 740 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
24745 | National Highways Authority Of India | 155597 | Kota Bypass (RJ-4) Project | 740 | Contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
24746 | National Highways Authority Of India | 155597 | Kota Logistics Park Project | 1356 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24747 | National Highways Authority Of India | 155597 | Kota-Chittorgarh Highway Project | 299 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
24748 | National Highways Authority Of India | 155597 | Kota-Chittorgarh Highway Project | 299 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24749 | National Highways Authority Of India | 155597 | Kota-Chittorgarh Highway Project | 299 | Supervision consultant | Stanley Consultants Inc. | 380296 | USA | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
24750 | National Highways Authority Of India | 155597 | Kotputli-Jaipur Highway Project | 12 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24751 | National Highways Authority Of India | 155597 | Kotputli-Jaipur Highway Project | 12 | Contractor | Siemens Ltd. | 226821 | India | Corporate Office:Birla Arora, Level 21, Plot No.1080, Dr. Annie Besant Road, Worli, | 400030 | Mumbai | Maharashtra | 91-22-62517000 | 91-22-24362403 | corporate-secretariat.in@siemens.com | www.siemens.co.in
24752 | National Highways Authority Of India | 155597 | Kotputli-Jaipur Highway Project | 12 | Machinery supplier | Metso Outotec India Pvt. Ltd. | 244102 | India | Registered Office:C-227, Ground Floor, Westend Marg Near Garden Of Five Senses, Paryavaran Complex, | 110030 | New Delhi | NCT of Delhi | 91-11-29536312 | 91-11-29536642 | amit.aggarwal@metso.com | www.metso.com
24753 | National Highways Authority Of India | 155597 | Kottukulangara-Start of Kollam Bypass (NH-66) Four/Six Lane Highway Project (Bharatmala) | 1885 | Consultant | S M E C International Pty. Ltd. | 203789 | India | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24754 | National Highways Authority Of India | 155597 | Kottukulangara-Start of Kollam Bypass (NH-66) Four/Six Lane Highway Project (Bharatmala) | 1885 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
24755 | National Highways Authority Of India | 155597 | Kottukulangara-Start of Kollam Bypass (NH-66) Four/Six Lane Highway Project (Bharatmala) | 1885 | Contractor | Vishwa Samudra Engg. Pvt. Ltd. | 585208 | India | Registered Office:Door No.59A-8/8-6B1, | 520008 | Vijayawada | Andhra Pradesh | 91-40-67996799 |  | info@vishwasamudra.in | www.vishwasamudra.in
24756 | National Highways Authority Of India | 155597 | Kotwa to Dewapur (LMNHP-10) Four-Laning Highway Project | 731 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
24757 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Krishnagiri-Vaniyambadi) Highway Project | 118 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24758 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Krishnagiri-Vaniyambadi) Highway Project | 118 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24759 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Krishnagiri-Vaniyambadi) Highway Project | 118 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24760 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Pallikonda-Ranipet&Walahjapet Bypass) Project | 120 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24761 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Pallikonda-Ranipet&Walahjapet Bypass) Project | 120 | Turnkey contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
24762 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Poonamalee-Kanchipuram) Highway Project | 122 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
24763 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Poonamalee-Kanchipuram) Highway Project | 122 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24764 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Poonamalee-Kanchipuram) Highway Project | 122 | Turnkey contractor | Afcons Infrastructure Ltd. | 7231 | India | Registered Office:Afcons House, 16, Shah Industrial Estate, Veera Desai Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-67191000 | 91-22-26730047 | rajendran@afcons.com | www.afcons.com
24765 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Vaniyambadi-Pallikonda) Highway Project | 119 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24766 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Vaniyambadi-Pallikonda) Highway Project | 119 | Turnkey contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
24767 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Walahjapet-Kanchipuram) Highway Project | 121 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
24768 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Walahjapet-Kanchipuram) Highway Project | 121 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24769 | National Highways Authority Of India | 155597 | Krishnagiri-Chennai(Walahjapet-Kanchipuram) Highway Project | 121 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24770 | National Highways Authority Of India | 155597 | Krishnapatnam Port (NH-16) SIx Lane Road Connectivity Project (Bharatmala) | 1487 | Contractor | V D B Projects Pvt. Ltd. | 406937 | India | Registered Office:#842/A, V D B House, 100, Feet Road Binnamangala, Indiranagar, | 560038 | Bengaluru | Karnataka |  |  | ksn@vdbgroup.in
24771 | National Highways Authority Of India | 155597 | Kudus-Dharmapuri (NH-965) Four Lane Highway Project (Package-III of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1454 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
24772 | National Highways Authority Of India | 155597 | Kudus-Dharmapuri (NH-965) Four Lane Highway Project (Package-III of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1454 | Contractor | Shri S M Autade Pvt. Ltd. | 510451 | India | Registered Office:Plot No. 17, CTS No. 1620, Giriraj Co-operative Housing Society | 411007 | Pune | Maharashtra | 91-20-25640391 |  | accounts@autadegroup.com | www.autadegroup.com
24773 | National Highways Authority Of India | 155597 | Kullu-Manali (NH-3) Highway Upgradation (2-Lane with Paved Shoulders) Project | 1070 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24774 | National Highways Authority Of India | 155597 | Kumarajapet-Veera Kaveri Raja Puram (NH-716B) Six Laning Expressway Project (Package-II of Chittor-Thatchur Expressway) | 2031 | Contractor | E K K Infrastructure Ltd. | 536863 | India | Corporate Office:IInd Floor, Municipal Building, A M Road, Perumbavoor, | 683542 | Ernakulam | Kerala | 91-484-2523603 | 91-484-2523603 | info@ekk.co.in | www.ekk.co.in
24775 | National Highways Authority Of India | 155597 | Kumarapalayam-Chengapalli (NH-47) Highway Project | 420 | Turnkey contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
24776 | National Highways Authority Of India | 155597 | Kunjwani-Vijaypur (NS-15/J&K) Highway Project | 305 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | Canada | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24777 | National Highways Authority Of India | 155597 | Kunjwani-Vijaypur (NS-15/J&K) Highway Project | 305 | Contractor | Border Roads Organisation | 37884 | India | Registered Office:Seema Sadak Bhawan, Ring Road, Delhi Cantt. | 110010 | New Delhi | NCT of Delhi | 91-11-25686914 | 91-11-25699618 | bro-adg@nic.in | http://www.bro.nic.in
24778 | National Highways Authority Of India | 155597 | Kurali-Kiratpur Sahib Road Widening Project | 707 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24779 | National Highways Authority Of India | 155597 | Kurali-Kiratpur Sahib Road Widening Project | 707 | Contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
24780 | National Highways Authority Of India | 155597 | Kurali-Kiratpur Sahib Road Widening Project | 707 | Contractor | C & C Constructions Ltd. | 39807 | India | Corporate Office:Plot No.70, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-4536666 | 91-124-4536799 | candc@candcinfrastructure.com | www.candcinfrastructure.com
24781 | National Highways Authority Of India | 155597 | Kurnool-Atmakur Two/Four Lane Highway Project (Kurnool-Dornala) | 1526 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24782 | National Highways Authority Of India | 155597 | Kurnool-Atmakur Two/Four Lane Highway Project (Kurnool-Dornala) | 1526 | Contractor | P S K Infrastructures & Projects Pvt. Ltd. | 395514 | India | Registered Office:8-2-248/1/7/51, Plot No. 51, Nagarjuna Hills, Punjagutta, | 500082 | Hyderabad | Telangana |  |  | pskhyd@yahoo.co.in
24783 | National Highways Authority Of India | 155597 | Kuru-Udaipura (NH-75) Four Lane Highway Project (Package-1) | 2051 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24784 | National Highways Authority Of India | 155597 | Kurukshetra Bypass Project | 1980 | Co-promoter | Haryana Public Works Department | 397047 | India | Registered Office:Haryana PWD (B& R) | NA | Chandigarh | Chandigarh | 91-172-2618251 |  |  | www.haryanapwd-bandr.org
24785 | National Highways Authority Of India | 155597 | Kushinagar & Gopalgarh Circle (NH-28) Flyover Project | 2044 | Contractor | J K Engicon Pvt. Ltd. | 555873 | India |  | NA
24786 | National Highways Authority Of India | 155597 | Kutchery Chowk Ranchi-Piska More-Biju Para (NH-75) Four Laning Highway Project (Package-I) | 1226 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24787 | National Highways Authority Of India | 155597 | Kutchery Chowk Ranchi-Piska More-Biju Para (NH-75) Four Laning Highway Project (Package-I) | 1226 | Contractor | Sunil Hitech Engineers Ltd. | 326027 | India | Corporate Office:MET Educational Complex, 6th Floor, C WIng, A K Vaidya Marg, Bandra Reclamation, Bandra (W), | 400050 | Mumbai | Maharashtra | 91-22-61872400 | 91-22-61872455 | cs@sunilhitech.com | www.sunilhitech.com
24788 | National Highways Authority Of India | 155597 | Kutchery Chowk Ranchi-Piska More-Biju Para (NH-75) Four Laning Highway Project (Package-I) | 1226 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
24789 | National Highways Authority Of India | 155597 | Kuttipuram-Edapally (NH-66) Six-Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 479 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24790 | National Highways Authority Of India | 155597 | Laddowal Four Lane Bypass Project | 1168 | Contractor | Eagle Infra India Ltd. | 421599 | India | Registered Office:BK No.758, Room No.16, Near Plot No.59, Chopra Court, | 421001 | Ulhasnagar | Maharashtra | 91-251-2569901 |  | eagleconstructionco@gmail.com | www.eagleinfraindialtd.com
24791 | National Highways Authority Of India | 155597 | Ladnu (Nimbi Jodha)-Degana-Merta City (NH-458) Two Lane Highway Project | 930 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24792 | National Highways Authority Of India | 155597 | Lakhani (NH-53) Flyover project | 1483 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
24793 | National Highways Authority Of India | 155597 | Lakhnadon-MP/MH Border (NS-1/BOT/MP-2) Highways project | 745 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24794 | National Highways Authority Of India | 155597 | Lakhnadon-MP/MH Border (NS-1/BOT/MP-2) Highways project | 745 | Contractor | Nava Ltd. | 155990 | India | Registered Office:'Nava Bharat Chambers', 6-3-1109/1, Raj Bhavan Road, | 500082 | Hyderabad | Telangana | 91-40-23403501 | 91-40-23403013 | nbvl@nbv.in | www.nbventures.com
24795 | National Highways Authority Of India | 155597 | Lalganj-Hanumanha (NH-135) Four Lane Highway Project (Package-III) | 1469 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24796 | National Highways Authority Of India | 155597 | Lalganj-Hanumanha (NH-135) Four Lane Highway Project (Package-III) | 1469 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24797 | National Highways Authority Of India | 155597 | Lalghati to Bhopal Bypass (Mubarakpur) (NH-12) Four-Laning Road Project (Package-I) (Bhopal-Biaora Section) | 1258 | Contractor | C D S Infra Projects Ltd. | 393833 | India | Registered Office:B -94, Okhla Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-26389595 | 91-11-41709590 | finance@cdsipl.com | www.cdsipl.com
24798 | National Highways Authority Of India | 155597 | Lalitpur-Sagar (NH-26) Highway Project | 292 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
24799 | National Highways Authority Of India | 155597 | Lalitpur-Sagar (NH-26) Highway Project | 292 | Contractor | I J M Corpn. Bhd | 96657 | Malaysia | Registered Office:2nd Floor, Wisma IJM, 46050, Talan Hong Shock, Peraling Jaya, Selangot Darul Ehsan, Malaysia, | NA
24800 | National Highways Authority Of India | 155597 | Lalitpur-Sagar (NH-26) Highway Project | 292 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24801 | National Highways Authority Of India | 155597 | Lambia-Jaitran-Raipur (NH-458) Two Lane Highway Project | 948 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24802 | National Highways Authority Of India | 155597 | Lambia-Jaitran-Raipur (NH-458) Two Lane Highway Project | 948 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24803 | National Highways Authority Of India | 155597 | Lambia-Jaitran-Raipur (NH-458) Two Lane Highway Project | 948 | Contractor | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24804 | National Highways Authority Of India | 155597 | Lanka-Daboka (AS-16) Highway Project | 700 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
24805 | National Highways Authority Of India | 155597 | Laxmannath-Baleshwar (OR-4) Highway Project | 134 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24806 | National Highways Authority Of India | 155597 | Laxmannath-Baleshwar (OR-4) Highway Project | 134 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24807 | National Highways Authority Of India | 155597 | lchhapuram-Narasannapeta (NH-16) Six Laning Highway Project (Package-I) | 1277 | Contractor | C C C Ltd. | 444816 | India |  | NA
24808 | National Highways Authority Of India | 155597 | lchhapuram-Narasannapeta (NH-16) Six Laning Highway Project (Package-I) | 1277 | Contractor | S P L Infrastructure Pvt. Ltd. | 516118 | India | Registered Office:No. 24 , Crescent Part Street, 1st Floor, T Nagar, | 600018 | Chennai | Tamil Nadu | 91-44-48674770 | 91-44-2364787 | info@splinfra.com | www.splinfra.com
24809 | National Highways Authority Of India | 155597 | Liberty Cinema-Mental Hospital (NH-69) Flyover Project | 1206 | Consultant | Holtec Consulting Pvt. Ltd. | 94858 | India | Corporate Office:Holtec Centre, A Block, Sushant Lok, | 122001 | Gurgaon | Haryana | 91-124-2385095 | 91-124-2385114 | dkj@holtecnet.com | www.holtecnet.com
24810 | National Highways Authority Of India | 155597 | Liberty Cinema-Mental Hospital (NH-69) Flyover Project | 1206 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24811 | National Highways Authority Of India | 155597 | Liberty Cinema-Mental Hospital (NH-69) Flyover Project | 1206 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24812 | National Highways Authority Of India | 155597 | Lonand-Dive Ghat (NH-965) Four Lane Highway Project (Package-V of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1893 | Consultant | Technocrats Advisory Services Pvt. Ltd. | 566226 | India | Registered Office:68, Ajanta Apartments, 36, I P Extension Patparganj, | 110092 | New Delhi | NCT of Delhi |  |  | kamleshkumar.77@gmail.com
24813 | National Highways Authority Of India | 155597 | Lonand-Dive Ghat (NH-965) Four Lane Highway Project (Package-V of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1893 | Contractor | Thakur Infra Projects Pvt. Ltd. | 407339 | India | Registered Office:House No 1221, At & Po : Jasai, Jasai Naka, Taluka Uran, Navi Mumbai, Raigad, | NA | Navi Mumbai | Maharashtra |  |  | thakurinfraprojects@gmail.com
24814 | National Highways Authority Of India | 155597 | Lonand-Dive Ghat (NH-965) Four Lane Highway Project (Package-V of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1893 | Contractor | T & T Infra Ltd. | 543147 | India | Registered Office:Office No.1 To 5, A1, Visnu Vihar, Bibwewadi Kondhwa Road, Marketyard, | 411037 | Pune | Maharashtra | 91-20-24275945 |  | groupt_t@yahoo.co.in | www.tandtinfra.com
24815 | National Highways Authority Of India | 155597 | Lucknow Bypass (EW-15/UP) Highway Project | 174 | Consultant | C E S Pvt. Ltd. [merged] | 372391 | India |  | NA
24816 | National Highways Authority Of India | 155597 | Lucknow Bypass (EW-15/UP) Highway Project | 174 | Contractor | N K G Infrastructure Ltd. | 359038 | India | Registered Office:204, Kailash Building 26, KG Marg, | 110001 | New Delhi | NCT of Delhi | 91-11-47682800 | 91-11-47682801 | nkg@nkginfra.com | www.nkginfra.com
24817 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Co-promoter | Uttar Pradesh Public Works Department | 375252 | India | Registered Office:Nirman Bhawan, 96, Mahatma Gandhi Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2236496 |  | pwdgislko@gmail.com | www.uppwd.gov.in
24818 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Co-promoter | Lucknow Development Authority | 375253 | India | Registered Office:Pradhikran Bhawan, Vipin Khand, Gomti Nagar, | 226001 | Lucknow | Uttar Pradesh | 91-522-2215045 | 91-522-2237210 | ldapro@yahoo.com | www.ldalucknow.co.in
24819 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Consultant | C E S Ltd. | 216887 | India | Registered Office:7th Floor, Tower A, Ramky Selenium, Nanakramguda, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-42421122 | 91-40-66259444 | info@cesltd.com | www.cesltd.com
24820 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24821 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
24822 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24823 | National Highways Authority Of India | 155597 | Lucknow Outer Ring Road (NH-56&24) Project | 1089 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24824 | National Highways Authority Of India | 155597 | Lucknow-Kanpur (NH-25) Section ROB, Underpass and Approach Road Project | 663 | Contractor | Niraj Cement Structurals Ltd. | 276926 | India | Registered Office:Niraj House, Sunder Baug, Near Deonar Bus Depot, Chembur-E, | 400088 | Mumbai | Maharashtra | 91-22-25513541 | 91-22-25518736 | cs@niraj.co.in | www.niraj.co.in
24825 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section (EW/3B) NH-25 Project | 179 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24826 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section (EW/3B) NH-25 Project | 179 | Contractor | Niraj Cement Structurals Ltd. | 276926 | India | Registered Office:Niraj House, Sunder Baug, Near Deonar Bus Depot, Chembur-E, | 400088 | Mumbai | Maharashtra | 91-22-25513541 | 91-22-25518736 | cs@niraj.co.in | www.niraj.co.in
24827 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-8/UP) Highway Project | 184 | Consultant | Archtech Consultants Pvt. Ltd. | 19112 | India | Registered Office:No. 11, Shakespeare Sarani, | 700071 | Kolkata | West Bengal | 91-33-2827255 | 91-33-2825377 | acplcal@cal3.vsnl.net.in | www.archtechconsultants.com
24828 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-8/UP) Highway Project | 184 | Turnkey contractor | Villayati Ram Mittal Builders & Promoters (india) Ltd. | 266845 | India | Registered Office:F-345, Krishna Nagar, Kotla Mubarakpur, | 110001 | New Delhi | Delhi
24829 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-9/UP) Highway Project | 229 | Consultant | Archtech Consultants Pvt. Ltd. | 19112 | India | Registered Office:No. 11, Shakespeare Sarani, | 700071 | Kolkata | West Bengal | 91-33-2827255 | 91-33-2825377 | acplcal@cal3.vsnl.net.in | www.archtechconsultants.com
24830 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW-9/UP) Highway Project | 229 | Contractor | T R Gupta Construction Pvt. Ltd. | 246348 | India | Registered Office:19/1, Manoramaganj Indoreday Ower Plasia, | 452001 | Indore | Madhya Pradesh |  |  | amitsurana_co@yahoo.com
24831 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW/2) Highway Project | 183 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24832 | National Highways Authority Of India | 155597 | Lucknow-Kanpur Section(EW/2) Highway Project | 183 | Contractor | Villayati Ram Mittal Builders & Promoters (india) Ltd. | 266845 | India | Registered Office:F-345, Krishna Nagar, Kotla Mubarakpur, | 110001 | New Delhi | Delhi
24833 | National Highways Authority Of India | 155597 | Ludhiana Logistic Park Project | 1372 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24834 | National Highways Authority Of India | 155597 | Ludhiana-Talwandi Bhai (NH-95) Four Laning Highway Project (Package-II) | 1060 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
24835 | National Highways Authority Of India | 155597 | Ludhiana-Talwandi Bhai (NH-95) Four Laning Highway Project (Package-II) | 1060 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24836 | National Highways Authority Of India | 155597 | Lumding-Daboka (AS-15) Highway Project | 277 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24837 | National Highways Authority Of India | 155597 | Lumding-Daboka (AS-15) Highway Project | 277 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24838 | National Highways Authority Of India | 155597 | Madathukulam-Pollachi (NH-83) Four Lane Highway Project (Package-3 of Dindigul-Pollachi) (Bharatmala) | 1501 | Contractor | D P Jain & Co Infrastructure Pvt. Ltd. | 409463 | India | Registered Office:U/6, Himalaya Accord Apartment Opp. Law College Amravati Road, | 440010 | Nagpur | Maharashtra | 91-712-2535357 | 91-712-2560836 | dpjain.company@dpjaingroup.com | www.dpjaingroup.com
24839 | National Highways Authority Of India | 155597 | Madhura Bazaar-Chullikad Road Upgradation Project (Bharatmala) | 1721 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24840 | National Highways Authority Of India | 155597 | Madiaon-IIM Crossing (NH-24) Elevated Corridor Project | 1310 | Contractor | Kaluwala Construction Pvt. Ltd. | 614021 | India | Registered Office:201, 2nd Floor, I T Space Tikri, Sector 48, IRIS Tech Park Sector-48, | 122103 | Gurugram | Haryana |  |  | kcc.bablu@gmail.com
24841 | National Highways Authority Of India | 155597 | Madurai Four Lane Ring Road Project | 1498 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
24842 | National Highways Authority Of India | 155597 | Madurai-Chettikulam (NH-785) Four Laning Elevated Highway (Flyover) Project | 1482 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
24843 | National Highways Authority Of India | 155597 | Madurai-Kanniakumari Section (NS-40/TN) NH-7 Project | 466 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
24844 | National Highways Authority Of India | 155597 | Madurai-Kanniyakumari (NS-41/TN) Highway Project | 467 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
24845 | National Highways Authority Of India | 155597 | Madurai-Kanniyakumari Section (NS-42/TN) NH-7 Highway Project | 468 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24846 | National Highways Authority Of India | 155597 | Madurai-Kanniyakumari Section (NS-42/TN) NH-7 Highway Project | 468 | Contractor | S M S Ltd. | 218106 | India | Corporate Office:20, I T Park, Parsodi, | 440022 | Nagpur | Maharashtra | 91-712-6665000 | 91-712-6665100 | info@smsl.co.in | www.smsl.co.in
24847 | National Highways Authority Of India | 155597 | Madurai-Paramakudi (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 888 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
24848 | National Highways Authority Of India | 155597 | Madurai-Paramakudi (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 888 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24849 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli section including Madurai Bypass (NS-39/TN) NH-7 Project | 268 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24850 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli section including Madurai Bypass (NS-39/TN) NH-7 Project | 268 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24851 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli Section To Panagudi (NS-43/TN) Highway Project | 414 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24852 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli Section To Panagudi (NS-43/TN) Highway Project | 414 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24853 | National Highways Authority Of India | 155597 | Madurai-Tirunelveli Section To Panagudi (NS-43/TN) Highway Project | 414 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24854 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Belgaum-Dharwad) Highway Project | 83 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24855 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Belgaum-Dharwad) Highway Project | 83 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
24856 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Belgaum-Dharwad) Highway Project | 83 | Contractor | Sunway Construction Bhd | 282631 | Malaysia | Registered Office:Level 8, Menara Sunway, Jalan Lagoon Timur, Bandar Sunway, 46150 Petaling Jaya, Selangor Darul Ehsan, Malaysia | NA
24857 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Belgaum-Dharwad) Highway Project | 83 | Contractor | R N Shetty & Co. | 332162 | India |  | NA
24858 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Hubli-Haveri) Highway Project | 114 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24859 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Hubli-Haveri) Highway Project | 114 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
24860 | National Highways Authority Of India | 155597 | Mah/Kar Border-Haveri(Hubli-Haveri) Highway Project | 114 | Contractor | Afcons Infrastructure Ltd. | 7231 | India | Registered Office:Afcons House, 16, Shah Industrial Estate, Veera Desai Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-67191000 | 91-22-26730047 | rajendran@afcons.com | www.afcons.com
24861 | National Highways Authority Of India | 155597 | Mahatma Gandhi Setu Revamp Project | 879 | Consultant | S N Bhobe & Associates Pvt. Ltd. | 383551 | India | Registered Office:Banking Complex No. II, Unit No. 10, Plot No. 9 & 10, Sector No. 19-A, Vashi, | 400705 | Navi Mumbai | Maharashtra | 91-22-27831070 | 91-22-27831173 | accounts@snbapl.com | www.snbapl.com
24862 | National Highways Authority Of India | 155597 | Mahatma Gandhi Setu Revamp Project | 879 | Consultant | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
24863 | National Highways Authority Of India | 155597 | Mahatma Gandhi Setu Revamp Project | 879 | Contractor | Afcons Infrastructure Ltd. | 7231 | India | Registered Office:Afcons House, 16, Shah Industrial Estate, Veera Desai Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-67191000 | 91-22-26730047 | rajendran@afcons.com | www.afcons.com
24864 | National Highways Authority Of India | 155597 | Mahatma Gandhi Setu Revamp Project | 879 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24865 | National Highways Authority Of India | 155597 | Maheshkhunt-Saharsa-Purnea (NH-107 & 231) Two Laning Road Project (Package-II) | 1250 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24866 | National Highways Authority Of India | 155597 | Maheshkoot-Saharsa-Purnea (NH-107 & 231) Two Laning Road Project (Package-I) | 1129 | Contractor | Gannon Dunkerley & Co. Ltd. | 78966 | India | Registered Office:New Excelsior Building, 3rd Floor, A K Nayak Marg, Fort, | 400001 | Mumbai | Maharashtra | 91-22-22051231 | 91-22-22051232 | gdho1@mtnl.net.in | www.gannondunkerley.com
24867 | National Highways Authority Of India | 155597 | Mahua-Jaipur Highway (NH-11) Project | 616 | Turnkey contractor | I J M Corpn. Bhd | 96657 | Malaysia | Registered Office:2nd Floor, Wisma IJM, 46050, Talan Hong Shock, Peraling Jaya, Selangot Darul Ehsan, Malaysia, | NA
24868 | National Highways Authority Of India | 155597 | Mahulia-Baharagora-JH/WB Border (NH-33 & NH-6) Four Laning Highway Project | 1036 | Consultant | Rodic Consultants Pvt. Ltd. | 307240 | India | Corporate Office:1, Jai Singh Road, | 110001 | New Delhi | NCT of Delhi | 91-11-49434500 | 91-11-49434501 | contact@rodicconsultants.com | www.rodicconsultants.com
24869 | National Highways Authority Of India | 155597 | Mahulia-Baharagora-JH/WB Border (NH-33 & NH-6) Four Laning Highway Project | 1036 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
24870 | National Highways Authority Of India | 155597 | Mahulia-Baharagora-JH/WB Border (NH-33 & NH-6) Four Laning Highway Project | 1036 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
24871 | National Highways Authority Of India | 155597 | Mahuva-Kagavadar (NH-8E & NH-51) (Package-III Bhavnagar-Veraval Section) Four Lane Highway Project | 1903 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24872 | National Highways Authority Of India | 155597 | Mahuva-Kagavadar (NH-8E & NH-51) (Package-III Bhavnagar-Veraval Section) Four Lane Highway Project | 1903 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24873 | National Highways Authority Of India | 155597 | Mahuva-Kagavadar (NH-8E & NH-51) (Package-III Bhavnagar-Veraval Section) Four Lane Highway Project | 1903 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
24874 | National Highways Authority Of India | 155597 | Majholi-Katra-Yajuar-Kharka Basant-Majhaur-Baher-Pupri-Charout (NH-527C)Two-Lane Highway Project | 1182 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
24875 | National Highways Authority Of India | 155597 | Major Bridge on Chakan River to Major Bridge on Mej River Eight Lane Carriageway Project (Package-11 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1562 | Contractor | L & T Construction | 560291 | India | Registered Office:Mount Poonamallee Road, Manapakkam, P B No.979, | 600089 | Chennai | Tamil Nadu | 91-44-22526000 | 91-44-22493317 | info@lntecc.com | www.lntecc.com
24876 | National Highways Authority Of India | 155597 | Major Bridge on Mej River to Junction with SH-37A Eight Lane Carriageway Project (Package 12 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1563 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24877 | National Highways Authority Of India | 155597 | Major bridge over Takli river near Nayagaon Jageer village to Rajasthan/MP Border Eight Lane Carriageway Project (Package 16 of Delhi-Mumbai Expressway) | 1569 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
24878 | National Highways Authority Of India | 155597 | Major bridge over Takli river near Nayagaon Jageer village to Rajasthan/MP Border Eight Lane Carriageway Project (Package 16 of Delhi-Mumbai Expressway) | 1569 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24879 | National Highways Authority Of India | 155597 | Mall Road-Lal Bahadur Shastri National Academy of Administration (LBSNAA) Two Lane Tunnel (Mussoorie Tunnel) Project | 2071 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24880 | National Highways Authority Of India | 155597 | Malout-Abohar-Sadhuwali Four Lane Road Project | 1804 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24881 | National Highways Authority Of India | 155597 | Mamallapuram-Mugaiyur section of NH-332A Four Lane Highway Project (Phase 1) | 1779 | Contractor | J S R Developers Pvt. Ltd. | 455098 | India | Registered Office:J S W Towers, 4th Floor, New No.17/ Old No.8, Vijayaragava Road, T Nagar, | 600017 | Chennai | Tamil Nadu | 91-44-28152840 |  | admin@jsrinfraa.com | www.jsrinfraa.com
24882 | National Highways Authority Of India | 155597 | Mancherial-Repallewada (NH-363) Four Lane Highway Project (Bharatmala) | 1426 | Contractor | Adani Road Transport Ltd. | 595357 | India | Registered Office:Adani House, Nr. Mithakhali Six Road, | 380009 | Ahmedabad | Gujarat | 91-79-26565555 |  | deepak.pandya@adani.com | www.adanienterprises.com
24883 | National Highways Authority Of India | 155597 | Mancherial-Repallewada (NH-363) Four Lane Highway Project (Bharatmala) | 1426 | Sub contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24884 | National Highways Authority Of India | 155597 | Mancherial-Warangal (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Ramaraopet village to Oorugonda village) | 1949 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24885 | National Highways Authority Of India | 155597 | Mancherial-Warangal (NH-163G) Four Lane Access Controlled Greenfield Highway Project (Ramaraopet village to Oorugonda village) | 1949 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24886 | National Highways Authority Of India | 155597 | Mandi Dabwali (Punjab/Haryana border)-Chautala Six Lane Road Project | 1807 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
24887 | National Highways Authority Of India | 155597 | Manewal (Ludhiana) to Bheora (Rupnagar) including Spur to Kharar with Ludhiana Bypass (Ludhiana-Rupnagar NH-205K) Six Lane Access Controlled Greenfield Highway Project (Package-2) | 1993 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
24888 | National Highways Authority Of India | 155597 | Mangalwar-Udaipur (KU-VI) Highway Project | 129 | Consultant | S M E C International Pty. Ltd. | 203789 | Australia | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
24889 | National Highways Authority Of India | 155597 | Mangalwar-Udaipur (KU-VI) Highway Project | 129 | Contractor | P B A Infrastructure Ltd. | 165960 | India | Registered Office:611/3, V N Purav Marg, Chembur (East), | 400071 | Mumbai | Maharashtra | 91-22-61277200 | 91-22-61277203 | pbamumbai@gmail.com | www.pbainfra.in
24890 | National Highways Authority Of India | 155597 | Mangalwar-Udaipur (KU-VI) Highway Project | 129 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
24891 | National Highways Authority Of India | 155597 | Mania-Dholpur Highway Project | 967 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24892 | National Highways Authority Of India | 155597 | Mania-Dholpur Highway Project | 967 | Contractor | M B L Infrastructure Ltd. | 136291 | India | Corporate Office:Banani Corporate One Tower, Suite #303-308, 3rd Floor, Jasola, Plot No.5, Commercial Centre, | 110025 | New Delhi | NCT of Delhi | 91-11-49593300 | 91-11-48593320 | delhi@mblinfra.com | www.mblinfra.com
24893 | National Highways Authority Of India | 155597 | Manoharpur-Dausa (NH-11A) Two-Laning Highway Project | 1190 | Contractor | H G Infratech Pvt. Ltd. | 529686 | India | Corporate Office:Govind Baag, Gandhi Road, (Near Shaheed Gate), Gwalior -474 011 (Madhya Pradesh) | NA |  |  |  |  | info@hggroup.co.in
24894 | National Highways Authority Of India | 155597 | Marripudi-Somavarappadu Six Lane Access Controlled Highway (NH-544G) Project (Package-13 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2112 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24895 | National Highways Authority Of India | 155597 | Mataur (Kangra)-Shimla (NH-88) Four Laning Highway Project | 1219 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24896 | National Highways Authority Of India | 155597 | Mataur (Kangra)-Shimla (NH-88) Four Laning Highway Project | 1219 | Contractor | N G Projects Ltd. | 363366 | India | Registered Office:N G Circle, Mehtapura, Himatnagar, | 383001 | Sabar Kantha | Gujarat | 91-2772-222404 | 91-2772-223950 | ngpl_hmt@rediffmail.com
24897 | National Highways Authority Of India | 155597 | Mataur (Kangra)-Shimla (NH-88) Four Laning Highway Project | 1219 | Contractor | Jandu Construction India Pvt. Ltd. | 646179 | India | Registered Office:H. No. 323 Aggarsain Colony, SBI Street, | 125055 | Sirsa | Haryana |  |  | janduconstco@yahoo.com
24898 | National Highways Authority Of India | 155597 | Mathura-Hathras-Badaun-Bareilly (NH-530B) Four Lane Highway Project | 1681 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
24899 | National Highways Authority Of India | 155597 | Mathura-Hathras-Badaun-Bareilly (NH-530B) Four Lane Highway Project | 1681 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24900 | National Highways Authority Of India | 155597 | Matsyafed Tourist Office-Munambam Road Upgradation Project | 1739 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24901 | National Highways Authority Of India | 155597 | Medshi-Washim (NH-161) Four Lane Highway project (Package-II) | 1696 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
24902 | National Highways Authority Of India | 155597 | Meensurutti-Chidambaram (NH-81 & NH-227) Two/Four Lane Highway Project (Package-III of Trichy-Chidambaram) (Bharatmala) | 1770 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24903 | National Highways Authority Of India | 155597 | Meensurutti-Chidambaram (NH-81 & NH-227) Two/Four Lane Highway Project (Package-III of Trichy-Chidambaram) (Bharatmala) | 1770 | Contractor | R N S Infrastructure Ltd. | 377885 | India | Corporate Office:7th Floor, Naveen Complex #14, M G Road, | 560001 | Bengaluru | Karnataka | 91-80-25584181 | 91-80-25584017 |  | www.rnsil.com
24904 | National Highways Authority Of India | 155597 | Meensurutti-Chidambaram (NH-81 & NH-227) Two/Four Lane Highway Project (Package-III of Trichy-Chidambaram) (Bharatmala) | 1770 | Contractor | Sunway Construction Group Bhd | 525925 | Malaysia |  | NA
24905 | National Highways Authority Of India | 155597 | Meerut New Bypass (NH-58) to Meerut-Najibabad (NH-119) (NH-709A) Four Lane Link Road Project (Four Lane Spur of Meerut-GarhMukteshwar Section) | 1938 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24906 | National Highways Authority Of India | 155597 | Meerut New Bypass (NH-58) to Meerut-Najibabad (NH-119) (NH-709A) Four Lane Link Road Project (Four Lane Spur of Meerut-GarhMukteshwar Section) | 1938 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24907 | National Highways Authority Of India | 155597 | Meerut New Bypass (NH-58) to Meerut-Najibabad (NH-119) (NH-709A) Four Lane Link Road Project (Four Lane Spur of Meerut-GarhMukteshwar Section) | 1938 | Contractor | Dev Yash Projects & Infrastructure Pvt. Ltd. | 604509 | India |  | NA
24908 | National Highways Authority Of India | 155597 | Meerut to after bridge over river Yamuna (Haryana) via Shamli (NH-709A) Four Lane Highway Project | 1684 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24909 | National Highways Authority Of India | 155597 | Meerut-Baghpat-UP/Haryana Border (Sonipat) (NH-334B) Two Lane Highway Project (Bharatmala) | 1672 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
24910 | National Highways Authority Of India | 155597 | Meerut-Budhana-Shamli-UP/Haryana Border (Karnal) NH-709A Four Lane Highway Project | 1674 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24911 | National Highways Authority Of India | 155597 | Meerut-Najibabad (NH-119) Four Lane Highway Project (Package-2) | 2116 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
24912 | National Highways Authority Of India | 155597 | Mehsi-Kotwa (LMNHP-11) Four-Laning Highway Project | 702 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24913 | National Highways Authority Of India | 155597 | Melur-Karaikudi (NH-338, 36 & 383 Ext) Four Lane Highway Project (Thanjavur-Madurai Greenfield Project) (Bharatmala) | 1495 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24914 | National Highways Authority Of India | 155597 | Melur-Karaikudi (NH-338, 36 & 383 Ext) Four Lane Highway Project (Thanjavur-Madurai Greenfield Project) (Bharatmala) | 1495 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
24915 | National Highways Authority Of India | 155597 | Melur-Karaikudi (NH-338, 36 & 383 Ext) Four Lane Highway Project (Thanjavur-Madurai Greenfield Project) (Bharatmala) | 1495 | Contractor | J S R Infra Developers Pvt. Ltd. | 527573 | India | Registered Office:No.4, 10 A, East Cross Road, Gandhi Nagar, | 632006 | Vellore | Tamil Nadu | 91-44-28152840 |  | akrishnamoorthyfca@gmail.com | www.jsrinfraa.com
24916 | National Highways Authority Of India | 155597 | Memmadpur-Dairi-Kharar Four Lane & IT City Chowk-Kurali Chandigarh Road Six Lane Highway Project (Bharatmala) | 1857 | Consultant | Voyants Solutions Pvt. Ltd. | 436055 | India | Registered Office:403, 4th Floor, Park Centra, Sector 30, Opp. 32nd Milestone, NH-8, | 122001 | Gurgaon | Haryana | 91-124-4598200 | 91-124-4019051 | arunkumar@adrasl.com | www.voyants.in
24917 | National Highways Authority Of India | 155597 | Memmadpur-Dairi-Kharar Four Lane & IT City Chowk-Kurali Chandigarh Road Six Lane Highway Project (Bharatmala) | 1857 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24918 | National Highways Authority Of India | 155597 | Memmadpur-Dairi-Kharar Four Lane & IT City Chowk-Kurali Chandigarh Road Six Lane Highway Project (Bharatmala) | 1857 | Consultant | G-eng Advisory Services Pvt. Ltd. | 604206 | India |  | NA
24919 | National Highways Authority Of India | 155597 | Memmadpur-Dairi-Kharar Four Lane & IT City Chowk-Kurali Chandigarh Road Six Lane Highway Project (Bharatmala) | 1857 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24920 | National Highways Authority Of India | 155597 | MES College Junction-Padinajrekar Road Widening Project | 1727 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24921 | National Highways Authority Of India | 155597 | MH/KT Border-Belgaum (NH-48) Six Lane Highway Project (Bharatmala) | 1850 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24922 | National Highways Authority Of India | 155597 | MH/KT Border-Belgaum (NH-48) Six Lane Highway Project (Bharatmala) | 1850 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
24923 | National Highways Authority Of India | 155597 | MH/KT Border-Belgaum (NH-48) Six Lane Highway Project (Bharatmala) | 1850 | Contractor | Shri S M Autade Pvt. Ltd. | 510451 | India | Registered Office:Plot No. 17, CTS No. 1620, Giriraj Co-operative Housing Society | 411007 | Pune | Maharashtra | 91-20-25640391 |  | accounts@autadegroup.com | www.autadegroup.com
24924 | National Highways Authority Of India | 155597 | Mirya-Hatkhamba & Pali-Sakharpa Four Lane Highway (Package-I of Ratnagiri-Kolhapur section of NH-166) Project | 1445 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
24925 | National Highways Authority Of India | 155597 | Mirza Chauki-Farakka (NH-80) Four Lane Highway Project (Package-I) | 1486 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
24926 | National Highways Authority Of India | 155597 | Miyati Village-MP-Gujarat Border Eight Lane Carriageway Project (Package 25 of Delhi-Mumbai Expressway) | 1606 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24927 | National Highways Authority Of India | 155597 | Miyati Village-MP-Gujarat Border Eight Lane Carriageway Project (Package 25 of Delhi-Mumbai Expressway) | 1606 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24928 | National Highways Authority Of India | 155597 | Mohari-Satai Ghat (NH-934) Four Lane Highway Project (Package-II) | 2082 | Contractor | Shree Girrajjee Infra Heights Pvt. Ltd. | 648186 | India |  | NA
24929 | National Highways Authority Of India | 155597 | Mohol-Wakhri (NH-965) Four Lane Highway Project (Package-I of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1441 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
24930 | National Highways Authority Of India | 155597 | Mohol-Wakhri (NH-965) Four Lane Highway Project (Package-I of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1441 | Contractor | Shri S M Autade Pvt. Ltd. | 510451 | India | Registered Office:Plot No. 17, CTS No. 1620, Giriraj Co-operative Housing Society | 411007 | Pune | Maharashtra | 91-20-25640391 |  | accounts@autadegroup.com | www.autadegroup.com
24931 | National Highways Authority Of India | 155597 | Mokalsar-Jalore (NH-325) Highway Project (Package-II) (Jalore-Barmer-Sirohi) | 1270 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
24932 | National Highways Authority Of India | 155597 | Mokama-Munger (NH-80) Four-Laning Road project | 1567 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24933 | National Highways Authority Of India | 155597 | Moradabad-Jaspur-Kashipur Four/Six Lane Road (NH-734) Project | 1855 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24934 | National Highways Authority Of India | 155597 | Morena-Rairu (Start of Gwalior bypass NS-21/MP) Highway Project | 192 | Consultant | Gherzi Eastern | 81368 | India |  | NA
24935 | National Highways Authority Of India | 155597 | Morena-Rairu (Start of Gwalior bypass NS-21/MP) Highway Project | 192 | Turnkey contractor | Backbone Projects Ltd. | 28349 | India | Registered Office:Dhanvir Near Ekta Jalaram PL 2, ST-9, University Road, | 360005 | Rajkot | Gujarat |  |  | tenderbpl@yahoo.co.in
24936 | National Highways Authority Of India | 155597 | Motihari (Piprakothi)-Raxaul (NH-28A) Two Lane Highway Project | 1698 | Consultant | F P India Project Mgmt. Consultancy Services Pvt. Ltd. | 75309 | India | Registered Office:No. 3/5, Balgovindwadi, New Prabhadevi Road, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-22001530 | 91-22-22017915
24937 | National Highways Authority Of India | 155597 | Motihari (Piprakothi)-Raxaul (NH-28A) Two Lane Highway Project | 1698 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24938 | National Highways Authority Of India | 155597 | Motihari (Piprakothi)-Raxaul (NH-28A) Two Lane Highway Project | 1698 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
24939 | National Highways Authority Of India | 155597 | Mozari Town (NH-53) Four Lane Bypass (Taluka-Tiwasa) | 2009 | Contractor | Dristti Structural Engg. Pvt. Ltd. | 533662 | India |  | NA
24940 | National Highways Authority Of India | 155597 | MP-Gujarat Border near Chhayan village ending after Bridge Over Hadaf River near Hathiyavan village Eight Lane Carriageway Project (Package 26 of Delhi-Mumbai Expressway) | 1818 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
24941 | National Highways Authority Of India | 155597 | MP-Gujarat Border near Chhayan village ending after Bridge Over Hadaf River near Hathiyavan village Eight Lane Carriageway Project (Package 26 of Delhi-Mumbai Expressway) | 1818 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
24942 | National Highways Authority Of India | 155597 | MP-Gujarat Border near Chhayan village ending after Bridge Over Hadaf River near Hathiyavan village Eight Lane Carriageway Project (Package 26 of Delhi-Mumbai Expressway) | 1818 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
24943 | National Highways Authority Of India | 155597 | MP-Gujarat Border near Chhayan village ending after Bridge Over Hadaf River near Hathiyavan village Eight Lane Carriageway Project (Package 26 of Delhi-Mumbai Expressway) | 1818 | Contractor | Atlas Constructions Pvt. Ltd. | 544067 | India | Registered Office:102, Sector-15, | 121007 | Faridabad | Haryana | 91-129-2299112 |  | hr.acplinfra@gmail.com | www.atlasconstructions.in
24944 | National Highways Authority Of India | 155597 | MP/Raj border-Sarai Cholla (NS/6) Highway Project | 190 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24945 | National Highways Authority Of India | 155597 | Mubarakpur-Biaora (NH-12) (New NH-46) Four-Laning Road Project (Package-II of Bhopal-Biaora) | 1241 | Contractor | C D S Infra Projects Ltd. | 393833 | India | Registered Office:B -94, Okhla Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-26389595 | 91-11-41709590 | finance@cdsipl.com | www.cdsipl.com
24946 | National Highways Authority Of India | 155597 | Mubarakpur-Biaora (NH-12) (New NH-46) Four-Laning Road Project (Package-II of Bhopal-Biaora) | 1241 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
24947 | National Highways Authority Of India | 155597 | Muchukota-Bugga (NH-544D) Four Lane Highway Project (Package-2) | 2046 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
24948 | National Highways Authority Of India | 155597 | Mudhiyam Beach-Madhura Bazaar Road Upgradation Project (Bharatmala) | 1723 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24949 | National Highways Authority Of India | 155597 | Mugaiyur-Marakkanam Four Laning section of NH-332 A Road Project (Package-II of Mahabalipuram-Puducherry section) (Bharatmala) | 1780 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24950 | National Highways Authority Of India | 155597 | Mugaiyur-Marakkanam Four Laning section of NH-332 A Road Project (Package-II of Mahabalipuram-Puducherry section) (Bharatmala) | 1780 | Contractor | S P L Infrastructure Pvt. Ltd. | 516118 | India | Registered Office:No. 24 , Crescent Part Street, 1st Floor, T Nagar, | 600018 | Chennai | Tamil Nadu | 91-44-48674770 | 91-44-2364787 | info@splinfra.com | www.splinfra.com
24951 | National Highways Authority Of India | 155597 | Mukarba Chowk-Mall Road (NS-3/DL) Highway Project | 97 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
24952 | National Highways Authority Of India | 155597 | Mukarba Chowk-Mall Road (NS-3/DL) Highway Project | 97 | Turnkey contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24953 | National Highways Authority Of India | 155597 | Mukkola-Kerala/Tamil Nadu Border (Karode) (NH-66) Four Laning Highway Project (Phase 2 of Kazhakuttam-Karode Highway) (Bharatmala) | 1084 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
24954 | National Highways Authority Of India | 155597 | Mukkola-Kerala/Tamil Nadu Border (Karode) (NH-66) Four Laning Highway Project (Phase 2 of Kazhakuttam-Karode Highway) (Bharatmala) | 1084 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
24955 | National Highways Authority Of India | 155597 | Mukkola-Kerala/Tamil Nadu Border (Karode) (NH-66) Four Laning Highway Project (Phase 2 of Kazhakuttam-Karode Highway) (Bharatmala) | 1084 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
24956 | National Highways Authority Of India | 155597 | Muli-Level Carriageway Project (Kanhan-Automotive Square) | 1263 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
24957 | National Highways Authority Of India | 155597 | Muli-Level Carriageway Project (Kanhan-Automotive Square) | 1263 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
24958 | National Highways Authority Of India | 155597 | Muli-Level Carriageway Project (Kanhan-Automotive Square) | 1263 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
24959 | National Highways Authority Of India | 155597 | Mumbai Logistic Park Project | 1386 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24960 | National Highways Authority Of India | 155597 | Mumbai-Nashik Highway Project | 415 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
24961 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
24962 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
24963 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | J Kumar Infraprojects Ltd. | 104004 | India | Corporate Office:CTS No. 448, 448/1, 449, Subhash Road, Vile Parle East, | 400057 | Mumbai | Maharashtra | 91-22-68717900 |  | info@jkumar.com | www.jkumar.com
24964 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
24965 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
24966 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | Patel Infrastructure Ltd. | 372691 | India | Corporate Office:Patcon House, 80 Ft. Road, Near Indira Gandhi Statue, | 388001 | Anand | Gujarat | 91-2692-245801 | 91-2692-245804 | anand@patelinfra.com | www.patelinfra.com
24967 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
24968 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | Agroh Infrastructure Developers Pvt. Ltd. | 389210 | India | Registered Office:Bunglow No. 74, Infront of Govt. Girls School, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-271225 |  | aidplindore@gmail.com | www.agrohinfra.com
24969 | National Highways Authority Of India | 155597 | Mumbai-Vadodara (Baroda) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 48 | Contractor | R K C Infrabuilt (ganjad-talasari) Road Project Pvt. Ltd. | 659617 | India | Registered Office:Building No.1, Aryans Corporate Park, Nr. Ambli Railway Crossing, Shilaj Road, Thaltej, | 380059 | Ahmedabad | Gujarat | 91-79-47544000 |  | caparth@rkc.co.in | www.rkc.co.in
24970 | National Highways Authority Of India | 155597 | Munabao (NH-25)-Sundra-Myajlar-Dhanana-Asutar-Ghotaru-Tanot-Kishangarh (Indo-Pak Boarder) Two/Four Laning Highway Project (BM/4) (Bharatmala) | 1096 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
24971 | National Highways Authority Of India | 155597 | Munambam-Kara Beach Road Widening Project | 1730 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
24972 | National Highways Authority Of India | 155597 | Munger-Mirzachowki (NH-80) Four Lane (Greenfield Corridor) Road Project | 1131 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
24973 | National Highways Authority Of India | 155597 | Munger-Mirzachowki (NH-80) Four Lane (Greenfield Corridor) Road Project | 1131 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
24974 | National Highways Authority Of India | 155597 | Munger-Mirzachowki (NH-80) Four Lane (Greenfield Corridor) Road Project | 1131 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
24975 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
24976 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
24977 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
24978 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Consultant | Nicholas O Dwyer & Co. Ltd. (ireland) | 537257 | Ireland |  | NA
24979 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Contractor | Uttar Pradesh State Bridge Corpn. Ltd. | 255951 | India | Registered Office:Setu Bhawan, 16, Madan Mohan Malviya Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2209702 | 91-522-2209798 | upsbcltd@gmail.com | www.bridgecorporationltd.com
24980 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Contractor | Sam India Builtwell Pvt. Ltd. | 387705 | India | Registered Office:435, Jaagriti Enclave, | 110092 | New Delhi | NCT of Delhi | 91-11-22163389 |  | samindiabuiltwell@yahoo.co.in
24981 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Contractor | Atlas Constructions Pvt. Ltd. | 544067 | India | Registered Office:102, Sector-15, | 121007 | Faridabad | Haryana | 91-129-2299112 |  | hr.acplinfra@gmail.com | www.atlasconstructions.in
24982 | National Highways Authority Of India | 155597 | Muzaffarnagar-Haridwar-Dehradun Highway (Delhi-Dehradun Corridor) Project | 1692 | Contractor | N K C Constructions Pvt. Ltd. | 582448 | India |  | NA
24983 | National Highways Authority Of India | 155597 | Muzaffarnagar-Miranpur (NH-709AD) Four Lane Highway Project (Package 3 of Panipat-Nagina Highway) | 1642 | Consultant | Casta Engineers Pvt. Ltd. | 450301 | India | Registered Office:D-84, Tikona Park Okhla, Ground Floor, Sarita Vihar Kalindi Kunj Rd, Shaheen Bagh, | 110025 | South Delhi | NCT of Delhi | 91-11-26841601 | 91-11-29941602 | info@casta.co.in | www.casta.co.in
24984 | National Highways Authority Of India | 155597 | Muzaffarnagar-Miranpur (NH-709AD) Four Lane Highway Project (Package 3 of Panipat-Nagina Highway) | 1642 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
24985 | National Highways Authority Of India | 155597 | Muzaffarnagar-Miranpur (NH-709AD) Four Lane Highway Project (Package 3 of Panipat-Nagina Highway) | 1642 | Contractor | R C C Developers Ltd. | 348357 | India | Corporate Office:109, Citi Centre, Begum Bridge Road, | 250001 | Meerut | Uttar Pradesh | 91-121-2402928 |  |  | www.tradeindia.com
24986 | National Highways Authority Of India | 155597 | Muzaffarpur-Mehsi (LMNHP-12) Highway Project | 703 | Consultant | C E S C Ltd. | 40112 | India | Corporate Office:2/4, Judges Court Road, Alipore, | 700027 | Kolkata | West Bengal | 91-33-24870000
24987 | National Highways Authority Of India | 155597 | Muzaffarpur-Mehsi (LMNHP-12) Highway Project | 703 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
24988 | National Highways Authority Of India | 155597 | Mydukur-Badvel-Nellore (NH-67) Four Laning Highway Project | 1529 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
24989 | National Highways Authority Of India | 155597 | Mydukur-Badvel-Nellore (NH-67) Four Laning Highway Project | 1529 | Contractor | Rithwik Projects Pvt. Ltd. | 198549 | India | Registered Office:Plot No. 37 & 39, Navodaya Colony, Banjara Hills, Road No. 2, # 8-2-268/K/37 & 39, | 500034 | Hyderabad | Telangana | 91-40-49113333 | 91-40-49113444 | rplhyd@rithwikprojects.com | www.rithwikprojects.com
24990 | National Highways Authority Of India | 155597 | Mydukur-Badvel-Nellore (NH-67) Four Laning Highway Project | 1529 | Contractor | N S P R Constructions (india) Pvt. Ltd. | 408060 | India |  | NA
24991 | National Highways Authority Of India | 155597 | Nagaon Bypass (AS-18) Highway Project | 706 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24992 | National Highways Authority Of India | 155597 | Nagaon Bypass (AS-18) Highway Project | 706 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
24993 | National Highways Authority Of India | 155597 | Nagaon Bypass (AS-18) Highway Project | 706 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
24994 | National Highways Authority Of India | 155597 | Nagaon-Dharmtul (NH-37) Highway Project | 279 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24995 | National Highways Authority Of India | 155597 | Nagaon-Dharmtul (NH-37) Highway Project | 279 | Supervision consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
24996 | National Highways Authority Of India | 155597 | Nagapattinam-Thanjavur (NH-83) Two-Laning Road Project | 545 | Consultant | Wilbur Smith Associates Inc. | 272295 | India | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
24997 | National Highways Authority Of India | 155597 | Nagapattinam-Thanjavur (NH-83) Two-Laning Road Project | 545 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
24998 | National Highways Authority Of India | 155597 | Nagapattinam-Thanjavur (NH-83) Two-Laning Road Project | 545 | Contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
24999 | National Highways Authority Of India | 155597 | Nagapattinam-Thanjavur (NH-83) Two-Laning Road Project | 545 | Contractor | Om Sakthi Constructions | 466079 | India | Registered Office:M 13/11 Navabarath Colony, Kalakshetra Colony, Besant Nagar, | 600090 | Chennai | Tamil Nadu
25000 | National Highways Authority Of India | 155597 | Nagaur (Karwar)-Dangyawas Road (NH-125A) (Phase 2 of Jodhpur Ring Road Project) | 1774 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25001 | National Highways Authority Of India | 155597 | Nagaur (Karwar)-Dangyawas Road (NH-125A) (Phase 2 of Jodhpur Ring Road Project) | 1774 | Contractor | O S S Construction Pvt. Ltd. | 608770 | India |  | NA
25002 | National Highways Authority Of India | 155597 | Nagina-Kashipur (NH-74) Four Lane Highway Project | 1020 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25003 | National Highways Authority Of India | 155597 | Nagina-Kashipur (NH-74) Four Lane Highway Project | 1020 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
25004 | National Highways Authority Of India | 155597 | Nagpur (Ajni) Inter-Modal Station Project | 1316 | Co-promoter | Government Of Maharashtra | 84858 | India | Registered Office:New Administrative Building, Churchgate, | 400020 | Mumbai | Maharashtra | 91-22-22025042 | 91-22-22028594 |  | www.maharashtra.gov.in
25005 | National Highways Authority Of India | 155597 | Nagpur (Ajni) Inter-Modal Station Project | 1316 | Co-promoter | Nagpur Municipal Corpn. | 153562 | India | Head Office:Mahanagar Palika Marg , Civil Lines, | 440001 | Nagpur | Maharashtra | 91-712-2561584 |  | mconagpur@gov.in | www.nmcnagpur.gov.in
25006 | National Highways Authority Of India | 155597 | Nagpur (Ajni) Inter-Modal Station Project | 1316 | Consultant | Sikka Associates Pvt. Ltd. | 517137 | India | Registered Office:12, Batala Road, | 143001 | Amritsar | Punjab |  |  | caamritsar@gmail.com
25007 | National Highways Authority Of India | 155597 | Nagpur (Ajni) Inter-Modal Station Project | 1316 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
25008 | National Highways Authority Of India | 155597 | Nagpur (Wardha Dry Port) Logistic Park Project | 1362 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25009 | National Highways Authority Of India | 155597 | Nagpur-Hyd & Hyd-Bangalore(NS-23/AP) Highway Project | 194 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25010 | National Highways Authority Of India | 155597 | Nagpur-Hyd & Hyd-Bangalore(NS-23/AP) Highway Project | 194 | Contractor | Maharia Re-surfacing Ltd. | 135760 | India |  | NA
25011 | National Highways Authority Of India | 155597 | Nagpur-Hyderabad Highway Project | 344 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25012 | National Highways Authority Of India | 155597 | Nagpur-Hyderabad Highway Project | 344 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
25013 | National Highways Authority Of India | 155597 | Nagpur-Hyderabad-Bangalore Expressway Project | 1205 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
25014 | National Highways Authority Of India | 155597 | Nagpur-Umred (NH-353 D) Four Lane Highway Project | 1685 | Contractor | D P Jain & Co Infrastructure Pvt. Ltd. | 409463 | India | Registered Office:U/6, Himalaya Accord Apartment Opp. Law College Amravati Road, | 440010 | Nagpur | Maharashtra | 91-712-2535357 | 91-712-2560836 | dpjain.company@dpjaingroup.com | www.dpjaingroup.com
25015 | National Highways Authority Of India | 155597 | Nagpur-Waingang-Bhandara (NH-6) Six Lane Highway Project | 1413 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
25016 | National Highways Authority Of India | 155597 | Naidupeta-Turpu Kanupur Six Lane Greenfield Highway Project | 2058 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
25017 | National Highways Authority Of India | 155597 | Naini-Allahabad Yamuna Bridge Project | 47 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25018 | National Highways Authority Of India | 155597 | Naini-Allahabad Yamuna Bridge Project | 47 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25019 | National Highways Authority Of India | 155597 | Naini-Allahabad Yamuna Bridge Project | 47 | Contractor | Hyundai Engg. & Construction Co. | 96226 | Korea Republic (South) | Registered Office:140-2,Kye Dong Chongro-Ku Seoul South Korea | NA
25020 | National Highways Authority Of India | 155597 | Najibabad Four Lane Bypass (NH-119) Project | 1937 | Contractor | Hillways Construction Co. Pvt. Ltd. | 456827 | India | Registered Office:3/64, West Punjabi Bagh, | 110026 | New Delhi | Delhi
25021 | National Highways Authority Of India | 155597 | Najibabad Four Lane Bypass (NH-119) Project | 1937 | Contractor | Velji Ratna Sorathia Infra Pvt. Ltd. | 521163 | India | Registered Office:A-401, Kalpvrux Complex, Gotri Road, | 390021 | Vadodara | Gujarat | 91-265-2320970 |  | mail@vrs.co.in | www.vrs.co.in
25022 | National Highways Authority Of India | 155597 | Najibabad-Kotdwar-Pauri (Meerut-Pauri) Highway Project | 1699 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25023 | National Highways Authority Of India | 155597 | Najibabad-Kotdwar-Pauri (Meerut-Pauri) Highway Project | 1699 | Contractor | Ajay Prakash Associates | 577133 | India |  | NA
25024 | National Highways Authority Of India | 155597 | Nalagampalli Village-AP/Karnataka Border (NH-69) Four Lane Highway Project (Package-II) | 1218 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25025 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | B L A Projects Pvt. Ltd. | 30242 | India | Registered Office:Indicon Viva, 3rd Floor, 53-A, Lella Roy Sarani, Gariahat, | 700019 | Kolkata | West Bengal |  |  | bla_acct@yahoo.co.in
25026 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | Brahmaputra Infrastructure Ltd. | 38163 | India | Registered Office:Brahmaputra House, A-7, Mahipalpur, (N H 8-Mahipalpur Crossing), | 110037 | New Delhi | NCT of Delhi | 91-11-42290200 | 91-11-41687880 | cs@brahmaputragroup.com | www.brahmaputragroup.com
25027 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | Infracon Pvt. Ltd. | 100701 | India | Registered Office:87, Bangur Avenue Block-C | 700055 | Kolkata | West Bengal
25028 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25029 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25030 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | EPC contractor | Dineshchandra R Agrawal Projects Pvt. Ltd. | 353137 | India | Registered Office:401, The Grand Mall, S M Road, Ambawadi, | 380015 | Ahmedabad | Gujarat | 91-79-26309789 |  | info@draipl.com | www.draipl.com
25031 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | Supervision consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25032 | National Highways Authority Of India | 155597 | Nalbari-Bijni Highway (NH-31) Project (East West Corridor) | 283 | Supervision consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25033 | National Highways Authority Of India | 155597 | Nallacheruvu Palli-Yerragudipadu Four/Six Lane Greenfield Expressway Project (Package-5 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2110 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25034 | National Highways Authority Of India | 155597 | Nanasa-Pidgaon (NH-47) Four Lane Highway Project (Package-III of Indore-Harda Economic Corridor) (Sagarmala) | 1654 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25035 | National Highways Authority Of India | 155597 | Nanasa-Pidgaon (NH-47) Four Lane Highway Project (Package-III of Indore-Harda Economic Corridor) (Sagarmala) | 1654 | Contractor | Adani Enterprises Ltd. | 5747 | India | Registered Office:Adani Corporate House, Shantigram, Near Vaishno Devi Circle,S. G. Highway, Khodiyar, | 382421 | Ahmedabad | Gujarat | 91-79-26565555 |  | customercare.irm@adani.com | www.adanienterprises.com
25036 | National Highways Authority Of India | 155597 | Nandi Hills Cross-Devanahalli & Meenakunte-Hebbal Six Lane Highway Project | 230 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25037 | National Highways Authority Of India | 155597 | Nandi Hills Cross-Devanahalli & Meenakunte-Hebbal Six Lane Highway Project | 230 | Turnkey contractor | Afcons Infrastructure Ltd. | 7231 | India | Registered Office:Afcons House, 16, Shah Industrial Estate, Veera Desai Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-67191000 | 91-22-26730047 | rajendran@afcons.com | www.afcons.com
25038 | National Highways Authority Of India | 155597 | Nandigama and Kanchikacherla (NH-65) Six Lane Bypass Project | 1337 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25039 | National Highways Authority Of India | 155597 | Nandigama and Kanchikacherla (NH-65) Six Lane Bypass Project | 1337 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
25040 | National Highways Authority Of India | 155597 | Nangloi Najafgarh Road-Dwarka Sector 24 Six Lane (NH-344M) Road Project (Package 3 of Delhi 3rd Ring Road or UER-2) | 1799 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
25041 | National Highways Authority Of India | 155597 | Nangloi Najafgarh Road-Dwarka Sector 24 Six Lane (NH-344M) Road Project (Package 3 of Delhi 3rd Ring Road or UER-2) | 1799 | Consultant | Aecom India Pvt. Ltd. | 462940 | India | Registered Office:9th Floor, Infinity Tower C, DLF Cyber City, DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-2818000 | 91-124-2816008 | pradeep.khurana@aecom.com | www.aecom.com
25042 | National Highways Authority Of India | 155597 | Nangloi Najafgarh Road-Dwarka Sector 24 Six Lane (NH-344M) Road Project (Package 3 of Delhi 3rd Ring Road or UER-2) | 1799 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25043 | National Highways Authority Of India | 155597 | Nangloi Najafgarh Road-Dwarka Sector 24 Six Lane (NH-344M) Road Project (Package 3 of Delhi 3rd Ring Road or UER-2) | 1799 | Contractor | E5 Infrastructure Pvt. Ltd. | 613495 | India | Registered Office:SCO-105 Pocket A, Sec-14, | 125001 | Hisar | Haryana |  |  |  | www.e5infra.com
25044 | National Highways Authority Of India | 155597 | Nani Bhadol village-Dodka village Eight Lane Access-Controlled Expressway Project (Package 31 of Delhi-Mumbai Expressway) | 1636 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25045 | National Highways Authority Of India | 155597 | Nani Bhadol village-Dodka village Eight Lane Access-Controlled Expressway Project (Package 31 of Delhi-Mumbai Expressway) | 1636 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25046 | National Highways Authority Of India | 155597 | Nani Bhadol village-Dodka village Eight Lane Access-Controlled Expressway Project (Package 31 of Delhi-Mumbai Expressway) | 1636 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
25047 | National Highways Authority Of India | 155597 | Narasannapeta-Ranastalam (NH-16) Six Laning Highway Project (Package-2) | 1253 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25048 | National Highways Authority Of India | 155597 | Narasannapeta-Ranastalam (NH-16) Six Laning Highway Project (Package-2) | 1253 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
25049 | National Highways Authority Of India | 155597 | Narayanmpet-Chandrasekharpuram Six Lane Access Controlled Highway (NH-544G) Project (Package-10 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1975 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25050 | National Highways Authority Of India | 155597 | Narmada Six/Eight Lane Expressway Project | 1546 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25051 | National Highways Authority Of India | 155597 | Narmada Six/Eight Lane Expressway Project | 1546 | Contractor | Bansal Construction Works Pvt. Ltd. | 470219 | India | Corporate Office:3rd Floor, Tawa Cplx, E-5, Bittan Market Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2423736 | 91-755-4224036 | sunilbcw@rediffmail.com
25052 | National Highways Authority Of India | 155597 | Narmada Six/Eight Lane Expressway Project | 1546 | Promoter | Madhya Pradesh Road Devp. Corpn. Ltd. | 352545 | India | Head Office:16-A, Arera Hills, | 462001 | Bhopal | Madhya Pradesh | 91-755-2765196 | 91-755-2572643 | mismprdc@mp.nic.in | www.mprdc.nic.in
25053 | National Highways Authority Of India | 155597 | Narnaul Bypass crossing to Paniyala Mor (NH-148B) (at NH-48 junction) and, Nizampur Link Road & Narnaul Bypass crossing to Pacheri Kalan Project (Bharatmala) | 1607 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25054 | National Highways Authority Of India | 155597 | Nashik (Adgaon) Logistics Park Project | 1358 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25055 | National Highways Authority Of India | 155597 | Natham-Tuvarankurichi section (NH-785E) Four Lane Highway Project (Bharatmala) | 1647 | Contractor | R R Infraprojects Pvt. Ltd. | 605893 | India |  | NA
25056 | National Highways Authority Of India | 155597 | Neeleshwaram-Thaliparambha (NH-66) Six Lanning Highway Project (Bharatmala) | 1802 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25057 | National Highways Authority Of India | 155597 | Nelamangala Junction to Devihalli Highway Project | 606 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25058 | National Highways Authority Of India | 155597 | Nelamangala-Tumkur (New NH-4 & 48) Six Lane Highway Project (Bharatmala) | 1668 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
25059 | National Highways Authority Of India | 155597 | Nelamangala-Tumkur (New NH-4 & 48) Six Lane Highway Project (Bharatmala) | 1668 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
25060 | National Highways Authority Of India | 155597 | Nellore-Chennai(Tada-Chennai) Highway Project | 104 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | India | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
25061 | National Highways Authority Of India | 155597 | Nellore-Chennai(Tada-Chennai) Highway Project | 104 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25062 | National Highways Authority Of India | 155597 | Ner Chowk-Pandoh (NH-21) Four Laning Highway Project (Package-I of Nerchowk-Kullu stretch) | 1033 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25063 | National Highways Authority Of India | 155597 | Neraluru-Thorapalli Agraharam section (NH-844) Four Lane Highway Project (Package 1 of Hosur-Dharmapuri) (Bharatmala) | 1687 | Consultant | Global Infrasolutions Ltd. | 500285 | India | Registered Office:C-57, Basant Vihar Delhi Road, | 247001 | Saharanpur | Uttar Pradesh |  |  | pankaj4361@gmail.com | www.globalinfrasolutions.org
25064 | National Highways Authority Of India | 155597 | Neraluru-Thorapalli Agraharam section (NH-844) Four Lane Highway Project (Package 1 of Hosur-Dharmapuri) (Bharatmala) | 1687 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25065 | National Highways Authority Of India | 155597 | Neraluru-Thorapalli Agraharam section (NH-844) Four Lane Highway Project (Package 1 of Hosur-Dharmapuri) (Bharatmala) | 1687 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
25066 | National Highways Authority Of India | 155597 | Neraluru-Thorapalli Agraharam section (NH-844) Four Lane Highway Project (Package 1 of Hosur-Dharmapuri) (Bharatmala) | 1687 | Contractor | S C C Infrastructure Pvt. Ltd. | 530963 | India |  | NA
25067 | National Highways Authority Of India | 155597 | New Four Lane Bridge across Varsova Creek (NH-48) (Surat-Dahisar Section) Project | 1139 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25068 | National Highways Authority Of India | 155597 | New Four Lane Bridge across Varsova Creek (NH-48) (Surat-Dahisar Section) Project | 1139 | Contractor | Vijay M Mistry Construction Pvt. Ltd. | 265955 | India | Registered Office:Mistry House, 9, Preyas Society, Gulbai Tekra Police Choki, Ambawadi, | 380015 | Ahmedabad | Gujarat | 91-79-26302531 | 91-79-32916260 | vmchouse@gmail.com | www.vmmcl.com
25069 | National Highways Authority Of India | 155597 | New Four Lane Bridge across Varsova Creek (NH-48) (Surat-Dahisar Section) Project | 1139 | Contractor | N G Projects Ltd. | 363366 | India | Registered Office:N G Circle, Mehtapura, Himatnagar, | 383001 | Sabar Kantha | Gujarat | 91-2772-222404 | 91-2772-223950 | ngpl_hmt@rediffmail.com
25070 | National Highways Authority Of India | 155597 | New Link (NH-133B) and Four Lane Bridge across Ganga connecting Sahibganj-Manihari (Katihar) (Package-I) Project | 1071 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25071 | National Highways Authority Of India | 155597 | New Link (NH-133B) and Four Lane Bridge across Ganga connecting Sahibganj-Manihari (Katihar) (Package-I) Project | 1071 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25072 | National Highways Authority Of India | 155597 | New Link (NH-133B) and Four Lane Bridge across Ganga connecting Sahibganj-Manihari (Katihar) (Package-I) Project | 1071 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25073 | National Highways Authority Of India | 155597 | New Mangalore Port Road Connectivity Improvement & Widening Project | 1148 | Contractor | R P P Infra Projects Ltd. | 187329 | India | Registered Office:SF No.454, Raghupathynaiken Palayam, Railway Colony Post, Poondural Road, | 638002 | Erode | Tamil Nadu | 91-424-2284077 | 91-424-2282077 | ipo@rppipl.com | www.rppipl.com
25074 | National Highways Authority Of India | 155597 | NH-148AE Road Tunnel Project (connection to NH-248BB and existingDelhi internal roads) | 1842 | Consultant | S M E C International Pty. Ltd. | 203789 | India | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
25075 | National Highways Authority Of India | 155597 | NH-148AE Road Tunnel Project (connection to NH-248BB and existingDelhi internal roads) | 1842 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
25076 | National Highways Authority Of India | 155597 | NHAI Dwarka 2nd Office Building Project | 846 | Contractor | Unity Infraprojects Ltd. | 258220 | India | Corporate Office:1252, Pushpanjali Apartment, Old Prabhadevi Road, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-66665500 | 91-22-66665599 | info@unityinfra.com | www.unityinfra.com
25077 | National Highways Authority Of India | 155597 | North-East side of Gorakhpur Bypass Four/Six Laning (Maniram (NH-29E)-Jagdispur (NH-28)) Project | 1924 | Contractor | Vijai Construction (india) Pvt. Ltd. | 530179 | India |  | NA
25078 | National Highways Authority Of India | 155597 | Northern Peripheral Road to Delhi-Dehradun National Highway (NH-709B) in Loni Link Road Project | 2080 | Co-promoter | Ghaziabad Development Authority | 332275 | India | Registered Office:Vikas Peth, Ghaziabad, Uttar Pradesh | NA |  | Uttar Pradesh | 91-120-2793073 | 91-120-2791078 |  | www.gdaghaziabad.com
25079 | National Highways Authority Of India | 155597 | Obedullaganj-Betul (NH-69) Four-Laning Highway Project | 1296 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25080 | National Highways Authority Of India | 155597 | Obedullaganj-Betul (NH-69) Four-Laning Highway Project | 1296 | Contractor | Longjian Road & Bridge Ltd. | 389090 | India | Registered Office:D-15, F5 & 6, New Delhi South Extention-II, | 110049 | New Delhi | NCT of Delhi |  |  | longjian@rediffmail.com
25081 | National Highways Authority Of India | 155597 | Obedullaganj-Betul (NH-69) Four-Laning Highway Project | 1296 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25082 | National Highways Authority Of India | 155597 | Ochira-Thiruvananthapuram (Kazhakuttam) (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 543 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25083 | National Highways Authority Of India | 155597 | Ochira-Thiruvananthapuram (Kazhakuttam) (NH-66) Six Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 543 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
25084 | National Highways Authority Of India | 155597 | Oddanchathram (NH-83) Four Lane Bypass Project | 1300 | Contractor | I Vetrivel | 456252 | India |  | NA
25085 | National Highways Authority Of India | 155597 | Oddanchathram (NH-83) Four Lane Bypass Project | 1300 | Contractor | Om Sakthi Constructions | 466079 | India | Registered Office:M 13/11 Navabarath Colony, Kalakshetra Colony, Besant Nagar, | 600090 | Chennai | Tamil Nadu
25086 | National Highways Authority Of India | 155597 | Orai to Jhansi (NH-25) Highway Project | 314 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
25087 | National Highways Authority Of India | 155597 | Orai to Jhansi (NH-25) Highway Project | 314 | Contractor | Sunway Construction India Pvt. Ltd. | 282606 | India | Registered Office:Mrurdeshwar Bhavan, 604/B, Gokul Road, | 580030 | Hubli | Karnataka
25088 | National Highways Authority Of India | 155597 | Orai to Jhansi (NH-25) Highway Project | 314 | Financial collaborator | Asian Development Bank | 22786 | India | Registered Office:4, San Martin Marg, Chanakyapuri, | 110021 | South West Delhi | NCT of Delhi | 91-11-24107200 | 91-11-26870945 |  | www.adb.org
25089 | National Highways Authority Of India | 155597 | Orai-Bhognipur-Bara Highway Project | 345 | Consultant | Wilbur Smith Associates Inc. | 272295 | India | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
25090 | National Highways Authority Of India | 155597 | Orai-Bhognipur-Bara Highway Project | 345 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25091 | National Highways Authority Of India | 155597 | Orai-Bhognipur-Bara Highway Project | 345 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
25092 | National Highways Authority Of India | 155597 | Ormanjhi-Gola (NH-320B) Four Lane Greenfield Highway Project (Package-II) | 1991 | Contractor | Barbrik Project Ltd. | 380698 | India | Corporate Office:15/198, Bramha Road, Ambikapur, | 497001 | Surguja | Chhattisgarh | 91-7774-220375 | 91-7774-220475 | apur@barbrik.in
25093 | National Highways Authority Of India | 155597 | Outer Ring Road-Eastern Peripheral Expressway (EPE) Link Road Project | 2081 | Co-promoter | Ghaziabad Development Authority | 332275 | India | Registered Office:Vikas Peth, Ghaziabad, Uttar Pradesh | NA |  | Uttar Pradesh | 91-120-2793073 | 91-120-2791078 |  | www.gdaghaziabad.com
25094 | National Highways Authority Of India | 155597 | Package-1 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1588 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25095 | National Highways Authority Of India | 155597 | Package-1 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1588 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25096 | National Highways Authority Of India | 155597 | Package-1 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1588 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25097 | National Highways Authority Of India | 155597 | Package-1 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1588 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25098 | National Highways Authority Of India | 155597 | Package-1 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1793 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25099 | National Highways Authority Of India | 155597 | Package-1 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1793 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25100 | National Highways Authority Of India | 155597 | Package-1 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1793 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
25101 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25102 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25103 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25104 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25105 | National Highways Authority Of India | 155597 | Package-1 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1579 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25106 | National Highways Authority Of India | 155597 | Package-1 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1589 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25107 | National Highways Authority Of India | 155597 | Package-1 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1589 | Contractor | Krishna Construction Pvt. Ltd. | 123264 | India | Registered Office:Shop No. 1, Basera Apartment, Upnagar, | 422007 | Nashik | Maharashtra
25108 | National Highways Authority Of India | 155597 | Package-1 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1589 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25109 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25110 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25111 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25112 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Contractor | Varindera Constructions Ltd. | 358589 | India | Corporate Office:Plot No.65, Sector 18, Vill. Sarhaul Opp. Hipa (Haryana Institute Of Public Administration), | 122001 | Gurugram | Haryana | 91-124-4046363 |  | info@vclgroup.in | www.vclgroup.in
25113 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
25114 | National Highways Authority Of India | 155597 | Package-2 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1575 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25115 | National Highways Authority Of India | 155597 | Package-2 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1795 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25116 | National Highways Authority Of India | 155597 | Package-2 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1795 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25117 | National Highways Authority Of India | 155597 | Package-2 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1795 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25118 | National Highways Authority Of India | 155597 | Package-2 of Rajasthan-Gujarat Border (Sanchore) to Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1795 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
25119 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25120 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25121 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25122 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25123 | National Highways Authority Of India | 155597 | Package-2 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1581 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25124 | National Highways Authority Of India | 155597 | Package-2 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1594 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25125 | National Highways Authority Of India | 155597 | Package-2 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1594 | Contractor | Krishna Construction Pvt. Ltd. | 123264 | India | Registered Office:Shop No. 1, Basera Apartment, Upnagar, | 422007 | Nashik | Maharashtra
25126 | National Highways Authority Of India | 155597 | Package-2 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1594 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25127 | National Highways Authority Of India | 155597 | Package-3 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1574 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25128 | National Highways Authority Of India | 155597 | Package-3 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1574 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25129 | National Highways Authority Of India | 155597 | Package-3 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1574 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25130 | National Highways Authority Of India | 155597 | Package-3 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1574 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25131 | National Highways Authority Of India | 155597 | Package-3 of Rajasthan-Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1792 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25132 | National Highways Authority Of India | 155597 | Package-3 of Rajasthan-Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1792 | Contractor | K R C Infraprojects Pvt. Ltd. | 514791 | India | Registered Office:101, K R Chambers, Rasulpur Road, | 121102 | Palwal | Haryana | 91-1275-247999 |  | info@krcinfraprojects.com | www.krcinfraprojects.com
25133 | National Highways Authority Of India | 155597 | Package-3 of Rajasthan-Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1792 | Contractor | S K S Infra Projects Pvt. Ltd. | 595556 | India | Registered Office:1/115-A/2, Babu Gulab Rai Marg Delhi Gate, | 282002 | Agra | Uttar Pradesh |  |  | sksharma.skcc@gmail.com
25134 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25135 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25136 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25137 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25138 | National Highways Authority Of India | 155597 | Package-3 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1580 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25139 | National Highways Authority Of India | 155597 | Package-3 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1595 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25140 | National Highways Authority Of India | 155597 | Package-3 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1595 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25141 | National Highways Authority Of India | 155597 | Package-3 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1595 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25142 | National Highways Authority Of India | 155597 | Package-4 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1577 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25143 | National Highways Authority Of India | 155597 | Package-4 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1577 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25144 | National Highways Authority Of India | 155597 | Package-4 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1577 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
25145 | National Highways Authority Of India | 155597 | Package-4 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1577 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25146 | National Highways Authority Of India | 155597 | Package-4 of Rajasthan/Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1794 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25147 | National Highways Authority Of India | 155597 | Package-4 of Rajasthan/Gujarat Border (Sanchore)-Santalpur (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1794 | Contractor | C D S Infra Projects Ltd. | 393833 | India | Registered Office:B -94, Okhla Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-26389595 | 91-11-41709590 | finance@cdsipl.com | www.cdsipl.com
25148 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25149 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25150 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25151 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25152 | National Highways Authority Of India | 155597 | Package-4 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1582 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25153 | National Highways Authority Of India | 155597 | Package-4 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1596 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25154 | National Highways Authority Of India | 155597 | Package-4 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1596 | Contractor | Krishna Construction Pvt. Ltd. | 123264 | India | Registered Office:Shop No. 1, Basera Apartment, Upnagar, | 422007 | Nashik | Maharashtra
25155 | National Highways Authority Of India | 155597 | Package-4 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1596 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25156 | National Highways Authority Of India | 155597 | Package-5 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1576 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25157 | National Highways Authority Of India | 155597 | Package-5 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1576 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25158 | National Highways Authority Of India | 155597 | Package-5 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1576 | Contractor | N G Projects Ltd. | 363366 | India | Registered Office:N G Circle, Mehtapura, Himatnagar, | 383001 | Sabar Kantha | Gujarat | 91-2772-222404 | 91-2772-223950 | ngpl_hmt@rediffmail.com
25159 | National Highways Authority Of India | 155597 | Package-5 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1576 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25160 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25161 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25162 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25163 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25164 | National Highways Authority Of India | 155597 | Package-5 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1585 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25165 | National Highways Authority Of India | 155597 | Package-5 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1597 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25166 | National Highways Authority Of India | 155597 | Package-5 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1597 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
25167 | National Highways Authority Of India | 155597 | Package-5 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1597 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25168 | National Highways Authority Of India | 155597 | Package-6 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1578 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25169 | National Highways Authority Of India | 155597 | Package-6 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1578 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25170 | National Highways Authority Of India | 155597 | Package-6 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1578 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
25171 | National Highways Authority Of India | 155597 | Package-6 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1578 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25172 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25173 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Consultant | Pentacle Consultants (i) Pvt. Ltd. | 594978 | India | Registered Office:B-406, Pranik Chambers Owners Co-op Premise Soc Ltd., Sakivihar Road, Sakinaka Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-66952533 |  | vishal.pancholi@pentacleconsultants.com | www.pentacleconsultants.com
25174 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Consultant | Jhunjhunu Engineers Pvt. Ltd. | 594979 | India | Registered Office:48-C, Arpit Nagar, Gandhi Path, Vaishali Nagar, | 302021 | Jaipur | Rajasthan | 91-141-2440400 |  | jhunjhunu786@gmail.com | www.jepl.net.in
25175 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25176 | National Highways Authority Of India | 155597 | Package-6 of Rasisar-Deogarh (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1586 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25177 | National Highways Authority Of India | 155597 | Package-6 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1590 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25178 | National Highways Authority Of India | 155597 | Package-6 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1590 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25179 | National Highways Authority Of India | 155597 | Package-6 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1590 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25180 | National Highways Authority Of India | 155597 | Package-7 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1583 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25181 | National Highways Authority Of India | 155597 | Package-7 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1583 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25182 | National Highways Authority Of India | 155597 | Package-7 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1583 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
25183 | National Highways Authority Of India | 155597 | Package-7 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1583 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25184 | National Highways Authority Of India | 155597 | Package-7 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1591 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25185 | National Highways Authority Of India | 155597 | Package-7 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1591 | Contractor | Rajendra Singh Bhamboo Infra Pvt. Ltd. | 475859 | India | Registered Office:KH-7, Mannagar Oppo Officers Club, | 333001 | Jhunjhunun | Rajasthan |  |  | Msd584@yahoo.co.in
25186 | National Highways Authority Of India | 155597 | Package-7 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1591 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25187 | National Highways Authority Of India | 155597 | Package-8 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1584 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25188 | National Highways Authority Of India | 155597 | Package-8 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1584 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25189 | National Highways Authority Of India | 155597 | Package-8 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1584 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
25190 | National Highways Authority Of India | 155597 | Package-8 of Deogarh (Dhandhaniya)-Rajasthan/Gujarat Border (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1584 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25191 | National Highways Authority Of India | 155597 | Package-8 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1592 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25192 | National Highways Authority Of India | 155597 | Package-8 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1592 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25193 | National Highways Authority Of India | 155597 | Package-8 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1592 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
25194 | National Highways Authority Of India | 155597 | Package-9 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1593 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25195 | National Highways Authority Of India | 155597 | Package-9 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1593 | Contractor | R C C Developers Ltd. | 348357 | India | Corporate Office:109, Citi Centre, Begum Bridge Road, | 250001 | Meerut | Uttar Pradesh | 91-121-2402928 |  |  | www.tradeindia.com
25196 | National Highways Authority Of India | 155597 | Package-9 of Sangariya (Chautala)-Rasisar (NH-754K) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) (Bharatmala) | 1593 | Contractor | Raj Shyama Constructions Pvt. Ltd. | 389920 | India | Registered Office:49 F/F Ring Road, Lajpatnagar, | 110024 | New Delhi | NCT of Delhi |  |  | rajshyama.gzb@gmail.com
25197 | National Highways Authority Of India | 155597 | Padalur-Trichy (Pkg VI-C) Highway Project | 497 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
25198 | National Highways Authority Of India | 155597 | Padinajrekar-Ottumpuram Road Upgradation Project | 1725 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25199 | National Highways Authority Of India | 155597 | Paijarwadi-Kerle & Kolhapur Bypass (Kerle-Chokak) Four Lane Highway (Package-III of Ratnagiri-Kolhapur section of NH-166) Project | 1447 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
25200 | National Highways Authority Of India | 155597 | Paijarwadi-Kerle & Kolhapur Bypass (Kerle-Chokak) Four Lane Highway (Package-III of Ratnagiri-Kolhapur section of NH-166) Project | 1447 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25201 | National Highways Authority Of India | 155597 | Palanpur-Dessa(EW-11/GJ) Highway Project | 196 | Consultant | F P India Project Mgmt. Consultancy Services Pvt. Ltd. | 75309 | India | Registered Office:No. 3/5, Balgovindwadi, New Prabhadevi Road, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-22001530 | 91-22-22017915
25202 | National Highways Authority Of India | 155597 | Palanpur-Swaroopganj Highway Project | 424 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25203 | National Highways Authority Of India | 155597 | Palanpur-Swaroopganj Highway Project | 424 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25204 | National Highways Authority Of India | 155597 | Palanpur-Swaroopganj Highway Project | 424 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25205 | National Highways Authority Of India | 155597 | Palia-Shahjahanpur (NH-731) Two/Four Lane Highway Project (Package-I of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2055 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
25206 | National Highways Authority Of India | 155597 | Palia-Shahjahanpur (NH-731) Two/Four Lane Highway Project (Package-I of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2055 | Contractor | Rajinder Infrastructure Pvt. Ltd. | 548932 | India |  | NA
25207 | National Highways Authority Of India | 155597 | Palia-Shahjahanpur (NH-731) Two/Four Lane Highway Project (Package-I of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2055 | Contractor | S R S C Infra Pvt. Ltd. | 611760 | India |  | NA
25208 | National Highways Authority Of India | 155597 | Palma-Gumla (Section of NH-23) Four Lane Highway Project | 1440 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
25209 | National Highways Authority Of India | 155597 | Palma-Gumla (Section of NH-23) Four Lane Highway Project | 1440 | Contractor | Bharat Road Network Ltd. | 500989 | India | Registered Office:Plot X1-2 & 3, Ground Floor, Block EP, Sector V, Salt Lake City, | 700091 | Kolkata | West Bengal | 91-33-66023609 |  | cs@brnl.in | www.brnl.in
25210 | National Highways Authority Of India | 155597 | Palsit-Dankuni (NH-19) Six Lane Highway Project (Bharatmala) | 1831 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25211 | National Highways Authority Of India | 155597 | Palsit-Dankuni(Durgapur Expressway) Highway Project | 193 | Contractor | Gamunda Berhad | 316076 | Malaysia | Registered Office:Malaysia | NA
25212 | National Highways Authority Of India | 155597 | Palsit-Dankuni(Durgapur Expressway) Highway Project | 193 | Contractor | W C T Engineering Bhd | 319497 | Malaysia | Registered Office:Malaysia | NA
25213 | National Highways Authority Of India | 155597 | Panagarh-Haldia Expressway Project | 1729 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25214 | National Highways Authority Of India | 155597 | Panaji Logistics Park Project | 1353 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25215 | National Highways Authority Of India | 155597 | Panchi Gujran-Kamaspur (Delhi-Haryana Section NS-17/HR) Six Lane Highway Project | 187 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25216 | National Highways Authority Of India | 155597 | Panchi Gujran-Kamaspur (Delhi-Haryana Section NS-17/HR) Six Lane Highway Project | 187 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
25217 | National Highways Authority Of India | 155597 | Pandoh-Bata (Tunnel) (NH-21) Highway Project (Package-II of Nerchowk-Kullu stretch) | 1044 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25218 | National Highways Authority Of India | 155597 | Pandoh-Bata (Tunnel) (NH-21) Highway Project (Package-II of Nerchowk-Kullu stretch) | 1044 | Contractor | Shapoorji Pallonji Pandoh Takoli Highway Pvt. Ltd. | 576634 | India | Registered Office:Shapoorji Pallonji Centre 41/44, Minoo Desai Marg, Colaba, | 400005 | Mumbai | Maharashtra | 91-22-67490000 | 91-22-66338176 | secretarial.infra@shapoorji.com | www.shapoorji.in
25219 | National Highways Authority Of India | 155597 | Pangare-Warangaphata (NH-161) Four Lane Highway project (Package-IV) | 1843 | Consultant | Marc Technocrats Pvt. Ltd. | 567218 | India | Registered Office:657, 1st Floor, Surya House, Above Corporation Bank, Main Rohtak Road, Mundka, | 110041 | New Delhi | NCT of Delhi |  |  | mct.rtk@gmail.com | www.mtplonline.com
25220 | National Highways Authority Of India | 155597 | Pangare-Warangaphata (NH-161) Four Lane Highway project (Package-IV) | 1843 | Contractor | Rajendra Singh Bhamboo Infra Pvt. Ltd. | 475859 | India | Registered Office:KH-7, Mannagar Oppo Officers Club, | 333001 | Jhunjhunun | Rajasthan |  |  | Msd584@yahoo.co.in
25221 | National Highways Authority Of India | 155597 | Panipat to Panchi Gujran Six Laning Highway Project | 310 | Consultant | E M A Unihorn (india) Pvt. Ltd. | 292893 | India | Registered Office:No. 2/31, Kalkaji Extension, | 110019 | New Delhi | Delhi
25222 | National Highways Authority Of India | 155597 | Panipat to Panchi Gujran Six Laning Highway Project | 310 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
25223 | National Highways Authority Of India | 155597 | Panipat-Shamli (NH-709AD) Four Lane Highway Project (Package 1 of Panipat-Nagina Highway) | 1540 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25224 | National Highways Authority Of India | 155597 | Panitanki-Bagdogra-Fulbari (AH-2) Road Project | 988 | Co-promoter | West Bengal Public Works Department | 437735 | India | Registered Office:Main Block, 2nd Floor, Writers, Buildings, | 700001 | Kolkata | West Bengal | 91-33-22143161 | 91-33-22144788 |  | www.pwdwb.in
25225 | National Highways Authority Of India | 155597 | Panitanki-Bagdogra-Fulbari (AH-2) Road Project | 988 | Financial collaborator | Asian Development Bank | 22786 | India | Registered Office:4, San Martin Marg, Chanakyapuri, | 110021 | South West Delhi | NCT of Delhi | 91-11-24107200 | 91-11-26870945 |  | www.adb.org
25226 | National Highways Authority Of India | 155597 | Panvel-Indapur (NH-17) Four Laning Highway Project (Mumbai-Goa NH 66 Highway) (Package-1) | 1553 | Consultant | F P India Project Mgmt. Consultancy Services Pvt. Ltd. | 75309 | India | Registered Office:No. 3/5, Balgovindwadi, New Prabhadevi Road, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-22001530 | 91-22-22017915
25227 | National Highways Authority Of India | 155597 | Panvel-Indapur (NH-17) Four Laning Highway Project (Mumbai-Goa NH 66 Highway) (Package-1) | 1553 | Contractor | China State Construction Engg. (hong Kong) Ltd. | 369281 | China |  | NA
25228 | National Highways Authority Of India | 155597 | Panvel-Indapur (NH-17) Four Laning Highway Project (Mumbai-Goa NH 66 Highway) (Package-1) | 1553 | Contractor | Mahavir Roads & Infrastructure Pvt. Ltd. | 386018 | India | Registered Office:5, Basement, Vasant Industrial Estate, Saki Vihar Road, Saki Naka, Andheri (East), | 400072 | Mumbai | Maharashtra | 91-22-28572290 |  | mripl07@rediffmail.com
25229 | National Highways Authority Of India | 155597 | Paonta Sahib-Ballupur Chowk (Dehradun) Four Lane (NH-72) Highway Project | 1934 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
25230 | National Highways Authority Of India | 155597 | Paonta Sahib-Ballupur Chowk (Dehradun) Four Lane (NH-72) Highway Project | 1934 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
25231 | National Highways Authority Of India | 155597 | Paradip Port Road Project | 207 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25232 | National Highways Authority Of India | 155597 | Paradip Port Road Project | 207 | EPC contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25233 | National Highways Authority Of India | 155597 | Paramakudi-Ramanathapuram (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 1280 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
25234 | National Highways Authority Of India | 155597 | Paramakudi-Ramanathapuram (NH-49) Four Laning Highway Project (Madurai-Ramanathapuram Highway) | 1280 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25235 | National Highways Authority Of India | 155597 | Pararia-Mohania Four Lane Highway (NH-319) Project (Package 2 of Mohania-Arrah) (Bharatmala) | 1835 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
25236 | National Highways Authority Of India | 155597 | Paravoor-Kottunkulangara (NH-66) Six Lane Highway Project (Bharatmala) | 1881 | Contractor | Sew Infrastructure Ltd. | 217307 | India | Head Office:6-3-871, Snehalata, 1st Floor, Greenlands Road, Begumpet, | 500016 | Hyderabad | Telangana | 91-40-23402153 | 91-40-23405016 | mail@sewconstructions.com | www.sewinfrastructure.com
25237 | National Highways Authority Of India | 155597 | Pardi Flyover (NH-6) (on Urban Link to Nagpur-Raipur) Project | 995 | Consultant | Creations Engineers Pvt. Ltd. | 581264 | India |  | NA
25238 | National Highways Authority Of India | 155597 | Pardi Flyover (NH-6) (on Urban Link to Nagpur-Raipur) Project | 995 | Contractor | Gannon Dunkerley & Co. Ltd. | 78966 | India | Registered Office:New Excelsior Building, 3rd Floor, A K Nayak Marg, Fort, | 400001 | Mumbai | Maharashtra | 91-22-22051231 | 91-22-22051232 | gdho1@mtnl.net.in | www.gannondunkerley.com
25239 | National Highways Authority Of India | 155597 | Pardi Flyover (NH-6) (on Urban Link to Nagpur-Raipur) Project | 995 | Contractor | S M S Ltd. | 218106 | India | Corporate Office:20, I T Park, Parsodi, | 440022 | Nagpur | Maharashtra | 91-712-6665000 | 91-712-6665100 | info@smsl.co.in | www.smsl.co.in
25240 | National Highways Authority Of India | 155597 | Pardi Flyover (NH-6) (on Urban Link to Nagpur-Raipur) Project | 995 | Promoter | Nagpur Municipal Corpn. | 153562 | India | Head Office:Mahanagar Palika Marg , Civil Lines, | 440001 | Nagpur | Maharashtra | 91-712-2561584 |  | mconagpur@gov.in | www.nmcnagpur.gov.in
25241 | National Highways Authority Of India | 155597 | Parwanoo-Solan (NH-5) (Parwanoo-Shimla Package-I) Two/Four Lane Highway Project | 662 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
25242 | National Highways Authority Of India | 155597 | Parwanoo-Solan (NH-5) (Parwanoo-Shimla Package-I) Two/Four Lane Highway Project | 662 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25243 | National Highways Authority Of India | 155597 | Parwanoo-Solan (NH-5) (Parwanoo-Shimla Package-I) Two/Four Lane Highway Project | 662 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25244 | National Highways Authority Of India | 155597 | Patan (Near Rajpur)-Gojariya (NH-68) Four/Six Lane Highway Project (Package-II) | 2004 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25245 | National Highways Authority Of India | 155597 | Patan (Near Rajpur)-Gojariya (NH-68) Four/Six Lane Highway Project (Package-II) | 2004 | Consultant | Arkitechno Consultants (india) Pvt. Ltd. | 609224 | India | Registered Office:N - 3/91, Village Nayapally, | 751015 | Bhubaneswar | Odisha | 91-674-2554205 |  | accounts@arkitechno.com | www.arkitechno.com
25246 | National Highways Authority Of India | 155597 | Patan (Near Rajpur)-Gojariya (NH-68) Four/Six Lane Highway Project (Package-II) | 2004 | Contractor | Rachana Infrastructure Ltd. | 341132 | India | Registered Office:404, 405, 4th Flr, Angel Complex, Nr. Income Tax Rly. Crossing, Nr. Oasis Hotel, Navrangpura, | 380009 | Ahmedabad | Gujarat | 91-79-26560327 | 91-79-26466424 | rachnainfra404@gmail.com | www.rachanainfra.com
25247 | National Highways Authority Of India | 155597 | Patan (Near Rajpur)-Gojariya (NH-68) Four/Six Lane Highway Project (Package-II) | 2004 | Contractor | Wagad Infraprojects Pvt. Ltd. | 482842 | India | Corporate Office:431-432, Tower-A, Atlantis K-10, Nr. Genda Circle, | 390007 | Vadodara | Gujarat | 91-265-2341132 |  | corporate@wagadinfra.com | www.wagadinfra.com
25248 | National Highways Authority Of India | 155597 | Patel Chowk (NH-33) Six Lane Underpass Project | 2101 | Contractor | Anand Construction | 583989 | India |  | NA
25249 | National Highways Authority Of India | 155597 | Pathankot-Bhogpur (NH-1A) Highway Project | 307 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
25250 | National Highways Authority Of India | 155597 | Pathankot-Bhogpur (NH-1A) Highway Project | 307 | Contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
25251 | National Highways Authority Of India | 155597 | Pathankot-Delhi(Ambala-Delhi) Highway Project | 70 | Contractor | Unitech Ltd. | 257777 | India | Corporate Office:1306-1308, 13 th Floor, Tower B, Signature Towers, South City-1, | 122007 | Gurgaon | Haryana | 91-124-4726860 | 91-124-2383332 | share.dept@unitechgroup.com | www.unitechgroup.com
25252 | National Highways Authority Of India | 155597 | Pathankot-Jammu & Kashmir Border (NS-36/J&K) Highways project | 739 | Contractor | M Venkata Rao Infra Projects Pvt. Ltd. | 384435 | India | Registered Office:D. No. 48-19-6, 2nd Floor M V R Complex, Srinagar, | 530016 | Visakhapatnam | Andhra Pradesh |  |  | mvr999act@yahoo.com
25253 | National Highways Authority Of India | 155597 | Pathankot-Mandi (NH-154) Four Laning Highway Project | 1313 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25254 | National Highways Authority Of India | 155597 | Pathankot-Mandi (NH-154) Four Laning Highway Project | 1313 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25255 | National Highways Authority Of India | 155597 | Pathankot-Mandi (NH-154) Four Laning Highway Project | 1313 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25256 | National Highways Authority Of India | 155597 | Pathrapali-Kathghora (NH-130) Four Lane Highway Project (Package 2 of Bilaspur-Kathghora section) (Bharatmala) | 1783 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25257 | National Highways Authority Of India | 155597 | Patiala Logistics Park Project | 1385 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25258 | National Highways Authority Of India | 155597 | Patiala-Bathinda (NH-64) Four-Laning Highway Project | 1014 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
25259 | National Highways Authority Of India | 155597 | Patna Four/Six Laning Ring Road Project | 1132 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
25260 | National Highways Authority Of India | 155597 | Patna Four/Six Laning Ring Road Project | 1132 | Contractor | Singla Constructions Ltd. | 501631 | India |  | NA
25261 | National Highways Authority Of India | 155597 | Patna Four/Six Laning Ring Road Project | 1132 | Contractor | J S P Projects Pvt. Ltd. | 549010 | India |  | NA
25262 | National Highways Authority Of India | 155597 | Patna-Gaya-Dobhi (NH-83) Four Lane Highway Project | 603 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25263 | National Highways Authority Of India | 155597 | Patna-Gaya-Dobhi (NH-83) Four Lane Highway Project | 603 | Contractor | I L & F S Engg. & Construction Co. Ltd. | 142276 | India | Registered Office:Door No.8-2-120/113/3/4F, Sanali Info Park, Cyber Towers, Road No.2, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-40409333 | 91-40-40409444 | cs@ilfsengg.com | www.ilfsengg.com
25264 | National Highways Authority Of India | 155597 | Patna-Gaya-Dobhi (NH-83) Four Lane Highway Project | 603 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
25265 | National Highways Authority Of India | 155597 | Patna-Koilwar (NH-30) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1010 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
25266 | National Highways Authority Of India | 155597 | Patna-Koilwar (NH-30) Four-Laning Highway Project (Section of Patna-Buxar Highway) | 1010 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
25267 | National Highways Authority Of India | 155597 | Patradevi-Pollem Four/Six Laning Road Project | 809 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
25268 | National Highways Authority Of India | 155597 | Payikulangara to Alappuzha Byass Road Project (Port Connectivity) | 1745 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25269 | National Highways Authority Of India | 155597 | Payyambalam-Azhikkal Road Widening Project (Bharatmala) | 1715 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25270 | National Highways Authority Of India | 155597 | Penchalakona-Yerpedu (NH-565) Two Lane Road Project | 971 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25271 | National Highways Authority Of India | 155597 | Phagwara Junction (NH-1) Flyover Project | 960 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25272 | National Highways Authority Of India | 155597 | Phagwara Junction (NH-1) Flyover Project | 960 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
25273 | National Highways Authority Of India | 155597 | Phagwara-Hoshiarpur (NH-344B) Four Lane Highway Project | 3011 | Contractor | Prakash Asphaltings & Toll Highways (india) Ltd. | 178735 | India | Registered Office:76, Mall Road, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-275001 | 91-7324-400318 | path@pathltd.com | www.pathltd.com
25274 | National Highways Authority Of India | 155597 | Phalodi-Jaisalmer (NH-15) Two/Four Lane Highway Project | 1030 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25275 | National Highways Authority Of India | 155597 | Phalodi-Jaisalmer (NH-15) Two/Four Lane Highway Project | 1030 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25276 | National Highways Authority Of India | 155597 | Phalodi-Jaisalmer (NH-15) Two/Four Lane Highway Project | 1030 | Contractor | Corsan Corviam Constructions Sa | 439998 | India |  | NA
25277 | National Highways Authority Of India | 155597 | Pimpalgaon-Nashik-Gonde (NH-3,60&160) Six-Laning Highway Project | 1396 | Consultant | Sheladia Associates Inc. | 287104 | India | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
25278 | National Highways Authority Of India | 155597 | Pimpalgaon-Nashik-Gonde (NH-3,60&160) Six-Laning Highway Project | 1396 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25279 | National Highways Authority Of India | 155597 | Pimpalgaon-Nashik-Gonde (NH-3,60&160) Six-Laning Highway Project | 1396 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25280 | National Highways Authority Of India | 155597 | Pimpalkutti Two Lane ROB (on Nagpur-Hyderabad NH-44 & NH-7) Project | 1301 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
25281 | National Highways Authority Of India | 155597 | Pimpalkutti Two Lane ROB (on Nagpur-Hyderabad NH-44 & NH-7) Project | 1301 | Contractor | Associated Engineering Enterprises | 561979 | India | Registered Office:H Block, Sector 9, | 201301 | Noida | Uttar Pradesh |  |  |  | www.associatedengineers.ind.in
25282 | National Highways Authority Of India | 155597 | Pindari-Rawalganj Bypass (NH-31) Four Lane Greenfield Highway Project (Package-III of Ghazipur-Ballia-UP/Bihar State Border) | 2104 | Co-promoter | Uttar Pradesh Expressways Indl. Devp. Authority | 430585 | India | Registered Office:C-13, 2nd Floor, Paryatan Bhawan, Vipin Khand, Gomti Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-2307542 | 91-522-4013560 | ceo.eida_up@gov.in, | https://upeida.up.gov.in/
25283 | National Highways Authority Of India | 155597 | Pindari-Rawalganj Bypass (NH-31) Four Lane Greenfield Highway Project (Package-III of Ghazipur-Ballia-UP/Bihar State Border) | 2104 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25284 | National Highways Authority Of India | 155597 | Pinjore Bypass connecting Surajpur-Baddi Project | 856 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
25285 | National Highways Authority Of India | 155597 | Pinjore Bypass-Baddi-Nalagarh (NH-21A) Four Laning Highway Project | 1609 | Contractor | Patel Infrastructure Ltd. | 372691 | India | Corporate Office:Patcon House, 80 Ft. Road, Near Indira Gandhi Statue, | 388001 | Anand | Gujarat | 91-2692-245801 | 91-2692-245804 | anand@patelinfra.com | www.patelinfra.com
25286 | National Highways Authority Of India | 155597 | Pirpaiti-Gandhigram (NH-80 & 133) Four Lane Highway Project | 1334 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25287 | National Highways Authority Of India | 155597 | Piska More-Palma (NH-23) Four Laning Highway Project | 1228 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25288 | National Highways Authority Of India | 155597 | Piska More-Palma (NH-23) Four Laning Highway Project | 1228 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
25289 | National Highways Authority Of India | 155597 | Polavaram-Marripudi (NH-544G) Six Lane Greenfield Expressway Project (Package-12 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2113 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25290 | National Highways Authority Of India | 155597 | Pondavakkam-Kannigaipair (NH-716B) Six Lane Road Project (Package-4 of Chittoor-Thatchur Expressway) | 2032 | Consultant | Global Infrasolutions Ltd. | 500285 | India | Registered Office:C-57, Basant Vihar Delhi Road, | 247001 | Saharanpur | Uttar Pradesh |  |  | pankaj4361@gmail.com | www.globalinfrasolutions.org
25291 | National Highways Authority Of India | 155597 | Pondavakkam-Kannigaipair (NH-716B) Six Lane Road Project (Package-4 of Chittoor-Thatchur Expressway) | 2032 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25292 | National Highways Authority Of India | 155597 | Pondavakkam-Kannigaipair (NH-716B) Six Lane Road Project (Package-4 of Chittoor-Thatchur Expressway) | 2032 | Consultant | Kaius Consulting Pvt. Ltd. | 660643 | India |  | NA
25293 | National Highways Authority Of India | 155597 | Pondavakkam-Kannigaipair (NH-716B) Six Lane Road Project (Package-4 of Chittoor-Thatchur Expressway) | 2032 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25294 | National Highways Authority Of India | 155597 | Porbander-Bhiladi NH-8B (Package 1) Project | 111 | Contractor | Soma Enterprise Ltd. | 230660 | India | Corporate Office:2 Avenue, 4, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-66538899 | 91-40-23321286 | info@soma.co.in | www.soma.co.in
25295 | National Highways Authority Of India | 155597 | Porbander-Bhiladi NH-8B (Package 1) Project | 111 | Contractor | Limak Construction Industry & Trade Inc. | 476630 | Turkey | Registered Office: | NA | [5 empty] | www.limak.com.tr
25296 | National Highways Authority Of India | 155597 | Puintola-Tangi (NH-16) Six/Four Lane Highway Project | 1472 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25297 | National Highways Authority Of India | 155597 | Pune-Khed (NH-50) Highway Project | 962 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25298 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj Realignment) Highway Project | 215 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25299 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj Realignment) Highway Project | 215 | Consultant | Symonds & Company Pvt. Ltd. | 330037 | India | Registered Office:23, L B Shastri Marg, | 211001 | Allahabad | Uttar Pradesh
25300 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj Realignment) Highway Project | 215 | Turnkey contractor | S M S Ltd. | 218106 | India | Corporate Office:20, I T Park, Parsodi, | 440022 | Nagpur | Maharashtra | 91-712-6665000 | 91-712-6665100 | info@smsl.co.in | www.smsl.co.in
25301 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj-Sarole) Highway Project | 214 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25302 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj-Sarole) Highway Project | 214 | Consultant | Symonds & Company Pvt. Ltd. | 330037 | India | Registered Office:23, L B Shastri Marg, | 211001 | Allahabad | Uttar Pradesh
25303 | National Highways Authority Of India | 155597 | Pune-Satara (Katraj-Sarole) Highway Project | 214 | Contractor | Satav Infrastructure Ltd. | 213682 | India | Registered Office:1, Raja Apts., Off Lalaki Road, Model Colony Shivaji Nagar, | 411005 | Pune | Maharashtra |  |  | aviyerandco@rediffmail.com
25304 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25305 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25306 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Consultant | Symonds & Company Pvt. Ltd. | 330037 | India | Registered Office:23, L B Shastri Marg, | 211001 | Allahabad | Uttar Pradesh
25307 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Contractor | B G Shirke Construction Technology Pvt. Ltd. | 26543 | India | Registered Office:72-76, Industrial Estate, Mundhwa, | 411036 | Pune | Maharashtra | 91-20-26708100 | 91-20-26871612 | bgstech@giaspn01.vsnl.net.in
25308 | National Highways Authority Of India | 155597 | Pune-Satara (Sarole-Wathar PS-2) Highway Project | 216 | Contractor | Birla G T M Entrepose Pvt. Ltd. | 36324 | India | Registered Office:Birla Building, 9/1, R N Mukherjee Road, | 700001 | Kolkata | West Bengal | 91-33-22430383 | 91-33-22101912 | neical@nbcbearings.in
25309 | National Highways Authority Of India | 155597 | Pune-Satara (Wathar-Satara) Highway Project | 217 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25310 | National Highways Authority Of India | 155597 | Pune-Satara (Wathar-Satara) Highway Project | 217 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25311 | National Highways Authority Of India | 155597 | Pune-Satara (Wathar-Satara) Highway Project | 217 | Consultant | Symonds & Company Pvt. Ltd. | 330037 | India | Registered Office:23, L B Shastri Marg, | 211001 | Allahabad | Uttar Pradesh
25312 | National Highways Authority Of India | 155597 | Pune-Satara (Wathar-Satara) Highway Project | 217 | Contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
25313 | National Highways Authority Of India | 155597 | Pune-Solapur (NH-9) Section Six Laning Highway Project | 562 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25314 | National Highways Authority Of India | 155597 | Punjab/Haryana Border-Jind (NH-71) Four Lane Road Project | 1211 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25315 | National Highways Authority Of India | 155597 | Purmepada VUP on Dhule-Pimplegaon section of NH-3 Project | 1921 | Contractor | Interbuild Infrastructure Pvt. Ltd. | 608011 | India |  | NA
25316 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-1) Road project | 708 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25317 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-1) Road project | 708 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
25318 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-2) Highway Project | 709 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25319 | National Highways Authority Of India | 155597 | Purnea-Forbesganj (BR-2) Highway Project | 709 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
25320 | National Highways Authority Of India | 155597 | Purnea-Gayakota Section(EW-12/BR) Highway Project | 199 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | UK | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
25321 | National Highways Authority Of India | 155597 | Purnea-Gayakota Section(EW-12/BR) Highway Project | 199 | Contractor | Lanco Infratech Ltd. | 126872 | India | Corporate Office:Lanco House, Plot No.397, Udyog Vihar, Phase-III, | 122016 | Gurgaon | Haryana | 91-124-4741000 | 91-124-4741878 | complianceofficer.litl@lancogroup.com | www.lancogroup.com
25322 | National Highways Authority Of India | 155597 | Purnea-Gayakota Section(EW-12/BR) Highway Project | 199 | Contractor | Rani Constructions Pvt. Ltd. | 193772 | India | Registered Office:407, Shiv Towers, 4th Floor, Patto Plaza, Panaji, | 403001 | Goa | Goa | 91-832-2438092
25323 | National Highways Authority Of India | 155597 | Purulia Bypass Four Lane Road (NH-32) Project | 2025 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25324 | National Highways Authority Of India | 155597 | Purulia Bypass Four Lane Road (NH-32) Project | 2025 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
25325 | National Highways Authority Of India | 155597 | Puruliya (JHR Border)-Balrampur-Chandil (NH-18) Two Lane Highway Project | 1326 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25326 | National Highways Authority Of India | 155597 | Puruliya (JHR Border)-Balrampur-Chandil (NH-18) Two Lane Highway Project | 1326 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25327 | National Highways Authority Of India | 155597 | Radhanpur-Deesa NH-14 (Package 6) Project | 236 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25328 | National Highways Authority Of India | 155597 | Radhanpur-Deesa NH-14 (Package 6) Project | 236 | Contractor | Daelim E & C India Ltd. | 54969 | India | Registered Office:28, Najafgarh Road, | 110001 | New Delhi | Delhi
25329 | National Highways Authority Of India | 155597 | Radhanpur-Deesa NH-14 (Package 6) Project | 236 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
25330 | National Highways Authority Of India | 155597 | Radhaswamy Ashram FOB Project | 834 | Contractor | Navyug Construction Pvt. Ltd. | 156615 | India | Registered Office:Plot No.379, Road No.10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.navayuga.com
25331 | National Highways Authority Of India | 155597 | Rae Bareli-Banda Highway Widening Project | 765 | Consultant | Mott Mac Donald Pvt. Ltd. | 375482 | USA | Registered Office:101, Nomura Hiranandani Gardens, Powai, | 400076 | Mumbai | Maharashtra |  |  | alkesh.parikh@mottmac.com | www.mottmac.com
25332 | National Highways Authority Of India | 155597 | Rae Bareli-Banda Highway Widening Project | 765 | Sub contractor | C D S Infra Projects Ltd. | 393833 | India | Registered Office:B -94, Okhla Phase II, | 110020 | New Delhi | NCT of Delhi | 91-11-26389595 | 91-11-41709590 | finance@cdsipl.com | www.cdsipl.com
25333 | National Highways Authority Of India | 155597 | Raebareli-Jagdishpur Two Lane Highway including Jagdishpur Bypass (NH-330A) Project | 2023 | Contractor | S K S Infra Projects Pvt. Ltd. | 595556 | India | Registered Office:1/115-A/2, Babu Gulab Rai Marg Delhi Gate, | 282002 | Agra | Uttar Pradesh |  |  | sksharma.skcc@gmail.com
25334 | National Highways Authority Of India | 155597 | Raebareli-Prayagraj (Allahabad) (NH-24B) Four lane Highway Upgradation Project | 1152 | Contractor | P P Pandey Infrastructure Pvt. Ltd. | 549600 | India |  | NA
25335 | National Highways Authority Of India | 155597 | Raghav Garh-Nanasa (NH-47) Four Lane Highway Project (Package-II of Indore-Harda Economic Corridor) | 2047 | Consultant | Holtec Consulting Pvt. Ltd. | 94858 | India | Corporate Office:Holtec Centre, A Block, Sushant Lok, | 122001 | Gurgaon | Haryana | 91-124-2385095 | 91-124-2385114 | dkj@holtecnet.com | www.holtecnet.com
25336 | National Highways Authority Of India | 155597 | Raghav Garh-Nanasa (NH-47) Four Lane Highway Project (Package-II of Indore-Harda Economic Corridor) | 2047 | Contractor | P R L Projects & Infrastructure Ltd. | 167393 | India | Registered Office:34/1, Vikas Apartment, Punjabi Bagh East, | 110026 | New Delhi | NCT of Delhi | 91-11-45540701 |  | prlprojects_infraltd@yahoo.co.in
25337 | National Highways Authority Of India | 155597 | Raghav Garh-Nanasa (NH-47) Four Lane Highway Project (Package-II of Indore-Harda Economic Corridor) | 2047 | Contractor | Shreeji Infrastructure India Pvt. Ltd. | 224014 | India | Registered Office:513, 5th Floor, Shubham Corporate Ring Road No. 1, Near Railway Crossing, Telibandha, | 492001 | Raipur | Chhattisgarh | 91-771-4022430 |  | shreejiinfrajbp@gmail.com | www.siipl.net
25338 | National Highways Authority Of India | 155597 | Raiganj-Dalkola (NH-34) Four Laning Highway (Kolkata-Dalkola) Project | 1400 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
25339 | National Highways Authority Of India | 155597 | Raiganj-Dalkola (NH-34) Four Laning Highway (Kolkata-Dalkola) Project | 1400 | Consultant | Rodic Consultants Pvt. Ltd. | 307240 | India | Corporate Office:1, Jai Singh Road, | 110001 | New Delhi | NCT of Delhi | 91-11-49434500 | 91-11-49434501 | contact@rodicconsultants.com | www.rodicconsultants.com
25340 | National Highways Authority Of India | 155597 | Raiganj-Dalkola (NH-34) Four Laning Highway (Kolkata-Dalkola) Project | 1400 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25341 | National Highways Authority Of India | 155597 | Raigarh (Dighi Port) Logistic Park Project | 1381 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25342 | National Highways Authority Of India | 155597 | Railway Over Bridge (ROB) at Saundad (NH-53) Project | 1754 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | Canada | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25343 | National Highways Authority Of India | 155597 | Railway Over Bridge (ROB) at Saundad (NH-53) Project | 1754 | Contractor | Rajdeep Buildcon Pvt. Ltd. | 355389 | India | Registered Office:Rajdeep House, Opp. Swastik Apartments, Savedi Naka, Savedi, | 414003 | Ahmadnagar | Maharashtra | 91-241-2424072 | 91-241-2424101 | info@rajdeepgroup.com | www.rajdeepgroup.com
25344 | National Highways Authority Of India | 155597 | Raipur (Arang Pachera) Logistic Park Project | 1352 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25345 | National Highways Authority Of India | 155597 | Raipur-Kodebad (NH-30) Four-Lane (NH-43) Highway Project | 812 | Contractor | G K C Projects Ltd. | 384672 | India | Registered Office:Sy. No. 9 (P), Hitec City, Cii Green Building Lane, Kandapur, | 500084 | Hyderabad | Telangana | 91-40-44554545 |  | info@gkcpl.com | www.gkcpl.com
25346 | National Highways Authority Of India | 155597 | Raipur-Simga (NH-30) Four/Six Laning Highway (Package-I of Raipur-Bilaspur) Project | 980 | Consultant | Sheladia Associates Inc. | 287104 | USA | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
25347 | National Highways Authority Of India | 155597 | Raipur-Simga (NH-30) Four/Six Laning Highway (Package-I of Raipur-Bilaspur) Project | 980 | Contractor | Punj Lloyd Infrastructure Ltd. | 393350 | India | Registered Office:Punj Lloyd House, 17-18, Nehru Place, | 110019 | New Delhi | NCT of Delhi | 91-11-2620123 | 91-124-2620111 | info@punjlloyd.com | www.punjlloyd.com
25348 | National Highways Authority Of India | 155597 | Raisinghnagar (Sri Ganganagar)-Anupgarh-Rojhri-Awa-Poogal Two/Four Laning Highway Project (BM/6) | 1098 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25349 | National Highways Authority Of India | 155597 | Raj/UP border-Mania (NS-19/UP/RJ) Highway Project | 188 | Consultant | Craphts Consultants India Pvt. Ltd. | 51920 | India | Head Office:14/3 Mathura Road, | 121003 | Faridabad | Haryana | 91-129-2278813 | 91-129-2256392 | info@craphts.com
25350 | National Highways Authority Of India | 155597 | Raj/UP border-Mania (NS-19/UP/RJ) Highway Project | 188 | Turnkey contractor | P N C Construction Pvt. Ltd. | 167138 | India |  | NA
25351 | National Highways Authority Of India | 155597 | Rajah-Eluru(Gowthami-Gundugolanu) Bridges AP-20 Project | 248 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
25352 | National Highways Authority Of India | 155597 | Rajah-Eluru(Gowthami-Gundugolanu) Bridges AP-20 Project | 248 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25353 | National Highways Authority Of India | 155597 | Rajah-Eluru(Gowthami-Gundugolanu) Bridges AP-20 Project | 248 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25354 | National Highways Authority Of India | 155597 | Rajahmu-Eluru(Divancheru-Gowthami) Bridges AP-19 Project | 247 | Consultant | S N C-lavalin Capital Inc. | 204139 | India | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
25355 | National Highways Authority Of India | 155597 | Rajahmu-Eluru(Divancheru-Gowthami) Bridges AP-19 Project | 247 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25356 | National Highways Authority Of India | 155597 | Rajahmu-Eluru(Divancheru-Gowthami) Bridges AP-19 Project | 247 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25357 | National Highways Authority Of India | 155597 | Rajahmundry-Eluru(Gowthami-Gundugolanu) Highway Project | 178 | Consultant | S N C-lavalin Capital Inc. | 204139 | Canada | Registered Office:1200-1075 West Georgia Street, Vancouver 43C, Canada V6E 3C9 | NA
25358 | National Highways Authority Of India | 155597 | Rajahmundry-Eluru(Gowthami-Gundugolanu) Highway Project | 178 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25359 | National Highways Authority Of India | 155597 | Rajahmundry-Eluru(Gowthami-Gundugolanu) Highway Project | 178 | Turnkey contractor | Limak-soma | 128730 | India |  | NA
25360 | National Highways Authority Of India | 155597 | Rajamunda-Barkote (NH-23&143) Four Laning Highway Project (Birmitrapur-Barkote) | 1283 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
25361 | National Highways Authority Of India | 155597 | Rajamunda-Barkote (NH-23&143) Four Laning Highway Project (Birmitrapur-Barkote) | 1283 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25362 | National Highways Authority Of India | 155597 | Rajasthan/MP Border to Jodmi village of Mandsaur Eight Lane Carriageway Project (Package 17 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1570 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25363 | National Highways Authority Of India | 155597 | Rajasthan/MP Border to Jodmi village of Mandsaur Eight Lane Carriageway Project (Package 17 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1570 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
25364 | National Highways Authority Of India | 155597 | Rajasthan/MP Border To Kota (RJ-10) Highway Project | 773 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25365 | National Highways Authority Of India | 155597 | Rajauli-Bakhtiyarpur (NH-31) Four Laning Highway Project | 1416 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25366 | National Highways Authority Of India | 155597 | Rajauli-Bakhtiyarpur (NH-31) Four Laning Highway Project | 1416 | Promoter | Bihar State Road Devp. Corpn. Ltd. | 387785 | India | Registered Office:RCD Mechanical Workshop Campus, (Near Patna Airport) Sheikpura, | 800014 | Patna | Bihar | 91-612-2227106 |  | bsrdcltd@gmail.com | www.bsrdcl.bih.nic.in
25367 | National Highways Authority Of India | 155597 | Rajiv Chowk-Bhondsi (NH-248A) Six Laning Highway Project (Package-1 of Rajasthan Border-Nuh-Gurugram) | 1317 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25368 | National Highways Authority Of India | 155597 | Rajiv Chowk-Bhondsi (NH-248A) Six Laning Highway Project (Package-1 of Rajasthan Border-Nuh-Gurugram) | 1317 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
25369 | National Highways Authority Of India | 155597 | Rajkot Logistic Park Project | 1354 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25370 | National Highways Authority Of India | 155597 | Rajkot-Gondal-Jetpur (NH-27) Six Lane Highway Project | 1669 | Contractor | Engineering Projects (india) Ltd. | 68320 | India | Corporate Office:Core 3, SCOPE Complex 7, Institutional Area, Lodhi Road, | 110003 | New Delhi | NCT of Delhi | 91-11-24361666 | 91-11-24363426 | epind@nde.vsnl.net | www.epi.gov.in
25371 | National Highways Authority Of India | 155597 | Rajkot-Gondal-Jetpur (NH-27) Six Lane Highway Project | 1669 | Contractor | Varaha Infra Ltd. | 401326 | India | Registered Office:Umesh Smariti, No.6, Jalam Vilas Scheme, Paota B Road, | 342024 | Jodhpur | Rajasthan | 91-291-2556877 | 91-291-2553861 | jp@varahinfra.com | www.varahainfra.com
25372 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-8) Highway Project | 748 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25373 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-8) Highway Project | 748 | Contractor | Ssangyong Engineering & Construction Co. Ltd. | 389286 | Korea Republic (South) |  | NA
25374 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-9) Highway Project | 294 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25375 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-9) Highway Project | 294 | Contractor | Ssangyong Engineering & Construction Co. Ltd. | 389286 | Korea Republic (South) |  | NA
25376 | National Highways Authority Of India | 155597 | Rajmarg Choraha-Lahknadon (ADB-II/C-9) Highway Project | 294 | Contractor | Renardet Sa | 417582 | Switzerland |  | NA
25377 | National Highways Authority Of India | 155597 | Ramanathapura (SH-86)-Terakanambi - Paschima vahini (NH-275) Four Lane Highway Project (Package-3 of Mysuru-Kushalnagar Highway) | 2099 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25378 | National Highways Authority Of India | 155597 | Ramanathapura-Terakanambi Road/ KR Nagar Junction to Yelawala-KR Nagara Road Junction Four Lane Highway Project (Package IV of Mysuru-Kushalnagar (NH-275) Highway) | 2098 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25379 | National Highways Authority Of India | 155597 | Ramanathapura-Terakanambi Road/ KR Nagar Junction to Yelawala-KR Nagara Road Junction Four Lane Highway Project (Package IV of Mysuru-Kushalnagar (NH-275) Highway) | 2098 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25380 | National Highways Authority Of India | 155597 | Ramanathapuram-Rameswaram Four Lane Highway Project | 969 | Consultant | Feedback Infrastructure Pvt. Ltd. | 72651 | India | Registered Office:7, Local Shopping Centre, Panchsheel Park, | 110017 | New Delhi | Delhi | 91-11-26495766 | 91-11-26495765 | fil@ndf.vsnl.net.in
25381 | National Highways Authority Of India | 155597 | Ramanattukara Junction-Start Of Valanchery Bypass Six Lane Highway (NH-66) Project | 1875 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25382 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25383 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Contractor | M G Contractors Pvt. Ltd. | 131217 | India | Registered Office:603, RIng Road Mall, Near Depali Chowk, Rohini, | 110085 | New Delhi | NCT of Delhi |  |  | mgcpl@mgcpl.com | www.mgcpl.com
25384 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Contractor | A B C I Infrastructures Pvt. Ltd. | 322707 | India | Head Office:Knowledge Hub, D N 23, 2nd Floor, Sector V, Salt Lake, | 700091 | Kolkata | West Bengal | 91-33-40044119 |  | kolkata@abciinfra.com | www.abciinfra.com
25385 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
25386 | National Highways Authority Of India | 155597 | Ramban-Banihal (NH-44) Section Four-Laning Highway Project | 586 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25387 | National Highways Authority Of India | 155597 | Ramban-Udhampur (NH-44) Section Four Laning Highway Project | 685 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
25388 | National Highways Authority Of India | 155597 | Ramban-Udhampur (NH-44) Section Four Laning Highway Project | 685 | Contractor | Ram Kumar Contractor Pvt. Ltd. | 592472 | India | Registered Office:Plot No 835, Sector 4, Urban Estate Panchkula, | 134112 | Panchkula | Haryana |  |  | RNJAIN_CA@YAHOO.COM
25389 | National Highways Authority Of India | 155597 | Rampur Four Lane Bypass (NH-530) Project | 2008 | Contractor | O S S Construction Pvt. Ltd. | 608770 | India |  | NA
25390 | National Highways Authority Of India | 155597 | Rampur-Kathgodam (NH-87) Four Lane Highway (Package-II) Project | 1156 | Consultant | Archtech Consultants Pvt. Ltd. | 19112 | India | Registered Office:No. 11, Shakespeare Sarani, | 700071 | Kolkata | West Bengal | 91-33-2827255 | 91-33-2825377 | acplcal@cal3.vsnl.net.in | www.archtechconsultants.com
25391 | National Highways Authority Of India | 155597 | Rampur-Kathgodam (NH-87) Four Lane Highway (Package-II) Project | 1156 | Contractor | Sadbhav Infrastructure Project Ltd. | 385775 | India | Registered Office:Sadbhav House, Ellibridge, Opp Law Garden Police Chowki, | 380006 | Ahmedabad | Gujarat | 91-79-26463384 | 91-79-26400210 | gaurav.vesasi@sadbhav.co.in | www.sadbhavinfra.co.in
25392 | National Highways Authority Of India | 155597 | Rampur-Kathgodam (NH-87) Four Lane Highway (Package-II) Project | 1156 | EPC contractor | Sadbhav Nainital Highway Ltd. | 549002 | India | Registered Office:Sadbhav House, Opp Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384 | 91-79-26400210 | investor@sadbhavinfra.co.in
25393 | National Highways Authority Of India | 155597 | Rampur-Khajuriya-Kesaria-end on NH-722 (NH-227A) Road Project | 1134 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25394 | National Highways Authority Of India | 155597 | Rampur-Khajuriya-Kesaria-end on NH-722 (NH-227A) Road Project | 1134 | Consultant | Mukesh & Associates | 150152 | India | Registered Office:5/3, Ragavan Street, Swarnapuri, | 636004 | Salem | Tamil Nadu | 91-427-330395 | 91-427-330209 | mukeshassociates@vsnl.com | www.mukeshassociates.com
25395 | National Highways Authority Of India | 155597 | Ranchi (NH-43) ROB Project (between Piska and Itki Railway Station) | 1996 | Contractor | Anand Construction | 583989 | India |  | NA
25396 | National Highways Authority Of India | 155597 | Ranchi (NH-75 & 23) Two Lane Elevated Corridor Project | 1492 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
25397 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25398 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25399 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25400 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Contractor | Bharat Vanijya Eastern Pvt. Ltd. | 33967 | India | Registered Office:No. 114, Chittaranjan Avenue, | 700073 | Kolkata | West Bengal | 91-33-2413114 | 91-33-2410844 | bvc@cal2.vsnl.net.in | www.bvepl.com
25401 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Contractor | Bhartia Infra Projects Ltd. | 34175 | India | Registered Office:201, Royal Arcade, 2nd Floor, Dr. B Baruah Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-24685222 | 91-361-2466693 | info@bhartiainfra.com | www.bhartiainfra.com
25402 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Contractor | Mcnally Bharat Engg. Co. Ltd. | 142553 | India | Corporate Office:Ecospace Business Park, Campus 2B, 11F/12, New Town, Rajarhat, | 700156 | North 24 Parganas | West Bengal | 91-33-30141111 | 91-33-30142277 | mbecal@mbecal.co.in | www.mcnallybharat.com
25403 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Contractor | Iron Triangle Ltd. | 384589 | India | Corporate Office:209, Akik Tower, Opp Rajpath Club, S G Highway, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-26840710 | 91-79-40040710 |  | www.irontriangle.in
25404 | National Highways Authority Of India | 155597 | Ranchi-Rargaon-Chandil-Jamshedpur-Mahulia (NH-33) Four Lane Highway Project | 1755 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
25405 | National Highways Authority Of India | 155597 | Ranichak Four Lane ROB-cum-Flyover Project (Bharatmala) | 1142 | Consultant | Kolkata Port Trust | 41439 | India | Registered Office:15, Strand Road, | 700001 | Kolkata | West Bengal | 91-33-22303451 | 91-33-22304901 | calport@kolkataporttrust.gov.in | www.smportkolkata.shipping.gov.in
25406 | National Highways Authority Of India | 155597 | Ranichak Four Lane ROB-cum-Flyover Project (Bharatmala) | 1142 | Consultant | Jacobs Ltd. | 105076 | India | Registered Office:Door No. XL/7546, Chittoor Road, | 682011 | Ernakulam | Kerala | 91-484-2366742 |  | praksmathew@yahoo.co.in
25407 | National Highways Authority Of India | 155597 | Ranichak Four Lane ROB-cum-Flyover Project (Bharatmala) | 1142 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25408 | National Highways Authority Of India | 155597 | Raniganj-Panagarh Highway Project | 41 | Consultant | Symonds Travers Morgan Ltd. | 245358 | UK |  | NA
25409 | National Highways Authority Of India | 155597 | Raniganj-Panagarh Highway Project | 41 | Contractor | B S C-r B M Pati | 27713 | India |  | NA
25410 | National Highways Authority Of India | 155597 | Raniganj-Panagarh Highway Project | 41 | Financial collaborator | Asian Development Bank | 22786 | Philippines | Registered Office:4, San Martin Marg, Chanakyapuri, | 110021 | South West Delhi | NCT of Delhi | 91-11-24107200 | 91-11-26870945 |  | www.adb.org
25411 | National Highways Authority Of India | 155597 | Ranirbazar-Arambagh Four Lane Road (NH-116A) Project | 2054 | Consultant | C E Testing Co. Pvt. Ltd. | 285272 | India | Corporate Office:124 A, N S C Bose Road, | 700092 | Kolkata | West Bengal | 91-33-24286221 | 91-33-24286220 | marketing@cetestindia.com | www.cetestindia.com
25412 | National Highways Authority Of India | 155597 | Ranni Village-Miyati Village Eight Lane Carriageway Project (Package 24 of Delhi-Mumbai Expressway) | 1603 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25413 | National Highways Authority Of India | 155597 | Ranni Village-Miyati Village Eight Lane Carriageway Project (Package 24 of Delhi-Mumbai Expressway) | 1603 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25414 | National Highways Authority Of India | 155597 | Ratanpur-Himatnagar NH-8 Four Lane Highway Project | 132 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25415 | National Highways Authority Of India | 155597 | Ratanpur-Himatnagar NH-8 Four Lane Highway Project | 132 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25416 | National Highways Authority Of India | 155597 | Ratanpur-Himatnagar NH-8 Four Lane Highway Project | 132 | Contractor | Ideal Road Builders Pvt. Ltd. | 97432 | India | Corporate Office:I R B Complex, Chandivli Farm, Chandivli, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | mhaiskar@bom2.vsnl.net.in
25417 | National Highways Authority Of India | 155597 | Ratanpur-Himatnagar NH-8 Four Lane Highway Project | 132 | Contractor | Mudajaya Corporation Berhad | 331066 | Malaysia |  | NA
25418 | National Highways Authority Of India | 155597 | Ratanpur-Satabhaya-Dharma-Basudevpur-Talapada-Chandipur-Chandaneshwar-Digha (NH-316A) Two/Four Laning Highway Project (BM/19) | 1108 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25419 | National Highways Authority Of India | 155597 | Rau junction (NH-52) Six Lane Flyover Project | 1667 | Contractor | Vindhya Construction (bombay) Pvt. Ltd. | 267335 | India |  | NA
25420 | National Highways Authority Of India | 155597 | Rayya Chowk Six Lane Flyover on Jalandhar-Amritsar Section (NH-03) Project | 2012 | Consultant | T P F Getinsa Euroestudios | 586015 | Spain |  | NA
25421 | National Highways Authority Of India | 155597 | Rayya Chowk Six Lane Flyover on Jalandhar-Amritsar Section (NH-03) Project | 2012 | Consultant | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. | 639672 | India | Registered Office:419-421, B4, Spaze IT Park, Sector 49, | 122018 | Gurgaon | Haryana | 91-124-4211847 |  | info@segmental.in | www.segmental.in
25422 | National Highways Authority Of India | 155597 | Rayya Chowk Six Lane Flyover on Jalandhar-Amritsar Section (NH-03) Project | 2012 | Contractor | D M R Builders Pvt. Ltd. | 412341 | India |  | NA
25423 | National Highways Authority Of India | 155597 | Recherla Village to Gurvaygudem Village (NH-365BG) Four Lane Access Controlled Greenfield Highway Project (Package 4 of Khammam-Devarapalle NH) (Bharatmala) | 1713 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25424 | National Highways Authority Of India | 155597 | Recherla Village to Gurvaygudem Village (NH-365BG) Four Lane Access Controlled Greenfield Highway Project (Package 4 of Khammam-Devarapalle NH) (Bharatmala) | 1713 | Consultant | K & J Projects Pvt. Ltd. | 539032 | India | Registered Office:Shivam, 16 Nit Layout, Ravinagar, | 440033 | Nagpur | Maharashtra | 91-712-2556402 | 91-712-2556403 | contact@knjprojects.com | www.knjprojects.com
25425 | National Highways Authority Of India | 155597 | Recherla Village to Gurvaygudem Village (NH-365BG) Four Lane Access Controlled Greenfield Highway Project (Package 4 of Khammam-Devarapalle NH) (Bharatmala) | 1713 | Contractor | Bekem Infra Projects Pvt. Ltd. | 389845 | India | Corporate Office:Plot No. 289, Avenue 1, Road No.6, Kakatiya Hills, Madhapur, | 500081 | Hyderabad | Telangana | 91-40-48587234 |  | info@bekemprojects.com | www.bekem.com
25426 | National Highways Authority Of India | 155597 | Rehabilitation & up-gradation to 4-laning of Birmitrapur-Brahmani Bypass End of NH-23 (NH-143) Project | 1265 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
25427 | National Highways Authority Of India | 155597 | Rehabilitation & up-gradation to 4-laning of Birmitrapur-Brahmani Bypass End of NH-23 (NH-143) Project | 1265 | Contractor | G K C Projects Ltd. | 384672 | India | Registered Office:Sy. No. 9 (P), Hitec City, Cii Green Building Lane, Kandapur, | 500084 | Hyderabad | Telangana | 91-40-44554545 |  | info@gkcpl.com | www.gkcpl.com
25428 | National Highways Authority Of India | 155597 | Rehabilitation and Up-gradation of Ambala-Saha (NH-444A) Four Lane Highway Project (Package-1) | 1768 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
25429 | National Highways Authority Of India | 155597 | Rehabilitation of Major Bridge Over River Hindon Project | 1841 | Co-promoter | Uttar Pradesh Public Works Department | 375252 | India | Registered Office:Nirman Bhawan, 96, Mahatma Gandhi Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2236496 |  | pwdgislko@gmail.com | www.uppwd.gov.in
25430 | National Highways Authority Of India | 155597 | Rehukaldhar-Aut(Tunnel) (NH-21) Highway Project (Package-IV of Nerchowk-Kullu stretch) | 1046 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25431 | National Highways Authority Of India | 155597 | Rehukaldhar-Aut(Tunnel) (NH-21) Highway Project (Package-IV of Nerchowk-Kullu stretch) | 1046 | Contractor | Shapoorji Pallonji Pandoh Takoli Highway Pvt. Ltd. | 576634 | India | Registered Office:Shapoorji Pallonji Centre 41/44, Minoo Desai Marg, Colaba, | 400005 | Mumbai | Maharashtra | 91-22-67490000 | 91-22-66338176 | secretarial.infra@shapoorji.com | www.shapoorji.in
25432 | National Highways Authority Of India | 155597 | Renigunta-Naidupeta (NH-71) Six Lane Highway Project (Bharatmala) | 1762 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25433 | National Highways Authority Of India | 155597 | Renigunta-Naidupeta (NH-71) Six Lane Highway Project (Bharatmala) | 1762 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25434 | National Highways Authority Of India | 155597 | Rimuli-Roxy (Koida)-Rajamunda (NH-215 & 520) Two/Four Laning Highway Project | 1689 | Consultant | Lee Associates | 127813 | India | Registered Office: | NA | [5 empty] | www.leeassociates.ca
25435 | National Highways Authority Of India | 155597 | Rimuli-Roxy (Koida)-Rajamunda (NH-215 & 520) Two/Four Laning Highway Project | 1689 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25436 | National Highways Authority Of India | 155597 | Rimuli-Roxy (Koida)-Rajamunda (NH-215 & 520) Two/Four Laning Highway Project | 1689 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25437 | National Highways Authority Of India | 155597 | Rimuli-Roxy (Koida)-Rajamunda (NH-215 & 520) Two/Four Laning Highway Project | 1689 | Contractor | R K D Construction Pvt. Ltd. | 199293 | India | Registered Office:B-20, Chandaka Industrial Estate, Bhubaneswar, | 751024 | Khordha | Odisha | 91-674-2725617 |  | rkdc@hotmail.com | www.rkdcpl.com
25438 | National Highways Authority Of India | 155597 | Ring bunds to Jhanjharpur (BR-6) Road Project | 732 | Consultant | Wilbur Smith Associates Inc. | 272295 | USA | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
25439 | National Highways Authority Of India | 155597 | Ring bunds to Jhanjharpur (BR-6) Road Project | 732 | Contractor | C & C Constructions Ltd. | 39807 | India | Corporate Office:Plot No.70, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-4536666 | 91-124-4536799 | candc@candcinfrastructure.com | www.candcinfrastructure.com
25440 | National Highways Authority Of India | 155597 | RJ/MP Border-Kota (RJ-11) Highway Project | 295 | Consultant | Wilbur Smith Associates Inc. | 272295 | USA | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
25441 | National Highways Authority Of India | 155597 | RJ/MP Border-Kota (RJ-11) Highway Project | 295 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25442 | National Highways Authority Of India | 155597 | Road approaches to Rail-cum Road Bridge across river Ganga on Munger Ghat (NH-333B) Project | 1242 | Consultant | Rodic Consultants Pvt. Ltd. | 307240 | India | Corporate Office:1, Jai Singh Road, | 110001 | New Delhi | NCT of Delhi | 91-11-49434500 | 91-11-49434501 | contact@rodicconsultants.com | www.rodicconsultants.com
25443 | National Highways Authority Of India | 155597 | Road approaches to Rail-cum Road Bridge across river Ganga on Munger Ghat (NH-333B) Project | 1242 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25444 | National Highways Authority Of India | 155597 | Road approaches to Rail-cum Road Bridge across river Ganga on Munger Ghat (NH-333B) Project | 1242 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
25445 | National Highways Authority Of India | 155597 | Road cum Flyover to Paradip Port Project (serving as 2nd exit) (near Atharbanki Chowk) | 1523 | Co-promoter | Indian Port Rail & Ropeway Corpn. Ltd. | 541532 | India | Corporate Office:4th Floor, Nirman Bhavan, Mumbai Port Trust Building, M P Road, Mazgaon (E), | 400010 | Mumbai | Maharashtra | 91-22-66566335 | 91-22-66566336 | iprclmumbai@gmail.com | www.iprcl.org
25446 | National Highways Authority Of India | 155597 | Road from SH-Alappuzha Bypass Intersection Project (Port Connectivity) (Sagarmala) | 1750 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25447 | National Highways Authority Of India | 155597 | RoB near junction with NH-11A to Junction with MDR-1 (Baonli-Jhalai Road) Eight Lane Carriageway Project (Package 8 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1587 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
25448 | National Highways Authority Of India | 155597 | RoB near village Itawa to Major Bridge on Chakan River Eight Lane Carriageway Project (Package-10 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1561 | Contractor | Crescent E P C Projects & Technical Services Ltd. | 413241 | India | Registered Office:IDA Phase-II, Patancheru, | 502319 | Hyderabad | Telangana |  |  | mabubasha.d@gvk.com
25449 | National Highways Authority Of India | 155597 | RoB near village Itawa to Major Bridge on Chakan River Eight Lane Carriageway Project (Package-10 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1561 | Contractor | Dhaya Maju Infrastructure (asia) Sdn Bhd | 639703 | India |  | NA
25450 | National Highways Authority Of India | 155597 | Rohna/Hassangarh-Jhajjar (NH-334B) Four Lane Highway Project (Package-II) (Meerut to Jhajjar) | 1433 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25451 | National Highways Authority Of India | 155597 | Rohtak Hissar Section Of NH-10 Project | 458 | Contractor | Era Projects (india) Ltd. | 68931 | India | Registered Office:E-43, Greater Kailash-III, Masjidmoth, | NA | New Delhi | Delhi
25452 | National Highways Authority Of India | 155597 | Rohtak Hissar Section Of NH-10 Project | 458 | Contractor | K C T Projects Pvt. Ltd. | 111657 | India | Registered Office:II-1-37, Lajpat Nagar, | 110024 | New Delhi | Delhi
25453 | National Highways Authority Of India | 155597 | Rohtak-Jind (NH-71) Four-Laning Highway Project (Bharatmala) | 1398 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
25454 | National Highways Authority Of India | 155597 | Rohtak-Jind (NH-71) Four-Laning Highway Project (Bharatmala) | 1398 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25455 | National Highways Authority Of India | 155597 | Rohtak-Jind (NH-71) Four-Laning Highway Project (Bharatmala) | 1398 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
25456 | National Highways Authority Of India | 155597 | Rudrapur Four Lane Bypass Project | 2117 | Consultant | Highway Engineering Consultant | 562725 | India | Registered Office:N S - 7, Mianwali Nagar , Paschim Vihar, | 110087 | Delhi | NCT of Delhi | 91-11-45660113 |  | hr@hceindia.com | www.hceindia.com
25457 | National Highways Authority Of India | 155597 | Rudrapur Four Lane Bypass Project | 2117 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25458 | National Highways Authority Of India | 155597 | Saadiya-Fort Vypin Road Upgradation Project | 1744 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25459 | National Highways Authority Of India | 155597 | Sagar Bypass (NH-26) Road Project | 425 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
25460 | National Highways Authority Of India | 155597 | Sagar-Mohari Four Lane Highway (NH-934) Project | 1914 | Contractor | Bansal Construction Works Pvt. Ltd. | 470219 | India | Corporate Office:3rd Floor, Tawa Cplx, E-5, Bittan Market Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2423736 | 91-755-4224036 | sunilbcw@rediffmail.com
25461 | National Highways Authority Of India | 155597 | Sagar-Rajmarg Choraha (ADB-II/C-6) Highway Project | 747 | Consultant | Roughton International Ltd. | 332163 | UK | Registered Office:Siri Residency, Flat No.504, Door No.6-3-680/8/2, Somajiguda, | 500082 | Hyderabad | Telangana |  |  | piouslin.samuel@roughton.com | www.roughton.com
25462 | National Highways Authority Of India | 155597 | Sagar-Rajmarg Choraha (ADB-II/C-6) Highway Project | 747 | Contractor | Ssangyong Engineering & Construction Co. Ltd. | 389286 | Korea Republic (South) |  | NA
25463 | National Highways Authority Of India | 155597 | Sagar-Rajmarg Choraha (ADB-II/C-7) Highway Project | 293 | Supervision consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25464 | National Highways Authority Of India | 155597 | Saha Junction-Shahabad (NH-444A) Four Lane Highway Project (Bharatmala) | 1763 | Contractor | Shiv Buildindia Pvt. Ltd. | 457770 | India | Registered Office:401/2, 4th Floor, Siddhraj Zavod, Sargasan, | 382421 | Gandhinagar | Gujarat | 91-79-29750425 |  | contact@shivbuildindia.com | www.shivbuildindia.com
25465 | National Highways Authority Of India | 155597 | Saha Junction-Shahabad (NH-444A) Four Lane Highway Project (Bharatmala) | 1763 | Contractor | Kaluwala Construction Pvt. Ltd. | 614021 | India | Registered Office:201, 2nd Floor, I T Space Tikri, Sector 48, IRIS Tech Park Sector-48, | 122103 | Gurugram | Haryana |  |  | kcc.bablu@gmail.com
25466 | National Highways Authority Of India | 155597 | Sakoli (NH-53) Flyover Project | 1423 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
25467 | National Highways Authority Of India | 155597 | Salasar-Nagaur (NH-65) Two Lane Highway Project | 1198 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25468 | National Highways Authority Of India | 155597 | Salem Bypass(NS/12) Highway Project | 53 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25469 | National Highways Authority Of India | 155597 | Salem Bypass(NS/12) Highway Project | 53 | Turnkey contractor | Sri Ranganathar & Co. | 234653 | India | Registered Office:4B-Lakshmipuram, Gandhi Road, | 636007 | Salem | Tamil Nadu | 91-427-412343 | 91-427-412622 | excavat@eth.net
25470 | National Highways Authority Of India | 155597 | Salem to Kerala Border (TN-7) Highway Project | 769 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
25471 | National Highways Authority Of India | 155597 | Salem-Karur (NS-2/TN-2) Highway Project | 771 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25472 | National Highways Authority Of India | 155597 | Salem-Karur (NS-2/TN-3) Highway Project | 772 | Contractor | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25473 | National Highways Authority Of India | 155597 | Salem-Karur (NS-2/TN-3) Highway Project | 772 | Contractor | Reliance Energy Ltd. [merged] | 389435 | India | Registered Office:1st Floor, H Block, Dhirubhai Ambani Knowledge City, Thane Belapur Road, | 400710 | Navi Mumbai | Maharashtra | 91-22-30386290 | 91-22-30099311 | rinfra.mcafiling@relianceada.com | www.relianceada.com
25474 | National Highways Authority Of India | 155597 | Salem-Namakkal Highway Project | 332 | Contractor | I V R C L Ltd. | 97156 | India | Corporate Office:Mihir,8-2-350/5/A/24/1-B & 2, Road No.2, Panchvati Colony, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23356613 | 91-40-23356693 | info@ivrinfra.com | www.ivrcl.com
25475 | National Highways Authority Of India | 155597 | Samakhiali-Gandhidham (Package I) Highway Project | 23 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25476 | National Highways Authority Of India | 155597 | Samakhiali-Gandhidham (Package I) Highway Project | 23 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25477 | National Highways Authority Of India | 155597 | Samakhiyali to Santalpur (NH-27) Six Lane Highway Project | 2087 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25478 | National Highways Authority Of India | 155597 | Samarlakota-Achampeta Junction Four Lane Road (NH-516F) (Part of Kakinada Port Connectivity to NH-16) Project | 2065 | Contractor | Rail Vikas Nigam Ltd. | 329799 | India | Corporate Office:1st Floor, August Kranti Bhawan, Bhikaji Cama Place, R K Puram, | 110066 | New Delhi | NCT of Delhi | 91-11-26738299 | 91-11-26182957 | info@rvnl.org | www.rvnl.org
25479 | National Highways Authority Of India | 155597 | Samrala Chowk-Ludhiana Municipal Limit (NH-95 & 5) Four Lane Highway Project | 1169 | Consultant | Stanley Consultants Inc. | 380296 | India | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
25480 | National Highways Authority Of India | 155597 | Samrala Chowk-Ludhiana Municipal Limit (NH-95 & 5) Four Lane Highway Project | 1169 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
25481 | National Highways Authority Of India | 155597 | Samrala Chowk-Ludhiana Municipal Limit (NH-95 & 5) Four Lane Highway Project | 1169 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
25482 | National Highways Authority Of India | 155597 | Sanath Nagar Industrial Cluster (Hyderabad)-JNPT Expressway Project | 1743 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25483 | National Highways Authority Of India | 155597 | Sanathnagar industrial cluster-Hyderabad to Vodarevu Expressway Project (Port Connectivity) | 1720 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25484 | National Highways Authority Of India | 155597 | Sanchi-Sagar NH-86 (Extn) (New NH-146) Widening Highway Project | 781 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25485 | National Highways Authority Of India | 155597 | Sangrur Logistic Park Project | 1374 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25486 | National Highways Authority Of India | 155597 | Sankha-Khajuri (NH-75) Four Lane Highway project (Rehla/Garhwa Bypass) (Package 4 of Garhwa-UP Border) | 1676 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
25487 | National Highways Authority Of India | 155597 | Sanquelim-Jamboti-Belagavi Two Lane Road (NH-748AA) Project | 1964 | Contractor | N S C Projects Pvt. Ld. | 559198 | India |  | NA
25488 | National Highways Authority Of India | 155597 | Saoner-Dhapewada-Kalmeshwar-Gondkhairi (NH-547E) Four Lane Highway Project | 1682 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25489 | National Highways Authority Of India | 155597 | Sarai Cholla-Morena (NS-20/MP) Highway Project | 191 | Consultant | Gherzi Eastern | 81368 | India |  | NA
25490 | National Highways Authority Of India | 155597 | Sarai Cholla-Morena (NS-20/MP) Highway Project | 191 | Contractor | Prakash Constructions Engg. Co. Ltd. | 178774 | India | Registered Office:513 Shrikant Chambers, V N Purav Marg, Chembur East, | 400071 | Mumbai | Maharashtra | 91-22-25202207 | 91-22-25205226
25491 | National Highways Authority Of India | 155597 | Saraighat Double Decker Rail cum Road Bridge across Brahmaputra River (Near Existing Saraighat Bridge) Project | 2066 | Co-promoter | Ministry Of Railways | 301846 | India | Registered Office:256-A, Raisina Road, Rajpath Area, Central Secretariat, | 110001 | New Delhi | NCT of Delhi | 91-11-23381213 |  | content-manage@gov.in | www.indianrailways.gov.in
25492 | National Highways Authority Of India | 155597 | Saraighat Second Bridge over Brahmhaputra Project | 1240 | Contractor | Gammon India Ltd. | 78250 | India | Head Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61153000 | 91-22-24300221 | gammon@gammonindia.com | www.gammonindia.com
25493 | National Highways Authority Of India | 155597 | Sardar Patel Ring Road-Sindhrej Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 1) (Bharatmala) | 1704 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25494 | National Highways Authority Of India | 155597 | Sardar Patel Ring Road-Sindhrej Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 1) (Bharatmala) | 1704 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25495 | National Highways Authority Of India | 155597 | Sargaon-Bilaspur (NH-130) Four Laning Highway (Package-III of Raipur-Bilaspur) Project | 1136 | Consultant | Sheladia Associates Inc. | 287104 | USA | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
25496 | National Highways Authority Of India | 155597 | Sargaon-Bilaspur (NH-130) Four Laning Highway (Package-III of Raipur-Bilaspur) Project | 1136 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25497 | National Highways Authority Of India | 155597 | Sarkhej(Ahemdabad)-Mundra Expressway Project | 1734 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25498 | National Highways Authority Of India | 155597 | Sarkhej-Ahmedabad-Pipavav Expressway Project (Port Connectivity) (Sagarmala) | 1717 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25499 | National Highways Authority Of India | 155597 | Sasaram-dehri-on-sone (GTRIP/IV-C) Highway Project | 691 | Consultant | Lea International Ltd. | 348703 | India |  | NA
25500 | National Highways Authority Of India | 155597 | Sasaram-dehri-on-sone (GTRIP/IV-C) Highway Project | 691 | Contractor | N C C Ltd. | 153366 | India | Corporate Office:Nagarjuna Hills, | 500082 | Hyderabad | Telangana | 91-40-23351753 | 91-40-23350214 | nccho@ncc-ltd.com | www.ncclimited.com
25501 | National Highways Authority Of India | 155597 | Sasaram-dehri-on-sone (GTRIP/IV-C) Highway Project | 691 | Contractor | Som Datt Builders Pvt. Ltd. | 457240 | India | Registered Office:Gajraj Chambers, 2B, 2nd Floor, 86 B/2 Topsia Road (South), | 700046 | Kolkata | West Bengal |  |  | sdbhoaccounts@rediffmail.com
25502 | National Highways Authority Of India | 155597 | Satna-Maihar Two Lane Highway (NH-135BG) Project | 1918 | Contractor | Gour Road Tar Coat Pvt. Ltd. | 442394 | India |  | NA
25503 | National Highways Authority Of India | 155597 | Satwari (Jammu Airport)-Kunjwani-Vijaypur (NH-144A/44) Six/Eight Lane Highway Project | 2036 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25504 | National Highways Authority Of India | 155597 | Savali Vihir to start of Ahmednagar Bypass (NH-160) Four Lane Highway Project | 1892 | Contractor | Shinde Developers Pvt. Ltd. | 220631 | India | Registered Office:S. No. 132/2 & 3, Plot No. 22, Gulmohar Park, ITI Road, Aundh, | 411007 | Pune | Maharashtra | 91-20-41004800 | 91-20-41004846 | info@sdplinfra.com | www.sdplinfra.in
25505 | National Highways Authority Of India | 155597 | Savali Vihir to start of Ahmednagar Bypass (NH-160) Four Lane Highway Project | 1892 | Contractor | A T S Housing Pvt. Ltd. | 541172 | India | Registered Office:711/92, Deepali, Nehru Place, | 110019 | New Delhi | NCT of Delhi |  |  | compliances@atsgreens.com | www.ats.org.in
25506 | National Highways Authority Of India | 155597 | Sector 29/31 roundabout (Tribune Chowk) Flyover Project | 1509 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25507 | National Highways Authority Of India | 155597 | Seoni-MP/MH Border (NH-7) (Delinked Stretch) Four Laning Highway Project | 1329 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25508 | National Highways Authority Of India | 155597 | Sethiyahopu-Cholopuram (NH-45C) Four Laning Highway (Pkg-II of Vikravandi-Thanjavur) Project | 1243 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
25509 | National Highways Authority Of India | 155597 | Sethiyahopu-Cholopuram (NH-45C) Four Laning Highway (Pkg-II of Vikravandi-Thanjavur) Project | 1243 | Consultant | Louis Berger Group - Usa | 536211 | USA |  | NA
25510 | National Highways Authority Of India | 155597 | Sethiyahopu-Cholopuram (NH-45C) Four Laning Highway (Pkg-II of Vikravandi-Thanjavur) Project | 1243 | Contractor | Patel Infrastructure Ltd. | 372691 | India | Corporate Office:Patcon House, 80 Ft. Road, Near Indira Gandhi Statue, | 388001 | Anand | Gujarat | 91-2692-245801 | 91-2692-245804 | anand@patelinfra.com | www.patelinfra.com
25511 | National Highways Authority Of India | 155597 | Shahapur-Pindari (NH-31) Four Lane Greenfield Highway Project (Package-II of Ghazipur-Ballia-UP/Bihar State Border) | 1646 | Contractor | Ravi Infrabuild Projects Pvt. Ltd. | 389581 | India | Registered Office:95, Hiran Magri, Sector 11, | 313002 | Udaipur | Rajasthan | 91-294-2482238 | 91-294-2482193 | raviinfra@gmail.com | www.raviinfra.com
25512 | National Highways Authority Of India | 155597 | Shahpur Bypass-Muktainagar Four Lane Road (NH-753L) Project (Package-II of Boregaon Buzurg-Muktainagar Road) | 2078 | Contractor | Agroh Infrastructure Developers Pvt. Ltd. | 389210 | India | Registered Office:Bunglow No. 74, Infront of Govt. Girls School, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-271225 |  | aidplindore@gmail.com | www.agrohinfra.com
25513 | National Highways Authority Of India | 155597 | Shahpur Bypass-Muktainagar Four Lane Road (NH-753L) Project (Package-II of Boregaon Buzurg-Muktainagar Road) | 2078 | Contractor | B N A Infrastructure Pvt. Ltd. | 606691 | India |  | NA
25514 | National Highways Authority Of India | 155597 | Shambu-Jalandhar Six laning Highway Project | 775 | Promoter | Government Of Punjab | 84865 | India | Registered Office:Plot No. D-241, Industrial Area, Phase-8B, Sector 74, | 160071 | Mohali (S A S Nagar) | Punjab | 91-172-2740769 |  | complaint.sewakendra@gmail.com | www.punjab.gov.in
25515 | National Highways Authority Of India | 155597 | Shamli-Muzaffarnagar (NH-709AD) Four Lane Highway Project (Package 2 of Panipat-Nagina Highway) | 1641 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25516 | National Highways Authority Of India | 155597 | Shamo-Matihani Six Lane Bridge (Begusarai Bridge) Project | 1846 | Consultant | Monarch Surveyors & Engg. Consultants Pvt. Ltd. | 148611 | India | Registered Office:3, Rujeta, 67, Panmala Pune Sinhagad Road, | 411030 | Pune | Maharashtra | 91-20-24330432 |  | enquiry@monarchpune.in | www.monarchpune.in
25517 | National Highways Authority Of India | 155597 | Shamo-Matihani Six Lane Bridge (Begusarai Bridge) Project | 1846 | Consultant | Rodic Consultants Pvt. Ltd. | 307240 | India | Corporate Office:1, Jai Singh Road, | 110001 | New Delhi | NCT of Delhi | 91-11-49434500 | 91-11-49434501 | contact@rodicconsultants.com | www.rodicconsultants.com
25518 | National Highways Authority Of India | 155597 | Shikohabad-Etawah (GTRIP/I-B) Highway Project | 501 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25519 | National Highways Authority Of India | 155597 | Shikohabad-Etawah (GTRIP/I-B) Highway Project | 501 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
25520 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25521 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Consultant | Meinhardt India Pvt. Ltd. | 345212 | India | Registered Office:301-303 CA Chambers, 18/12 WEA, Karol Bagh, | 110001 | Central Delhi | NCT of Delhi |  |  | accounts@meinhardtindia.com
25522 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Contractor | S P Singla Constructions Pvt. Ltd. | 204670 | India | Corporate Office:47, Sector-9, | 134113 | Panchkula | Haryana | 91-172-2571595 | 91-172-4620941 | spscpki@gmail.com | www.spsingla.com
25523 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Contractor | Rail Vikas Nigam Ltd. | 329799 | India | Corporate Office:1st Floor, August Kranti Bhawan, Bhikaji Cama Place, R K Puram, | 110066 | New Delhi | NCT of Delhi | 91-11-26738299 | 91-11-26182957 | info@rvnl.org | www.rvnl.org
25524 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25525 | National Highways Authority Of India | 155597 | Shimla Bypass (NH-5) (Parwanoo-Shimla Package-III) Two/Four Lane Highway Project | 1068 | Contractor | Bharat Constructions (india) Pvt. Ltd. | 660681 | India |  | NA
25526 | National Highways Authority Of India | 155597 | Shivpuri Bypass & upto MP/RJ Border (NH-76&25) Highway Project | 550 | Consultant | Renardet Sa | 417582 | Switzerland |  | NA
25527 | National Highways Authority Of India | 155597 | Shivpuri Bypass & upto MP/RJ Border (NH-76&25) Highway Project | 550 | Contractor | Soma Enterprise Ltd. | 230660 | India | Corporate Office:2 Avenue, 4, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-66538899 | 91-40-23321286 | info@soma.co.in | www.soma.co.in
25528 | National Highways Authority Of India | 155597 | Shiwrampur-Ramnagar Four Lane Highway (Package-II of Amas-Darbhanga Expressway) Project | 1890 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25529 | National Highways Authority Of India | 155597 | Shiwrampur-Ramnagar Four Lane Highway (Package-II of Amas-Darbhanga Expressway) Project | 1890 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25530 | National Highways Authority Of India | 155597 | Sikandara-Bhaunti (TNHP/II-A) Highway Project | 148 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25531 | National Highways Authority Of India | 155597 | Sikandara-Bhaunti (TNHP/II-A) Highway Project | 148 | Consultant | Aarvee Associates Pvt. Ltd. | 331065 | India | Registered Office:8-2-5, Ravula Residency, Srinagar City, Main Road, | 500082 | Hyderabad | Telangana | 91-40-23737633 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25532 | National Highways Authority Of India | 155597 | Sikandara-Bhaunti (TNHP/II-A) Highway Project | 148 | Contractor | S D B Infrastructure Pvt. Ltd. | 230617 | India | Registered Office:Gajraj Chambers, 2B, Second Floor, 86B/2, Topsia Road South, | 700046 | Kolkata | West Bengal | 91-33-40613087 |  | sdbhoaccounts@rediffmail.com
25533 | National Highways Authority Of India | 155597 | Silchar-Udarband (NH-54) Four-Laning Highway Project | 274 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25534 | National Highways Authority Of India | 155597 | Silchar-Udarband (NH-54) Four-Laning Highway Project | 274 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25535 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-6) Four Lane Highway Project | 287 | Consultant | Stanley Consultants Inc. | 380296 | USA | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
25536 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-6) Four Lane Highway Project | 287 | EPC contractor | B S C P L Infrastructure Ltd. | 27892 | India | Registered Office:M No. 8-2-502/1/A, Jivi Towers, Road No. 7, Banjara Hills, | 500034 | Hyderabad | Telangana
25537 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-7) Four-Laning Highway Project | 701 | Consultant | Stanley Consultants Inc. | 380296 | USA | Registered Office:206 & 206A, 2nd Floor, Rectangle 1, D-4 Saket District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-29565322 |  | doe@stanleyconsultants.com | www.stanleyconsultants.com
25538 | National Highways Authority Of India | 155597 | Siliguri-Islampur (WB-7) Four-Laning Highway Project | 701 | Contractor | Ircon International Ltd. | 102632 | India | Registered Office:Plot No.C-4, District Centre, Saket, | 110017 | New Delhi | NCT of Delhi | 91-11-26522000 | 91-11-26522000 | info@ircon.org | www.ircon.org
25539 | National Highways Authority Of India | 155597 | Simaria-Khagaria (NH-31) Four Laning Highway Project (Package 3 of Khagaria-Bakhtiarpur Highway) | 1073 | Consultant | Craphts Consultants India Pvt. Ltd. | 51920 | India | Head Office:14/3 Mathura Road, | 121003 | Faridabad | Haryana | 91-129-2278813 | 91-129-2256392 | info@craphts.com
25540 | National Highways Authority Of India | 155597 | Simaria-Khagaria (NH-31) Four Laning Highway Project (Package 3 of Khagaria-Bakhtiarpur Highway) | 1073 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25541 | National Highways Authority Of India | 155597 | Simga-Sargaon (NH-130) Four Laning Highway (Package-II of Raipur-Bilaspur) Project | 1135 | Consultant | Sheladia Associates Inc. | 287104 | USA | Registered Office:Amsri Class., Flat No 1, 1A, 2 & 2A, Door No 9-1-127/4, & 127/4/1, 4th Floor, Sarojini Devi Road, | 500003 | Secunderabad | Telangana |  |  | sksharma@sheladia.com | www.sheladia.com
25542 | National Highways Authority Of India | 155597 | Simga-Sargaon (NH-130) Four Laning Highway (Package-II of Raipur-Bilaspur) Project | 1135 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25543 | National Highways Authority Of India | 155597 | Simrahi To Ring Bund Missing link (BR-4) Road Project | 710 | Consultant | Wilbur Smith Associates Inc. | 272295 | USA | Registered Office: | NA | [5 empty] | www.cdmsmith.com/en-AU
25544 | National Highways Authority Of India | 155597 | Simrahi To Ring Bund Missing link (BR-4) Road Project | 710 | Contractor | Simplex Infrastructures Ltd. | 227710 | India | Registered Office:Simplex House, 27, Shakespeare Sarani, | 700017 | Kolkata | West Bengal | 91-33-23011600 | 91-33-22835964 | secretarial.legal@simplexinfra.com | www.simplexinfra.com
25545 | National Highways Authority Of India | 155597 | Sindhrej Village-Vejalka Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 2) | 1705 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25546 | National Highways Authority Of India | 155597 | Sindhrej Village-Vejalka Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 2) | 1705 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25547 | National Highways Authority Of India | 155597 | Sindhrej Village-Vejalka Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package 2) | 1705 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25548 | National Highways Authority Of India | 155597 | Singhara-Binjabahal (NH-6) (New NH-49) Four Laning Highway Project | 946 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25549 | National Highways Authority Of India | 155597 | Singhara-Binjabahal (NH-6) (New NH-49) Four Laning Highway Project | 946 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25550 | National Highways Authority Of India | 155597 | Sinnar-Sirdi (NH-160) Four Lane Highway Project | 1422 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25551 | National Highways Authority Of India | 155597 | Sira Bypass Highway Project | 63 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25552 | National Highways Authority Of India | 155597 | Sira Bypass Highway Project | 63 | Contractor | Maytas Infrastructure Co. Ltd. | 365513 | India |  | NA
25553 | National Highways Authority Of India | 155597 | Sitarganj-Pilibhit-Bareily (NH-74) Two/Four Laning Road Project | 1147 | Consultant | Holtec Consulting Pvt. Ltd. | 94858 | India | Corporate Office:Holtec Centre, A Block, Sushant Lok, | 122001 | Gurgaon | Haryana | 91-124-2385095 | 91-124-2385114 | dkj@holtecnet.com | www.holtecnet.com
25554 | National Highways Authority Of India | 155597 | Sitarganj-Pilibhit-Bareily (NH-74) Two/Four Laning Road Project | 1147 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25555 | National Highways Authority Of India | 155597 | Sitarganj-Pilibhit-Bareily (NH-74) Two/Four Laning Road Project | 1147 | Contractor | Raj Corporation Ltd. | 482680 | India | Registered Office:Gali No. 3 Punjabi Colony, | 205001 | Mainpuri | Uttar Pradesh |  |  | rcllko @gmail.com
25556 | National Highways Authority Of India | 155597 | Sitarganj-Tanakpur via Khatima (NH-125) Two Laning Highway Project | 1031 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25557 | National Highways Authority Of India | 155597 | Sitarganj-Tanakpur via Khatima (NH-125) Two Laning Highway Project | 1031 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
25558 | National Highways Authority Of India | 155597 | Six Lane access controlled Highway from Junction with Jaitpur-Pushta Road-Junction with Sector-62/65 dividing Road on Faridabad-Ballabhgarh Bypass (NH-148NA) Project (Pkg-2) (Delhi-Mumbai Expressway) | 1678 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25559 | National Highways Authority Of India | 155597 | Six Lane access controlled Highway from Junction with Sector-62/65 (on Faridabad -Ballabhgarh Bypass) to Junction near KMP E-way with NH-148N Project (Package-3) (Delhi-Mumbai Expressway) | 1679 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25560 | National Highways Authority Of India | 155597 | Six Lane Bridge over Phalguni River at Kuloor (NH-66) Project | 1868 | Contractor | Shinde Developers Pvt. Ltd. | 220631 | India | Registered Office:S. No. 132/2 & 3, Plot No. 22, Gulmohar Park, ITI Road, Aundh, | 411007 | Pune | Maharashtra | 91-20-41004800 | 91-20-41004846 | info@sdplinfra.com | www.sdplinfra.in
25561 | National Highways Authority Of India | 155597 | Six lane Capital Region Ring Road (Palatotapada (NH-16) to Kuspangi ( NH-42) | 1756 | Consultant | Geo Designs & Research Pvt. Ltd. | 611148 | India | Registered Office:Krishna, B-10 Opposite, Industrial Estate Road, BIDC Gorwa Estate, | 390016 | Vadodara | Gujarat | 91-265-2290222 |  | info@geogroup.in | www.geogroup.in
25562 | National Highways Authority Of India | 155597 | Six Lane Elevated Road Project (on Kona Expressway to connect Vidyasagar Setu) | 2033 | Contractor | Rail Vikas Nigam Ltd. | 329799 | India | Corporate Office:1st Floor, August Kranti Bhawan, Bhikaji Cama Place, R K Puram, | 110066 | New Delhi | NCT of Delhi | 91-11-26738299 | 91-11-26182957 | info@rvnl.org | www.rvnl.org
25563 | National Highways Authority Of India | 155597 | Six Lane Flyover and Six Lane Vehicular Underpass (VUP) on Jalandhar-Amritsar Section of NH-03 Project | 2026 | Consultant | T P F Getinsa Euroestudios | 586015 | Spain |  | NA
25564 | National Highways Authority Of India | 155597 | Six Lane Flyover and Six Lane Vehicular Underpass (VUP) on Jalandhar-Amritsar Section of NH-03 Project | 2026 | Consultant | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. | 639672 | India | Registered Office:419-421, B4, Spaze IT Park, Sector 49, | 122018 | Gurgaon | Haryana | 91-124-4211847 |  | info@segmental.in | www.segmental.in
25565 | National Highways Authority Of India | 155597 | Six Lane Flyover and Six Lane Vehicular Underpass (VUP) on Jalandhar-Amritsar Section of NH-03 Project | 2026 | Contractor | M Y C Infra Pvt. Ltd. | 660725 | India | Registered Office:50A, PKT-B HIG Flats, Sector-105, Noida, | 201304 | Gautam Buddha Nagar | Uttar Pradesh |  |  | info@mycinfra.com
25566 | National Highways Authority Of India | 155597 | Six Lane Flyover Near Tangra Town and Six Lane Vehicular Underpass (VUP) Near Mallian Town (NH-03) Project | 2027 | Consultant | T P F Getinsa Euroestudios | 586015 | Spain |  | NA
25567 | National Highways Authority Of India | 155597 | Six Lane Flyover Near Tangra Town and Six Lane Vehicular Underpass (VUP) Near Mallian Town (NH-03) Project | 2027 | Consultant | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. | 639672 | India | Registered Office:419-421, B4, Spaze IT Park, Sector 49, | 122018 | Gurgaon | Haryana | 91-124-4211847 |  | info@segmental.in | www.segmental.in
25568 | National Highways Authority Of India | 155597 | Six Lane Flyover Near Tangra Town and Six Lane Vehicular Underpass (VUP) Near Mallian Town (NH-03) Project | 2027 | Contractor | M Y C Infra Pvt. Ltd. | 660725 | India | Registered Office:50A, PKT-B HIG Flats, Sector-105, Noida, | 201304 | Gautam Buddha Nagar | Uttar Pradesh |  |  | info@mycinfra.com
25569 | National Highways Authority Of India | 155597 | Six Lane Grade Separator Project (Barhi-Hazaribagh NH-20 section) | 1994 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25570 | National Highways Authority Of India | 155597 | Six Lane Grade Separator Project (Barhi-Hazaribagh NH-20 section) | 1994 | Contractor | P R L Projects & Infrastructure Ltd. | 167393 | India | Registered Office:34/1, Vikas Apartment, Punjabi Bagh East, | 110026 | New Delhi | NCT of Delhi | 91-11-45540701 |  | prlprojects_infraltd@yahoo.co.in
25571 | National Highways Authority Of India | 155597 | Six lane Greenfield connectivity from DND-Faridabad-Ballabhgarh bypass to Jewar International Airport Project | 1943 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
25572 | National Highways Authority Of India | 155597 | Six Lane Jalandhar Bypass starting from Kahlwan (NH-3) ending at Kang Sahbu (NH-703) via Sarmastpur (NH-44)-Madara (NH-3)-Khajurla (NH-44) Project | 1990 | Contractor | Krishna Constructions Co. | 433105 | India |  | NA
25573 | National Highways Authority Of India | 155597 | Six Lane Minor Bridge (Paloli Palam), Major Bridge (Moorad) and Carriageway (NH-66) Project | 1661 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25574 | National Highways Authority Of India | 155597 | Six Lane Minor Bridge (Paloli Palam), Major Bridge (Moorad) and Carriageway (NH-66) Project | 1661 | Contractor | E S Infraserve Pvt. Ltd. | 581118 | India |  | NA
25575 | National Highways Authority Of India | 155597 | Six Laning of Tuticorin Port Road (section of NH-7A New NH-138) Project | 3014 | Contractor | P S T Engineering Construction | 568954 | India |  | NA
25576 | National Highways Authority Of India | 155597 | Six-Lane Access-Controlled Spur to Haridwar from Delhi-Saharanpur-Dehradun Economic Corridor Project (Halgoya Village to Badheri Village) | 2024 | Contractor | Krishna Constellation Pvt. Ltd. | 660693 | India |  | NA
25577 | National Highways Authority Of India | 155597 | Sohna-Gurugram Road near Alipur Village-KMP Expressway Eight Lane Carriageway Project (Package 1 of Delhi-Vadodara Expressway on NH-148N) (Delhi-Mumbai Expressway) | 1612 | Contractor | Apco Infratech Pvt. Ltd. | 384948 | India | Registered Office:B-9, Vibhuti Khand, Gomati Nagar, | 226010 | Lucknow | Uttar Pradesh | 91-522-4036111 | 91-522-4036100 | admin@apcoinfra.com | www.apcoinfra.com
25578 | National Highways Authority Of India | 155597 | Solan Logistic Park Project | 1355 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25579 | National Highways Authority Of India | 155597 | Solan-Kaithlighat (NH-5) (Parwanoo-Shimla Package-II) Two/Four Lane Highway Project | 1067 | Contractor | Prakash Asphaltings & Toll Highways (india) Ltd. | 178735 | India | Registered Office:76, Mall Road, Mhow, | 453441 | Indore | Madhya Pradesh | 91-7324-275001 | 91-7324-400318 | path@pathltd.com | www.pathltd.com
25580 | National Highways Authority Of India | 155597 | Solan-Kaithlighat (NH-5) (Parwanoo-Shimla Package-II) Two/Four Lane Highway Project | 1067 | Contractor | Airef Engineers Pvt. Ltd. | 531139 | India | Registered Office:117, Tagore Park, Model Town, | 110009 | Delhi | NCT of Delhi | 91-11-27445208 |  | monikamoorjani@gmail.com
25581 | National Highways Authority Of India | 155597 | Somavarappadu-Muppavaram (NH-544G) Six Lane Greenfield Expressway Project (Package-14 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2111 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25582 | National Highways Authority Of India | 155597 | Sonapur-Guwahati (AS-3) Four-Laning Highway Project | 713 | Contractor | M B L Infrastructure Ltd. | 136291 | India | Corporate Office:Banani Corporate One Tower, Suite #303-308, 3rd Floor, Jasola, Plot No.5, Commercial Centre, | 110025 | New Delhi | NCT of Delhi | 91-11-49593300 | 91-11-48593320 | delhi@mblinfra.com | www.mblinfra.com
25583 | National Highways Authority Of India | 155597 | Sonapur-Guwahati (AS-3) Four-Laning Highway Project | 713 | Contractor | Telecommunications Consultants India Ltd. | 249369 | India | Head Office:TCIL Bhawan, Greater Kailash Part-I, | 110048 | South Delhi | NCT of Delhi | 91-11-26202020 | 91-11-26242266 | tcil@tcil-india.com | www.tcil-india.com
25584 | National Highways Authority Of India | 155597 | Sonapur-Guwahati (AS-3) Four-Laning Highway Project | 713 | Supervision consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25585 | National Highways Authority Of India | 155597 | Sonepat-Baghpat Six Lane Expressway Project (Package 1 of Eastern Peripheral Expressway) | 438 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25586 | National Highways Authority Of India | 155597 | Sonepat-Baghpat Six Lane Expressway Project (Package 1 of Eastern Peripheral Expressway) | 438 | Financial collaborator | Japan International Cooperation Agency | 434751 | Japan | Registered Office:2nd Floor, Dr. Gopal Das Bhawan, 28, Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-47685500 | 91-11-4768555 |  | www.jica.go.jp
25587 | National Highways Authority Of India | 155597 | Sonepurbigha Village to Junction with NH-22 (Chatra Bypass) near Chatra Four/Six Lane Greenfield Access Control Expressway Project (Package-8 of Varanasi-Kolkata Expressway) | 1981 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25588 | National Highways Authority Of India | 155597 | Sonepurbigha Village to Junction with NH-22 (Chatra Bypass) near Chatra Four/Six Lane Greenfield Access Control Expressway Project (Package-8 of Varanasi-Kolkata Expressway) | 1981 | Contractor | Tracks & Towers Infratech Pvt. Ltd. | 407612 | India | Registered Office:8-2-293/82/A/J/III, Plot No.206, Road No.76, Jubilee Hills, | 500033 | Hyderabad | Telangana |  |  | tracksntowers@gmail.com
25589 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25590 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25591 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
25592 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Contractor | Prasad & Co. | 179311 | India | Registered Office:6-3-871/3, Snchalatha Complex, Begumpet, | 500016 | Hyderabad | Telangana | 91-40-23404951 | 91-40-23413687 | contact@prasadandco.com | www.prasadandco.com
25593 | National Highways Authority Of India | 155597 | Srikakulam-Icchapuram-Visakha. Bridges-AP5&6 Project | 143 | Contractor | Sew Infrastructure Ltd. | 217307 | India | Head Office:6-3-871, Snehalata, 1st Floor, Greenlands Road, Begumpet, | 500016 | Hyderabad | Telangana | 91-40-23402153 | 91-40-23405016 | mail@sewconstructions.com | www.sewinfrastructure.com
25594 | National Highways Authority Of India | 155597 | Srinagar Bypass (NS-30) Project | 237 | Contractor | Quartz India Mining Sources Pvt. Ltd. | 178748 | India | Registered Office:Plot No. 107, Phase-I, Kamalapuri Colony, | 500006 | Hyderabad | Andhra Pradesh
25595 | National Highways Authority Of India | 155597 | Srinagar Bypass (NS-30) Project | 237 | Contractor | Valecha Engineering Ltd. | 261759 | India | Registered Office:Valecha Chambers, 4th Floor, Andheri New Link Road, Andheri (W), | 400053 | Mumbai | Maharashtra | 91-22-26733625 | 91-22-26733945 | ho@valecha.in | www.valecha.in
25596 | National Highways Authority Of India | 155597 | Srinagar Four Lane Ring Road (Galander-Sumbel Road) Project | 924 | Consultant | Louis Berger Intl. Inc. | 287149 | India | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
25597 | National Highways Authority Of India | 155597 | Srinagar Four Lane Ring Road (Galander-Sumbel Road) Project | 924 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25598 | National Highways Authority Of India | 155597 | Sriperumbudur-Karaipettai (NH-48) Six Lane Highway (Pkg-1) Project | 1220 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
25599 | National Highways Authority Of India | 155597 | Sriperumbudur-Karaipettai (NH-48) Six Lane Highway (Pkg-1) Project | 1220 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25600 | National Highways Authority Of India | 155597 | Sriperumbudur-Karaipettai (NH-48) Six Lane Highway (Pkg-1) Project | 1220 | Contractor | Welspun Enterprises Ltd. | 318534 | India | Corporate Office:Welspun House, 4th Flr, Kamala City, Senapati Bapat Marg, Lower Parel-W, | 400013 | Mumbai | Maharashtra | 91-22-66136000 | 91-22-24908020 | companysecretary_wpl@welspun.com | www.welspunenterprises.com
25601 | National Highways Authority Of India | 155597 | Start of DSIR Zone-Adhelai Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-4) | 1707 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25602 | National Highways Authority Of India | 155597 | Start of DSIR Zone-Adhelai Village (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-4) | 1707 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25603 | National Highways Authority Of India | 155597 | Start of Kollam Bypass- Kadambattukonam (NH-66) (Old NH-47) Six Lane Highway Project (Bharatmala) | 1894 | Consultant | S M E C International Pty. Ltd. | 203789 | India | Registered Office:Chowdhury Bhawan, House No.33, 2nd Floor, Barthakur Mill Road, Ulubari, | 781007 | Guwahati | Assam | 91-361-2460042 | 91-361-2461482 | statutoryinfo.india@smec.com | www.smec.com
25604 | National Highways Authority Of India | 155597 | Start of Kollam Bypass- Kadambattukonam (NH-66) (Old NH-47) Six Lane Highway Project (Bharatmala) | 1894 | Consultant | S M E C (india) Pvt. Ltd. | 320431 | India | Corporate Office:5th Floor, Tower C, Building No. 8, DLF Cyber City Phase 2, | 122002 | Gurgaon | Haryana | 91-124-4552800 | 91-124-4380043 | india@smec.com
25605 | National Highways Authority Of India | 155597 | Start of Kollam Bypass- Kadambattukonam (NH-66) (Old NH-47) Six Lane Highway Project (Bharatmala) | 1894 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
25606 | National Highways Authority Of India | 155597 | Start of Shahjahanpur Bypass to End of Hardoi Bypass (NH-731) Four Lane Highway Project (Package-II of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2067 | Consultant | Wadia Techno-engineering Services Ltd. | 81370 | India | Registered Office:Neville House, J N Heredia Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-67021380 | 91-22-26673193 | gel@gherzieastern.com | www.wadiaengg.com
25607 | National Highways Authority Of India | 155597 | Start of Shahjahanpur Bypass to End of Hardoi Bypass (NH-731) Four Lane Highway Project (Package-II of Palia-Shahjahanpur-Hardoi-Lucknow Highway) | 2067 | Contractor | Raj Corporation Ltd. | 482680 | India | Registered Office:Gali No. 3 Punjabi Colony, | 205001 | Mainpuri | Uttar Pradesh |  |  | rcllko @gmail.com
25608 | National Highways Authority Of India | 155597 | Subway/LVUP at Adhegaon Junction and Mohol Junction on NH-65 (Pune-Solapur Section) Project | 2028 | Contractor | A K Shivhare Infrastructure Pvt. Ltd. | 466959 | India |  | NA
25609 | National Highways Authority Of India | 155597 | Suhagada-Bardiya Amra (NH-148) Four Lane Highway Project (Package-3 of Ujjain-Garoth Section) | 1962 | Consultant | Wolkem India Ltd. | 321676 | India | Registered Office:E-101, Mewar Industrial Area, Madri, Post Box No.21, | 313003 | Udaipur | Rajasthan | 91-294-2494600 | 91-294-2494608 | mktg@wolkem.com | www.wolkem.com
25610 | National Highways Authority Of India | 155597 | Suhagada-Bardiya Amra (NH-148) Four Lane Highway Project (Package-3 of Ujjain-Garoth Section) | 1962 | Contractor | M K C Infrastructure Ltd. | 395810 | India | Registered Office:M K C House, Plot No. 10, Shivnagar Society, Bhuj-Bypass, Anjar, | 370110 | Kachchh | Gujarat | 91-2836-245730 |  | hrm@mkcinfrastructureltd.com | www.mkcinfrastructureltd.com
25611 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-I) | 895 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25612 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-I) | 895 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25613 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-II) | 1074 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25614 | National Highways Authority Of India | 155597 | Sultanpur-Varanasi (NH-56) Four Laning Highway Project (Package-II) | 1074 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25615 | National Highways Authority Of India | 155597 | Sumdoh-Kaza-Gramphu (NH-505) Two Lane Road Project | 1845 | Co-promoter | Border Roads Organisation | 37884 | India | Registered Office:Seema Sadak Bhawan, Ring Road, Delhi Cantt. | 110010 | New Delhi | NCT of Delhi | 91-11-25686914 | 91-11-25699618 | bro-adg@nic.in | http://www.bro.nic.in
25616 | National Highways Authority Of India | 155597 | Sundar Nagar Four Lane (NH-21) Bypass Project (Part of Kiratpur-Nerchowk Highway) | 1995 | Contractor | Kaluwala Construction Pvt. Ltd. | 614021 | India | Registered Office:201, 2nd Floor, I T Space Tikri, Sector 48, IRIS Tech Park Sector-48, | 122103 | Gurugram | Haryana |  |  | kcc.bablu@gmail.com
25617 | National Highways Authority Of India | 155597 | Sundargarh Logistics Park Project | 1349 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25618 | National Highways Authority Of India | 155597 | Surat (Chalthan)-Atul Highway Project | 37 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25619 | National Highways Authority Of India | 155597 | Surat (Chalthan)-Atul Highway Project | 37 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25620 | National Highways Authority Of India | 155597 | Surat (Chalthan)-Atul Highway Project | 37 | Contractor | Dodsal Enterprises Pvt. Ltd. | 62282 | India | Head Office:Plot No.1, Udyog Nagar Estate, S.V.Road, Goregaon (West), | 400062 | Mumbai | Maharashtra | 91-22-28711031
25621 | National Highways Authority Of India | 155597 | Surat (Chalthan)-Atul Highway Project | 37 | Contractor | S K Engineering & Construction | 203024 | Korea Republic (South) | Registered Office: | NA | [5 empty] | www.skec.com
25622 | National Highways Authority Of India | 155597 | Surat-Manor (Chaltan-Bhilad) Road Project | 262 | Contractor | L G Engineering Co. Ltd. | 125281 | India |  | NA
25623 | National Highways Authority Of India | 155597 | Surat-Manor (Chaltan-Bhilad) Road Project | 262 | Contractor | Patel Engineering Ltd. | 172333 | India | Corporate Office:B-26/1, Aver House, Veera Desai Industrial Road, Off New Link Road, Andheri (West), | 400053 | Mumbai | Maharashtra | 91-22-26767500 |  | investors@pateleng.com | www.pateleng.com
25624 | National Highways Authority Of India | 155597 | Takoli-Kullu Section (NH-21) Four Laning Highway Project (Package-VI of Nerchowk-Kullu stretch) | 1048 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25625 | National Highways Authority Of India | 155597 | Talaja-Mahuva (NH-8E) (Package-II Bhavnagar-Veraval Section) Four Lane Highway Project | 1927 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25626 | National Highways Authority Of India | 155597 | Talaja-Mahuva (NH-8E) (Package-II Bhavnagar-Veraval Section) Four Lane Highway Project | 1927 | Contractor | Kalthia Engineering & Construction Ltd. | 114870 | India | Corporate Office:28, Rangin Park, Opp. Rajpath Club, S G Highway, Bodakdev, | 380059 | Ahmedabad | Gujarat | 91-79-26870501 | 91-79-26870501 | kecl@kathiagroup.com | www.kalthiagroup.com
25627 | National Highways Authority Of India | 155597 | Talaja-Mahuva (NH-8E) (Package-II Bhavnagar-Veraval Section) Four Lane Highway Project | 1927 | Promoter | National Highways Authority Of India | 155597 | India | Head Office:Plot No. G-5 & 6, Sector-10, Dwarka, | 110075 | New Delhi | NCT of Delhi | 91-11-25074100 | 91-11-25093507 | nhaiweb@nhai.org | www.nhai.gov.in
25628 | National Highways Authority Of India | 155597 | Talapady-Chengala (NH-66) Six Lane Highway Project | 1345 | Contractor | Uralungal Labourcontract Co-op. Society Ltd. | 387892 | India | Head Office:PO Madappally Collage, Vatakara, | 673102 | Kozhikode | Kerala | 91-496-2514042 | 91-496-2516402 | uralungal@ulccsltd.com | www.ulccsltd.com
25629 | National Highways Authority Of India | 155597 | Talapady-Chengala (NH-66) Six Lane Highway Project | 1345 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
25630 | National Highways Authority Of India | 155597 | Talasari-Karvad Package-10 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1625 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25631 | National Highways Authority Of India | 155597 | Talasari-Karvad Package-10 of Vadodara-Kim (Phase-1-Part-A) (NH-8) Expressway Project (Delhi-Mumbai Expressway) | 1625 | Contractor | Roadway Solutions India Infra Ltd. | 606355 | India | Registered Office:S N-29, H N-20, Nr. Kubex Soc., Nr. Shera School, Kondhwa (KD), | 411048 | Pune | Maharashtra |  |  | info@rsipl.net | www.rsipl.net
25632 | National Highways Authority Of India | 155597 | Talcher-Kamakhyanagar Bypass (NH-149 & 53) Four Lane Road Project | 1403 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25633 | National Highways Authority Of India | 155597 | Talcher-Kamakhyanagar Bypass (NH-149 & 53) Four Lane Road Project | 1403 | Contractor | Iron Triangle Ltd. | 384589 | India | Corporate Office:209, Akik Tower, Opp Rajpath Club, S G Highway, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-26840710 | 91-79-40040710 |  | www.irontriangle.in
25634 | National Highways Authority Of India | 155597 | Talwandi Bhai-Firozpur (NH-05) Four Lane Highway Project | 1418 | Contractor | Ceigall India Ltd. | 353351 | India | Registered Office:A-898, Tagore Nagar, Opp. K V M School, | 141001 | Ludhiana | Punjab | 91-161-4623666 |  | info@ceigall.com | www.ceigall.com
25635 | National Highways Authority Of India | 155597 | Talwandi Bhai-Firozpur (NH-05) Four Lane Highway Project | 1418 | Contractor | Shiv Buildindia Pvt. Ltd. | 457770 | India | Registered Office:401/2, 4th Floor, Siddhraj Zavod, Sargasan, | 382421 | Gandhinagar | Gujarat | 91-79-29750425 |  | contact@shivbuildindia.com | www.shivbuildindia.com
25636 | National Highways Authority Of India | 155597 | Tambaram-Red Hills By-Pass Project | 62 | Contractor | Uttar Pradesh State Bridge Corpn. Ltd. | 255951 | India | Registered Office:Setu Bhawan, 16, Madan Mohan Malviya Marg, | 226001 | Lucknow | Uttar Pradesh | 91-522-2209702 | 91-522-2209798 | upsbcltd@gmail.com | www.bridgecorporationltd.com
25637 | National Highways Authority Of India | 155597 | Tamil Nadu/Karnataka Border-Bangalore (NH-209) Two/Four Laning Highway Project | 785 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25638 | National Highways Authority Of India | 155597 | Tamilnadu/Karnataka Border-Hoskote (NH-648) Four/Six Laning Highway Project | 1200 | Consultant | Kitco Ltd. | 121500 | India | Head Office:M M Gardens, Church Landing Road, Near Fine Arts Hall, Pallimukku, | 682016 | Kochi | Kerala | 91-484-4129000 | 91-484-2805066 | mail@kitco.in | www.kitco.in
25639 | National Highways Authority Of India | 155597 | Tamilnadu/Karnataka Border-Hoskote (NH-648) Four/Six Laning Highway Project | 1200 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
25640 | National Highways Authority Of India | 155597 | Tamilnadu/Karnataka Border-Hoskote (NH-648) Four/Six Laning Highway Project | 1200 | Contractor | Skylark Infra Engg. Pvt. Ltd. | 534566 | India |  | NA
25641 | National Highways Authority Of India | 155597 | Tanda-Raibareilly Two Lane Highway Project | 870 | Consultant | Mott Mac Donald Pvt. Ltd. | 375482 | USA | Registered Office:101, Nomura Hiranandani Gardens, Powai, | 400076 | Mumbai | Maharashtra |  |  | alkesh.parikh@mottmac.com | www.mottmac.com
25642 | National Highways Authority Of India | 155597 | Tanda-Raibareilly Two Lane Highway Project | 870 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25643 | National Highways Authority Of India | 155597 | Tanda-Raibareilly Two Lane Highway Project | 870 | Contractor | G K C Projects Ltd. | 384672 | India | Registered Office:Sy. No. 9 (P), Hitec City, Cii Green Building Lane, Kandapur, | 500084 | Hyderabad | Telangana | 91-40-44554545 |  | info@gkcpl.com | www.gkcpl.com
25644 | National Highways Authority Of India | 155597 | Tangi-Bhubaneshwar (NH-16) Six Laning Highway Project | 1477 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25645 | National Highways Authority Of India | 155597 | Tangi-Chhatarpur-Satapada and Konark-Astarang-Naugaon-Paradwip Port-Ratanpur Two/Four Laning Highway Project (BM/18) | 1107 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25646 | National Highways Authority Of India | 155597 | Taran Taran Flyover to Golden Gate Stretch of Jalandhar-Amritsar Section (NH-03) Six Lane Road Project | 2016 | Consultant | T P F Getinsa Euroestudios | 586015 | Spain |  | NA
25647 | National Highways Authority Of India | 155597 | Taran Taran Flyover to Golden Gate Stretch of Jalandhar-Amritsar Section (NH-03) Six Lane Road Project | 2016 | Consultant | Segmental Consulting & Infrastructure Advisory Pvt. Ltd. | 639672 | India | Registered Office:419-421, B4, Spaze IT Park, Sector 49, | 122018 | Gurgaon | Haryana | 91-124-4211847 |  | info@segmental.in | www.segmental.in
25648 | National Highways Authority Of India | 155597 | Taran Taran Flyover to Golden Gate Stretch of Jalandhar-Amritsar Section (NH-03) Six Lane Road Project | 2016 | Contractor | D M R Builders Pvt. Ltd. | 412341 | India |  | NA
25649 | National Highways Authority Of India | 155597 | Tatibandh Chowk (NH-6/53) Flyover Project | 1551 | Contractor | Chevrox Constructions Pvt. Ltd. | 592217 | India | Registered Office:C-3/802, Anushruti Apartment, Opp. New York Tower, S G Highway, Taltej, | 380059 | Ahmedabad | Gujarat | 91-79-40037937 |  | info@chevrox.com | www.chevrox.com
25650 | National Highways Authority Of India | 155597 | Teesta Bazar-Pedong Two Lane Road Project | 1858 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25651 | National Highways Authority Of India | 155597 | Tejaji Nagar-Balwara (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package II) (Bharatmala) | 1851 | Consultant | Lion Engineering Consultants | 551358 | India | Registered Office:Plot No. 97, Lion Tower, Near Mother Teresa School, Kolar Road, | 462042 | Bhopal | Madhya Pradesh | 91-755-2879496 | 91-755-2879499 | info@liongroup.in | www.lionengineering.in
25652 | National Highways Authority Of India | 155597 | Tejaji Nagar-Balwara (NH-347 BG) Four Lane Highway Project (Indore-Edlabad Package II) (Bharatmala) | 1851 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25653 | National Highways Authority Of India | 155597 | Telebani-Sambalpur (NH-6) Two/Four Lane Highway Project | 1022 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25654 | National Highways Authority Of India | 155597 | Telebani-Sambalpur (NH-6) Two/Four Lane Highway Project | 1022 | Contractor | Punj Lloyd Ltd. | 183757 | India | Corporate Office:78, Institutional Area, Sector 32, | 122001 | Gurgaon | Haryana | 91-124-2620493 | 91-124-2620111 | investors@punjilloyd.com | www.punjlloyd.com
25655 | National Highways Authority Of India | 155597 | Tendesara Village to Khatti Village 4/6 Lane Highway Project (Package 1A of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1547 | Consultant | A T Kearney India Pvt. Ltd. | 342760 | India | Registered Office:818 Indraprakash Building, 21 Barakhamba Road, | 110001 | New Delhi | NCT of Delhi | 91-11-4090700 |  | shikha.gupta@atkeamey.com | www.atkearney.in
25656 | National Highways Authority Of India | 155597 | Tendesara Village to Khatti Village 4/6 Lane Highway Project (Package 1A of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1547 | Consultant | Transys Consulting Pvt. Ltd. | 541410 | India | Registered Office:12th Floor, J M D Regent Square, M G Road, | 122002 | Gurgaon | Haryana | 91-124-4195950 |  | info@transysconsulting.co.in | www.transys.in
25657 | National Highways Authority Of India | 155597 | Tendesara Village to Khatti Village 4/6 Lane Highway Project (Package 1A of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1547 | Contractor | S M S Ltd. | 218106 | India | Corporate Office:20, I T Park, Parsodi, | 440022 | Nagpur | Maharashtra | 91-712-6665000 | 91-712-6665100 | info@smsl.co.in | www.smsl.co.in
25658 | National Highways Authority Of India | 155597 | Tendesara Village to Khatti Village 4/6 Lane Highway Project (Package 1A of Durg-Raipur Bypass Section (NH-53) of Mumbai-Kolkata Economic Corridor) (Bharatmala) | 1547 | Contractor | Mehrotra Buildcon Pvt. Ltd. | 399923 | India | Registered Office:9, Industrial Estate, | 485001 | Satna | Madhya Pradesh | 91-7672-250370 | 91-7672-250368 | mbplsatna@yahoo.com | www.mehrotrabuildcon.in
25659 | National Highways Authority Of India | 155597 | Tetali Junction (NH-216A) Flyover Project | 2064 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
25660 | National Highways Authority Of India | 155597 | Thalassery-Mahe Bypass (NH-66) Four Laning Highway Project | 1233 | Consultant | Aecom Asia Co. Ltd. | 453427 | Hong Kong | Registered Office:9th Floor, Infinity Tower-C, DLF Cyber City DLF Phase II, | 122002 | Gurgaon | Haryana | 91-124-4830100 | 91-124-4830108 | sunil2.kumar@aecom.com | www.aecom.com
25661 | National Highways Authority Of India | 155597 | Thalassery-Mahe Bypass (NH-66) Four Laning Highway Project | 1233 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
25662 | National Highways Authority Of India | 155597 | Thalassery-Mahe Bypass (NH-66) Four Laning Highway Project | 1233 | Contractor | E K K Infrastructure Ltd. | 536863 | India | Corporate Office:IInd Floor, Municipal Building, A M Road, Perumbavoor, | 683542 | Ernakulam | Kerala | 91-484-2523603 | 91-484-2523603 | info@ekk.co.in | www.ekk.co.in
25663 | National Highways Authority Of India | 155597 | Thalikulam-Kodungallur (NH-66) Six Lane Highway Project | 1879 | Contractor | Shivalaya Construction Co. Pvt. Ltd. | 221327 | India | Registered Office:Plot No.137, Pocket -10, Sector-24, Rohini, | 110085 | New Delhi | NCT of Delhi | 91-11-45088679 |  | shivalayaco@yahoo.com | www.shivalaya.webs.com
25664 | National Highways Authority Of India | 155597 | Thaliparambha-Muzhapilangad (NH-66) Six Lane Highway Project (Bharatmala) | 1803 | Contractor | Vishwa Samudra Engg. Pvt. Ltd. | 585208 | India | Registered Office:Door No.59A-8/8-6B1, | 520008 | Vijayawada | Andhra Pradesh | 91-40-67996799 |  | info@vishwasamudra.in | www.vishwasamudra.in
25665 | National Highways Authority Of India | 155597 | Thanjavur-Pudukottai (NH-226) Two-Laning Highway Project | 667 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25666 | National Highways Authority Of India | 155597 | Thanjavur-Pudukottai (NH-226) Two-Laning Highway Project | 667 | Contractor | S P L Infrastructure Ltd. | 395144 | India | Registered Office:278 Katra Peran Tilak Bazar, | 110006 | Central Delhi | NCT of Delhi |  |  | arungoelca@yahoo.co.in
25667 | National Highways Authority Of India | 155597 | Tharad-Ahmedabad Six/Eight Lane Greenfield Expressway Project | 2041 | Consultant | Intercontinental Consultants & Technocrats Pvt. Ltd. | 101811 | India | Corporate Office:A - 8 & A -9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | business@ictonline.com | www.ictonline.com
25668 | National Highways Authority Of India | 155597 | Thevara-Kundanoor Willingdon Bridge Project | 20 | Turnkey contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25669 | National Highways Authority Of India | 155597 | Thirumayam-Manamadurai (NH-226) Two Laning Highway Project | 998 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25670 | National Highways Authority Of India | 155597 | Thiruvananthapuram (Trivendrum)-Kottarkarra-Kottayam-Angamali (NH-183) Four Lane Highway Project (Parallel to MC Road) | 1986 | Consultant | Highway Engineering Consultant | 562725 | India | Registered Office:N S - 7, Mianwali Nagar , Paschim Vihar, | 110087 | Delhi | NCT of Delhi | 91-11-45660113 |  | hr@hceindia.com | www.hceindia.com
25671 | National Highways Authority Of India | 155597 | Thiruvananthapuram (Trivendrum)-Kottarkarra-Kottayam-Angamali (NH-183) Four Lane Highway Project (Parallel to MC Road) | 1986 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
25672 | National Highways Authority Of India | 155597 | Thiruvananthapuram International Airport-NH-66 Bypass Connectivity Project | 1193 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25673 | National Highways Authority Of India | 155597 | Thondapalli to Farukhanagar (NS/9) Project | 227 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25674 | National Highways Authority Of India | 155597 | Thondapalli to Farukhanagar (NS/9) Project | 227 | Turnkey contractor | Maharia Re-surfacing Ltd. | 135760 | India |  | NA
25675 | National Highways Authority Of India | 155597 | Thondupally-Kothur (NH-44) Six Lane Highway Project (Hyderabad-Bangalore Section) | 1960 | Contractor | Lakshmi Infrastructure & Developers India Pvt. Ltd. | 569185 | India | Registered Office:D No 54-16-12/28, G 1, A - Block, Vasanth Apartments, Sri Nagar Colony, Vijayawada, | 520010 | Srikakulam | Andhra Pradesh | 91-866-2477186 |  | hr.ho@lidipl.com | www.lidipl.com
25676 | National Highways Authority Of India | 155597 | Thopurghar section (NS/14) Highway Project | 228 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25677 | National Highways Authority Of India | 155597 | Thopurghar section (NS/14) Highway Project | 228 | Contractor | P T Sumber Mitra | 167833 | Indonesia |  | NA
25678 | National Highways Authority Of India | 155597 | Thopurghat to Thumpipadi (NS-25/TN) Road Project | 416 | Consultant | Mukesh & Associates | 150152 | India | Registered Office:5/3, Ragavan Street, Swarnapuri, | 636004 | Salem | Tamil Nadu | 91-427-330395 | 91-427-330209 | mukeshassociates@vsnl.com | www.mukeshassociates.com
25679 | National Highways Authority Of India | 155597 | Thopurghat to Thumpipadi (NS-25/TN) Road Project | 416 | Contractor | J S R Constructions Pvt. Ltd. | 104773 | India | Registered Office:No. 3415, IInd Stage, Indiranagar, | 560038 | Bengaluru | Karnataka
25680 | National Highways Authority Of India | 155597 | Thorapalli Agraharam-Jittandahalli section (NH-844) Four Lane Highway Project (Package 2 of Hosur-Dharmapuri) (Bharatmala) | 1688 | Contractor | Sunway Construction Bhd | 282631 | India | Registered Office:Level 8, Menara Sunway, Jalan Lagoon Timur, Bandar Sunway, 46150 Petaling Jaya, Selangor Darul Ehsan, Malaysia | NA
25681 | National Highways Authority Of India | 155597 | Thorapalli Agraharam-Jittandahalli section (NH-844) Four Lane Highway Project (Package 2 of Hosur-Dharmapuri) (Bharatmala) | 1688 | Contractor | R N S Infrastructure Ltd. | 377885 | India | Corporate Office:7th Floor, Naveen Complex #14, M G Road, | 560001 | Bengaluru | Karnataka | 91-80-25584181 | 91-80-25584017 |  | www.rnsil.com
25682 | National Highways Authority Of India | 155597 | Three Lane Bridge Across River Tapi (NH-8) Project | 11 | Contractor | Hindustan Construction Co. Ltd. | 93997 | India | Registered Office:Hincon House, 11th Floor, 247 Park, L B S Marg, Vikhroli (West), | 400083 | Mumbai | Maharashtra | 91-22-25751000 | 91-22-25777568 | secretarial@hccindia.com | www.hccindia.com
25683 | National Highways Authority Of India | 155597 | Thumpipadi-Salem Highway Project | 331 | Consultant | Mukesh & Associates | 150152 | India | Registered Office:5/3, Ragavan Street, Swarnapuri, | 636004 | Salem | Tamil Nadu | 91-427-330395 | 91-427-330209 | mukeshassociates@vsnl.com | www.mukeshassociates.com
25684 | National Highways Authority Of India | 155597 | Thumpipadi-Salem Highway Project | 331 | Contractor | Bhagheeratha Engineering Ltd. | 33012 | India | Head Office:3rd Flr, Bhagheeratha Residency, Opp. Bank Of Baroda, (Ernakulam North Br.), Banerji Road, | 682018 | Ernakulam | Kerala | 91-484-2397906 | 91-484-2397983 | info@belkochi.com | www.belkochi.com
25685 | National Highways Authority Of India | 155597 | Thuravoor Thekku-Paravoor (NH-66) Six Lane Highway Project (Bharatmala) | 1895 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
25686 | National Highways Authority Of India | 155597 | Tiba-Dharamkot Package-1 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1907 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25687 | National Highways Authority Of India | 155597 | Tiba-Dharamkot Package-1 of Amritsar-Bathinda (NH-754A) Six Lane Access Controlled Greenfield Highway Project (Part of Amritsar-Jamnagar Economic Corridor) | 1907 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25688 | National Highways Authority Of India | 155597 | Tindivanam-Krishnagiri (NH-77) Two Laning Highway Project | 1613 | Consultant | Mukesh & Associates | 150152 | India | Registered Office:5/3, Ragavan Street, Swarnapuri, | 636004 | Salem | Tamil Nadu | 91-427-330395 | 91-427-330209 | mukeshassociates@vsnl.com | www.mukeshassociates.com
25689 | National Highways Authority Of India | 155597 | Tindivanam-Krishnagiri (NH-77) Two Laning Highway Project | 1613 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25690 | National Highways Authority Of India | 155597 | Tindivanam-Krishnagiri (NH-77) Two Laning Highway Project | 1613 | Contractor | S P K & Co. | 515978 | India | Registered Office:2/67, R C Middil Street, Killamudimannarkottai, | 623603 | Madurai | Tamil Nadu
25691 | National Highways Authority Of India | 155597 | Tindivanam-Ulundurpet (Pkg -VI-A) Highway Project | 417 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25692 | National Highways Authority Of India | 155597 | Tindivanam-Ulundurpet (Pkg -VI-A) Highway Project | 417 | Contractor | G M R Airports Infrastructure Ltd. | 76718 | India | Corporate Office:Skip House, 25/1, Museum Road, | 560025 | Bengaluru | Karnataka | 91-80-2279949 | 91-80-2998118 |  | www.gmrgroup.in
25693 | National Highways Authority Of India | 155597 | Tindivanam-Ulundurpet (Pkg -VI-A) Highway Project | 417 | Contractor | G M R Energy Ltd. | 247422 | India | Registered Office:701, 7th Floor, Naman Centre, Plot No. C-31, Bandra Kurla Complex, Bandra East, | 400051 | Mumbai | Maharashtra | 91-11-49882200 | 91-11-49882227 | energy-secretarial@gmrgroup.in | www.gmrgroup.in
25694 | National Highways Authority Of India | 155597 | Tirupur Industrial Cluster (Coimbatore)-Enayam Expressway Project | 1738 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25695 | National Highways Authority Of India | 155597 | Tonk-Sawaimadhopur (NH-116) Two-Laning Highway Project | 1491 | Contractor | H G Infratech Pvt. Ltd. | 529686 | India | Corporate Office:Govind Baag, Gandhi Road, (Near Shaheed Gate), Gwalior -474 011 (Madhya Pradesh) | NA |  |  |  |  | info@hggroup.co.in
25696 | National Highways Authority Of India | 155597 | Tovaramkurchi-Madurai (Package-VIIB) Highway Project | 495 | Consultant | Dalal Mott Macdonald Pvt. Ltd. | 55303 | India | Corporate Office:86, Annie Besant Road, Worli, | 400018 | Mumbai | Maharashtra | 91-22-24934891
25697 | National Highways Authority Of India | 155597 | Tovaramkurchi-Madurai (Package-VIIB) Highway Project | 495 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
25698 | National Highways Authority Of India | 155597 | Trichy Bypass-Tovaramkurchi (Package-VII A) Highway Project | 407 | Consultant | Dalal Mott Macdonald Pvt. Ltd. | 55303 | India | Corporate Office:86, Annie Besant Road, Worli, | 400018 | Mumbai | Maharashtra | 91-22-24934891
25699 | National Highways Authority Of India | 155597 | Trichy Bypass-Tovaramkurchi (Package-VII A) Highway Project | 407 | Contractor | J M C Projects (india) Ltd. [merged] | 104087 | India | Corporate Office:6th Floor, Kalpatru Synergy, Opp. Grand Hyatt, Santacruz-East, | 400055 | Mumbai | Maharashtra | 91-22-68851500 | 91-22-68851555 | cs@jmcprojects.com | www.jmcprojects.com
25700 | National Highways Authority Of India | 155597 | Trichy-Dindigul (NH-45) Highway Project | 446 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
25701 | National Highways Authority Of India | 155597 | Trichy-Dindigul (NH-45) Highway Project | 446 | Contractor | Reliance Infrastructure Ltd. | 27747 | India | Registered Office:Reliance Centre, Ground Floor 19, Walchand Hirachand Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-43031000 | 91-22-43033664 | rinfra.investor@relianceada.com | www.rinfra.com
25702 | National Highways Authority Of India | 155597 | Tumakuru (NH-206)-Honnavar Port Two to Four Lane Road Project (Port Connectivity) | 1728 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25703 | National Highways Authority Of India | 155597 | Tumkur (NH-48 & 206) Four Lane Bypass Project | 1513 | Consultant | Indian Technocrat Ltd. | 99026 | India | Registered Office:Plot No.8, Sector B-7, Local Shopping Complex, Vasant Kunj, | 110070 | New Delhi | NCT of Delhi | 91-11-49531100 | 91-11-49531166 | info@itl.net.in | www.itl.net.in
25704 | National Highways Authority Of India | 155597 | Tupudana-Itre Four Lane Road (NH-75E) (NH-20) Project (Package-1 of Ranchi-Jaintgarh-Paradip Economic Corridor) | 2124 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25705 | National Highways Authority Of India | 155597 | Two Lane Bridge across Kosi River (NH-527 A) Project (Umagaon-Saharsa Package-IV) (Bharatmala) | 1637 | Contractor | Transrail Lighting Ltd. | 387140 | India | Registered Office:501 A,B,C,E Fortune 2000, Block G Bandra Kurla Complex, Bandra East, | 400051 | Mumbai | Maharashtra |  | 91-7104-265765 | contact@transrailltd.com
25706 | National Highways Authority Of India | 155597 | Two Lane Bridge across Kosi River (NH-527 A) Project (Umagaon-Saharsa Package-IV) (Bharatmala) | 1637 | Contractor | Gammon Engineers & Contractors Pvt. Ltd. | 542071 | India | Registered Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61114000 | 91-22-24300221 | marketing@gammonengineers.com | www.gammonengineers.com
25707 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25708 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | UK | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
25709 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25710 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25711 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Kesariaji-Ratanpur) Highway Project | 131 | Contractor | Ranjit Construction Co. | 286134 | India | Registered Office:Near Newrang Bagh, Baipura Road, Hatkeshawar, Khokhar, Maninagar East, Ahmedabad, Gujarat | 380008 |  | Gujarat | 91-79-5854163
25712 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Udaipur-Kesariaji (UG-I)) Highway Project | 130 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25713 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Udaipur-Kesariaji (UG-I)) Highway Project | 130 | Consultant | Scott Wilson Kirkpatrick & Paratners | 215515 | UK | Registered Office:Scott House Basing View Basingstoke RG 21 2 JG Hampshire U.K | NA
25714 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Udaipur-Kesariaji (UG-I)) Highway Project | 130 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25715 | National Highways Authority Of India | 155597 | Udaipur-Ratanpur-Chiloda(Udaipur-Kesariaji (UG-I)) Highway Project | 130 | Turnkey contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25716 | National Highways Authority Of India | 155597 | Udaipura-Bhogu (NH-75) Four Lane Highway Project (Package-2) | 2050 | Consultant | L N Malviya Infra Projects Pvt. Ltd. | 512280 | India | Registered Office:Plot No. 1, City Centre, T-10, 3rd Floor, M P Nagar, Zone I, Press Complex, | 462011 | Bhopal | Madhya Pradesh | 91-755-4295421 | 91-755-4295421 | hec_bhopal@rediffmail.com | www.lninfra.com
25717 | National Highways Authority Of India | 155597 | Udaipura-Bhogu (NH-75) Four Lane Highway Project (Package-2) | 2050 | Contractor | Dineshchandra R Agarwal Infracon Pvt. Ltd. | 396222 | India | Registered Office:Agarwal Complex Near Lions Hall, | 385535 | Banas Kantha | Gujarat | 91-2744-222115 |  | dra99@rediffmail.com | www.draipl.com
25718 | National Highways Authority Of India | 155597 | Umagaon-Basopatti-Kalauhi-Saharghat-Benipatti-Rahika-Pokhrauni-Madubani-Rampatti-Bideshwarsthan-Awam-Loufa-Bheja-Supaul-Saharsa Two Lane Port Connectivity Project | 1558 | Consultant | V K S Infratech Mgmt. Pvt. Ltd. | 260181 | India | Corporate Office:1102, Nirmal Tower, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23358786 |  | corp@vksinfra.com | www.vksinfra.com
25719 | National Highways Authority Of India | 155597 | Umagaon-Basopatti-Kalauhi-Saharghat-Benipatti-Rahika-Pokhrauni-Madubani-Rampatti-Bideshwarsthan-Awam-Loufa-Bheja-Supaul-Saharsa Two Lane Port Connectivity Project | 1558 | Contractor | Ram Kripal Singh Construction Pvt. Ltd. | 384939 | India | Corporate Office:308 & 309, Suncity Shopping Arcade, Sector-54, | 122002 | Gurgaon | Haryana | 91-124-2572879 |  | rkscpl@rkscpl.com | www.rkscpl.com
25720 | National Highways Authority Of India | 155597 | Umagaon-Basopatti-Kalauhi-Saharghat-Benipatti-Rahika-Pokhrauni-Madubani-Rampatti-Bideshwarsthan-Awam-Loufa-Bheja-Supaul-Saharsa Two Lane Port Connectivity Project | 1558 | Contractor | Dhariwal Buildtech Ltd. | 604954 | India |  | NA
25721 | National Highways Authority Of India | 155597 | Una-Kodinar (NH-8E) (Package-V Bhavnagar-Veraval Section) Four Lane Highway Project | 1016 | Consultant | Stup Consultants Pvt. Ltd. | 237364 | India | Registered Office:Unit No. 2702, 27th Floor, Rupa Renaissance, Plot D-33, D-207, Juinagar, MIDC TTC Industrial Area, | 400705 | Mumbai | Maharashtra |  |  | mumbai@stupmail.com | www.stupco.com
25722 | National Highways Authority Of India | 155597 | Una-Kodinar (NH-8E) (Package-V Bhavnagar-Veraval Section) Four Lane Highway Project | 1016 | Contractor | Sadbhav Infrastructure Project Ltd. | 385775 | India | Registered Office:Sadbhav House, Ellibridge, Opp Law Garden Police Chowki, | 380006 | Ahmedabad | Gujarat | 91-79-26463384 | 91-79-26400210 | gaurav.vesasi@sadbhav.co.in | www.sadbhavinfra.co.in
25723 | National Highways Authority Of India | 155597 | Una-Kodinar (NH-8E) (Package-V Bhavnagar-Veraval Section) Four Lane Highway Project | 1016 | EPC contractor | Sadbhav Una Highway Ltd. | 549008 | India | Registered Office:Sadbhav House, Opp Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat |  |  | hardik.modi@sadbhav.co.in
25724 | National Highways Authority Of India | 155597 | Uncha-Nagla-Khanuawa-Roppas-Dholpur (NH-123) Two Laning Highway Project | 1009 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25725 | National Highways Authority Of India | 155597 | Uncha-Nagla-Khanuawa-Roppas-Dholpur (NH-123) Two Laning Highway Project | 1009 | Contractor | H G Infra Engg. Ltd. | 410701 | India | Corporate Office:III Floor, Sheel Mohar Plaza, A-1 Tilak Marg, C-Scheme, | 302001 | Jaipur | Rajasthan | 91-141-4106040 | 91-141-4106044 | cs@hginfra.com | www.hginfra.com
25726 | National Highways Authority Of India | 155597 | Undrajavaram Four Lane Flyover Project | 2062 | Contractor | Shrushti Contech Pvt. Ltd. | 409385 | India | Registered Office:HIG - 49, A P H B Colony Proddatur, | 516360 | Cuddapah | Andhra Pradesh |  |  | praveen.t@shrushtigroup.com
25727 | National Highways Authority Of India | 155597 | Uniara-Nainwa-Hindoli-Jahajpur-Shahpura-Gulabpura (NH-148D) Two Lane Road Project | 932 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25728 | National Highways Authority Of India | 155597 | Uniara-Nainwa-Hindoli-Jahajpur-Shahpura-Gulabpura (NH-148D) Two Lane Road Project | 932 | Consultant | Theme Engineering Services Pvt. Ltd. | 442985 | India | Registered Office:B-24, Gokul Vatika, Jawahar Circle, | 302018 | Jaipur | Rajasthan | 91-141-2724495 |  | theme@themeengineering.com | www.themeengineering.com
25729 | National Highways Authority Of India | 155597 | Uniara-Nainwa-Hindoli-Jahajpur-Shahpura-Gulabpura (NH-148D) Two Lane Road Project | 932 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25730 | National Highways Authority Of India | 155597 | Uniara-Nainwa-Hindoli-Jahajpur-Shahpura-Gulabpura (NH-148D) Two Lane Road Project | 932 | Contractor | Ranjit Buildcon Ltd. | 395126 | India | Corporate Office:Ranjit House, Opp Sun Residency, B/H Bhagwat Bunglows, Rt. Side Road To G M Mandir, Thaltej Shilaj Rd, | 380059 | Ahmedabad | Gujarat | 91-79-40200555 | 91-40-40200565 | accounts.rbl@gmail.com | www.ranjitbuildcon.com
25731 | National Highways Authority Of India | 155597 | UP/Bihar Border-Kasia (LMNHP-8) Highway Project | 714 | Consultant | Feedback Consultants Pvt. Ltd. | 72648 | India | Registered Office:Flat No.3, A I I M S Apts., Near Chilla Regulator, Vasundhra Enclave, | 110096 |  | Delhi
25732 | National Highways Authority Of India | 155597 | UP/Bihar Border-Kasia (LMNHP-8) Highway Project | 714 | Contractor | Simplex Construction Pvt. Ltd. | 227713 | India | Registered Office:24, C-Block Community Centre, Janak Puri, | 110058 | New Delhi | Delhi | 91-11-5515086
25733 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-I) | 976 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25734 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-I) | 976 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25735 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-II) | 1003 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25736 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-II) | 1003 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25737 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-III) | 1043 | Consultant | Consulting Engineers Group Ltd. | 328249 | India | Registered Office:7th Floor, B-11(G), Industrial Area, Malviya Nagar, | 302017 | Jaipur | Rajasthan | 91-141-2751801 | 91-141-2751806 | accounts@cegindia.com | www.cegindia.com
25738 | National Highways Authority Of India | 155597 | UP/Haryana Border-Panchkula (NH-73) Four-Laning Highway Project (Package-III) | 1043 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25739 | National Highways Authority Of India | 155597 | UP/Haryana Border-Rohna (Package-I) NH-334B Four Laning Highway Project (Meerut to Jhajjar) | 1286 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25740 | National Highways Authority Of India | 155597 | Upgradation of Bhangbar-Kangra Bypass (NH-88) (New NH-303,503) Four Lane Highway Project (Package-VB of Shimla-Mataur Highway) | 1905 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25741 | National Highways Authority Of India | 155597 | Upgradation of Hinterland Road from Naidupeta-Krishnagiri Project | 1719 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25742 | National Highways Authority Of India | 155597 | Upgradation of Multai-Seoni section & Narsinghpur-Saoner Section including Chhindwara Town Ring Road Project | 810 | Contractor | Sadbhav Engineering Ltd. | 206660 | India | Head Office:'Sadbhav House', Opp. Law Garden Police Chowki, Ellisbridge, | 380006 | Ahmedabad | Gujarat | 91-79-26463384,26460047 | 91-79-26400210 | sadbhavad1@sancharnet.in | www.sadbhaveng.com
25743 | National Highways Authority Of India | 155597 | Upgradation of Multai-Seoni section & Narsinghpur-Saoner Section including Chhindwara Town Ring Road Project | 810 | Sub contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25744 | National Highways Authority Of India | 155597 | Upgradation of Old NH-6 (NH-53) Four Lane Highway Project (Khamgaon City) | 1449 | Contractor | Jandu Construction Pvt. Ltd. | 584006 | India |  | NA
25745 | National Highways Authority Of India | 155597 | Upgradation of Two Laning of Sriganganagar to Raisinghnagar (NH-911) Highway Project | 1888 | Contractor | V R C Constructions (india) Pvt. Ltd. | 326267 | India | Registered Office:Plot No.16, VRC Tower, Paschim Vihar Ext., Rohtak Road, Paschim Vihar, | 110063 | Delhi | NCT of Delhi |  |  | vrcon@hotmail.com | www.vrccon.co.in
25746 | National Highways Authority Of India | 155597 | Urukunnu-Kadampattukonam Four/Six Lane Economic Corridor Project | 2040 | Consultant | Chaitanya Projects Consultancy Pvt. Ltd. | 576447 | India | Registered Office:1st Floor, Tower 3, Okaya Centre, Sector 62, | 201301 | Noida | Uttar Pradesh | 91-120-4110472 |  | info@cpcmail.in | www.chaitanyaprojects.com
25747 | National Highways Authority Of India | 155597 | Vadape-Thane (NH-848) Six/Eight Laning Highway Project | 1941 | Contractor | M S R D C Infrastructure Projects Ltd. | 595369 | India |  | NA
25748 | National Highways Authority Of India | 155597 | Vadodara Logistics Park Project | 1373 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25749 | National Highways Authority Of India | 155597 | Vadodara-Bharuch (NH-8) Six-Laning Highway Project | 430 | Contractor | Vadodara Bharuch Tollway Ltd. | 370957 | India | Corporate Office:Toll Plaza, KM-157, NH-8, Bharthana, Ta. Karjan, | 391244 | Vadodara | Gujarat | 91-2666-230000 | 91-2666-230050
25750 | National Highways Authority Of India | 155597 | Vadodara-Surat (NH-8) Six-Laning Highway (Four-lane Bridge over Narmada River in Bharuch along with Six-Lane Approach Roads) Project (Extra Dosed Bridge) | 901 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25751 | National Highways Authority Of India | 155597 | Vadodara-Surat (NH-8) Six-Laning Highway (Four-lane Bridge over Narmada River in Bharuch along with Six-Lane Approach Roads) Project (Extra Dosed Bridge) | 901 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25752 | National Highways Authority Of India | 155597 | Vadodara-Surat (NH-8) Six-Laning Highway (Four-lane Bridge over Narmada River in Bharuch along with Six-Lane Approach Roads) Project (Extra Dosed Bridge) | 901 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25753 | National Highways Authority Of India | 155597 | Vadodara-Surat (NH-8) Six-Laning Highway (Four-lane Bridge over Narmada River in Bharuch along with Six-Lane Approach Roads) Project (Extra Dosed Bridge) | 901 | Contractor | Ranjit Buildcon Ltd. | 395126 | India | Corporate Office:Ranjit House, Opp Sun Residency, B/H Bhagwat Bunglows, Rt. Side Road To G M Mandir, Thaltej Shilaj Rd, | 380059 | Ahmedabad | Gujarat | 91-79-40200555 | 91-40-40200565 | accounts.rbl@gmail.com | www.ranjitbuildcon.com
25754 | National Highways Authority Of India | 155597 | Vadodara-Surat Four Lane Highway Project | 90 | Contractor | I R B Infrastructure Developers Ltd. | 373589 | India | Corporate Office:3rd Floor, IRB Complex, Chandivali Farm, Chandivali Village, Andheri East, | 400072 | Mumbai | Maharashtra | 91-22-66404220 | 91-22-66751024 | info@irb.co.in | www.irb.co.in
25755 | National Highways Authority Of India | 155597 | Vakalapudi Light House-Uppada-Annavaram (NH-516F) Four Lane Access controlled Highway Project | 2061 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25756 | National Highways Authority Of India | 155597 | Vakalapudi Light House-Uppada-Annavaram (NH-516F) Four Lane Access controlled Highway Project | 2061 | Contractor | Aurobindo Realty & Infrastructure Pvt. Ltd. | 597543 | India | Registered Office:21st Floor, Wing A, Galaxy, Plot No 1, Sy No.83/1, Knowledge City, Raidurg (Panmaktha), | 500081 | Hyderabad | Telangana
25757 | National Highways Authority Of India | 155597 | Valsad (Bulsar) Logistics Park Project | 1364 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25758 | National Highways Authority Of India | 155597 | Vanavolu-Vankarakunta Four/Six Lane Greenfield Expressway Project (Package-2 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 1974 | Contractor | Raj Path Infracon Pvt. Ltd. | 190016 | India | Registered Office:Office No. 403, 4th Floor, Pride House, 108, Ganesh Khind Road,Opp Pune University, | 411016 | Pune | Maharashtra | 91-20-25636060 | 91-20-25633344 | raj@rajgrouppune.net
25759 | National Highways Authority Of India | 155597 | Vankarakunta-Odulapalle (NH-544G) Four/Six Lane Greenfield Expressway Project (Package-3 of Bengaluru-Kadapa-Pulivendula-Vijayawada Expressway) | 2109 | Contractor | Raj Path Infracon Pvt. Ltd. | 190016 | India | Registered Office:Office No. 403, 4th Floor, Pride House, 108, Ganesh Khind Road,Opp Pune University, | 411016 | Pune | Maharashtra | 91-20-25636060 | 91-20-25633344 | raj@rajgrouppune.net
25760 | National Highways Authority Of India | 155597 | Varadharajula-Kumarajapet (NH-716B) Six Laning Expressway Project (Package-I of Chittoor-Thatchur Expressway) | 1638 | Consultant | Louis Berger Consulting Pvt. Ltd. | 406754 | India | Registered Office:Regus Business Centre, Level-3, Vasant Square Mall Pocket V, Sector B, | 110070 | New Delhi | NCT of Delhi |  |  | neeraj.kumar2@wsp.com | www.wsp.com
25761 | National Highways Authority Of India | 155597 | Varadharajula-Kumarajapet (NH-716B) Six Laning Expressway Project (Package-I of Chittoor-Thatchur Expressway) | 1638 | Contractor | K C C Buildcon Pvt. Ltd. | 413692 | India | Registered Office:B U 5, 2nd Floor, S F S Flats, Outer Ring Road, Pitampura, | 110034 | Delhi | NCT of Delhi | 91-11-47581001 |  | kcc.del@gmail.com | www.kccbuildcon.co.in
25762 | National Highways Authority Of India | 155597 | Varanasi (Kashi) Intermodal Station Project | 1458 | Consultant | Mahindra Consulting Engineers Ltd. | 136445 | India | Corporate Office:5th Floor, Mahindra Towers, P K Kume Chowk, Worli, | 400018 | Mumbai | Maharashtra | 91-22-24905650 | 91-22-24900833
25763 | National Highways Authority Of India | 155597 | Varanasi (Kashi) Intermodal Station Project | 1458 | Consultant | Pricewaterhouse Coopers Pvt. Ltd. | 181337 | India | Head Office:Sukh Sagar, 2/5 Sarat Bose Road, | 700020 | Kolkata | West Bengal | 91-33-4752910 | 91-33-4746134 | abhijit.roy@in.pwcglobal.com | www.pwcglobal.com
25764 | National Highways Authority Of India | 155597 | Varanasi (Kashi) Intermodal Station Project | 1458 | Consultant | Ardanuy Ingenieria S A | 589247 | Spain |  | NA
25765 | National Highways Authority Of India | 155597 | Varanasi (Kashi) Intermodal Station Project | 1458 | Promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25766 | National Highways Authority Of India | 155597 | Varanasi (NH-29) Four Laning Bypass (Phase 2) Project (Package-II) | 1327 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25767 | National Highways Authority Of India | 155597 | Varanasi (NH-29) Four Laning Bypass (Phase 2) Project (Package-II) | 1327 | Consultant | Worley India Pvt. Ltd. | 105074 | India | Registered Office:New Energy House, Ramakrishna Mandir Road,Kondivita, Andheri (East), | 400059 | Mumbai | Maharashtra | 91-22-26812000 |  | dhananjay.dumbre@jacobs.com
25768 | National Highways Authority Of India | 155597 | Varanasi (NH-29) Four Laning Bypass (Phase 2) Project (Package-II) | 1327 | Contractor | Gammon Engineers & Contractors Pvt. Ltd. | 542071 | India | Registered Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61114000 | 91-22-24300221 | marketing@gammonengineers.com | www.gammonengineers.com
25769 | National Highways Authority Of India | 155597 | Varanasi (NH-56) Four Laning Bypass (Phase 2) Project (Package-I) | 1328 | Consultant | C E S Ltd. | 216887 | India | Registered Office:7th Floor, Tower A, Ramky Selenium, Nanakramguda, Gachibowli, | 500032 | Hyderabad | Telangana | 91-40-42421122 | 91-40-66259444 | info@cesltd.com | www.cesltd.com
25770 | National Highways Authority Of India | 155597 | Varanasi (NH-56) Four Laning Bypass (Phase 2) Project (Package-I) | 1328 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25771 | National Highways Authority Of India | 155597 | Varanasi Ring Road (Near Rewasa Village) to Chandauli-Chainpur Road (Near Khainti Village) Four/Six Lane Greenfield Access Control Expressway Project (Package-1 of Varanasi-Kolkata Expressway) | 1983 | Consultant | S A Infrastructure Consultants Pvt. Ltd. | 537251 | India | Registered Office:B-4/8, Glaxo Apartments, Mayur Vihar, Phase-I, | 110091 | New Delhi | NCT of Delhi | 91-120-6148000 |  | fidele.sra@gmail.com | www.sainfra.com
25772 | National Highways Authority Of India | 155597 | Varanasi Ring Road (Near Rewasa Village) to Chandauli-Chainpur Road (Near Khainti Village) Four/Six Lane Greenfield Access Control Expressway Project (Package-1 of Varanasi-Kolkata Expressway) | 1983 | Contractor | N K C Projects Pvt. Ltd. | 394083 | India | Registered Office:Unit No. 154, Vardhman Crown Mall, Plot No. 2 Sec-19, Plot No. 2, Sec-19 Dwarka, | 110075 | New Delhi | NCT of Delhi |  |  | compliance@nkcproject.com | www.nkcproject.com
25773 | National Highways Authority Of India | 155597 | Varanasi Ring Road (NH-31) Project (Varanasi-Gorakhpur NH-29) | 910 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25774 | National Highways Authority Of India | 155597 | Varanasi Ring Road (NH-31) Project (Varanasi-Gorakhpur NH-29) | 910 | Contractor | Gammon Engineers & Contractors Pvt. Ltd. | 542071 | India | Registered Office:Gammon House, Veer Savarkar Marg, Prabhadevi, | 400025 | Mumbai | Maharashtra | 91-22-61114000 | 91-22-24300221 | marketing@gammonengineers.com | www.gammonengineers.com
25775 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Dehri on-sone--Aurangabad) Highway Project | 156 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25776 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Dehri on-sone--Aurangabad) Highway Project | 156 | Contractor | Oriental Structural Engineers Pvt. Ltd. | 165003 | India | Registered Office:Ose Commercial Block, Hotel Aloft, Asset 5B, Aerocity, Hospitality District, I G I Airport, | 110037 | New Delhi | NCT of Delhi | 91-11-46044604 |  | info@orientalindia.com | www.orientalindia.com
25777 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Dehri on-sone--Aurangabad) Highway Project | 156 | Contractor | Ssangyong Corpn. | 235585 | Korea Republic (South) |  | NA
25778 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Mohania-Sasaram) Highway Project | 154 | Consultant | I C T Pvt. Ltd. | 284672 | India | Registered Office:A - 8 & A - 9, Green Park Main, | 110016 | New Delhi | NCT of Delhi | 91-11-40863000 | 91-11-26855252 | info@ictonline.com | www.ictonline.com
25779 | National Highways Authority Of India | 155597 | Varanasi-Aurangabad(Mohania-Sasaram) Highway Project | 154 | Contractor | L G Engineering & Construction Ltd. | 476274 | Korea Republic (South) |  | NA
25780 | National Highways Authority Of India | 155597 | Varanasi-Dagmagpur (NH-7) Four Lane Highway Project (Package-I) | 1414 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25781 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-24) Four Laning Highway (Package-IV Amilla Village-Gorakhpur) Project | 1051 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25782 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-24) Four Laning Highway (Package-IV Amilla Village-Gorakhpur) Project | 1051 | Contractor | Jaiprakash Associates Ltd. | 108841 | India | Corporate Office:JA House', 63, Basant Lok Vasant Vihar, | 110057 | New Delhi | NCT of Delhi | 91-11-4982500 | 91-11-26145389 | jalinvestor@jalindia.co.in | www.jalindia.com
25783 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-II from Sandah-Birnon) Project | 1049 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25784 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-II from Sandah-Birnon) Project | 1049 | Contractor | P N C Infratech Ltd. | 296258 | India | Corporate Office:P N C Tower, 3/22-D, Civil Lines, Agra Delhi Bypass Road, National Highway 2, | 282005 | Agra | Uttar Pradesh | 91-562-4054400 | 91-562-4070011 | complianceofficer@pncinfratech.com | www.pncinfratech.com
25785 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-III Birnon Village-Amilla Village) Project | 1050 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25786 | National Highways Authority Of India | 155597 | Varanasi-Gorakhpur (NH-29) Four Laning Highway (Package-III Birnon Village-Amilla Village) Project | 1050 | Contractor | Jaiprakash Associates Ltd. | 108841 | India | Corporate Office:JA House', 63, Basant Lok Vasant Vihar, | 110057 | New Delhi | NCT of Delhi | 91-11-4982500 | 91-11-26145389 | jalinvestor@jalindia.co.in | www.jalindia.com
25787 | National Highways Authority Of India | 155597 | Varanasi-Mohania (GTRIP/IV-A) Highway Project | 153 | Consultant | N D Lea International | 151866 | Canada |  | NA
25788 | National Highways Authority Of India | 155597 | Varanasi-Mohania (GTRIP/IV-A) Highway Project | 153 | Contractor | Progressive Constructions Ltd. | 182710 | India | Registered Office:7th Flr, Raghava North Block, Raghav Ratna Tower, Chirag Ali Lane, Abids, | 500001 | Hyderabad | Telangana | 91-40-23204687 | 91-40-23204688
25789 | National Highways Authority Of India | 155597 | Varanasi-Mohania (GTRIP/IV-A) Highway Project | 153 | Contractor | Sunway Construction Bhd | 282631 | Malaysia | Registered Office:Level 8, Menara Sunway, Jalan Lagoon Timur, Bandar Sunway, 46150 Petaling Jaya, Selangor Darul Ehsan, Malaysia | NA
25790 | National Highways Authority Of India | 155597 | Vashista River Bridge Project | 173 | Turnkey contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25791 | National Highways Authority Of India | 155597 | Vehicular Underpasses at Kalabadia Chowk and Kuliana Village Road in Balasore-Baripada-Jharpokharia Section of NH-5 Project | 1840 | Contractor | E5 Infrastructure Pvt. Ltd. | 613495 | India | Registered Office:SCO-105 Pocket A, Sec-14, | 125001 | Hisar | Haryana |  |  |  | www.e5infra.com
25792 | National Highways Authority Of India | 155597 | Vejalka Village-Start of DSIR Zone (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-3) | 1706 | Consultant | Enviro Infra Solutions Pvt. Ltd. | 570121 | India | Registered Office:301,302 & 305, SRBC, Plot No. INS-12, Sector-9, Vasundhara, | 201012 | Ghaziabad | Uttar Pradesh | 91-120-4151183 |  | eis@enviroinfrasolutions.com | www.enviroinfrasolutions.com
25793 | National Highways Authority Of India | 155597 | Vejalka Village-Start of DSIR Zone (NH-751) Four Lane Expressway Project (Ahmedabad-Dholera Greenfield Alignment Package-3) | 1706 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
25794 | National Highways Authority Of India | 155597 | Vellora Square (Balasore and Kharagpur) (NH-60) Underpass Project | 1428 | Consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25795 | National Highways Authority Of India | 155597 | Vellora Square (Balasore and Kharagpur) (NH-60) Underpass Project | 1428 | Contractor | K K Narsaria Construction | 586396 | India |  | NA
25796 | National Highways Authority Of India | 155597 | Vengalam-Kuttipuram (NH-66) Four Laning Highway Project (Kasaragod District-Thiruvananthapuram District) | 539 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
25797 | National Highways Authority Of India | 155597 | Verka Chowk to Attari-Wagha Border Four-Laning Road Project | 783 | Contractor | Rohan Rajdeep Tollways Ltd. | 380205 | India | Registered Office:1, Modibaug, Commercial Building, CTS No.2254, Ganeshkhind Road, Shivaji Nagar, | 411016 | Pune | Maharashtra
25798 | National Highways Authority Of India | 155597 | Vijayawada Multi-Modal Logistics Park Project | 1267 | Co-promoter | Andhra Pradesh Indl. Infrastructure Corpn. Ltd. | 15266 | India | Registered Office:5-9-58/B, Dateh Maidan Road, 6th Floor, Parisrama Bhavanam, Basheerbagh, | 500004 | Hyderabad | Telangana | 91-40-23237622 | 91-40-23233251 | chairman_ap@apiic.in | www.apiic.in
25799 | National Highways Authority Of India | 155597 | Vijayawada Six Lane Bypass Project (Chinna Autupalli-Gollapudi & Gollapudi-Chinnakakani Section) (Vijayawada-Gundugolanu section) | 1510 | Contractor | Adani Enterprises Ltd. | 5747 | India | Registered Office:Adani Corporate House, Shantigram, Near Vaishno Devi Circle,S. G. Highway, Khodiyar, | 382421 | Ahmedabad | Gujarat | 91-79-26565555 |  | customercare.irm@adani.com | www.adanienterprises.com
25800 | National Highways Authority Of India | 155597 | Vijayawada Six Lane Bypass Project (Chinna Autupalli-Gollapudi & Gollapudi-Chinnakakani Section) (Vijayawada-Gundugolanu section) | 1510 | Contractor | Navayuga Engineering Co. Ltd. | 156086 | India | Corporate Office:Plot No 379, Road No 10, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23339990 | 91-40-23337789 | nec@navayuga.com | www.necltd.com
25801 | National Highways Authority Of India | 155597 | Vijayawada Six Lane Bypass Project (Chinna Autupalli-Gollapudi & Gollapudi-Chinnakakani Section) (Vijayawada-Gundugolanu section) | 1510 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25802 | National Highways Authority Of India | 155597 | Vijayawada Six Lane Bypass Project (Chinna Autupalli-Gollapudi & Gollapudi-Chinnakakani Section) (Vijayawada-Gundugolanu section) | 1510 | Contractor | Vijayawada Bypass Project Pvt. Ltd. | 645841 | India |  | NA
25803 | National Highways Authority Of India | 155597 | Vijayawada-Chilkaluripet (Package IV) Highway Project | 177 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25804 | National Highways Authority Of India | 155597 | Vijayawada-Chilkaluripet (Package IV) Highway Project | 177 | Turnkey contractor | U P State Indl. Devp. Corpn. Ltd. | 259430 | India | Registered Office:UPSIDC Complex, A-1/4, Lakhanpur, | 208024 | Kanpur | Uttar Pradesh | 91-512-2582851 | 91-512-2580797 | feedback@upside.com | www.onlineupsidc.com
25805 | National Highways Authority Of India | 155597 | Vijayawada-Machilipatnam (NH-65) Four-Laning Highway Project (Bharatmala) | 990 | Consultant | U R S Scott Wilson India Pvt. Ltd. | 215516 | India | Registered Office:416/7, & 8, 1st Floor, Opp. Karkarduma Metro Station, Near Barat Ghar, | 110092 | New Delhi | NCT of Delhi |  |  | mayank.maheshwari@aecom.com | www.aecom.com
25806 | National Highways Authority Of India | 155597 | Vijayawada-Machilipatnam (NH-65) Four-Laning Highway Project (Bharatmala) | 990 | Contractor | Dilip Buildcon Ltd. | 386908 | India | Corporate Office:E-5/99, Arera Colony, | 462016 | Bhopal | Madhya Pradesh | 91-755-2461064 | 91-755-4247574 | contactus@dbl.co.in | www.dilipbuildcon.com
25807 | National Highways Authority Of India | 155597 | Vijayawada-Rajamundry Section (near Eluru) HIghway Project | 46 | Consultant | Senior Consultant Engg. Group Pvt. Ltd. | 216656 | India | Head Office:2/95, Nayapalli, | NA | Bhubaneswar | Orissa | 91-674-550563 | 91-674-539400/403931
25808 | National Highways Authority Of India | 155597 | Vijayawada-Rajamundry Section (near Eluru) HIghway Project | 46 | Turnkey contractor | Madhucon Projects Ltd. | 134113 | India | Corporate Office:Madhucon House, Plot No.1129/A, Road No.36, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23556001 | 91-40-23556005 | cs@madhucon.com | www.madhucon.com
25809 | National Highways Authority Of India | 155597 | Vijaypur-Pathankot Highway Project | 306 | Contractor | I T D Cementation India Ltd. | 228935 | India | Registered Office:9th Floor, Prima Bay, Tower-B, Gate No. 5,Saki Vihar Road, Powai, | 400072 | Mumbai | Maharashtra | 91-22-66931600 | 91-22-66931628 | investors.relation@itdcem.co.in | www.itdcem.co.in
25810 | National Highways Authority Of India | 155597 | Vijaypur-Pathankot Highway Project | 306 | Supervision consultant | Lea Associates South Asia Pvt. Ltd. | 127666 | India | Registered Office:B 1/E-27, 2nd Floor, Mohan Co-, Operative Industrial Estate, Mathura Road, | 110044 | New Delhi | NCT of Delhi | 91-11-41678150 | 91-11-41678659 | cs@sigmalegal.in | www.lasaindia.com
25811 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageII) Highway Project | 175 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25812 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageII) Highway Project | 175 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
25813 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageII) Highway Project | 175 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25814 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageII) Highway Project | 175 | Contractor | I J M Constructions Sdn Bhd | 324217 | Malaysia | Registered Office:Malaysia | NA
25815 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageIII) Highway Project | 176 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25816 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageIII) Highway Project | 176 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
25817 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageIII) Highway Project | 176 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25818 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet (PackageIII) Highway Project | 176 | Contractor | I J M Constructions Sdn Bhd | 324217 | Malaysia | Registered Office:Malaysia | NA
25819 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet(Package I) Highway Project | 55 | Consultant | Consulting Engineering Services (india) Pvt. Ltd. | 50581 | India | Registered Office:2nd Floor, Platinum Tower, Plot No. 184, Udyog Vihar, Phase- 1, | 122016 | Gurgaon | Haryana | 91-124-3317000 | 91-124-3372999 | Bajrang.prasad@jacobs.com
25820 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet(Package I) Highway Project | 55 | Consultant | Louis Berger Intl. Inc. | 287149 | USA | Registered Office:114, M L A Colony, Road No.12, Banjara Hills, | 500034 | Hyderabad | Telangana | 91-40-23305138 |  |  | www.louisberger.com
25821 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet(Package I) Highway Project | 55 | Contractor | Gayatri Projects Ltd. | 80013 | India | Corporate Office:B-1, 1st Floor, T S R Towers, 6-3-1090, Rajbhavan Road, Somajiguda, | 500082 | Hyderabad | Telangana | 91-40-23314284 | 91-40-23398435 | gplhyd@gayatri.co.in | www.gayatri.co.in
25822 | National Highways Authority Of India | 155597 | Vijaywada-Chilkaluripet(Package I) Highway Project | 55 | Contractor | I J M Constructions Sdn Bhd | 324217 | Malaysia | Registered Office:Malaysia | NA
25823 | National Highways Authority Of India | 155597 | Vijaywada-Hyderabad(Vijay-Ibrahimpatnam & Hyderabad City) Highway Project | 10 | Turnkey contractor | Construction Industry Devp. Board. | 50553 | Malaysia |  | NA
25824 | National Highways Authority Of India | 155597 | Vijaywada-Ranchi Highway Project | 435 | Contractor | A R S S Infrastructure Projects Ltd. | 370768 | India | Corporate Office:A R S S Mail, Plot No.40, Community Centre, Block-A, Paschim Vihar, Opp. To Jwalaheri Market, | 110063 | New Delhi | NCT of Delhi | 91-11-25252024 | 91-11-48636339 | delhi@arssgroup.in | www.arssgroup.in
25825 | National Highways Authority Of India | 155597 | Vikkaravandi-Sethiyahopu (NH-45 C) Four Laning Highway (Pkg-I of Vikravandi-Thanjavur) Project | 890 | Consultant | Vax Consultants Pvt. Ltd. | 263468 | India | Registered Office:E & F II Floor, 1 Vardaraja Street, T Nagar, Kannama Pet, | 600017 | Chennai | Tamil Nadu | 91-44-24311085 | 91-44-24314837 | vaxcon@vsnl.in
25826 | National Highways Authority Of India | 155597 | Vikkaravandi-Sethiyahopu (NH-45 C) Four Laning Highway (Pkg-I of Vikravandi-Thanjavur) Project | 890 | Consultant | Louis Berger Group - Usa | 536211 | USA |  | NA
25827 | National Highways Authority Of India | 155597 | Vikkaravandi-Sethiyahopu (NH-45 C) Four Laning Highway (Pkg-I of Vikravandi-Thanjavur) Project | 890 | Contractor | Reliance Infrastructure Ltd. | 27747 | India | Registered Office:Reliance Centre, Ground Floor 19, Walchand Hirachand Marg, Ballard Estate, | 400001 | Mumbai | Maharashtra | 91-22-43031000 | 91-22-43033664 | rinfra.investor@relianceada.com | www.rinfra.com
25828 | National Highways Authority Of India | 155597 | Village Kalyanpur to Village Balbhadrapur Four Lane Access Controlled Greenfield Highway (NH-119D) Project (Package-III of Amas-Darbhanga Expressway) | 1946 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25829 | National Highways Authority Of India | 155597 | Villukuri-Kanyakumari (NH-47 & NH-66) & Nagercoil-Kavalkinaru (NH-47B) Four Laning Highway Project | 351 | Consultant | Secon Pvt. Ltd. | 215980 | India | Corporate Office:Plot No. 147, 7-B, Road, Whitefield, | 560066 | Bengaluru | Karnataka | 91-80-51197778 | 91-80-51194277 | sesvy@blr.vsnl.net.in | www.secon-india.net
25830 | National Highways Authority Of India | 155597 | Villukuri-Kanyakumari (NH-47 & NH-66) & Nagercoil-Kavalkinaru (NH-47B) Four Laning Highway Project | 351 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25831 | National Highways Authority Of India | 155597 | Villukuri-Kanyakumari (NH-47 & NH-66) & Nagercoil-Kavalkinaru (NH-47B) Four Laning Highway Project | 351 | Contractor | Shinde Developers Pvt. Ltd. | 220631 | India | Registered Office:S. No. 132/2 & 3, Plot No. 22, Gulmohar Park, ITI Road, Aundh, | 411007 | Pune | Maharashtra | 91-20-41004800 | 91-20-41004846 | info@sdplinfra.com | www.sdplinfra.in
25832 | National Highways Authority Of India | 155597 | Virnoda-Mopa Four/Six Lane (NH-166S) Highway Project | 1629 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25833 | National Highways Authority Of India | 155597 | Virnoda-Mopa Four/Six Lane (NH-166S) Highway Project | 1629 | Co-promoter | Goa Public Works Department | 469662 | India | Registered Office:Altinho Panaji, City Panjim, | NA | North Goa | Goa | 91-832-2224984 |  | pce-pwd.goa@nic.in | www.pwd.goa.gov.in
25834 | National Highways Authority Of India | 155597 | Virnoda-Mopa Four/Six Lane (NH-166S) Highway Project | 1629 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
25835 | National Highways Authority Of India | 155597 | Visakhapatnam (NH-516C) Four Lane Port Road Connectivity Project (Sheelanagar to Sabbavaram) (Bharatmala) | 1826 | Consultant | Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. | 391779 | India | Registered Office:8-2-5, Ravula Residency, Srinagar Cly, Main Road, | 500082 | Hyderabad | Telangana | 91-40-48483456 | 91-40-23736277 | aarvee@aarvee.net | www.aarvee.com
25836 | National Highways Authority Of India | 155597 | Visakhapatnam Port-NH-5/NH-16 Balance Connectivity Four Lane Road Project | 1237 | Co-promoter | Visakhapatnam Port Trust | 268492 | India | Registered Office:HPCL Steel Plant, | 530035 | Visakhapatnam | Andhra Pradesh | 91-891-2876000 | 91-891-2565023 | e-reg.vpt@gov.in | www.vizagport.com
25837 | National Highways Authority Of India | 155597 | Visakhapatnam Port-NH-5/NH-16 Balance Connectivity Four Lane Road Project | 1237 | Contractor | M Venkata Rao Infra Projects Pvt. Ltd. | 384435 | India | Registered Office:D. No. 48-19-6, 2nd Floor M V R Complex, Srinagar, | 530016 | Visakhapatnam | Andhra Pradesh |  |  | mvr999act@yahoo.com
25838 | National Highways Authority Of India | 155597 | Vishakhapatnam Multi-Modal Logistics Park Project | 1287 | Co-promoter | Visakhapatnam Port Trust | 268492 | India | Registered Office:HPCL Steel Plant, | 530035 | Visakhapatnam | Andhra Pradesh | 91-891-2876000 | 91-891-2565023 | e-reg.vpt@gov.in | www.vizagport.com
25839 | National Highways Authority Of India | 155597 | Vizhinjam Bypass-Navaikulam (Kollam Border) Four/Six Lane Outer Ring Road Project (Thiruvananthpuram Outer Ring Road) | 1651 | Co-promoter | Government Of Kerala | 84856 | India | Registered Office:ICT Campus, Vellayambalam, K G Camp, | 695033 | Thiruvananthapuram | Kerala | 91-471-2726881 | 91-471-2314284 | admin.ksitm@kerala.gov.in | www.kerala.gov.in
25840 | National Highways Authority Of India | 155597 | Vizhinjam Bypass-Navaikulam (Kollam Border) Four/Six Lane Outer Ring Road Project (Thiruvananthpuram Outer Ring Road) | 1651 | Consultant | Kitco Ltd. | 121500 | India | Head Office:M M Gardens, Church Landing Road, Near Fine Arts Hall, Pallimukku, | 682016 | Kochi | Kerala | 91-484-4129000 | 91-484-2805066 | mail@kitco.in | www.kitco.in
25841 | National Highways Authority Of India | 155597 | Vizhinjam Bypass-Navaikulam (Kollam Border) Four/Six Lane Outer Ring Road Project (Thiruvananthpuram Outer Ring Road) | 1651 | Financial collaborator | Kerala Infrastructure Investment Fund Board | 119248 | India | Registered Office:2nd Floor, Felicity Square, Koder, Ln, Palayam, | 695001 | Thiruvananthapuram | Kerala | 91-471-2780900 |  | financeadmin@kiifb.org | www.kiifb.kerala.gov.in
25842 | National Highways Authority Of India | 155597 | Wadner-Devdhari (NS-60/MH) Highway Project | 949 | Consultant | S N C-lavalin Infrastructure Pvt. Ltd. | 232230 | India | Registered Office:E-3-5, 2nd Floor, J-Block Local Shopping Complex, Sacket, | NA | New Delhi | Delhi | 91-11-6565838 | 91-11-6866768 |  | www.snclavalininfra.com
25843 | National Highways Authority Of India | 155597 | Wadner-Devdhari (NS-60/MH) Highway Project | 949 | Consultant | Span Consultant Pvt. Ltd. | 586307 | India | Registered Office:92-C, Gurudwara Road, Madangir, | 110062 | New Delhi | NCT of Delhi | 91-11-29955645
25844 | National Highways Authority Of India | 155597 | Wadner-Devdhari (NS-60/MH) Highway Project | 949 | Contractor | G H V (india) Pvt. Ltd. | 394926 | India | Registered Office:1st Floor, Aml Center 1, 8 Maha Kali Caves Road, Andheri East, | 400093 | Mumbai | Maharashtra | 91-22-67250014 |  | info@ghvgroup.com | www.ghvgroup.com
25845 | National Highways Authority Of India | 155597 | Wainganga Bridge-Bhandara (NH-53) Six Lane Highway Project | 2011 | Consultant | T P F Engineering Pvt. Ltd. | 578734 | India | Registered Office:Unit No 10, Banking Complex, No II, Plot No 9 & 10m Sector 19 A, Vashi, | 400705 | Mumbai | Maharashtra | 91-22-41273303 | 91-22-41273306 | tenders@tpfepl.com | www.tpfepl.com
25846 | National Highways Authority Of India | 155597 | Wainganga Bridge-Bhandara (NH-53) Six Lane Highway Project | 2011 | Contractor | Shri Swami Samarth Engineers Ltd. | 517585 | India |  | NA
25847 | National Highways Authority Of India | 155597 | Wakhri-Kudus (NH-965) Four Lane Highway Project (Package-II of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1439 | Contractor | J M Mhatre Infra Pvt. Ltd. | 451830 | India | Registered Office:Plot No 492, Market Yard, | 410206 | Panvel | Maharashtra | 91-22-27451625 | 91-22-27460537 | admin@jmminfra.com | www.jmminfra.com
25848 | National Highways Authority Of India | 155597 | Wakhri-Kudus (NH-965) Four Lane Highway Project (Package-II of Sant Dnyaneshwar Maharaj PalkhiMarg) (section of Mohol-Alandi) | 1439 | Contractor | Shri S M Autade Pvt. Ltd. | 510451 | India | Registered Office:Plot No. 17, CTS No. 1620, Giriraj Co-operative Housing Society | 411007 | Pune | Maharashtra | 91-20-25640391 |  | accounts@autadegroup.com | www.autadegroup.com
25849 | National Highways Authority Of India | 155597 | Warangal-Khammam Four Lane Access Controlled Greenfield Highway Project | 1930 | Consultant | S M Consultancy Pvt. Ltd. | 203764 | India | Registered Office:Hemakapada Chhak, Sunhat, | 756002 | Balasore | Odisha | 91-6782-251981 | 91-6782-251982 | smcbls@smcindia.com | www.smcindia.com
25850 | National Highways Authority Of India | 155597 | Warangal-Khammam Four Lane Access Controlled Greenfield Highway Project | 1930 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in
25851 | National Highways Authority Of India | 155597 | Warangal-Khammam Four Lane Access Controlled Greenfield Highway Project | 1930 | Contractor | G R Infraprojects Ltd. | 380699 | India | Corporate Office:2nd Floor, Novus Tower, Plot No. 18, Sector 18, | 122015 | Gurgaon | Haryana | 91-124-6435000 |  | cs@grinfra.com | www.grinfra.com
25852 | National Highways Authority Of India | 155597 | Warangal-Khammam Four Lane Access Controlled Greenfield Highway Project | 1930 | Contractor | V D B Projects Pvt. Ltd. | 406937 | India | Registered Office:#842/A, V D B House, 100, Feet Road Binnamangala, Indiranagar, | 560038 | Bengaluru | Karnataka |  |  | ksn@vdbgroup.in
25853 | National Highways Authority Of India | 155597 | Washim-Pangare (NH-161) Four Lane Highway project (Package-III) | 1697 | Contractor | Montecarlo Ltd. | 148976 | India | Corporate Office:Montecarlo House,Sindhu Bhavan Road, Bodakdev, | 380058 | Ahmedabad | Gujarat | 91-79-26409333 | 91-79-26408444 | mail@mclindia.com | www.mclindia.com
25854 | National Highways Authority Of India | 155597 | Westerly Diversion Highway Project | 58 | Consultant | Rites Ltd. | 189557 | India | Corporate Office:Shikhar, Rites Bhawan, Plot No.1, Sector-29, | 122001 | Gurgaon | Haryana | 91-124-2571666 | 91-124-2571660 | info@rites.com | www.rites.com
25855 | National Highways Authority Of India | 155597 | Westerly Diversion Highway Project | 58 | Contractor | Ashoka Buildcon Ltd. | 22247 | India | Registered Office:S No.861, Ashoka House, Ashoka Marg, Ashoka Nagar, | 422011 | Nashik | Maharashtra | 91-253-6633705 | 91-253-2236704 | investors@ashokabuildcon.com | www.ashokabuildcon.com
25856 | National Highways Authority Of India | 155597 | Westerly Diversion Highway Project | 58 | Contractor | Birla G T M Entrepose Pvt. Ltd. | 36324 | India | Registered Office:Birla Building, 9/1, R N Mukherjee Road, | 700001 | Kolkata | West Bengal | 91-33-22430383 | 91-33-22101912 | neical@nbcbearings.in
25857 | National Highways Authority Of India | 155597 | Whitefield industrial cluster-Bangalore to Enayam Expressway Project (Port Connectivity) | 1722 | Co-promoter | Ministry Of Road Transport & Highways | 301849 | India | Registered Office:Transport Bhavan, 1, Parliament Street, | 110001 | New Delhi | Delhi | 91-11-23753991 |  | nr.gokarn@nic.in | www.morth.nic.in
25858 | National Highways Authority Of India | 155597 | Widening & Strengthening of Garhmukteshwar-Meerut (NH-709A) Highway Project | 1673 | Consultant | Sai Consulting Engineers Pvt. Ltd. | 380312 | India | Registered Office:Sai House, Block-A, Satyam Corporate Square, B/h Rajpath Club, Opp. Kishan Bunglows, Bodakdev, | 380054 | Ahmedabad | Gujarat | 91-79-66142600 | 91-79-66142800 | mail@saiindia.com | www.saiindia.com
25859 | National Highways Authority Of India | 155597 | Widening & Strengthening of Garhmukteshwar-Meerut (NH-709A) Highway Project | 1673 | Contractor | Tata Projects Ltd. | 248168 | India | Registered Office:Mithona Towers-1, 1-7-80 To 87, Opp. Wesley Co-Ed. Jr. College, Prenderghast Road, | 500003 | Secunderabad | Telangana | 91-40-66238801 | 91-40-66172535 | cstpl@tataprojects.com | www.tataprojects.com
25860 | National Highways Authority Of India | 155597 | Widening and Rehabilitation of Champa-Korba-Katghora (NH-149B) Four Lane Road Project | 1882 | Contractor | Gawar Construction Ltd. | 395417 | India | Corporate Office:SF-01, JMD Galleria, Sohna Road, | 122001 | Gurgaon | Haryana | 91-124-4854000 | 91-124-4854001 | finance@gawar.in
25861 | National Highways Authority Of India | 155597 | Widening of Thirumangalam-Rajapalayam-Shencottai (NH-744) Four Lane Highway project | 1695 | Consultant | Artefact Projects Ltd. | 20451 | India | Corporate Office:1st Floor, Bhiwapurkar Chambers, Opp. Yeshwant Stadium, Dhantoli, | 440012 | Nagpur | Maharashtra | 91-712-2425219 | 91-712-2427830 | asflswf_ngp@sancharnet.in | www.artefactprojects.com
25862 | National Highways Authority Of India | 155597 | Widening of Thirumangalam-Rajapalayam-Shencottai (NH-744) Four Lane Highway project | 1695 | Contractor | K M C Constructions Ltd. | 112439 | India | Corporate Office:Plot No 85, Road No 72, Prashasan Nagar, Jubilee Hills, | 500033 | Hyderabad | Telangana | 91-40-23558061 | 91-40-23558060 |  | www.kmcgroup.co.in
25863 | National Highways Authority Of India | 155597 | Widening of Thirumangalam-Rajapalayam-Shencottai (NH-744) Four Lane Highway project | 1695 | Contractor | S & P Infrastructure Developers Pvt. Ltd. | 440653 | India | Registered Office:907, New Delhi House, Barakhamba Road, Connaught Place, | 110001 | New Delhi | NCT of Delhi | 91-11-23753726 | 91-11-45850311 | info@spinfra.in | www.spinfra.in
25864 | National Highways Authority Of India | 155597 | Willingdon Island to Kundanoor/Aroor (NH-66) Four Lane Road Project (Connectivity to Cochin Port Trust) | 2100 | Consultant | Dhruv Consultancy Services Ltd. | 511448 | India | Registered Office:501, Pujit Plaza, Palm Beach Road, Sector-11, Opp. K Star Hotel, Near CBD Station, CBD Belapur, | 400614 | Navi Mumbai | Maharashtra | 91-22-27570710 | 91-22-27570710 | cs@dhruvconsultancy.in | www.dhruvconsultancy.in
25865 | National Highways Authority Of India | 155597 | Yadgiri-Warangal (NH-163) Four Laning Highway Project | 992 | Contractor | Larsen & Toubro Ltd. | 127106 | India | Head Office:L & T House, Ballard Estate, Post Box 278, | 400001 | Mumbai | Maharashtra | 91-22-67525656 | 91-22-23420814 | Nehal.Shah@larsentoubro.com | www.larsentoubro.com
25866 | National Highways Authority Of India | 155597 | Yalachahalli Near SH-117 Yelawala-KR Nagara Road to Srirangapatna Bypass Four Lane Highway Project (Package V of Mysuru-Kushalnagar (NH-275) Highway) | 2097 | Consultant | Feedback Infra Pvt. Ltd. | 72655 | India | Registered Office:311, 3rd Floor, Vardhman Plaza, Plot No.6, Pocket 7, Sector 12, Dwarka, | 110078 | New Delhi | NCT of Delhi | 91-11-28035884 |  | secretarial@feedbackinfra.com | www.feedbackinfra.com
25867 | National Highways Authority Of India | 155597 | Yalachahalli Near SH-117 Yelawala-KR Nagara Road to Srirangapatna Bypass Four Lane Highway Project (Package V of Mysuru-Kushalnagar (NH-275) Highway) | 2097 | Contractor | K N R Constructions Ltd. | 112667 | India | Corporate Office:KNR House, 3rd & 4th Floors, Plot No.114, Phase-I, Kavuri Hills, | 500033 | Hyderabad | Telangana | 91-40-40268759 | 91-40-40268760 | investors@knrcl.com | www.knrcl.com
25868 | National Highways Authority Of India | 155597 | Yanam ROB (Yanam-Yedurulanka) Project | 206 | Turnkey contractor | Navayuga Engineering Corpn. Pvt. Ltd. | 156087 | India |  | NA
25869 | National Highways Authority Of India | 155597 | Yerragudipadu-Audireddipalle (NH-44 / 544G) Six Lane Greenfield Expressway Project (Package-6) (Part of Bengaluru-Kadapa-Pulivendula-Vijayawada Brownfield/Greenfield Expressway) | 3015 | Contractor | Megha Engineering & Infrastructures Ltd. | 379812 | India | Head Office:S-2, Technocrat Industrial Estate, Balanagar, | 500037 | Hyderabad | Telangana | 91-40-44336700 | 91-40-44336800 | info@meil.in | www.meil.in